## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Material Requisition To Resource Division |  |  | 2839/HD | 23/12/2022 |  | Resource Division | 33.91 | 0 | 0
2 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | 3592/ED | 28/08/2023 |  | R.N.S. TRADING | 21.83 | 0 | 0
3 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | 3448/ED | 11/08/2023 |  | R.M.D TRADING. | 11 | 0 | 0
4 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Preparation of DPR for new piped water supply scheme of Deulpur PWSS, Panchla Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | 318/AE/USD | 16/08/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 4.25 | 100
5 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Deulpur Gangadharpur Zone-II PWSS of Panchla Block under Howrah Division PHE Dte. | AE/SADAR |  | 1507/HD | 21/07/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.13 | 100
6 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Material Requisition To Resource Division |  |  | 446/HD | 06/02/2023 |  | Resource Division | 307.95 | 0 | 0
7 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Quotation for new service connection charge at Gangadharpur Deulpur PWSS, Zone-II, TW - I |  |  | 529 | 15/12/2023 |  | WBSEDCL | 0.32 | 0 | 0
8 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 352- 405 to Node Section 532-534 Part 8 | AE/SADAR | je_how_rws_jagat | 875/H.D | 02/03/2023 |  | M/S MSS RISING ENTERPRISE | 74.39 | 19.67 | 30
9 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 130-152 to Node Section 201-217 Part 6 | AE/SADAR | je_how_rws_jagat | 876/HD | 02/03/2023 |  | K.B ENTERPRISE | 69.39 | 54.96 | 80
10 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 88-94 to Node Section 97-98 Part 3 | AE/SADAR | je_how_rws_jagat | 855/HD | 01/03/2023 |  | DEBABRATA CHAKRABORTY | 16.89 | 14.16 | 58
11 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 97-127 to Node Section 423-425 Part 5 | AE/SADAR | je_how_rws_jagat | 856/HD | 01/03/2023 |  | S.S ENTERPRISE | 23.46 | 8.01 | 42
12 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 255-287 to Node Section 90-91 From Node Section 287-304 to Node Section 448-450 (P-2,&4) | AE/SADAR | je_how_rws_jagat | 1532/HD | 04/04/2023 |  | N. G ENGINEERING | 91.11 | 77.74 | 85
13 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Joynagar bazar to deulpur H.C Road from 2.730km to 3.00 km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the District of Howrah.under deulpur gangadharpur Zone-II water supply scheme for Panchla Block. |  |  | BP-2024-25-442 | 04/10/2024 |  | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 2.05 | 0 | 0
14 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-II) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H.E. Dte. | AE/SADAR | je_how_rws_jagat | 172/HD | 13/01/2023 |  | PRANTIK DRILLING AGENCY | 50.26 | 16.17 | 35
15 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 217-230 to Node Section 352-361 Part 7 | AE/SADAR | je_how_rws_jagat | 857/HD | 01/03/2023 |  | DULAL MAJUMDER | 67.69 | 48.57 | 75
16 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. From Node Section R1-1 to Node Section 280-281, Part 1 | AE/SADAR | je_how_rws_jagat | 1696/HD | 21/04/2023 |  | PRAVAT SARKAR | 351.82 | 108.89 | 30
17 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-405 NOS) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 456-457 to Node Section 522-530 Part 9 | AE/SADAR | je_how_rws_jagat | 1533/HD | 04/04/2023 |  | JHARNA ENTERPRISE | 41.43 | 29.16 | 100
18 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Construction of 1 (one) no.Pump House (5.40m x 3.60m) at 4th tube well site,Construction of 1(One) no. boundary wall at 4th Tube well site, Construction of approch road and land Devlopment at 4th tubewell site and allied pipe laying work (DI) for Connecting 4th tubewell with the distribution main for Deulpur Gangadharpur Zone II PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | 861/HD | 07/02/2025 |  | MANIRUL ISLAM | 20.91 | 0 | 0
19 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Additional Laying Distribution pipeline with C.C. Road Restoration for Deulpur Gangadharpur Zone II PWSS at Panchla Block of Howrah District under Howrah Sadar Sub Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | 858/HD | 07/02/2025 |  | N. G ENGINEERING | 82.84 | 0 | 60
20 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Construction of 1(One) no. Boundary Wall at OHR site for Deulpur Gangadharpur (Zone-II) PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | 3132/HD | 14/07/2025 |  | M/S ASHIRBAD (INDIA) | 9.06 | 0 | 0
21 | HOWRAH | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Construction of 1 (one) no.Pump House (5.40m x 3.60m) at 3rd tube well site,Construction of 1(One) no. boundary wall at 3 rd Tube well site, Construction of land Development and approach road at 3rd tubewell site and allied pipe laying work (DI and UPVC) for connecting 3 rd tubewell with the distribution main at Deulpur Gangadharpur Zone-II PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | 1070/HD | 27/02/2025 |  | S.S ENTERPRISE | 21.99 | 0 | 0
Total | [12 empty] | 1305.67 | 384.69 | 29.46