## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Material Requisition To Resource Division |  |  | 4024/HD | 07/11/2023 |  | Resource Division | 116.49 | 0 | 0
2 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Material Requisition To Resource Division |  |  | 1049/HD | 04/03/2024 |  | Resource Division | 36.78 | 0 | 0
3 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Material Requisition To Resource Division |  |  | 3884/HD | 05/09/2024 |  | Resource Division | 9.98 | 0 | 0
4 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Quotation Bill for New Service Connection at Uttar Manashree W/S. Sch. |  |  | 703 | 24/01/2024 |  | WBSEDCL | 14.99 | 0 | 0
5 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Manasri water supply scheme, T.W. No. I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 4542/ED | 23/11/2023 |  | M/S DAS ENTERPRISE | 22.04 | 0 | 50
6 | HOWRAH | Howrah Division | Uttar Manasri Piped Water Supply Scheme. | SM/18914 | New | Construction of 600 cum capacity RCC OHR with 20.0 mtr. staging height including soil investigation, Sinking of 2 nos. 300 mm X 200 mm dia X 230 m deep Tubewell, Construction of 2 nos Switch Room with sanitary arrangement, Laying Distribution System, providing Functional Household Tap Connection (FHTC) for UTTAR MANASRI Piped Water Supply Scheme under Udaynarayanpur block under Howrah Division, PHE Dte. [No. of FHTC=3307] | AE/RWS | JE/RWS/Udaynaryanpur | 3825/HD | 16/10/2023 |  | SAMIRON GHOSH | 825.77 | 0 | 25
Total | [12 empty] | 1026.05 | 0 | 0