## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | SM/07589 | Retrofitting | Route Survey for Providing FHTC at Srikrishnanagar W/S Scheme, Block Kakdwip and Dakshin Shibganj W/S Scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | 578/KSD | 10/09/2021 |  | INDRANIL DUTTA & ASSOCIATES | 4.24 | 4.24 | 100
2 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | SM/07589 | Retrofitting | Connection of Tubewell with distribution line of Head Work Site of Srikrishnanagar W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | 761/KSD | 29/11/2021 |  | MANDAL ENTERPRISE (JOYNAGAR) | 0.36 | 0.36 | 95
3 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | SM/07589 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation and laying extension pipe line for providing FHTC for Srikrishnanagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | 5920/AD | 19/10/2022 |  | L.N. ENTERPRISE | 14.03 | 14.03 | 95
4 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | SM/07589 | Retrofitting | Material Requisition To Resource Division |  |  | 674/AD | 30/01/2024 |  | Resource Division | 7.15 | 0 | 0
5 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srikrishnanagar W/S Scheme inc | SM/07589 | Retrofitting | Operation and maintenance of distribution system including rising main and FHTC for Srikrishnanagar Piped Water Supply Scheme of Kakdwip Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [for 6 months] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 228/KSD | 28/01/2025 |  | L.N. ENTERPRISE | 1.75 | 0 | 100
Total | [12 empty] | 27.52 | 18.63 | 67.68