## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Laying PVC and UPVC pipe line for providing FHTC at Gobindapur Abad Water Supply Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 3066/AD | 13/07/2022 |  | M/S A.K. GHATAK | 10.71 | 0 | 100
2 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Trial Run of distribution system including rising main for Gobindapur Abad Piped Water Supply Scheme under JJM of Pathar Pratima Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [for 3 month] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 130/KSD | 20/04/2022 |  | TANMAY ROY CHOWDHURY | 1.26 | 0 | 92
3 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Construction of deep foundation with earth work protection in connection with construction of boundary wall at 2nd Tubewell Site of Gobindapur Abad W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 339/KSD | 01/08/2022 |  | MOUMITA ENTERPRISE | 4.73 | 0 | 100
4 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Supply, Delivery & Laying of Specials Required for Laying Rising Main & Inter - Connection Line between Tubewells in Gobindapur Abad Water Supply Scheme at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | 335/KSD | 01/08/2022 |  | TANMAY ROY CHOWDHURY | 4.41 | 0 | 100
5 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Material Requisition To Resource Division |  |  | 5595/AD | 29/09/2022 |  | Resource Division | 14.31 | 0 | 0
6 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gobindapur Abad W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09006)(2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 3360/AD | 14/08/2024 |  | S. CHAKRABORTY AND CO. | 3.16 | 0 | 0
7 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Construction, placing and fixing of FHTC Platform at every individual beneficiary etc for Retrofitting of Gobindapur Abad W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09006) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 3076/AD | 25/07/2024 |  | M/S B. ENTERPRISE | 90.93 | 0 | 0
8 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 931/KSD | 19/12/2023 |  | M/S B. ENTERPRISE | 0.2 | 0 | 100
9 | SOUTH 24 PARGANAS | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection FHTC to the households for 15 fifteen nos. habitation of all the households in connection with Jal Jeevan Mission JJM and Jal Swapna for Gobindapur Abad WS Scheme includ | SM/09006 | Retrofitting | Surging of 1 no. Tubewell for retrofitting of Gobindapur Abad W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 354/KSD | 09/08/2023 |  | S.K.GOLUI | 2.17 | 0 | 100
Total | [12 empty] | 131.88 | 0 | 0