## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation and commissioning of 20 KVA voltage stabilizer at P.H No.- 2 of Sadhupur W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1102/SMD. | 17/09/2021 |  | SUBHRA ENTERPRISE | 4.07 | 3.52 | 0
2 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and submersible pumping machinery with allied accessories at Tube Well no.2 , Zone-I of Chottokhali Molla Khali W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1087/SMD | 16/09/2021 |  | DEY ENTERPRISE | 4.99 | 4.82 | 0
3 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of 25 KVA voltage stabilizer at P.H No.- 1 of Sarisha W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 2353/SMD. | 07/08/2020 |  | RMD TRADING | 3.65 | 3.65 | 0
4 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing pumping machinery and related accessories with other allied works at P.H No.- 3 of Chemaguri W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 830/SMD | 14/07/2021 |  | NITESH MANAGEMENT | 3.43 | 2.91 | 0
5 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I of Raidighi water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 90/YAAS/SMD. | 26/05/2021 |  | M.S.C ENTERPRISE | 1.16 | 0 | 0
6 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of auto cum manual Motor control panel for P.H No.-3 of Chemaguri under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 909/SMD | 09/08/2021 |  | SIPRA ENTERPRISE | 2.53 | 0 | 0
7 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Tube Well no. 2 of Mallik Kati W/S Scheme of Canning - II Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 293/SMD. | 28/02/2020 |  | UNIVERSAL ENTERPRISES | 6.22 | 1.56 | 0
8 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochloride hydrated granules at PH -3 of Kumiramari w/s Scheme under South 24pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1098/SMSD | 26/08/2021 |  | WIZARDTECH SOLUTION | 0.51 | 0 | 0
9 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring charges of 15 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Herembogopalpur water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 742/AMP/AE-I/SMD | 06/06/2020 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.68 | 0.68 | 0
10 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Tube Well no. 4 , Zone-II of Choto Molla Khali W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1092/SMD. | 16/09/2021 |  | SIPRA ENTERPRISE | 4.99 | 0 | 0
11 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories of water supply scheme at Sitarampur, TW-1 under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 770/SMD | 28/06/2021 |  | DEPALI CONSTRUCTION | 5.86 | 5.43 | 0
12 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring & running charges of 01 No. 62.5 KVA Mobile silent type diesel generator set at PH-1 of Srinagar w/s scheme till the restoration of WBSEDCL power after super cyclone AMPHAN under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 507/AMP/SMSD | 07/06/2020 |  | S.K. ENTERPRISE | 0.5 | 0.5 | 0
13 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation at PH-1 of Akshaynagar Aug. w/s scheme of AMPHAN under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 708/AMP/AE-I/SMD | 04/06/2020 |  | S.K. ENTERPRISE | 0.67 | 0.67 | 0
14 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches at Basanti in connection with service cyclone YAAS 2021 under SMD, PHE Dte.(PT-C) | Assistant Engineer | Junior Engineer | 74/YAAS/SMSD | 24/05/2021 |  | M/S. S.S. ENTERPRISE | 0.86 | 0.86 | 0
15 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite granules at Raghudevpur W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 376/SMSD. | 27/07/2020 |  | M/S. PS & ASSOCIATES | 0.86 | 0.86 | 0
16 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, delivery and installation of DG set for Guest House at BS-II (Krishnamohan) Under SMD PHE Dte. | Assistant Engineer | Junior Engineer | 975/SMD | 26/08/2021 |  | DEPALI CONSTRUCTION | 4.28 | 4.28 | 0
17 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2 of Uttar Kashinagar PH-2 water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 54/AMP/AE-I/SMSD | 19/05/2020 |  | DEPALI CONSTRUCTION | 0.9 | 0.9 | 0
18 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring & running charges of 01 No. 62.5 KVA Mobile silent type diesel generator set at PH-1 of Daharani w/s scheme till the restoration of WBSEDCL power after super cyclone AMPHAN under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 131/AMP/SMSD | 19/05/2020 |  | S.K. ENTERPRISE | 0.81 | 0.81 | 0
19 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring & running charges of 01 No. 62.5 KVA Mobile silent type diesel generator set at PH-1 of Jivantala w/s scheme till the restoration of WBSEDCL power after super cyclone AMPHAN under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 506/AMP/SMSD | 07/06/2020 |  | S.K. ENTERPRISE | 0.81 | 0.81 | 0
20 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring & running charges of 01 No. 62.5 KVA Mobile silent type diesel generator set at PH-1 of Jivantala w/s scheme till the restoration of WBSEDCL power after super cyclone AMPHAN under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 438/A/AMP/SMSD | 04/06/2020 |  | S.K. ENTERPRISE | 0.81 | 0.81 | 0
21 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of 20 KVA voltage stabilizer at P.H No.- 1 at Uttar Durgapur W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 2136/SMD | 30/06/2020 |  | ANJAN ENTERPRISE | 3.14 | 3.14 | 0
22 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring charges of 15 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Herembogopalpur water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 143/AMP/AE-I/SMD | 19/05/2020 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.68 | 0.68 | 0
23 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency running charges of 30 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2 of Muriganga Bungalow water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 430/AMO/AE-I/SMD | 21/05/2020 |  | ORIENTAL ENGINEERING CO. | 0.82 | 0.82 | 0
24 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories of Asuti-2 of Asuti 1 and 2 Gram Panchayet area under Thakurpukur Maheshtala Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 915/SMD | 09/08/2021 |  | A.K.SIKDAR | 6.35 | 4.1 | 0
25 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Emergency hiring & running charges of 01 No. 62.5 KVA Mobile silent type diesel generator set at PH-2, Zone-I of Nagartala w/s scheme till the restoration of WBSEDCL power after super cyclone AMPHAN under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 510/AMP/SMSD | 07/06/2020 |  | S.K. ENTERPRISE | 0.86 | 0.86 | 0
26 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of automatic chlorinatorat Bijoynagar Tube Well No.-4 Gosaba Block W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 737/SMSD | 25/05/2021 |  | M/S. PS & ASSOCIATES | 0.79 | 0.79 | 0
27 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules for Parbatipur & Harekrishnapur W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1037/SMSD. | 04/08/2021 |  | MOUMITA ENTERPRISE | 0.98 | 0.98 | 0
28 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules for Debipur W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1038/SMSD. | 04/08/2021 |  | MOUMITA ENTERPRISE | 0.98 | 0.98 | 0
29 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I, Zone-I of Nagendrapur water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 86/YAAS/SMD | 26/05/2021 |  | SHIVAM ENTERPRISE | 1.36 | 1.36 | 0
30 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Hiring and running of DG set for providing back up power for BS-II Guest House in connection with GLAE- 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 421/SMSD. | 03/04/2021 |  | DEY ENTERPRISE | 0.51 | 0.51 | 0
31 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Supply and delivery of Polyfilm roll for MTU at Basanti in connection with ensuing WBAGE 2021 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 514/SMD. | 30/03/2021 |  | J.D.J ENTERPRISE | 4.99 | 4.99 | 0
32 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing pumping machinery and related accessories with other allied works other allied works at Zone-13 of Tentultala under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 3274/SMD | 26/11/2020 |  | DEY ENTERPRISE | 0.43 | 0.43 | 0
33 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I, Zone-II of Nagendrapur water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 87/YAAS/SMD | 26/05/2021 |  | SHIVAM ENTERPRISE | 1.36 | 1.36 | 0
34 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply ,delivery & installation of automatically controlled diaphragm type chlorinator dosing pump for P.H No.-3 of Chemaguri W/S Scheme under SMD PHE Dte. | Assistant Engineer | Junior Engineer | 835/SMD | 16/07/2021 |  | M/S. PS & ASSOCIATES | 3.45 | 3.45 | 0
35 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I of Bharatgarh water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 05/YAAS/SMD | 26/05/2021 |  | SIPRA ENTERPRISE | 1.31 | 1.31 | 0
36 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I of Harbhangi water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 06/YAAS/SMD | 26/05/2021 |  | SIPRA ENTERPRISE | 1.31 | 1.31 | 0
37 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, delivery & installation of automatically controlled type chlorinator dosing pump for Tube Well No.-2 of Kachukhali W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 918/SMD | 11/08/2021 |  | EMCON | 3.45 | 3.45 | 0
38 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-2, Zone-II of Chunakhali water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 02/YAAS/SMD | 26/05/2021 |  | R.K. CONSTRUCTION | 2.07 | 2.07 | 0
39 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, delivery & installation of automatically controlled diaphragm type chlorinator dosing pump for Tube Well No.-1 of Koutala W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1051/SMD. | 14/09/2021 |  | M/S. PS & ASSOCIATES | 3.3 | 3.3 | 0
40 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Washing, cleaning of chlorine machine unit at different w/s of Budge Budge-I block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1674/AE-II/SMD | 22/06/2021 |  | M/S. PS & ASSOCIATES | 0.49 | 0.49 | 0
41 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-3 of Goranbose water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 04/YAAS/SMD | 26/05/2021 |  | JAGANNATH ENTERPRISE | 0.9 | 0.9 | 0
42 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-1 of Goranbose water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 03/YAAS/SMD | 26/05/2021 |  | JAGANNATH ENTERPRISE | 0.9 | 0.9 | 0
43 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-2 of Abad Bhagabanpur water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 82/YAAS/SMD | 26/05/2021 |  | M/S. S.R. ENTERPRISE | 2.07 | 2.07 | 0
44 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-1 of Purba Jatardeul water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 85/YAAS/SMD | 26/05/2021 |  | M/S. S.R. ENTERPRISE | 2.07 | 2.07 | 0
45 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Rectification of Motor Control Panel Voltage corrector device at PH-2 of Banibada Belekhali W/S Scheme and S-F of FASD at PH-3 at Dakshin Redokhali w/s scheme under SMD, PHE Dte. after YAAS | Assistant Engineer | Junior Engineer | 922/SMSD | 08/07/2021 |  | GANGULY ENGINEERING CO. | 0.6 | 0.6 | 0
46 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Running of 10 KVA DG set for pumping machinery towards the augmentation of w/s from Sonakhali Zone-II, PH-3 w/s scheme under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1300/SMSD | 08/11/2021 |  | DEPALI CONSTRUCTION | 0.87 | 0.87 | 0
47 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Bishnupur-I Block Zone-9 under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1510/A/AE-II/SMD | 27/05/2021 |  | S.P. CONSTRUCTION | 0.74 | 0.74 | 0
48 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Rectification of outdoor and indoor lighting arrangement with allied works at P.H No.-1 & 3 of Budhakhali w/s scheme (Block-Canning -I) under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 1010/SMSD | 27/07/2021 |  | ROY & BISWAS ENGG. CO. | 0.87 | 0.87 | 0
49 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Rectification of outdoor and indoor lighting arrangement with allied works at P.H No.-1 & 3 of Banibada Belekhali w/s scheme (Block-Canning -I) under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 39/SMSD | 13/01/2021 |  | ROY & BISWAS ENGG. CO. | 0.46 | 0.46 | 0
50 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I of Batiswar water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 81/YAAS/SMD | 26/05/2021 |  | DEPALI CONSTRUCTION | 1.54 | 1.54 | 0
51 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Rectification of outdoor and indoor lighting arrangement with allied works at P.H No.-1 & 3 of Banibada Belekhali w/s scheme (Block-Canning -I) under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 38/SMSD | 13/01/2021 |  | ROY & BISWAS ENGG. CO. | 0.76 | 0.76 | 0
52 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I, Zone-I of Chunakhali water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 01/YAAS/SMD | 26/05/2021 |  | R.K. CONSTRUCTION | 2.07 | 2.07 | 0
53 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules for Koutala W/S Scheme under SMD, PHE Dte.(Mathurapur - II Block) | Assistant Engineer | Junior Engineer | 244/SMSD | 26/02/2021 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.86 | 0.86 | 0
54 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochloride hydrated granules at Ajyodhanagar & Kalipota w/s Scheme under South 24pgs Mechanical Division PHE Dte. (Mathurapur-II Block) | Assistant Engineer | Junior Engineer | 1041/SMSD | 04/08/2021 |  | WIZARDTECH SOLUTION | 0.98 | 0.98 | 0
55 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules for PH-2 of Khandalia W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1388/AE-II/SMD | 23/04/2021 |  | SHIVAM ENTERPRISE | 0.86 | 0.86 | 0
56 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I, Zone-II of Gilarchat water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 91/YAAS/SMD | 26/05/2021 |  | M.S.C ENTERPRISE | 1.16 | 1.16 | 0
57 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-I of Raidighi water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 90/YAAS/SMD | 26/05/2021 |  | M.S.C ENTERPRISE | 1.16 | 1.16 | 0
58 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-2, Zone-I (Sonagaon) of Gosaba water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 179/YAAS/SMD. | 05/06/2021 |  | AVINABA ENGINEERING CONCERN | 2.1 | 2.1 | 0
59 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-2 of Satjelia water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 187/YAAS/SMD. | 11/06/2021 |  | AVINABA ENGINEERING CONCERN | 1.82 | 1.82 | 0
60 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Rectification of 4(Four) Nos Voltage correctional device of BANSRA (Z-1, P/H-2 & 3; Z-2, P/H-1) & mOUKHALI (P/H No. 4) W/S Scheme ( Block- Canning-I) under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1256/SMSD | 25/10/2021 |  | JAGANNATH ENTERPRISE | 0.86 | 0.86 | 0
61 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply , delivery & installation of automatically controlled type chlorinator dosing pump at Jibantala P/H No- 1 of W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1071/SMD | 15/09/2021 |  | JAGANNATH ENTERPRISE | 3.3 | 3.3 | 0
62 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and delivery of submersible pumping machinery as standby for PH-I of Darikrishnanagar w/s scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1097/AE-II/SMD | 24/02/2021 |  | SHIVAM ENTERPRISE | 0.84 | 0.84 | 0
63 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of 20 KVA voltage stabilizer at P.H No.- 3 of Chemaguri W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 831/SMD | 14/07/2021 |  | NITESH MANAGEMENT | 3.27 | 3.27 | 0
64 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches at Basanti in connection with service cyclone YAAS 2021 under SMD, PHE Dte.(PT-D) | Assistant Engineer | Junior Engineer | 260/YAAS/SMSD | 15/06/2021 |  | M/S. S.S. ENTERPRISE | 0.86 | 0.86 | 0
65 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and fitting fixing of electrical accessories & renovation of internal wiring P.H No.-4 of DH W/S scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1378/AE-II/SMD | 23/04/2021 |  | SHIVAM ENTERPRISE | 0.47 | 0.47 | 0
66 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and fitting fixing of electrical renovation system at Mongrajpur PH-1 under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1332/AE-II/SMD | 06/04/2021 |  | SHIVAM ENTERPRISE | 0.24 | 0.24 | 0
67 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing of 20 KVA voltage stabilizer and other allied works at Zone-20 W/S scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1327/AE-II/SMD | 05/04/2021 |  | SHIVAM ENTERPRISE | 0.31 | 0.31 | 0
68 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1171/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
69 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1159/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
70 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to Gosaba Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 287/C/SMSD. | 01/03/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
71 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing & installation of 7.5HP pump motor set at Atkrishnarampur W/S Scheme P.H No.-1 under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 1422/AE-II/SMD | 06/05/2021 |  | SHIVAM ENTERPRISE | 0.23 | 0.23 | 0
72 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing of motor control panel at Khordanala W/S Scheme P.H No.-1 W/S Scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 1432/AE-II/SMD | 10/05/2021 |  | SHIVAM ENTERPRISE | 0.51 | 0.51 | 0
73 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Replacement of pumping machinery and allied work at PH-4 of Dharmatala w/s scheme (Block - Canning -I) under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1067/SMSD | 17/08/2021 |  | ROY & BISWAS ENGG. CO. | 0.79 | 0.79 | 0
74 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 291/A/SMSD.. | 05/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
75 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 51/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
76 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing of pump motor set and Supply-fixing of 80 mm dia NRV at Banibada Belekhali W/S Scheme P.H No.-4 under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 940/SMSD | 09/07/2021 |  | ROY & BISWAS ENGG. CO. | 0.23 | 0.23 | 0
77 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Cap at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1144/SMSD | 03/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
78 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Cap at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1140/SMSD | 03/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
79 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Renovation of Illumination arranagement for OHR No-13 under South 24pgs Mechanical division, PHE Dte. | Assistant Engineer | Junior Engineer | 49-AE-II/SMD | 10/01/2022 |  | SIPRA ENTERPRISE | 0.29 | 0.29 | 0
80 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing of 15 KVA voltage stabilizer and other allied works & repairing of panel at Zone No-13 W/S scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 2261/A/AE-II/SMD | 03/11/2021 |  | SIPRA ENTERPRISE | 0.48 | 0.48 | 0
81 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of automatic chlorinator for Tube Well No.-2 of Ajodhyanagar W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1039/SMSD | 04/08/2021 |  | SIPRA ENTERPRISE | 0.91 | 0.91 | 0
82 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of automatic chlorinator for Tube Well No.-1, of Ajodhyanagar W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1033/SMSD | 04/08/2021 |  | SIPRA ENTERPRISE | 0.91 | 0.91 | 0
83 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches at Basanti in connection with service cyclone YAAS 2021 under SMD, PHE Dte.(PT-F) | Assistant Engineer | Junior Engineer | 290/YAAS/SMSD | 25/06/2021 |  | M/S. S.S. ENTERPRISE | 0.86 | 0.86 | 0
84 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 50/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
85 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, delivery & installation of automatically controlled type chlorinator dosing pump at Deuli Zone-I PH-1 of W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1117/SMD | 27/09/2021 |  | EMCON | 3.3 | 3.3 | 0
86 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 75/YAAS/SMSD | 24/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
87 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different Islands of Gosaba Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 48/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
88 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different Islands of Gosaba Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 46/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
89 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH -1, Zone -I & PH-1 Zone-II of Kachuberia water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | 53-Yaas/SMD | 26/05/2021 |  | DEY ENTERPRISE | 0.95 | 0.95 | 0
90 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH -1, Zone -I & PH-1 Zone-II of Ganga Sagar Mouza water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | 52-Yaas/SMD | 26/05/2021 |  | DEY ENTERPRISE | 1.15 | 1.15 | 0
91 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning of 15KVA voltage stabilizer at PH No-4 of Kumirmari W/S Scheme ( Newly electrified) in SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1257/SMD | 17/11/2021 |  | TAMAL ENTERPRISE | 3.92 | 3.92 | 0
92 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to Gosaba Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 384/A/SMSD | 24/03/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
93 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to Gosaba Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 391/A/SMSD. | 25/03/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
94 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Lumination at Raidighi Hospital in the dist of South 24-Pgs Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | 1191/SMSD | 17/09/2021 |  | DEPALI CONSTRUCTION | 0.6 | 0.6 | 0
95 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to Gosaba Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 392/SMSD. | 25/03/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
96 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 361/SMSD. | 19/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
97 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite granules at Gilarchat & Nandakumarpur W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.(Mathurapur -II Block) | Assistant Engineer | Junior Engineer | 1034/SMSD | 04/08/2021 |  | SIPRA ENTERPRISE | 0.98 | 0.98 | 0
98 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, delivery & installation of automatically controlled diaphragm type chlorinator dosing pump at p.h nO. 2 of Uttar Sultanpur of W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 927/SMD | 12/08/2021 |  | M/S. A.K. BANERJEE | 3.3 | 3.3 | 0
99 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of automatic chlorinator for Tube Well No.-1 of Narayangarh W/S Schemeof Canning-I Block under SMD, PHE Dte | Assistant Engineer | Junior Engineer | 2031/SMD | 15/06/2021 |  | M/S. A.K. BANERJEE | 0.91 | 0.91 | 0
100 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Yard lighting arrangement at PH-1 of Daimond Harbour District Hospital W/S scheme of under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 457/SMD | 23/03/2021 |  | ABHISEK ENGINEERING CONCERN | 2.79 | 2.79 | 0
101 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Yard lighting arragement at PH-2 of Diamond Harbour Minicipality Augmentation water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 735/SMD | 18/06/2021 |  | M.D ENTERPRISE | 1.1 | 1.1 | 0
102 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-3 of Lahiripur water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 177/YAAS/SMD. | 05/06/2021 |  | AVINABA ENGINEERING CONCERN | 2.67 | 2.67 | 0
103 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH-4, Zone-II (Rajapur) of Gosaba water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 185/YAAS/SMD. | 09/06/2021 |  | AVINABA ENGINEERING CONCERN | 2.24 | 2.24 | 0
104 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-2 of Pathankhali water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 189A/YAAS/SMD | 14/06/2021 |  | AVINABA ENGINEERING CONCERN | 1.99 | 1.99 | 0
105 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-2 of Purba Radhanagar water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 180A/YAAS/SMD | 06/06/2021 |  | AVINABA ENGINEERING CONCERN | 1.96 | 1.96 | 0
106 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Rectification of 3(Three) Nos Voltage correction devices of Bhaleya (P/H No. II), Daria (P/H No.II) & Moukhali (P/H No. III) W/S Scheme and 1 (One) no.motor control panel of Bansra (P/H No. II,Z-I) W/S Scheme(Block- Canning -I) Under SMD PHE Dte. | Assistant Engineer | Junior Engineer | 1272/SMSD | 29/01/2021 |  | BHUNIA BUILDERS | 0.6 | 0.6 | 0
107 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing of Chlorine machines installation of the same at Sagar Block under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 696/AE-I/SMD | 29/09/2021 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.68 | 0.68 | 0
108 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 52/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
109 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1168/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
110 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1202/SMSD | 20/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
111 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1158/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
112 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1151/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
113 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 383/A/SMSD. | 24/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
114 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different Islands of Gosaba Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 77/YAAS/SMSD | 24/05/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
115 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to Gosaba Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 387/SMSD. | 24/03/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
116 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 360/SMSD. | 19/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
117 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 287/B/SMSD. | 01/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
118 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 382/SMSD. | 24/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
119 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1190/SMSD | 15/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
120 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1172/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
121 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1142/SMSD | 03/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
122 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Cap at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1143/SMSD | 03/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
123 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1155/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
124 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 76/YAAS/SMSD | 24/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
125 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different Islands of Gosaba Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 49/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
126 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Construction of Temporary water proof Pandal for continuous safe storage of Drinking water pouches at Basanti in connection with service cyclone YAAS 2021 under SMD, PHE Dte.(PT-D) | Assistant Engineer | Junior Engineer | 190/YAAS/SMSD | 04/06/2021 |  | M/S. S.S. ENTERPRISE | 0.86 | 0.86 | 0
127 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different Islands of Gosaba Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 47/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
128 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different Islands of Gosaba Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 41/YAAS/SMSD | 20/05/2021 |  | M/S. S.S. ENTERPRISE | 0.96 | 0.96 | 0
129 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 39/YAAS/SMSD | 20/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
130 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-3 of Amtali water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 186A/YAAS/SMD | 11/06/2021 |  | S.K. ENTERPRISE | 2.8 | 2.8 | 0
131 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite hydrated granules for Pathankhali PH-1W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 531/SMD. | 29/04/2021 |  | M/S. PS & ASSOCIATES | 0.9 | 0.9 | 0
132 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Calcium Hypochlorite granules at PH-2 of Mollapukur W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1386/AE-II/SMD | 23/04/2021 |  | M/S. PS & ASSOCIATES | 0.86 | 0.86 | 0
133 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Replacement of 100A TPN MCCB, 100A Rewirable type fuse unit and other allied works at Kalaria w/s cheme ( p/H No-2, Zone -1) & Moukhali w/s cheme ( P/H No-4) w/s scheme (P/H No-4) w/s cheme south 24 pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1215/SMSD | 30/09/2021 |  | JAGANNATH ENTERPRISE | 0.29 | 0.29 | 0
134 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Installation of automatic chlorinator for Tube Well No.-2 of Budhakhali W/S Scheme under SMD, PHE Dte. (Block- Canning - I) | Assistant Engineer | Junior Engineer | 1066/SMSD | 17/08/2021 |  | SIPRA ENTERPRISE | 0.33 | 0.33 | 0
135 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 317/A/SMSD. | 12/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
136 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 287/A/SMSD. | 01/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
137 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at Basanti Yard water supply scheme under Canning sub-Division for preparedness of cyclonic storm YAAS to maintain uninterrupted drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 172/YASS/SMD | 03/06/2021 |  | DEPALI CONSTRUCTION | 2.77 | 2.77 | 0
138 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 366/A/SMSD.. | 22/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
139 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at BS-II to different Block ( Baruipur, Mathurapur, Sonarpur etc) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 366/A/SMSD... | 22/03/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
140 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Withdrawing, repairing and installation of defective pump motor set at PH No.-1 of Mosat W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1042/AE-II/SMD | 15/02/2021 |  | DIYA ENTERPRISE | 0.76 | 0.76 | 0
141 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-2 of Luxbagan water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 178A/YAAS/SMD | 05/06/2021 |  | AVINABA ENGINEERING CONCERN | 2.8 | 2.8 | 0
142 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1157/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
143 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1152/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
144 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and installation of Automatic Chlorinator for Pump House No. 1 of Sitarampur water supply scheme under South 24pgs Mechanical Division. | Assistant Engineer | Junior Engineer | 840/SMD | 19/07/2021 |  | R.K. CONSTRUCTION | 3.3 | 3.3 | 0
145 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery, installation of computer spare parts for the office of the Executive Engineer, South 24pgs Mechanical Division. | Assistant Engineer | Junior Engineer | 2185/AE-II/SMD | 23/09/2021 |  | WIZARDTECH SOLUTION | 0.82 | 0.82 | 0
146 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Operation and guarding of the electric operated auto/manual control pumping machinery at P.H.No- 2 of Uttar Sultanpur W/S Scheme under south 24 pgs Mechanical Division PHE Dte. (Mandirbazar Block) | Assistant Engineer | Junior Engineer | 3259/SMD. | 26/11/2020 |  | WIZARDTECH SOLUTION | 1.58 | 1.58 | 0
147 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and installation of automatic chlorinator for TW-1, of Bhogali W/S Scheme under south 24 pgs Mechanical Division PHE Dte. (block- Banghar-II) | Assistant Engineer | Junior Engineer | 1056/SMSD | 16/08/2021 |  | WIZARDTECH SOLUTION | 0.97 | 0.97 | 0
148 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and installation of automatically controlled diaphragm type chlorinator dosing pump at PH No-I, Zone-II of Gilarchat W/S Scheme under south 24 pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 1038/SMSD | 10/09/2021 |  | WIZARDTECH SOLUTION | 3.3 | 3.3 | 0
149 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Canning-I & II and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 40/YAAS/SMSD | 20/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
150 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1175/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
151 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1169/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
152 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1200/SMSD | 17/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
153 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1176/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
154 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1173/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
155 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1174/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
156 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at OHR No-25 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 65/YASS/SMD | 26/05/2021 |  | DEY ENTERPRISE | 1.78 | 1.78 | 0
157 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH -2&3 of Purusottampur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 55-Yaas/SMD | 26/05/2021 |  | DEY ENTERPRISE | 1.08 | 1.08 | 0
158 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1153/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
159 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1186/SMSD | 13/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
160 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1156/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
161 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at PH -1&2 of Naraharipur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | 54-Yaas/SMD | 26/05/2021 |  | DEY ENTERPRISE | 1.04 | 1.04 | 0
162 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at OHR No-24 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | 64/YAAS/SMD | 26/05/2021 |  | DEY ENTERPRISE | 1.53 | 1.53 | 0
163 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Cap at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1141/SMSD | 03/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
164 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Cap at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1145/SMSD | 03/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
165 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Providing diesel generator set at BS-I & II under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | 62-Yaas/SMD | 26/05/2021 |  | B.T.PROJECTS PVT.LTD. | 0.48 | 0.48 | 0
166 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Continuation order for servicing & overhauling of different types of air condtioner of different buildings at Ganga Sagar PHE Comples uner SMD PHE Dte. | Assistant Engineer | Junior Engineer | 752/SMD | 21/06/2021 |  | DEPALI CONSTRUCTION | 1.78 | 1.78 | 0
167 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and fitting fixing of electrical accessories & renovation of internal wiring at Zone No-13 W/S scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 2229/A/AE-II/SMD | 21/10/2021 |  | SIPRA ENTERPRISE | 0.84 | 0.84 | 0
168 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply,delivery & installation of automatically controlled diaphragm type chlorinator dosing pump at P/H No-I of Purba Bishnupur W/S Scheme under SMD, PHE Dte | Assistant Engineer | Junior Engineer | 1053/SMD | 14/09/2021 |  | M/S.UTTAM KUMAR CHATTERJEE | 3.3 | 3.3 | 0
169 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and fitting fixing of electrical accessories & renovation of internal wiring P.H No.-1 of Kashinagar W/S scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 561/AE-I/SMD | 04/08/2021 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.89 | 0.89 | 0
170 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Repairing and rewinding of Chlorine dosing machine at Sagar Block South 24 pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 560/AE-I/SMD | 04/08/2021 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.64 | 0.64 | 0
171 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Withdrawing repairing & installation of defective pump motor & repairing of Panel at PH No.-1 of Kashinagar W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 562/AE-I/SMD | 04/08/2021 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.27 | 0.27 | 0
172 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and delivery of Calcium Hypochloride hydrated granules at PH-3 & 4 of Kumirmari w/s scheme under SMD,PHE Dte | Assistant Engineer | Junior Engineer | 1098/SMSD. | 26/08/2021 |  | WIZARDTECH SOLUTION | 0.51 | 0.51 | 0
173 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Providing diesel generator set at PH-1 of Bijoynagar water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 188A/YAAS/SMD | 12/06/2021 |  | AVINABA ENGINEERING CONCERN | 3.37 | 3.37 | 0
174 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply delivery and storage of Electrical switch gear & ancilliaries at BS -II store under SMD PHE Dte. | Assistant Engineer | Junior Engineer | 176/YAAS/SMSD | 02/06/2021 |  | S.P. CONSTRUCTION | 0.86 | 0.86 | 0
175 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply and delivery of gunny bags for emergency carriage of drinking water pouch for Combat YAAS under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 6/YAAS/I/ SMSD | 27/05/2021 |  | S.P. CONSTRUCTION | 0.1 | 0.1 | 0
176 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for supply and delivery of gunny bags for emergency carriage of drinking water pouch for combet YAAS under SMD PHE Dte. | Assistant Engineer | Junior Engineer | 20/YAAS/I/SMSD | 04/06/2021 |  | S.P. CONSTRUCTION | 0.91 | 0.91 | 0
177 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1160/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
178 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & installation of automatic chlorinatorat Kalikatola Tube Well No.-2 , Zone-I of Canning -II Block W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 768/SMSD | 31/05/2021 |  | DEY ENTERPRISE | 0.79 | 0.79 | 0
179 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU shed at Basanti to different places of Basanti Canning and Kultali Block tentative storm situation under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 53/YAAS/SMSD | 21/05/2021 |  | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 0
180 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at BS-II to Gosaba Block under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 392/A/SMSD. | 25/03/2021 |  | M/S. S.S. ENTERPRISE | 0.57 | 0.57 | 0
181 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Installation of departmentally supplied 20 KVA servo motor operated copper wound line voltage corrector at PH-1, Zone-II of Kalaria w/s scheme under SMD PHE Dte. (Block-Canning) | Assistant Engineer | Junior Engineer | 695/SMSD | 19/05/2021 |  | DEPALI CONSTRUCTION | 0.74 | 0.74 | 0
182 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1170/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
183 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply & delivery of Preform at Bottling Plant (Rana Paschim Ramnagar) under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 1154/SMSD | 10/09/2021 |  | J.D.J ENTERPRISE | 0.99 | 0.99 | 0
184 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Electric Bills |  |  | 66/PFMS | 23/02/2022 |  | WBSEDCL | 3.64 | 0 | 0
185 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Electric Bill |  |  | 20/PFMS | 26/04/2022 |  | WBSEDCL | 0.73 | 0 | 0
186 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery , voltage stabilizer, automatic chlorinator and related accessories at Tube Well no.1of Ganga Cheri W/S Scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 2001/SMD. | 30/11/2021 |  | BIJAN ENTERPRISE | 9.8 | 8.36 | 75
187 | SOUTH 24 PARGANAS | null | Providing packaged drinking water, DG sets and allied works at Gosaba Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical Division. | SM/09195 | Disaster | Supply, installation, commissioning and submersible pumping machinery with allied accessories at Tube Well no. 3, Zone-I of Chottokhali Molla Khali W/S Scheme of under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 1088/SMD. | 16/09/2021 |  | JAGANNATH ENTERPRISE | 4.99 | 4.43 | 0
Total | [12 empty] | 274.44 | 250.31 | 91.21