## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (8 Nos. Model-2) (Group-11) | AE SWSD-II |  | 2237/SWD-I | 15/02/2022 |  | SUKALPA NIRMAN | 14.26 | 0 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (31 Nos. Model-6) (Group-6) | AE SWSD-II |  | 2175/SWD-I | 15/02/2022 |  | NIRMAL UDYOG | 82.1 | 0 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 10 Nos. Model-6) (Group-15) |  |  | 2210/SWD-I | 15/02/2022 |  | NILKAMAL BASAK | 31.79 | 0 | 80
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (17 Nos. Model-6) (Group-14) | AE SWSD-II |  | 2200/SWD-I | 15/02/2022 |  | SRIJON ENTERPRISE | 43.11 | 0 | 0
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (9 Nos. Model-6) (Group-17) | AE SWSD-II |  | 2217/SWD-I | 15/02/2022 |  | NIRMAL UDYOG | 21.98 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-5 and 1 No. Model-7) (Group-13) | AE SWSD-II |  | 2258/SWD-I | 15/02/2022 |  | SOMNATH ENTERPRISE | 5.48 | 0 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 2 Nos. Model-6) (Group-1) | AE SWSD-II |  | 2252/SWD-I | 15/02/2022 |  | ADRIK ENTERPRISE | 7.95 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-3 and 2 Nos. Model-4) (Group-12) | AE SWSD-II |  | 2268/SWD-I | 15/02/2022 |  | SANJAY MIDDEY | 5.06 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR II block under South 24-Parganas W/S Division-I, PHE Dte. (21 Nos. Model-6) (Group-16) | AE SWSD-II |  | 2190/SWD-I | 15/02/2022 |  | RAJLAXMI CONSTRUCTION | 51.02 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (22 Nos. Model-6) (Group-2) |  |  | 2188/SWD-I | 15/02/2022 |  | MANAS CHATTERJEE | 38.1 | 0 | 100
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Material Requisition To Resource Division |  |  | 2103/SWD-I | 11/02/2022 |  | Resource Division | 321.23 | 0 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (33 Nos. Model-6) (Group-5) | AE SWSD-II | JE2 | 2171/SWD-I | 15/02/2022 |  | MS SARADA UDYOG | 38.79 | 0 | 70
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-7 and 2 Nos. Model-8) (Group-3) | AE SWSD-II | JE2 | 2225/SWD-I | 15/02/2022 |  | M/S. FAIZUL HAQUE BISWAS | 17.54 | 0 | 80
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-6) (Group-9) | AE SWSD-II | JE2 | 2231/SWD-I | 15/02/2022 |  | ELECTRONIC SURVILLANCE | 13.94 | 0 | 10
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 6 Nos. Model-6) (Group-10) | AE SWSD-II | JE4 | 2223/SWD-I | 15/02/2022 |  | J. ENTERPRISE | 20.08 | 0 | 98
16 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRANGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 209 NOS IN BISHNUPUR-I & II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10113 | School | Water Supply arrangement for AWCs as per different models of work under BISHNUPUR I block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-7 and 14 Nos. Model-6) (Group-4) | AE SWSD-II | JE1 | 2203/SWD-I | 15/02/2022 |  | NIRMAL UDYOG | 37.02 | 0 | 97
Total | [12 empty] | 749.44 | 0 | 0