## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (31 Nos. Model-6) (Group-39) | AE SWSD-I |  | 2176/SWD-I | 15/02/2022 |  | KARUNAMOYEE ENTERPRISE | 82.05 | 0 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-8 and 3 Nos. Model-9) (Group-44) | AE SWSD-I |  | 2249/SWD-I | 15/02/2022 |  | M/S. SREEJIT ENTERPRISE | 10.96 | 0 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (18 Nos. Model-6) (Group-49) | AE SWSD-I |  | 2198/SWD-I | 15/02/2022 |  | SUKUMAR DEBNATH | 47.65 | 0 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-5) (Group-48) | AE SWSD-I |  | 2240/SWD-I | 15/02/2022 |  | S.M ENTERPRISE | 13.45 | 0 | 0
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-4 and 6 Nos. Model-5) (Group-47) | AE SWSD-I |  | 2233/SWD-I | 15/02/2022 |  | SOMBHUNATH BHATTACHARJEE | 15.31 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-3) (Group-36) | AE SWSD-I |  | 2247/SWD-I | 15/02/2022 |  | JOY GURU TRADING | 12.68 | 0 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (13 Nos. Model-3) (Group-46) | AE SWSD-I |  | 2219/SWD-I | 15/02/2022 |  | TIYASHA ENTERPRISE | 23.53 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-1 and 10 Nos. Model-2) (Group-45) | AE SWSD-I |  | 2224/SWD-I | 15/02/2022 |  | MOUMITA ENTERPRISE | 19.35 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2) (Group-35) | AE SWSD-I |  | 2278/SWD-I | 15/02/2022 |  | S.M ENTERPRISE | 5.34 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-8) (Group-52) | AE SWSD-I |  | 2260/SWD-I | 15/02/2022 |  | SUKUMAR DEBNATH | 8.09 | 0 | 0
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-7) (Group-41) | AE SWSD-I |  | 2226/SWD-I | 15/02/2022 |  | RAMASISH ENTERPRISE | 18.65 | 0 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-2) (Group-54) | AE SWSD-I |  | 2248/SWD-I | 15/02/2022 |  | JOY GURU TRADING | 12.47 | 0 | 0
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-4 and 2 Nos. Model-5) (Group-37) | AE SWSD-I |  | 2235/SWD-I | 15/02/2022 |  | SANJAY MIDDEY | 15.04 | 0 | 0
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-7) (Group-42) | AE SWSD-I |  | 2230/SWD-I | 15/02/2022 |  | MS A M ENTERPRISE PROP GULSAN SARWAR | 15.87 | 0 | 0
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (29 Nos. Model-6) (Group-40) | AE SWSD-I |  | 2179/SWD-I | 15/02/2022 |  | PROJECT AND MAINTENANCE | 76.73 | 0 | 0
16 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-6) (Group-55) | AE SWSD-I |  | 2244/SWD-I | 15/02/2022 |  | SNEHA CONSTRUCTION | 13.18 | 0 | 0
17 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (13 Nos. Model-7) (Group-51) | AE SWSD-I |  | 2208/SWD-I | 15/02/2022 |  | M/S. S.D. CONSTRUCTION | 34.33 | 0 | 0
18 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-8) (Group-43) | AE SWSD-I |  | 2275/SWD-I | 15/02/2022 |  | GOUTAM MAZUMDER | 5.36 | 0 | 0
19 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (10 Nos. Model-6) (Group-38) | AE SWSD-I |  | 2214/SWD-I | 15/02/2022 |  | AYUSH ENTERPRISE | 25.8 | 0 | 0
20 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (16 Nos. Model-6) (Group-50) | AE SWSD-I |  | 2202/SWD-I | 15/02/2022 |  | NILKAMAL BASAK | 41.91 | 0 | 0
21 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-9) (Group-53) | AE SWSD-I |  | 2229/SWD-I | 15/02/2022 |  | ELECTRONIC SURVILLANCE | 16.3 | 0 | 0
22 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Material Requisition To Resource Division |  |  | 2102/SWD-I | 11/02/2022 |  | Resource Division | 135.93 | 0 | 0
Total | [12 empty] | 649.99 | 0 | 0