## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (BODRE GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2 and 1 No. Model-7) (Group-110) | AE HQ-I |  | 2265/SWD-I | 15/02/2022 |  | M/S. JAYDEEP DASGUPTA | 8.01 | 4.34 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (CH-I GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (4 Nos. Model-2 and 1 No. Model-3) (Group-99) | AE HQ-I |  | 2256/SWD-I | 15/02/2022 |  | MANIRUL ISLAM | 8.04 | 8.04 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (BODRE GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (28 Nos. Model-6) (Group-112) | AE HQ-I |  | 2182/SWD-I | 15/02/2022 |  | M/S. JAYDEEP DASGUPTA | 74.11 | 73.33 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (CH-I GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (25 Nos. Model-6 and 3 Nos. Model-7) (Group-101) | AE HQ-I |  | 2181/SWD-I | 15/02/2022 |  | MUNNA AGROTECH ENTERPRISE | 74.16 | 73.22 | 0
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (CH-I GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-6 and 1 No. Model-7) (Group-100) | AE HQ-I |  | 2280/SWD-I | 15/02/2022 |  | NARAYAN ENTERPRISE | 5.33 | 5.26 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (BODRE GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (9 Nos. Model-7) (Group-113) | AE HQ-I |  | 2216/SWD_I | 15/02/2022 |  | G S CONSTRUCTION AND CO | 24.08 | 23.87 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (BODRE GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (4 Nos. Model-6) (Group-111) | AE HQ-I |  | 2254/SWD-I | 15/02/2022 |  | ELECTRONIC SURVILLANCE | 10.6 | 10.23 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (DURGAPUR GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-6) (Group-96) | AE HQ-I |  | 2246/SWD-I | 15/02/2022 |  | ELECTRONIC SURVILLANCE | 13.25 | 12.83 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (CH-II GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (21 Nos. Model-6) (Group-104) | AE HQ-I |  | 2191/SWD-I | 15/02/2022 |  | CHANDAN ROY | 55.59 | 55.08 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (TARDAH GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-6) (Group-114) |  |  | 2227/SWD-I | 15/02/2022 |  | RAMASISH ENTERPRISE | 18.54 | 10.54 | 60
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BHANGAR-I block (DURGAPUR GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-2 and 1 No. Model-7) (Group-95) | AE HQ-I |  | 2271/SWD-I | 15/02/2022 |  | NARAYAN ENTERPRISE | 6.24 | 5.69 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (SANKSAHAR GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (4 Nos. Model-6 and 1 No. Model-7) (Group-109) | AE HQ-I |  | 2243/SWD-I | 15/02/2022 |  | TOJO ENTERPRISE | 12.79 | 12.79 | 0
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (TARDAH GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (32 Nos. Model-6) (Group-115) | AE HQ-I |  | 2291/SWD-I | 16/02/2022 |  | M/S. S.S. ENTERPRISE | 83.71 | 83.71 | 100
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (SANKSAHAR GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (18 Nos. Model-6) (Group-108) | AE HQ-I |  | 2199/SWD-I | 15/02/2022 |  | MUNNA AGROTECH ENTERPRISE | 47.27 | 47.27 | 0
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (TARDAH GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-6 and 1 No. Model-7) (Group-116) | AE HQ-I |  | 2253/SWD-I | 15/02/2022 |  | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 9.49 | 9.49 | 100
16 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Material Requisition To Resource Division |  |  | 2104/SWD-I | 11/02/2022 |  | Resource Division | 391.25 | 0 | 0
17 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC) 225 NOS IN DURGAPUR, CH-I, CH-II, SANKSAHAR, BODRE AND TARDAH GPS OF BHANGAR-I BLOCK (CANNING PURBA A.C.) 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PH | SM/10118 | School | Water Supply arrangement for AWCs as per different models of work under BHANGAR-I block (DURGAPUR GP of CANNING PURBA AC) under South 24-Parganas W/S Division-I, PHE Dte. (19 Nos. Model-6) (Group-97) | AE HQ-I,AE HQ-II | JE-3 | 2196/SWD-I | 15/02/2022 |  | S.P. CONSTRUCTION | 48.31 | 0 | 100
Total | [12 empty] | 890.76 | 435.67 | 48.91