## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Construction of 02 (Two) nos. chlorination room at GOBINDAPUR of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD | JE-1 | 1410/SWD-I | 22/09/2022 |  | J H K ENTERPRISE | 11.01 | 0 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Material Requisition To Resource Division |  |  | 292/SWD-I | 24/04/2023 |  | Resource Division | 45.97 | 0 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Preparation and submission of Detailed Project Report of GOBINDAPUR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | 1962/SWD-I | 21/01/2022 |  | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GOBINDAPUR PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010741] | AE BSD |  | 1685/SWD-I | 01/11/2022 |  | SIMPLEX DRILLING COMPANY | 42.98 | 36.72 | 90
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-423 | 16/12/2023 |  | WBSEDCL | 15.69 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | 545/SMD | 21/02/2023 |  | DEBJYOTI BASU | 19.37 | 0 | 90
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at GOBINDAPUR Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1510) | AE BSD | JE-1 | 1737/SWD-I | 10/08/2023 |  | TAAS ENTERPRISE | 511.22 | 0 | 80
Total | [12 empty] | 648.99 | 39.48 | 6.08