## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009671] | AE BSD |  | 1230/SWD-I | 07/09/2022 |  | DIPALI CONSTRUCTION | 20.07 | 0 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Harendrapally water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | 441/SMD | 17/02/2023 |  | K.S.P ENTERPRISE | 13 | 0 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD |  | 3674/SWD-I | 29/03/2023 |  | DIPALI CONSTRUCTION | 2.2 | 0 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Material Requisition To Resource Division |  |  | 294/SWD-I | 25/04/2023 |  | Resource Division | 7.02 | 0 | 0
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of BARUIPUR Block for under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/009671] | AE BSD | JE-2 | 323/SWD-I | 11/01/2024 |  | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 18.15 | 18.15 | 100
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD | JE RWS,JE-1,JE-2 | 324/SWD-I | 11/01/2024 |  | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 2.11 | 2.11 | 100
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) |  |  | BP-2024-25-793 | 25/10/2024 |  | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Charges for new service connection at Harendrapally pump house-I |  |  | BP-2024-25-72 | 16/05/2024 |  | WBSEDCL | 13.08 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Construction of chlorination room at HARENDRAPALLY of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009671] | AE BSD | JE-2 | 1787\SWD-I | 07/11/2022 |  | SANJAY ENTERPRISE | 5.8 | 0 | 100
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Harendrapally ( Atniramish, J.L-141) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 910) | AE BSD | JE-2 | 1842/SWD-I | 11/11/2022 |  | A. G. ENTERPRISE | 121.8 | 63.91 | 75
Total | [12 empty] | 204.58 | 84.17 | 41.14