## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Preparation and submission of Detailed Project Report of "BHARU RAMKRISHNAPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | 463/SWD-I | 24/05/2022 |  | GEO SOLUTION | 2.55 | 0 | 100
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for BHARU RAMKRISHNAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE2 | 918/SWD-I | 19/07/2022 |  | SIMPLEX DRILLING CO. | 14.19 | 0 | 100
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of BHARU RAMKRISHNAPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11497) | AE SWSD-II | JE2 | 2575/SWD-I | 10/01/2023 |  | OHAB SK. | 6.05 | 0 | 1
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BHARU RAMKRISHNAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011211] | AE SWSD-II | JE2 | 2974/SWD-I | 17/02/2023 |  | SIMPLEX DRILLING COMPANY | 1.58 | 0 | 100
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bharu Ramkrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | 472/SMD | 20/02/2023 |  | AHALYA ENGINEERING WORKS | 26.76 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Material Requisition To Resource Division |  |  | 3249/SWD-I | 01/03/2023 |  | Resource Division | 59 | 0 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Material Requisition To Resource Division |  |  | 1583/SWD-I | 17/10/2022 |  | Resource Division | 5.25 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-126 | 17/07/2023 |  | WBSEDCL | 7.84 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BHARU RAMKRISHNAPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011211] | AE SWSD-II | JE2 | 3106/SWD-I | 24/02/2023 |  | MOULI CONSTRUCTION | 15.89 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Development of low land and temporary aproach road for entering Tubewell site for proposed BHARU RAMKRISHNAPUR Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011211] | AE SWSD-II | JE2 | 3704/SWD-I | 30/03/2023 |  | SIMPLEX DRILLING COMPANY | 0.6 | 0 | 100
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, approach road and land development for BHARU RAMKRISHNAPUR PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/11497) | AE SWSD-II | JE2 | 3363/SWD-I | 26/07/2024 |  | ODISSI INNOVATIONS | 132.11 | 0 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Land Development at 1st Tubewell site including development of approach road under Bharu Ramkrishnapur Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns Water Supply Division-I, PHE Dte. (TSM/011211) | AE SWSD-II | JE2 | 435/SWD-I | 22/01/2024 |  | ROYAL CONSTRUCTION | 6.5 | 0 | 50
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-452 | 09/01/2024 |  | WBSEDCL | 2.36 | 0 | 0
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed BHARU RAMKRISHNAPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 853] | AE SWSD-II | JE2 | 1391/SWD-I | 21/09/2022 |  | ODISSI INNOVATIONS ENGINEERS PVT. LTD. | 132.6 | 0 | 90
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11497 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | 1377/SWD-I | 12/07/2023 |  | CONCORD PROJECTS PVT. LTD. | 8.79 | 0 | 60
Total | [12 empty] | 422.07 | 0 | 0