## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Preparation and submission of Detailed Project Report of BELGACHHI Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | 1937/SWD-I | 27/01/2022 |  | GEO SOLUTION | 2.76 | 0 | 100
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Material Requisition To Resource Division |  |  | 294/SWD-I | 25/04/2023 |  | Resource Division | 14.96 | 0 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at BELEGACHI Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1604) | AE BSD |  | 2148/SWDI | 08/12/2022 |  | M/S. S.S. ENTERPRISE | 524.03 | 0 | 50
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for BELEGACHI PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD | JE RWS,JE-2 | 1196/SWD-I | 02/09/2022 |  | VISHAL CONSTRUCTION CO. | 25.99 | 0 | 100
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Belegachi at Baruipur Block for under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-2 | 2202/SWD-I | 13/12/2022 |  | M/S. TORSA ENTERPRISE | 7.82 | 0 | 100
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of BELEGACHI PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011099] | AE BSD | JE RWS,JE-2 | 2110/SWD-I | 30/08/2023 |  | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 0 | 100
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) |  |  | BP-2024-25-792 | 25/10/2024 |  | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.34] |  |  | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 0.68 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BP-2023-24-611 | 28/03/2024 |  | WBSEDCL | 8.73 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Charges for New service connection at Pump house no-2 of Belegachi water supply scheme.(Baruipur Block) |  |  | BP-2024-25-397 | 27/09/2024 |  | WBSEDCL | 4.19 | 0 | 0
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Belegachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | 3928/SMD | 30/12/2022 |  | M/S.UTTAM KUMAR CHATTERJEE | 22.36 | 0 | 80
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Belegachhi water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | Assistant Engineer | Junior Engineer | 387/SMSD | 19/03/2025 |  | ASKWORK INFRASTRUCTURES PRIVATE LIMITED | 0.79 | 0 | 0
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Belegachi W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11771) | Assistant Engineer | Junior Engineer | 1443/SMSD | 22/10/2024 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.91 | 0 | 100
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Belegachi W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11771) | Assistant Engineer | Junior Engineer | 1442/SMSD | 22/10/2024 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.58 | 0 | 100
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based BELEGACHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 p | SM/11771 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Belegachi W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11771) | Assistant Engineer | Junior Engineer | 1444/SMSD | 22/10/2024 |  | M/S.UTTAM KUMAR CHATTERJEE | 0.91 | 0 | 100
Total | [12 empty] | 619.18 | 0 | 0