## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for PURBO BEGAMPUR (ZONE-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD |  | 1192/SWD-I | 02/09/2022 |  | TAPAS KUMAR GIRI | 40.13 | 18.94 | 100
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Begampur (Zone-I) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | 2207/SWD-I | 13/12/2022 |  | PRAGATI CONSTRUCTION AND CO. | 11.51 | 0 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Preparation and submission of Detailed Project Report of BEGAMPUR(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | 1951/SWD_I | 27/01/2022 |  | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Preparation and submission of Detailed Project Report of SITAKUNDU(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 1951/SWD-I | 27/01/2022 |  | MS R. DUTTA AND CO | 2.76 | 0 | 100
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Material Requisition To Resource Division |  |  | 294/SWD-I | 25/04/2023 |  | Resource Division | 12.85 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-19 | 15/05/2023 |  | WBSEDCL | 6.66 | 0 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Construction of boundary walls including development of land and other allied works for Ground water based PURBA BEGAMPUR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11784) |  |  | 1249/SWD-I | 13/03/2024 |  | SRIJON ENTERPRISE | 43.44 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Construction of Platform for providing FHTC for Ground Water Based PURBA BEGAMPUR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11784) |  |  | 3215/SWD-I | 18/07/2024 |  | SRIJON ENTERPRISE | 36.54 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-521 | 17/02/2024 |  | WBSEDCL | 17.79 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-435 | 27/12/2023 |  | WBSEDCL | 4 | 0 | 0
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Road restoration Construction of road mom Kanlokhal Bazar lo Begampur Colony Ghalonika Bridge |  |  | BP-2024-25-790 | 25/10/2024 |  | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.5 | 0 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Purba Begampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | 3925/SMD | 30/12/2022 |  | M/S. S.R. ENTERPRISE | 22.37 | 0 | 45
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at BEGAMPUR (ZONE-I) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1967) | AE BSD | JE-1 | 2149/SWD-I | 08/12/2022 |  | GHOSH ENTERPRISE | 557.87 | 451.71 | 90
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PURBA BEGAMPUR [Zone-I] PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11748] | AE BSD | JE-1 | 1290/SWD-I | 15/03/2024 |  | TAPAS KUMAR GIRI | 4.41 | 0 | 100
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Purba Begampur (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11784) | Assistant Engineer | Junior Engineer | 78/SMSD | 17/01/2025 |  | M/S. S.R. ENTERPRISE | 0.91 | 0 | 0
16 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based PURBA BEGAMPUR ZONE - I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns distri | SM/11784 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Purba Begampur (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11784) | Assistant Engineer | Junior Engineer | 77/SMSD | 17/01/2025 |  | M/S. S.R. ENTERPRISE | 0.58 | 0 | 0
Total | [12 empty] | 767.06 | 473.41 | 61.72