## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SHIBPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 1748/AD | 15/06/2022 |  | M/S R.DUTTA & CO. | 4.54 | 4.54 | 100
2 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Phase-B) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 250] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 11557/AD | 17/02/2023 |  | R.P. ENTERPRISE | 176.39 | 0 | 0
3 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Shibpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | 3818/SMD | 29/12/2022 |  | MAHAMAYA ENTERPRISE | 9.63 | 0 | 0
4 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibpur (Part-B) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 41/KSD | 27/04/2023 |  | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 0
5 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Material Requisition To Resource Division |  |  | 3081/AD | 28/09/2023 |  | Resource Division | 0.6 | 0 | 0
6 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Sibpur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 969/AD | 12/02/2024 |  | M/S ASHA ENGINEERING | 9.66 | 0 | 0
7 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2022 to 30.11.2023. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | 562/KSD | 02/12/2022 |  | SARADA CONSTRUCTION | 4.8 | 4.33 | 0
8 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2024 to 31.05.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | 410/KSD | 27/02/2024 |  | SARADA CONSTRUCTION | 1.2 | 1.08 | 0
9 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.06.2024 to 31.08.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | 982/KSD | 27/05/2024 |  | SARADA CONSTRUCTION | 1.2 | 1.16 | 0
10 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2023 to 29.02.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | 713/KSD | 30/11/2023 |  | SARADA CONSTRUCTION | 1.2 | 1.12 | 0
11 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of Rising Main, Platform, Road Restoration and Y junction for Augmentation of Shibpur (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-I) (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 3188/AD | 31/07/2024 |  | BIMALENDU GIRI | 40.92 | 0 | 0
12 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 938/KSD | 19/12/2023 |  | M/S B. ENTERPRISE | 0.16 | 0.16 | 100
13 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Providing support services for data mapping of available data within command area for preparation of GMIS of Shibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 467/KSD | 22/09/2023 |  | INDRANIL DUTTA & ASSOCIATES | 3.8 | 3.8 | 100
14 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Shibpur W/S Scheme, Block - Namkhana, for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 4092/AD | 03/10/2024 |  | MEHAI TECHNOLOGY LIMITED | 19.43 | 0 | 100
15 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Material Requisition To Resource Division |  |  | 1779/AD | 27/03/2024 |  | Resource Division | 37.58 | 0 | 0
16 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Material Requisition To Resource Division |  |  | 643/AD | 30/01/2024 |  | Resource Division | 3.38 | 0 | 0
17 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of Platform, rising main and Road Restoration for Augmentation of Shibpur (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 3420/AD | 21/08/2024 |  | BIMALENDU GIRI | 58.17 | 8.57 | 30
18 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.09.2024 to 30.11.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | 1255/KSD | 28/08/2024 |  | SARADA CONSTRUCTION | 1.2 | 1.07 | 0
19 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2024 to 28.02.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | 1654/KSD | 26/11/2024 |  | SARADA CONSTRUCTION | 1.2 | 1.13 | 0
20 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2025 to 31.05.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | 350/KSD | 27/02/2025 |  | SARADA CONSTRUCTION | 1.2 | 0.74 | 0
21 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Repairing of Pump House and Boundary wall at 1st Tube well site of Sibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 1980/KSD | 23/12/2024 |  | USHA ENTERPRISE | 2.43 | 0 | 98
22 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Repairing of Pump House and Boundary wall at 2nd Tube well site of Sibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 1981/KSD | 23/12/2024 |  | USHA ENTERPRISE | 1.81 | 0 | 95
Total | [12 empty] | 380.99 | 28.18 | 7.4