## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for GARANBERIA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | 1779/SWD-I | 07/11/2022 |  | MOMINUL BISWAS | 24.44 | 24.44 | 100
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for GARANBERIA PWSS at headwork site & 2nd Tubewell site of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12206] | AE HQ-I |  | 2809/SWD-I | 02/02/2023 |  | MOMINUL BISWAS | 3.13 | 3.13 | 100
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Material Requisition To Resource Division |  |  | 287/SWD-I | 24/04/2023 |  | Resource Division | 11.8 | 0 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Material Requisition To Resource Division |  |  | 1007/SWD- I | 09/06/2023 |  | Resource Division | 7.06 | 0 | 0
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Payment of Electric Bill for new service connection under SMD PHE Dte. |  |  | BP-2023-24-28 | 17/05/2023 |  | WBSEDCL | 2.84 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-181 | 02/08/2023 |  | WBSEDCL | 7.31 | 0 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Payment of Electric Bill for new service connection under SMD PHE Dte. |  |  |  | 04/05/2023 |  | WBSEDCL | 2.9 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-181 | 02/08/2023 |  | WBSEDCL | 0.05 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.45] |  |  | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 53.13 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Construction of 200 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Garanberia Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 1146] | AE HQ-I | JE-4 | 3566/SWD-I | 22/03/2023 |  | SRI RAM CONSTRUCTION | 355.71 | 159.13 | 60
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of GARANBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12206) | AE HQ-I | JE-4 | 4237/SWD-I | 30/09/2024 |  | SRI RAM CONSTRUCTION | 81.81 | 0 | 30
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | GARANBARIA piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12206 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Garanbearia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | 231/SMD | 24/01/2023 |  | B.T.PROJECTS PVT.LTD. | 23.28 | 22.16 | 100
Total | [12 empty] | 573.46 | 208.86 | 36.42