## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply of water through pipe line connection at BL & LRO Basanti office from existing pipe line of Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | 1180/CSD | 15/12/2020 |  | A.P. CONSTRUCTION | 0.65 | 0 | 0
2 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 11666/AD | 20/02/2023 |  | SARKAR CONSTRUCTION | 7.11 | 0 | 0
3 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Basanti Zone-I water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | 292/SMD | 03/02/2023 |  | SRI KRISHNA NIRMAN | 11.69 | 0 | 0
4 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 506/AD | 11/05/2023 |  | A.P. CONSTRUCTION | 13.02 | 0 | 0
5 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Inter connection in between the replacement tubewell towards distribution system for Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-1) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 1205/CSD | 10/11/2023 |  | SUSHANTA MANDAL | 1.06 | 0 | 0
6 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | 10941/AD | 06/02/2023 |  | INDRANIL DUTTA & ASSOCIATES | 7.25 | 0 | 99
7 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Material Requisition To Resource Division |  |  | 1053/AD | 15/06/2023 |  | Resource Division | 16.16 | 0 | 0
8 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Material Requisition To Resource Division |  |  | 227/AD | 24/04/2023 |  | Resource Division | 110.78 | 0 | 0
9 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Material Requisition To Resource Division |  |  | 3042/AD | 28/09/2023 |  | Resource Division | 94.19 | 0 | 0
10 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 10216/AD | 19/01/2023 |  | SNEHA CONSTRUCTION | 58.47 | 0 | 36
11 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Basanti (Zone-1) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | 956/SMD | 04/04/2023 |  | M/S. S.R. ENTERPRISE | 29.05 | 0 | 30
12 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 11664/AD | 20/02/2023 |  | LASKAR CONSTRUCTION | 7.04 | 0 | 98
13 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 11665/AD | 20/02/2023 |  | SUJOY SADHUKHAN | 6.73 | 0 | 98
14 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Pipe line connection from Petrol Pump of Rambabu to basanti Chowmatha TV Relay Centre at Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 1129/CSD | 30/10/2023 |  | KAYAL ENTERPRISE | 1.62 | 0 | 100
15 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Charges for service connection at Pump house no- 2 of Basanti Aug (Z-I) |  |  | BP-2024-25-113 | 14/06/2024 |  | WBSEDCL | 10.42 | 0 | 0
16 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Restoration of Basanti Goran Bose Ganga Mela block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BP-2024-25-624 | 30/09/2024 |  | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 49.87 | 0 | 0
17 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Restoration ofChurchgate Chandur More Road block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BP-2024-25-623 | 30/09/2024 |  | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 5.53 | 0 | 0
18 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | 1659/AD | 20/07/2023 |  | M/S PATH MAKERS | 575.77 | 0 | 35
19 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-1 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 114/SMSD | 22/01/2025 |  | M/S. S.R. ENTERPRISE | 0.59 | 0 | 0
20 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-3 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 115/SMSD | 22/01/2025 |  | M/S. S.R. ENTERPRISE | 0.59 | 0 | 0
21 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1,2 & 3 of Basanti Aug (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15053) | Assistant Engineer | Junior Engineer | 1274/SMSD | 12/09/2024 |  | M/S. S.R. ENTERPRISE | 0.87 | 0 | 0
22 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & delivery of Actuator Valve at Pump House no-1 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 118/SMSD | 22/01/2025 |  | M/S. S.R. ENTERPRISE | 0.99 | 0 | 0
23 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 117/SMSD | 22/01/2025 |  | M/S. S.R. ENTERPRISE | 0.85 | 0 | 0
24 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 116/SMSD | 22/01/2025 |  | M/S. S.R. ENTERPRISE | 0.85 | 0 | 0
25 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & delivery of Actuator Valve at Pump House no-3 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 119/SMSD | 22/01/2025 |  | M/S. S.R. ENTERPRISE | 0.99 | 0 | 0
26 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Basanti (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 1278/SMSD | 12/09/2024 |  | M/S. S.R. ENTERPRISE | 0.85 | 0 | 100
27 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & delivery of Actuator Valve at Pump House no-2 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 1279/SMSD | 12/09/2024 |  | M/S. S.R. ENTERPRISE | 0.99 | 0 | 100
28 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-2 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer | Junior Engineer | 1277/SMSD | 12/09/2024 |  | M/S. S.R. ENTERPRISE | 0.59 | 0 | 100
Total | [12 empty] | 1014.55 | 0 | 0