## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Ramdhari ( Zone-27) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | 946/SMD | 04/04/2023 |  | ORIENTAL ENGINEERING CO. | 44.52 | 0 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based RAMDHARI Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 1181/SWD-I | 01/09/2022 |  | ASTER CONSULTANCY | 3.04 | 0 | 100
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Material Requisition To Resource Division |  |  | 295/SWD-I | 25/04/2023 |  | Resource Division | 23.39 | 0 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMDHARI MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2971] [TSM/018366] | AE BSD | JE-1 | 97/SWD-I | 10/04/2023 |  | TANMOY ROY CHOWDHURY | 396.58 | 0 | 80
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Construction of Pump house cum Chlorine room (Four nos.) at RAMDHARI piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/15337) |  |  | 4306/SWD-I | 04/10/2024 |  | ALISHA CONSTRUCTION | 19.94 | 0 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.33] |  |  | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 4.06 | 0 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) |  |  | BP-2024-25-778 | 23/10/2024 |  | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. |  |  | BP-2024-25-332 | 24/09/2024 |  | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 65 | 0 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Sinking of 04 (Four) nos. Rig Ground bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for RAMDHARI PWSS of Baruipur Block under South 24 Pgns. W/S Division-I, PHE Dte. (SM/15337) | AE BSD | JE-1 | 3753/SWD-I | 28/08/2024 |  | ASIT PRAMANIK | 63.36 | 0 | 50
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-4 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | Assistant Engineer | Junior Engineer | 701/SMSD | 15/05/2025 |  | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at 2 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | Assistant Engineer | Junior Engineer | 420/SMSD | 20/03/2025 |  | ORIENTAL ENGINEERING CO. | 0.92 | 0 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at 1 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | Assistant Engineer | Junior Engineer | 419/SMSD | 20/03/2025 |  | ORIENTAL ENGINEERING CO. | 0.92 | 0 | 0
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-2,3 & 4 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | Assistant Engineer | Junior Engineer | 399/SMSD | 19/03/2025 |  | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | Assistant Engineer | Junior Engineer | 700/SMSD | 15/05/2025 |  | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | Assistant Engineer | Junior Engineer | 398/SMSD | 19/03/2025 |  | ORIENTAL ENGINEERING CO. | 0.76 | 0 | 0
16 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Charges for new service connection at pump house no- 3 of Ramdhari water supply scheme ( Baruipur Block) |  |  |  | 18/06/2025 |  | WBSEDCL | 4.54 | 0 | 0
17 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Charges for new service connection at pump house no-4 of Ramdhari (OHR Zone-27) water supply scheme (Baruipur Block) |  |  |  | 19/05/2025 |  | WBSEDCL | 4.02 | 0 | 0
18 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based RAMDHARI (ZONE-27) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/15337 | Augmentation | Charges for new service connection at pump house no-2 of Ramdhari water supply scheme (Baruipur Block) |  |  |  | 18/06/2025 |  | WBSEDCL | 4.88 | 0 | 0
Total | [12 empty] | 639.11 | 0 | 0