## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | SM/15474 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division |  | 5725/AD | 31/01/2022 |  | SUPRITI ENTERPRISE | 3.37 | 0 | 100
2 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | SM/15474 | Augmentation | Dismantling and restoration of concrete village road for laying pipe line and Constriction of an steel structure for khal crossing at Zone-X of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | 3059/AD | 13/07/2022 |  | DIPTI ENTERPRISE | 8.85 | 0 | 100
3 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | SM/15474 | Augmentation | Providing FHTC including parallel distribution pipeline at Zone- X of Mathurapur -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | 12720/AD | 14/03/2023 |  | R.S.CONSTRUCTION CO. | 77.04 | 0 | 60
4 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | SM/15474 | Augmentation | Repairing of pump house-1 including boundary wall and approach road and plinth protection at Krishnarampur W/S Scheme, modified as Zone- X of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | 434/RSD | 08/01/2024 |  | SUKUMAR HALDAR | 4.63 | 0 | 100
5 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | SM/15474 | Augmentation | Material Requisition To Resource Division |  |  | 245/AD | 15/01/2024 |  | Resource Division | 5.01 | 0 | 0
6 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-X, KRISHNARAMPUR PWSS, MATHURAPUR-I BLOCK FOR PROVIDING FHTC TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION UNDER MEGA SURFACE BASED WATER SUPPLY CSHEME FOR FALTA MATHURAPUR UNDER ALIPORE DIVISION P | SM/15474 | Augmentation | Laying distribution system of piped water supply at Zone- X of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | 4204/AD | 23/10/2024 |  | R.S.CONSTRUCTION CO. | 30.57 | 0 | 0
Total | [12 empty] | 129.48 | 0 | 0