## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI | SM/15505 | Augmentation | Material Requisition To Resource Division |  |  | 2914/AD | 20/09/2023 |  | Resource Division | 13.83 | 0 | 0
2 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI | SM/15505 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- V of Mathurapur-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 4138 ] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | 498/AD | 11/05/2023 |  | JAL PRAVAHIKA PVT. LTD. | 561.15 | 0 | 41
3 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI | SM/15505 | Augmentation | Material Requisition To Resource Division |  |  | 249/AD | 15/01/2024 |  | Resource Division | 8.36 | 0 | 0
4 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI | SM/15505 | Augmentation | Laying of additional Pipe Line at Zone - V of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer1, Raidghi Sub Division | 4660/AD | 20/11/2024 |  | HARIDAS DUTTA | 16.64 | 0 | 2
5 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM OF ZONE-V, MATHURAPUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR UNDER ALIPORE DI | SM/15505 | Augmentation | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | 2575/AD | 03/06/2025 |  | SOURAV DEBNATH | 5.4 | 0 | 0
Total | [12 empty] | 605.38 | 0 | 0