## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | 4778/AD | 19/12/2023 |  | Resource Division | 36.29 | 0 | 0
2 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 2264/AD | 14/08/2023 |  | SARADA CONSTRUCTION | 61.08 | 0 | 60
3 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 819/AD | 05/02/2024 |  | S.M. ENTERPRISE | 30.06 | 0 | 0
4 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 511/AD | 25/01/2024 |  | SRI DURGA ENTERPRISE | 9.58 | 0 | 0
5 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Shibnagar Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] |  |  | 684/SMD | 01/02/2024 |  | PS & ASSOCIATES | 22.42 | 0 | 0
6 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 914/AD | 08/02/2024 |  | CAMELIA CONSTRUCTION | 26.92 | 0 | 0
7 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 516/KSD | 15/03/2024 |  | M/S SANKARI ENTERPRISE (II) | 3.82 | 0 | 0
8 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of Platform and Road Restoration for Shibnagar Abad W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 3418/AD | 21/08/2024 |  | SARADA CONSTRUCTION | 8.48 | 0 | 0
9 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Shibnagar Abad W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 2560/AD | 18/06/2024 |  | SUKUMAR HALDAR | 9.6 | 0 | 0
10 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 2542/AD | 18/06/2024 |  | M/S SAKTI GIRI ENTERPRISE | 5.62 | 0 | 0
11 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded GravelFilter for Shibnagar Abad W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129)(2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 3359/AD | 14/08/2024 |  | SARADA CONSTRUCTION | 20.39 | 0 | 100
12 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 13255/AD | 31/03/2023 |  | AQUATECH ENGINEERS | 36.61 | 0 | 40
13 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 936/KSD | 19/12/2023 |  | ANANTA KUMAR GIRI | 0.16 | 0 | 100
14 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibnagar Abad PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | 956/KSD | 19/12/2023 |  | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
15 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | 50/AD | 03/01/2024 |  | Resource Division | 8.93 | 0 | 0
16 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | 1770/AD | 27/03/2024 |  | Resource Division | 3.32 | 0 | 0
17 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Material Requisition To Resource Division |  |  | 632/AD | 30/01/2024 |  | Resource Division | 0.43 | 0 | 0
18 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Payment for New Service connection of Shibnagarbad PH-1 W/S Scheme JL No-:- 004, Khatian No;- 1714, Plot:- 3348, Mouza:- Shibnagarabad Application No:- 1007514909 Reference ID:- 106460088 |  |  | BP-2024-25-66 | 16/05/2024 |  | WBSEDCL | 3.86 | 0 | 0
19 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 3671/AD | 01/11/2023 |  | PRINCE INDUSTRIES (INDIA) | 381.91 | 0 | 75
20 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Construction of Platform, Rising Main, Road Restoration for Shibnagar Abad W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [Part-I] (SM/18129) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | 925/AD | 05/03/2025 |  | JHARNA ENTERPRISE | 0.36 | 0 | 0
21 | SOUTH 24 PARGANAS | Alipore Division | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/18129 | New | Payment for New Service connection of Shibnagarabad PH-2 W/S Scheme Application No- 1008252336 Reference ID:- 106851336 |  |  | BP-2024-25-533 | 24/01/2025 |  | WBSEDCL | 3.39 | 0 | 0
Total | [12 empty] | 673.69 | 0 | 0