## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kalaria (Zone-IB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2245/AD | 11/08/2023 |  | B.K. ENTERPRISE. | 55.95 | 0 | 98
2 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IA & IB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2271/AD | 14/08/2023 |  | INDRANIL DUTTA & ASSOCIATES | 7.51 | 0 | 98
3 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Material Requisition To Resource Division |  |  | 268/AD | 24/04/2023 |  | Resource Division | 42.51 | 0 | 0
4 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2133] (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2143/AD | 09/08/2023 |  | PUTUL RANI MAITY | 127.34 | 0 | 70
5 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 3547/AD | 02/09/2024 |  | SUPRITI ENTERPRISE | 34.28 | 0 | 0
6 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IA & IB for Augmentation of Kalaria Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | 1128/SMD | 24/04/2023 |  | PADMA ENGINEERING CO. | 26.83 | 0 | 100
7 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2076/AD | 07/08/2023 |  | ASHIS ENTERPRISE | 6.73 | 0 | 100
8 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-III) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2077/AD | 07/08/2023 |  | ASHIS ENTERPRISE | 6.86 | 0 | 100
9 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2075/AD | 07/08/2023 |  | S.M. ENTERPRISE | 7.16 | 0 | 100
10 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Supply & installation of LED board at Zone-I B PH-I of Kalaria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- [ Block- Canning-I ] | Assistant Engineer | Junior Engineer | 371/SMSD | 21/03/2024 |  | KUSHANI ENTERPRISES | 0.39 | 0 | 100
11 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Supply & installation of LED board at Zone-I A PH-I & 2 of Kalaria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Canning-I ] | Assistant Engineer | Junior Engineer | 372/SMSD | 21/03/2024 |  | S.B.ENTERPRISE | 0.78 | 0 | 100
12 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BP-2023-24-396 | 02/12/2023 |  | WBSEDCL | 4.09 | 0 | 0
13 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Quotation for 25 KVA DTR Shifting at Kalaria Zone-IA, PH-2 Water supply scheme under canning-I block. Reference ID-860304112. Application ID-100000111622. |  |  | BP-2024-25-154 | 10/07/2024 |  | WBSEDCL | 1.81 | 0 | 0
14 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1422] (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2141/AD | 09/08/2023 |  | SUPRITI ENTERPRISE | 270.46 | 0 | 85
15 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 2142/AD | 09/08/2023 |  | PUTUL RANI MAITY | 195.09 | 0 | 97
16 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | 1512/AD | 13/03/2024 |  | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 93.08 | 0 | 30
17 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 1701/CSD | 15/03/2024 |  | SAILEN CHANDRA DAS | 4.8 | 0 | 0
18 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Kalaria (Zone- IB) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | 1792/AD | 26/07/2023 |  | S.B. ENTERPRISE | 6.63 | 0 | 100
19 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1A PH-1 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 195/SMSD | 12/02/2024 |  | PADMA ENGINEERING CO. | 0.89 | 0 | 100
20 | SOUTH 24 PARGANAS | Alipore Division | AUGMENTATION OF KALARIA (ZONE-IA & IB) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-I,DISTRICT-SOUTH 24 PARGANAS | SM/18676 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1A PH-2 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | 190/SMSD | 09/02/2024 |  | PADMA ENGINEERING CO. | 0.89 | 0 | 100
Total | [12 empty] | 894.08 | 0 | 0