## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kapasda Piped Water Supply Scheme. | SM/06923 | Retrofitting | Extension of pipe line in connection with of FHTC Work at Mouza Kapasda, Uttar Bansboni, Rambar, Khepal at Kapasda PWSS within Sabang Block under Kharagpur Sub-Division Within Midnapore Division, Phe.Dte. District- Paschim Midnapore. | AE Kharagpur Sub-division |  | 68/AE/KSD | 03/02/2022 |  | KRISHNENDU SEKHAR DAS | 4.82 | 0 | 0
2 | PASCHIM MEDINIPUR | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kapasda Piped Water Supply Scheme. | SM/06923 | Retrofitting | Continuation Work for Hiring of Bharat Stage-II/III/diesel motor cab(Lusury Taxi)(Standard Non-AC) having contract carriage permit from the reginal transport authority for the office of the Assistant Engineer, Kharagpur Sub-Division, P.H.E. Dte.(For 3 Months) | Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | 116/AE/KSD | 30/01/2023 |  | GOBINDA MAITY | 0.48 | 0 | 100
Total | [12 empty] | 5.3 | 0 | 0