## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Electric quotation BIRSINGHA CCC at Masharpur, chowka, Ghatal, T/W-I P/H-II Pin-721232 |  |  |  | 17/11/2022 |  | WBSEDCL | 0.11 | 0 | 0
2 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Electric quotation BIRSINGHA CCC at Jamira, chowka, Ghatal, T/W-I P/H-II Pin-721232 |  |  |  | 17/11/2022 |  | WBSEDCL | 0.11 | 0 | 0
3 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Jamira (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | 1731/MD | 23/08/2022 |  | MIDNAPUR PIPE CONCERN | 45.86 | 0 | 80
4 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Jamira (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | 1732/MD | 23/08/2022 |  | MIDNAPUR PIPE CONCERN | 39.37 | 0 | 100
5 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Zone-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | 229/W/MMD | 13/02/2023 |  | RISHAV ENTERPRISE | 6 | 0 | 100
6 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Electric quotation BIRSINGHA CCC at Jamira, chowka, Ghatal, T/W-I Pin-721232 |  |  | BP-2022-23-70 | 14/12/2022 |  | WBSEDCL | 0.11 | 0 | 0
7 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Electric quotation BIRSINGHA CCC at Masharpur, chowka, Ghatal, P/H-II Pin-721232 |  |  | BP-2022-23-71 | 14/12/2022 |  | WBSEDCL | 0.11 | 0 | 0
8 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Service Connection charges of WBSEDCL at P/H-II of Jamira W/S Scheme |  |  | BP-2022-23-99 | 11/01/2023 |  | WBSEDCL | 0.13 | 0 | 0
9 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Material Requisition To Resource Division |  |  | 3353/MD | 25/11/2024 |  | Resource Division | 2.34 | 0 | 0
10 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10655 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | 2316/W/MMD | 29/12/2022 |  | M/S EMMESS | 6 | 0 | 100
Total | [12 empty] | 100.12 | 0 | 0