## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | SM/17946 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing (i) Chakmakrampur PWSS within Kharagpur-II block & (ii) Shyamsundarpur PWSS within Sabang Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | 2063/MD | 30/09/2022 |  | GOBINDA MAITY | 5.83 | 5.83 | 0
2 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | SM/17946 | Augmentation | Material Requisition To Resource Division |  |  | 204/MD | 16/01/2023 |  | Resource Division | 6.8 | 0 | 0
3 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | SM/17946 | Augmentation | Material Requisition To Resource Division |  |  | 3436/MD | 25/11/2024 |  | Resource Division | 18.82 | 0 | 0
4 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | SM/17946 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur.under JJM Program under MMD. PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | 539/W/MMD | 20/03/2023 |  | M/S. S.R. ENTERPRISE | 22.75 | 10.57 | 65
5 | PASCHIM MEDINIPUR | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur. | SM/17946 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Chakmakrampur PWSS in Kharagpur-II Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | 948/MD | 06/04/2023 |  | ASIS KUMAR SARANGI | 292.42 | 54.7 | 45
Total | [12 empty] | 346.62 | 71.1 | 20.51