## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Material Requisition To Resource Division |  |  | 181/MD | 16/01/2023 |  | Resource Division | 48.33 | 0 | 0
2 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | 3097/W/MMD | 29/11/2023 |  | DEBJYOTI BASU | 43.72 | 0 | 65
3 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Material Requisition To Resource Division |  |  | 3441/MD | 25/11/2024 |  | Resource Division | 21.6 | 0 | 0
4 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-III, T W NO I [ SADATPUR ] , JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004887943, REFERENCE ID 204392629, NIMPURA CCC, WBSEDCL |  |  | C092445635685 | 30/09/2024 |  | WBSEDCL | 6.69 | 0 | 0
5 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, [ SUNDRABANDHA ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004776663, REFERENCE ID 204331299, NIMPURA CCC, WBSEDCL |  |  | BP-2024-25-429 | 16/07/2024 |  | WBSEDCL | 3.37 | 0 | 0
6 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [ SOBHAPUR ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004792617, REFERENCE ID 204341188, NIMPURA CCC, WBSEDCL |  |  | BP-2024-25-428 | 16/07/2024 |  | WBSEDCL | 3.51 | 0 | 0
7 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | 2465/MD | 14/07/2023 |  | GOBINDA MAITY | 954.46 | 0 | 42
8 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | 3100/W/MMD | 29/11/2023 |  | S.S.GHORAI | 22.81 | 0 | 88
9 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-I, T W NO II , JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2005013068, REFERENCE ID 204476960, NIMPURA CCC, WBSEDCL |  |  | C012553211992 | 31/01/2025 |  | WBSEDCL | 9.62 | 0 | 0
10 | PASCHIM MEDINIPUR | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-I, T W NO I , JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2005003271, REFERENCE ID 204470135, NIMPURA CCC, WBSEDCL |  |  | C012553190218 | 31/01/2025 |  | WBSEDCL | 4.81 | 0 | 0
Total | [12 empty] | 1118.92 | 0 | 0