## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Different work under Tamluk Division, PHE Dte. |  |  | 8443/77 | 14/09/2020 |  | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 0.97 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Different work under Tamluk Division, PHE Dte. |  |  | 121 | 26/06/2020 |  | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 12.93 | 0 | 0
3 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Providing services for Operation of 7 (seven) Nos. PHED managed Laboratory by engaging laboratory personnel under Tamluk Division, PHE Dte. (Period from 01/11/20 to 31/12/20). |  |  | 818/W | 24/02/2021 |  | UTSAV AGENCY | 3.85 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Chemical and Glassware etc. required for routine water testing of 17 (seventeen) nos. Water Testing Laboratories under Tamluk Division, PHE Dte. |  |  | 1041/W | 30/03/2021 |  | UTSAV AGENCY | 34 | 0 | 0
5 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Providing services for Operation of 7 (seven) Nos. PHED managed Laboratory by engaging laboratory personnel under Tamluk Division, PHE Dte. (Period from 01/11/19 to 31/10/20). |  |  | 817/W | 24/02/2021 |  | UTSAV AGENCY | 1.93 | 0 | 0
6 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Chemical and Glassware etc. required for routine water testing of 17 (seventeen) nos. Water Testing Laboratories under Tamluk Division, PHE Dte. |  |  | BP-2021-22-31 | 19/07/2021 |  | UTSAV AGENCY | 8.12 | 0 | 0
7 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Engagement of 2 (two) nos. Laboratory personnel for Digha Sub-Divisional laboratory under Tamluk Division, PHE Dte. (Period from 11/12/19 to 10/04/20) |  |  | 860/W | 12/03/2021 |  | ARUNALOY SCIENTIFICE HOUSE | 1.14 | 0 | 0
8 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Supply and Delivery of Chemical and Regents for Onsite Mobile Analysis System (OMAS) for different laboratories under Tamluk Division, PHE Dte. |  |  | BP-2021-22-61 | 13/08/2021 |  | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.85 | 0 | 0
9 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Engagement of 03 nos. Sampling Assistants and 06 nos. Laboratory Attendants for different PHED Managed Water Testing Laboratories under Tamluk Division, PHE Dte. For the period 1 (One) Year. | Assistant Engineer |  | 1123/TD | 22/11/2021 |  | CANVAS | 12.35 | 5.06 | 0
10 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Regular analysis, testing and monitoring of water sample by experienced & trained personnel of District Laboratory activities of Tamluk District Water Testing Laboratory of PHE Dte at Tamluk PHE Complex, Purba Medinipur under Tamluk Sub-division of Tamluk Division PHE Dte. For the period from 01.10.2021 to 30.09.2022 = 12 Months. | Assistant Engineer |  | 809/TD | 30/09/2021 |  | M/S EL-CON | 2.38 | 2.38 | 0
11 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Engagement of 3 nos. laboratory Personal (one no. Chemist / Bacteriologist, one no. laboratory Assistant & one no. Sampling Assistant) for regular analysis, testing and monitoring of water sample and others allied minor Mtc. works of Digha Sub-Divisional Laboratory under Digha Sub-Division of Tamluk Division, P.H.E.Dte. for the period from 01/10/2021 to 30/09/2022 i.e. 12 (twelve) months. | Assistant Engineer |  | 811-A/TD | 30/09/2021 |  | ARUNALOY SCIENTIFIC HOUSE | 4.83 | 4.83 | 0
12 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Procurement of Chemicals and Reagents for On site mobile analysis system (OMAS) kits for 03 (Three) nos. laboratories under Tamluk Division, PHE Dte. | Assistant Engineer |  | 357/TD | 17/05/2022 |  | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.86 | 3.86 | 0
13 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Procurement of required items for testing of water samples (collected from different sources of JJM sites) at Purba Medinipur District Laboratory on emergency basis under Tamluk Division, PHE Dte. | Assistant Engineer |  | 55/RWS./TSD | 06/05/2022 |  | UTSAV AGENCY | 0.53 | 0.53 | 0
14 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under SRIRAMAKRISHNA GUCHHA SAMITY Laboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-220 | 05/08/2022 |  | SRIRAMAKRISHNA GUCHHA SAMITY | 0.99 | 0 | 0
15 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under BHAGWANPURII VIVEKANANDA KALYAN PARISHAD Laboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-222 | 05/08/2022 |  | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 0.99 | 0 | 0
16 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under VIVEKANANDA YUBA PARISHADISP Laboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-224 | 05/08/2022 |  | VIVEKANANDA YUBA PARISHADISP | 0.99 | 0 | 0
17 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under TAMRALIPTA GUCHHA SAMITYLaboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-223 | 05/08/2022 |  | TAMRALIPTA GUCHHA SAMITY | 0.99 | 0 | 0
18 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under ABHYUDAYA HALDIA Laboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-226 | 05/08/2022 |  | ABHYUDAYA HALDIA | 0.99 | 0 | 0
19 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Engagement of 03 Nos. Sampling Assistants and 06 Nos. Laboratory Attendants for different PHED managed water testing laboratories under Tamluk Division, PHE Dte. w.e.f. 01/10/2021 to 30/11/2021 |  |  | BP-2022-23-278 | 16/09/2022 |  | CLIFFORD FACILITY SERVICES PVT LTD | 1.54 | 0 | 0
20 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under LOKAJAGARAN Laboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-221 | 05/08/2022 |  | LOKAJAGARAN | 0.99 | 0 | 0
21 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist & Laboratory Assistant under Grammangal Laboratory for the period from March, 22 to May, 22 |  |  | BP-2022-23-225 | 05/08/2022 |  | GRAMMANGAL WATER TESTING LAB | 0.99 | 0 | 0
22 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Annual Maintenance of Computer and Peripherals (One set of Monitor, CPU, Keyboard, UPS, Mouse and Printer all without major spare parts) including refilling of cartridge of the printers, replacement of battery of UPS (if required), software up-gradation & installation, troubleshooting, supervision and service charge for configuration for different laboratories in Purba Medinipur District under Tamluk Division, PHE Dte. for the period from 01/11/2021 to 31/10/2022. | Assistant Engineer |  | 262/RWS/TSD | 28/10/2021 |  | MISHRA ENTERPRISE | 2.33 | 1.16 | 100
23 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Supply and Delivery of 02 (two) nos. Printers for one no. RWS Tamluk Sub-Division, PHE Dte. and one no. Kudi Sub-District Laboratory and one no. Monitor of Moyna Sub-District Laboratory under Tamluk Division, PHE Dte. | Assistant Engineer |  | 251/RWS/TSD | 01/09/2022 |  | MISHRA ENTERPRISE | 0.45 | 0.45 | 100
24 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Electrical item works of Erashal Sub-District Laboratory under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer |  | 1079/TSD | 18/08/2022 |  | SUDIP MANNA | 0.42 | 0.42 | 0
25 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Electrical item works of Tamluk District Laboratory due to application for NABL Accreditation under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer |  | 1080/TSD | 18/08/2022 |  | SUDIP MANNA | 0.38 | 0.38 | 0
26 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus |  |  | BP-2022-23-603 | 11/01/2023 |  | LOKAJAGARAN | 1.13 | 0 | 0
27 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus. |  |  | BP-2022-23-602 | 11/01/2023 |  | SRIRAMAKRISHNA GUCHHA SAMITY | 1.13 | 0 | 0
28 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus |  |  | BP-2022-23-607 | 11/01/2023 |  | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.13 | 0 | 0
29 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus |  |  | BP-2022-23-606 | 11/01/2023 |  | GRAMMANGAL WATER TESTING LAB | 1.13 | 0 | 0
30 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus |  |  | BP-2022-23-604 | 11/01/2023 |  | ABHYUDAYA HALDIA | 1.13 | 0 | 0
31 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus |  |  | BP-2022-23-605 | 11/01/2023 |  | TAMRALIPTA GUCHHA SAMITY | 1.13 | 0 | 0
32 | PURBA MEDINIPUR | Tamluk Division | Annual operation, maintenance, Procurement of Chemicals, Consumables, Glassware & AMC of computers of different water testing Laboratories. | SM/06626 | Support-WQMSP | Honorarium of Chemist, Bacteriologist and laboratory Assistant personnel of NGO Managed Laboratory for the period from June -22 to August-22 and Festival Bonus |  |  | BP-2022-23-608 | 11/01/2023 |  | VIVEKANANDA YUBA PARISHADISP | 1.13 | 0 | 0
Total | [12 empty] | 110.74 | 19.08 | 17.23