## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri, JL-76.)PART-F | Assistant Engineer |  | 2832/TD | 05/02/2021 |  | SHAKEEL KHAN | 9.71 | 0 | 100
2 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- C | Assistant Engineer |  | 2829/TD | 05/02/2021 |  | S.D. CONSTRUCTION | 9.69 | 0 | 100
3 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- D | Assistant Engineer |  | 2830/TD | 05/02/2021 |  | S.D. CONSTRUCTION | 9.7 | 0 | 100
4 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos(Barsuri-28 nos + Belun-140nos,Soyadighi-37) Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri , Belun & Soyadighi, JL-76 , 75 & 36.) PART-G. | Assistant Engineer |  | 2833/TD | 05/02/2021 |  | TARUN KOLEY | 9.71 | 0 | 100
5 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- E. | Assistant Engineer |  | 2831/TD | 05/02/2021 |  | J.M. CONSTRUCTION | 0.32 | 0.32 | 100
6 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap connection to the 750 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Shirui, JL-74.)PART- A. | Assistant Engineer |  | 2827/TD | 05/02/2021 |  | DILIP KUMAR GHOSH | 6.34 | 6.34 | 100
7 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | unctional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- B | Assistant Engineer |  | 2828/TD | 05/02/2021 |  | DEBDUT CONSTRUCTION | 0.44 | 0.44 | 100
8 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Block under Tamluk Division, PHE Dte. |  |  | 1117/W | 30/03/2021 |  | DILIP KUMAR GHOSH | 29.1 | 0 | 0
9 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | 1099/W | 30/03/2021 |  | S.D. CONSTRUCTION | 9.36 | 0 | 0
10 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | 1109/W | 30/03/2021 |  | S.D. CONSTRUCTION | 9.26 | 0 | 0
11 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. |  |  | 1111/W | 30/03/2021 |  | J.M. CONSTRUCTION | 9.37 | 0 | 0
12 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. |  |  | 1107/W | 30/03/2021 |  | SHAKEEL KHAN | 9.41 | 0 | 0
13 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Retrofitting to accomodate FHTC 205 Nos. connection under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | BP-2021-22-54 | 05/08/2021 |  | DEBDUT CONSTRUCTION | 9.25 | 0 | 0
14 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | 1110/W | 30/03/2021 |  | TARUN KOLEY | 9.48 | 0 | 0
15 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Left out of ( 90 mm & 75 mm) OD pvc laying distribution system of pipe line and its allied works for Alinan zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | 1150/TD | 31/08/2022 |  | TARUN KOLEY | 3.39 | 0 | 100
16 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Left out of 110 mm OD pvc laying distribution system of pipe line and its allied works for Alinan Zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | 1151/TD | 31/08/2022 |  | TARUN KOLEY | 0.41 | 0.41 | 100
17 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- II PWSS under Sahid Matangini Block. | SM/07485 | Retrofitting | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | 2209/TD | 01/09/2023 |  | MISHRA ENTERPRISE | 2.28 | 0 | 100
Total | [12 empty] | 137.2 | 7.5 | 5.47