## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Route survey and all releated field works for preparation and submission of zone wise Geo tagged reference drawing with desinged pipe network system at Chandipur Development Block and Nandakumar Development Block within Purba Medinipur District Under Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters |  | 844/TD | 31/05/2023 |  | ENVIROTECH SOLUTIONS | 85.01 | 0 | 100
2 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipment's at Newly sunk Tube well within NANDAKUMAR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 3174/W/MMD | 18/12/2023 |  | SOUMEN ELECTRIC | 96.15 | 0 | 20
3 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Electro-mechanical works for Nandakumar and Chandipur WTP SITE under Midnapore Mechanical Division, PHE Dte. under JJM in Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 42/W/MMD | 10/01/2024 |  | MACHINE SUPPLIERS SYNDICATE (P) LTD | 734.46 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well within CHANDIPUR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 903/W/MMD | 21/02/2024 |  | DEBJYOTI BASU | 192.31 | 0 | 20
5 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Electro-Mechanical works for Nandakumar GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 92/W/MMD | 24/01/2024 |  | ORIENTAL ENGINEERING CO. | 1405.35 | 0 | 20
6 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | 11/0.433 KV, 1600 KVA Electrical Substation allied Electrical works at Chandipur GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 41/W/MMD | 10/01/2024 |  | THE MARKET ELECTRICAL ENGINEERING WORKS | 532.18 | 0 | 20
7 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Nandakumar GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 44/W/MMD | 10/01/2024 |  | APEX ENGINEERING & PROJECT CO | 533.06 | 0 | 20
8 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Electro-Mechanical works for Chandipur GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | 43/W/MMD | 10/01/2024 |  | WEST BENGAL ENGINEERING CO. | 1578.72 | 0 | 20
9 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Design & Construction of GSLR (4900 Cum) at Nandakumar Block & GSLR (3800 Cum ) at Chandipur Block including High lift Pump House, Chlorine room, Store room, Sub Station Building, Administrative Building, Guard Room, Staff quarter and other allied Structures and Construction of Zonal Overhead Reservior (27 Nos) including Soil Investigation of Different Capacity along with CW Rising Main ,Laying of Distribution Pipeline and FHTC (51946 Nos) including sinking of Big Dia Tube Wells and its connections and other allied works as per direction of EIC including 1 years Operation and Maintenance after successful Trail Run(180 Days) for Surface water based Water supply scheme for Nandakumar Block and Chandipur Block under Tamluk Division PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engiener,Junior Engineer | 2707/TD | 23/08/2024 |  | R SANDESH INFRACONTRACTS PRIVATE LIMITED | 16926.01 | 0 | 10
10 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | 1070/W/MMD | 14/03/2024 |  | THE GODFATHER TRADING COMPANY | 1.04 | 0 | 100
11 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XII (Kulup) at Chandipur Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | 668/TD | 03/03/2025 |  | D N SARKAR & SONS | 0.95 | 0 | 100
12 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Zone-XIII (Sultanpur) at Chandipur Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | 672/TD | 03/03/2025 |  | D N SARKAR & SONS | 0.95 | 0 | 100
13 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VIII (Atattar) at Chandipur Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | 669/TD | 03/03/2025 |  | D N SARKAR & SONS | 0.95 | 0 | 100
14 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-IX (Baroj) at Chandipur Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | 671/TD | 03/03/2025 |  | D N SARKAR & SONS | 0.95 | 0 | 100
15 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-V (Narandanri) at Chandipur Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | 670/TD | 03/03/2025 |  | D N SARKAR & SONS | 0.95 | 0 | 100
16 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Hiring Vehicle for Site inspection of Nandakumar Chnadipur Surface based Project and Pingla Panskura Surface based Project under Midnapore Mechanical Division , P.H.E.Dte (Vehical No. WB-31A-3738) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | 781//WMMD | 24/02/2025 |  | SUDIP KUMAR ROY | 7.78 | 0 | 0
17 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Material Requisition To Resource Division |  |  | 697/TD | 05/03/2025 |  | Resource Division | 6581.11 | 0 | 0
18 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Material Requisition To Resource Division |  |  | 48/TD | 06/01/2025 |  | Resource Division | 146.53 | 0 | 0
19 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Material Requisition To Resource Division |  |  | 805/TD | 18/03/2025 |  | Resource Division | 44.15 | 0 | 0
20 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Quotation for new service connection at Kulup PWSS within Chandipur Block ,Application No - 2005015711 , Ref ID- 204478036 |  |  | C022509341382 | 05/02/2025 |  | WBSEDCL | 5.34 | 0 | 0
21 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Quotation for new service connection at Sultanpur PWSS within Chandipur Block ,Application No - 2005015716 , Ref ID- 204478037 |  |  | C022509328157 | 05/02/2025 |  | WBSEDCL | 3.73 | 0 | 0
22 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Quotation for new service connection at Narandari PWSS within Chandipur Block ,Application No - 2005015718 , Ref ID- 204478031 |  |  | C022509346213 | 05/02/2025 |  | WBSEDCL | 4.57 | 0 | 0
23 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Quotation for new service connection at Jalpai Part - II PWSS within Chandipur Block ,Application No - 2005015706 , Ref ID- 204478033 |  |  | C022509332396 | 04/02/2025 |  | WBSEDCL | 7.71 | 0 | 0
24 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Quotation for new service connection at Burunda PWSS within Chandipur Block ,Application No - 2005015699 , Ref ID- 204478035 |  |  | C022509338458 | 05/02/2025 |  | WBSEDCL | 4.47 | 0 | 0
25 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | SHIFTING OF LT POLE AT - DHITAIBASAN |  |  | BP-2024-25-657 | 06/02/2025 |  | WBSEDCL | 0.8 | 0 | 0
26 | PURBA MEDINIPUR | Tamluk Division | Providing Safe Drinking Water with House to House Connection for Covering 215 Mouzas under Nandakumar & Chandipur Block of the District of Purba Medinipur | SM/18402 | New | Quotation for new service connection at Atattar PWSS within Chandipur Block ,Application No - 2005015013 , Ref ID- 204478032 |  |  | C032554591547 | 17/03/2025 |  | WBSEDCL | 3.41 | 0 | 0
Total | [12 empty] | 28898.65 | 0 | 0