## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under JHOSHODANGA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 1284/ALD | 05/01/2021 |  | MADHAB SAHA | 45.08 | 42.78 | 99
2 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 1159/ALD | 15/12/2020 |  | TAPASH KUMAR BHOWMICK | 34.36 | 17.18 | 98
3 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Providing House connection and construction of different dia. sluice valve chamber including supply of CI materials for Jashodanga WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 1316/ALD | 05/10/2021 |  | HARI CONSTRUCTION | 25.66 | 12.83 | 99
4 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Supply delivery & installation of various machineries at Alipurduar Division Office & allied Sub-Division Offices and laboratories under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | 1287/ALD | 01/10/2021 |  | MATRI ENTERPRISE | 1.75 | 1.75 | 97
5 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | 846/ALD | 26/08/2021 |  | EXECUTIVE ENGINEER, RESOURCE DIVISION | 18 | 18 | 100
6 | ALIPURDUAR | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jashodanga Piped Water Supply Scheme | SM/07184 | Retrofitting | Providing House connection for CHANDIRJHAR water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. |  |  | 909/ALD | 16/10/2020 |  | SREE MAA CONSTRUCTION & CO. | 4.98 | 9.96 | 0
Total | [12 empty] | 129.82 | 102.49 | 78.95