## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Providing balance FHTC from existing distribution system as per specification for HASIMARA PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | 1990/ALD | 15/09/2023 |  | BRAJA GOPAL SAHA | 73.9 | 0 | 0
2 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Special repairing of road for providing of FHTC at Northen side of Hasimara PWSS under Alipurduar, Division, PHE Dte. | HQ-A.E | Birpara Sub Division | 2178/ALD | 06/10/2023 |  | SHIB RATAN BHOWMIK | 0.93 | 0 | 0
3 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Soil investigation work at proposed OHR construction site of Hasimara PWSS under Alipurduar Division PHE Dte. | HQ-A.E |  | 2790/ALD | 10/01/2023 |  | MOYTEC | 0.95 | 0.95 | 100
4 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Material Requisition To Resource Division |  |  | 185/ALD | 28/04/2023 |  | Resource Division | 33.51 | 0 | 0
5 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of 700cum OHR for Augmentation of HASIMARA Water Supply Scheme under Alipurduar Division, PHE Dte.(3rd call) | HQ-A.E | RWS Kalchini Block | 3196/ALD | 27/02/2023 |  | BRAJA GOPAL SAHA | 121.92 | 85.66 | 90
6 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Laying of DI & HDPE pipeline from Santali TG and Malangi TG to the existing OHR at Hasimara PWSS area, kalchini Block under Alipurduar division, PHE Dte. | HQ-A.E | Birpara Sub Division,RWS Kalchini Block,RWS Kumargram Block | 388/ALD | 19/05/2023 |  | D. K. & SONS | 26.33 | 13.59 | 100
7 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation of work of "Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Deputy Superintending Engineer, North Bengal Circle-I , P.H.E. Dte.(from 01.03.2024 to 31.07.2024)" | HQ-A.E |  | 602/ALD | 27/02/2024 |  | MAHENDRA CHHETRI | 2 | 0 | 0
8 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation order for the work of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. (in soft copy) Part-B" | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | 3424/ALD | 26/09/2024 |  | TAPASH KUMAR BHOWMICK | 5.91 | 1.24 | 100
9 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Material Requisition To Resource Division |  |  | 3611/ALD | 24/10/2024 |  | Resource Division | 9.89 | 0 | 0
10 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | 1415/CDD | 21/09/2023 |  | JHARGRAM SPV PRIVATE LIMITED | 18.44 | 0 | 11
11 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Restoration of pipeline for Gap filling and other allied works under Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | 5170/ALD | 25/02/2025 |  | BRAJA GOPAL SAHA | 4.47 | 0 | 0
12 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of 1no. Pump House boundary wall, at new Hasimara PWSS Area under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | 5171/ALD | 25/02/2025 |  | BRAJA GOPAL SAHA | 17.18 | 0 | 0
13 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | 5287/ALD | 07/03/2025 |  | APEX ENGINEERING | 1.49 | 0 | 65
14 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.02.2025 to 31.07.2025) | Alipurduar Sadar Sub Division | Birpara Sub Division | 4920/ALD | 31/01/2025 |  | CHANDAN KIRTONIA | 2.4 | 0 | 0
15 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at Headwork site of HASIMARA PWSS Under Alipurduar Division PHE DTE. |  |  | 5427/ALD | 19/03/2025 |  | DOOARS SOCIAL WELFARE ORGANISATION | 0.78 | 0 | 0
16 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | RWS Kalchini Block | 1052/ALD | 17/06/2025 |  | MOTI INDUSTRIES | 4.53 | 0 | 0
17 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer ,Birpara Sub- Division ,P.H.E. Dte..(from 01.04.2025 to 30.09.2025) | Birpara A.E | Birpara Sub Division | 5760/ALD | 28/03/2025 |  | PARITOSH SUTRADHAR | 2.4 | 0 | 0
18 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Construction of deep TW by ODEX-165 method of drilling for Subhashini TG under Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | 1184/ALD | 26/06/2025 |  | SWARAN ENTERPRISE | 8.73 | 0 | 0
19 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | 343/ALD | 29/04/2025 |  | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0
20 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at 3rd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | 1576/ALD | 31/07/2025 |  | NARENDRA BHADANI. | 0.78 | 0 | 0
21 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at Headwork site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | 1577/ALD | 31/07/2025 |  | NARENDRA BHADANI. | 0.94 | 0 | 0
22 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of hiring of diesel vehicle maxi cab (At least 7 seater) for Deputy Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. (from 01.03.2024 to 31.10.2024) | HQ-A.E | Alipurduar Sub Division | 620/ALD | 29/02/2024 |  | MAHENDRA CHHETRI | 3.2 | 0 | 0
23 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.08.2025 to 31.01.2026) | Alipurduar Sadar Sub Division | Birpara Sub Division | 1557/ALD | 30/07/2025 |  | CHANDAN KIRTONIA | 2.4 | 0 | 0
24 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Reparing of Pump House at 2nd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | 1575/ALD | 31/07/2025 |  | NARENDRA BHADANI. | 0.94 | 0 | 0
25 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Restoration of pipeline and FHTC and allied works at Madhu TG under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | 2103/ALD | 23/09/2025 |  | NARENDRA BHADANI. | 6.46 | 0 | 0
26 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Painting of Old OHR of 300 cum at Madhu under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | 2104/ALD | 23/09/2025 |  | NARENDRA BHADANI. | 3.39 | 0 | 0
27 | ALIPURDUAR | Alipurduar Division | AUGMENTATION OF HASIMARA WATER SUPPLY SCHEME | SM/12361 | Augmentation | Continuation for the work of hiring of additional Diesel vehicle maxi cab (At least 7 seater) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte. (from 01.10.2025 to 31.12.2025) | Birpara A.E | Birpara Sub Division | 2121/ALD | 24/09/2025 |  | PARITOSH SUTRADHAR | 1.2 | 0 | 0
Total | [12 empty] | 359.35 | 101.43 | 28.23