## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | KALIMPONG | Neorakhola W/S Mnt. Division | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | SM/10820 | New | Material Requisition To Resource Division |  |  | 2369/NKWSMD | 03/02/2023 |  | Resource Division | 2.13 | 0 | 0
2 | KALIMPONG | Neorakhola W/S Mnt. Division | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | SM/10820 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. |  |  | 826/NKWSMD | 30/06/2022 |  | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 177.55 | 0 | 100
Total | [12 empty] | 179.68 | 0 | 0