## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. | SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Gairibas SSK/SC under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Maintenance Division ,Kalimpong PHE Dte(Part2) |  | Junior Engineer I | 626/NKWSMD | 26/05/2022 |  | DORJEE SHERPA | 4.43 | 4.43 | 0
2 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. | SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Kumai Sub Centre under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte(Part 2) |  | Junior Engineer III | 624/NKWSMD | 26/05/2022 |  | DORJEE SHERPA | 4.32 | 4.32 | 0
3 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. | SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Kumai Sub Centre under Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply Division ,Kalimpong PHE Dte. (Part1) |  | Junior Engineer I | 625/NKWSMD | 26/05/2022 |  | TOPGAY BHUTIA | 0.65 | 0.65 | 0
4 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. | SM/11367 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Gairibas SSK/SC under Gorubathan Block in the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division, Kalimpong P.H.E. Dte (Part1) | Assistant Engineer I | Junior Engineer I | 627/ NKWSMD | 26/05/2022 |  | TOPGAY BHUTIA | 0.37 | 0.37 | 100
Total | [12 empty] | 9.77 | 9.77 | 100