## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS | SM/12880 | New | Material Requisition To Resource Division |  |  | 958/JHD | 22/06/2023 |  | Resource Division | 30.92 | 0 | 0
2 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS | SM/12880 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of RAMPURA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | 164/GPSD | 05/03/2024 |  | MAHAVIR SAMPARK PVT. LTD. | 3.9 | 3.9 | 100
3 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS | SM/12880 | New | New service connection charges for Rampura w/s scheme, t/w no.- II |  |  | 123/JMD | 20/05/2024 |  | WBSEDCL | 10.17 | 0 | 0
4 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS | SM/12880 | New | New Service Connection Charges for Rampura P.H - I PWSS |  |  | 203/JMD | 14/06/2024 |  | WBSEDCL | 3.14 | 0 | 0
5 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS | SM/12880 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | 607/JHD | 04/05/2023 |  | GOBINDA MAITY | 349.04 | 146.64 | 20
6 | JHARGRAM | Jhargram Division | RAMPURA AND ADJOINING MOUJAS | SM/12880 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | 1415/CDD | 21/09/2023 |  | JHARGRAM SPV PRIVATE LIMITED | 40.69 | 34.12 | 11
Total | [12 empty] | 437.86 | 184.66 | 42.17