## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Construction of OHR(200 Cum) and Soil Investigation for augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | 1344/JHD | 10/08/2023 |  | M.RAHAMAN CONSTRUCTION | 81.74 | 0 | 0
2 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Connection to Tail End Habitation from Clear Water Rising Main of Bamundiha Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | 969/JSD | 10/11/2023 |  | SUNIL DULE | 3.5 | 3.5 | 100
3 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Laying of Distribution pipe line for Augmentation of Ground based Barasukjora Pond Based PWSS in Binpur-II with in Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | 1143/JHD | 21/07/2023 |  | SAIKAT DANDAPAT | 18.31 | 16.46 | 100
4 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA SHYAMPUR UNDER BARASUKJORA W/S SCHEME (ZONE-II) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (PHASE-II) | Assistant Engineer | Junior Engineer-II | 1081/JSD | 27/11/2024 |  | SAIKAT DANDAPAT | 0.96 | 0 | 0
5 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA SHYAMPUR UNDER BARASUKJORA W/S SCHEME (ZONE-II) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (PHASE-I) | Assistant Engineer | Junior Engineer-II | 1080/JSD | 27/11/2024 |  | SAIKAT DANDAPAT | 0.96 | 0 | 0
6 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Re-Laying of Distribution Line Orgonda to Biridanga Village (Orgonda Mouza) under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-II) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | 149/JHD | 29/01/2024 |  | SAIKAT DANDAPAT | 4.67 | 4.67 | 100
7 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer-II | 739/JSD | 02/08/2024 |  | ASSOCIATED ENGINEERS & TRADERS | 4.7 | 0 | 100
8 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - II) | Assistant Engineer | Junior Engineer-II | 740/JSD | 02/08/2024 |  | ASSOCIATED ENGINEERS & TRADERS | 4.82 | 0 | 100
9 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - IV) | Assistant Engineer | Junior Engineer-II | 742/JSD | 02/08/2024 |  | ASSOCIATED ENGINEERS & TRADERS | 4.67 | 0 | 100
10 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - III) | Assistant Engineer | Junior Engineer-II | 741/JSD | 02/08/2024 |  | ASSOCIATED ENGINEERS & TRADERS | 1.73 | 0 | 100
11 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Repair, Renewing of existing water storage pond, Approach Road towards WTP also inspection Road round the pond embankment & Construction of Boundary wall on periphery of down stream toe wall cum guard wall of existing water storage pond under Augmentation of Barasukjora Surface water based P.W.S.S, Block: - Binpur - II, District: - Jhargram, under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | 2009/JHD | 01/12/2023 |  | GEE BEE NIRMAN CO. PRIVATE LIMITED | 1590.58 | 108.91 | 40
12 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Laying Left Out Habitation pipeline of Bamundiha (Mahuldanga) Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Part:I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | 275/JSD | 21/03/2025 |  | SAIKAT DANDAPAT | 3.8 | 0 | 0
13 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C. AT BAMUNDIHA VILLAGE UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase: I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | 248/JSD | 17/03/2025 |  | SAIKAT DANDAPAT | 3.96 | 0 | 0
14 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | LAFT OUT HOUSEHOLD FOR ACCOMODATE FUNCTIONAL HOUSE TAP CONNECTION (F.H.T.C.) & REPAIRING OF EXISTING F.H.T.C. AT BARASUKJORA VILLAGE UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase: I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | 233/JSD | 12/03/2025 |  | SAIKAT DANDAPAT | 4.4 | 0 | 0
15 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Laying Damage pipeline of Barasukjora; & Kharpal Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | 274/JSD | 21/03/2025 |  | SAIKAT DANDAPAT | 4.23 | 0 | 0
16 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | REPAIRING OF EXISTING F.H.T.C. AT BARASUKJORA VILLAGE UNDER BARASUKJORA W/S SCHEME (ZONE-I) WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE (Phase: II) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | 234/JSD | 12/03/2025 |  | SAIKAT DANDAPAT | 2 | 0 | 0
17 | JHARGRAM | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Laying Left Out Habitation pipeline of Bamundiha (Mahuldanga) Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Part:II) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | 276/JSD | 21/03/2025 |  | SAIKAT DANDAPAT | 3.5 | 0 | 0
Total | [12 empty] | 1738.53 | 133.54 | 7.68