## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Pandabeswar of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C2) | Assistant Engineer 2 | Junior Engineer | 2133/RCD-I | 29/11/2021 |  | MRITYUNJOY MUKHERJEE & CO. | 18.7 | 12.53 | 0
2 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B2) | Assistant Engineer 2 | Junior Engineer | 2131/RCD-I | 29/11/2021 |  | M/S B.K. CONSTRUCTION | 18.13 | 18.13 | 0
3 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Supply, fitting fixing of street stand posts and crossing of distribution water branch main through Khandra main road and etc. including interconnection work under Khandra Zone under RCFA Part-II W/S Scheme. (Sl No. 11) | Assistant Engineer 2 | Junior Engineer | 223/RCD I | 01/02/2022 |  | UNITED CONSTRUCTION | 2.61 | 2.61 | 0
4 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Laying of different dia HDPE pipe line including repairing work of UPVC pipe line and etc. allied works under Khandra Zone distribution pipe line under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 2 | Junior Engineer | 222/RCD I | 01/02/2022 |  | UNITED CONSTRUCTION | 4.79 | 4.79 | 0
5 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Maira area Dakshin Khnada (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 2212/RCD-I | 14/09/2022 |  | UNITED CONSTRUCTION | 44.65 | 9.74 | 0
6 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B1) | Assistant Engineer 2 | Junior Engineer | 2130/RCD-I | 29/11/2021 |  | D.S. ENTERPRISE | 12.86 | 12.86 | 0
7 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C1) | Assistant Engineer 2 | Junior Engineer | 2132/RCD-I | 29/11/2021 |  | KHEPI MAA TRADERS | 17.52 | 17.52 | 0
8 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for Laying of different dia HDPE pipe line towards Bisserari, Anandapally and etc. adjacent area under Khandra area Block Andal & Pandabeswar of Improvement of RCFA Part-II Water Supply scheme under RCFA Division-I PHE Dte. |  |  | 372/RCD I | 30/01/2023 |  | M/S B.K. CONSTRUCTION | 1.11 | 1.11 | 100
9 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order Interconnection work of 200 distribution main at Ukhra Zone and emergency repairing of 400 mm dia rising main at Khandra Zone under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 1285/ RCD I | 27/03/2023 |  | RANJIB GHATAK | 4.26 | 4.26 | 100
10 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Material Requisition To Resource Division |  |  | 2283 | 12/12/2021 |  | Resource Division | 18.59 | 0 | 0
11 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Fuel bill of WB 37D 0482 |  |  | 263/23-24 | 27/09/2023 |  | RANAJIT AUTO | 0.22 | 0 | 0
12 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Hire charges and fuel bill 16.05.2023 to 15.08.2023 |  |  | 264/23-24 | 27/09/2023 |  | PRAMIT CHATTERJEE | 1.2 | 0 | 0
13 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Hire charges for the month of August 2023 |  |  | 262/23-24 | 27/09/2023 |  | SHYAMAL MAJI | 0.15 | 0 | 0
14 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Bill for GST Return Oct 2023 to Feb 2024 24 Q 1 & Q 2 2023-2024 and 16 A 26 Q 23-24 |  |  | 172/24-25 | 25/07/2024 |  | SHRESTHA & ASSOCIATES | 0.44 | 0 | 0
15 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Color Xerox repairing and supply of color xerox toner |  |  | 131/24-25 | 11/07/2024 |  | MUKHERJEE TRADERS | 0.17 | 0 | 0
16 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Arrangement of Stationary items , Flex and Tea snacks for Krmashree meeting held on 12.07.2024 at RTC Hall Asansol |  |  | 171/24-25 | 26/07/2024 |  | BLESSING ENTERPRISE | 0.14 | 0 | 0
17 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order Laying of different dia HDPE pipe line towards Ruidas Para and Baouripara under Dakshin Khanda (Jl No. 36) area Block - Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 1272/ RCD I | 27/03/2023 |  | DURGADAS MONDAL | 3.71 | 3.68 | 0
18 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order Laying of different 140 mm dia HDPE pipe line including interconnection and fitting, fixing sluice valves and etc allied works at Maira Dipu area under Khandra Zone under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 1259/ RCD I | 27/03/2023 |  | TARA CONSTRUCTION | 2.32 | 2.16 | 0
19 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Formal work order for Providing FHTC through Retrofitting at Khandra (CT) (JL no. 32, Block - Andal) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | 2145/RCD-I | 29/11/2021 |  | DAS & CHAKRABORTY | 92.1 | 68.92 | 100
20 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Acceptance cum work order for laying of different dia distribution pipe line and allied works etc at Bisseswari Muslimpara and adjacent area of Khandra area under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. |  |  | 334/RCD I | 30/01/2023 |  | M/S B.K. CONSTRUCTION | 0.73 | 0.73 | 100
21 | PASCHIM BARDHAMAN | RCFA Division I | RETROFITTING OF PIPED WATER SUPPLY SCHEME FOR KHANDRA (CT) UNDER RCFA PART - II PWSS FOR PROVIDING FHTC WITH IN ANDAL BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION - I, P.H.E. DTE. | SM/09387 | Retrofitting | Material Requisition To Resource Division |  |  | 2544/RCD-I | 01/09/2025 |  | Resource Division | 3.35 | 0 | 0
Total | [12 empty] | 247.72 | 159.03 | 64.2