## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Material Requisition To Resource Division |  |  | 2952/RCD-I | 11/10/2023 |  | Resource Division | 6.78 | 0 | 0
2 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Supply fitting and allining of 250 mm dia non return valve and 80 mm dia air valve and etc allied works at Bilpahari OCP area on distribution main under Kendra Khottamdihi water supply scheme under RCFA Div-I, PHE Dte. |  | Junior Engineer | 2896_RCD-I | 06/10/2023 |  | M/S UNIT CONSTRUCTION | 2.42 | 0 | 0
3 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | 3437_RCD_I | 24/11/2023 |  | M/S UNIT CONSTRUCTION | 9.31 | 0 | 0
4 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc) at Kunustoria for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I.PHE Dte.(Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | 1017/RCD-I | 16/03/2024 |  | B.T.M. CONCERN | 22.8 | 21.52 | 100
5 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA div-I PHE Dte (w.e.f 01.08.2023 to 31.01.2024) | Assistant Engineer 2 | Junior Engineer | 2319_RCD-I | 31/07/2023 |  | M/S KALYANI ENTERPRISE | 4.49 | 0 | 0
6 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology at 4 nos location (Dabor more, Achhra Road, Rupnarayanpur Phari, Rupnarayanpur Chittaranjan Road) of Salanpur Block under Improvement of RCFA Part-I (Zone-7, Part-F) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 2338/RCD-I | 01/08/2023 |  | GITA CONSTRUCTION | 63.53 | 63.53 | 100
7 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Construction of Guard room with toilet at Dendua under Salanpur Block for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 3280/RCD-I | 08/11/2023 |  | D.S.ENTERPRISE | 7.29 | 7.29 | 100
8 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Allied work Balance Work of Road restoration in connection with Distribution Network including FHTC and allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | 454/RCD-1 | 12/02/2024 |  | MRITYUNJOY MUKHERJEE & CO. | 43.8 | 43.8 | 50
9 | PASCHIM BARDHAMAN | RCFA Division I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Formal work order for Distribution Network Including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | 1763/RCD I | 16/05/2023 |  | MACHINO TECHNO | 541.2 | 167.23 | 30
Total | [12 empty] | 701.61 | 303.37 | 43.24