## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Resource Material | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | PURULIA | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | TSM/005788 | SM/06826 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 28/08/2020 | 473 | 81.48 | Yes | 81.48 |  | 0 | 30/03/2021 | 9 | 81.24 | 76.66 | MVS
2 | PURULIA | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006310 | SM/06939 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-1 | 25/09/2020 | 1259 | 81.16 | Yes | 81.16 |  | 0 | 29/12/2020 | 4 | 99.69 | 69.89 | MVS
3 | PURULIA | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006312 | SM/06940 | Retrofitting | Purulia Sadar Sub-Division | Assistant Engineer |  | 25/09/2020 | 1849 | 96.09 | Yes | 96.09 |  | 0 | 08/03/2021 | 10 | 140.01 | 95.86 | MVS
4 | PURULIA | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006316 | SM/06941 | Retrofitting | Purulia Sadar Sub-Division | Assistant Engineer |  | 25/09/2020 | 1112 | 68.58 | Yes | 68.58 | 05/09/2024 | 0 | 18/03/2021 | 11 | 92.36 | 63.88 | MVS
5 | PURULIA | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006313 | SM/06942 | Retrofitting | Purulia Sadar Sub-Division | Assistant Engineer |  | 25/09/2020 | 1241 | 86.91 | Yes | 86.91 |  | 0 | 25/02/2021 | 8 | 70.31 | 70.31 | MVS
6 | PURULIA | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006307 | SM/07563 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-1 | 25/09/2020 | 5324 | 185.57 | Yes | 185.57 |  | 0 | 16/02/2022 | 8 | 185.54 | 130.44 | MVS
7 | PURULIA | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006308 | SM/07564 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-2 | 25/09/2020 | 2672 | 128.34 | Yes | 128.34 |  | 0 | 21/04/2021 | 38 | 156.49 | 124.6 | MVS
8 | PURULIA | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006309 | SM/07565 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-3 | 25/09/2020 | 2058 | 159.92 | Yes | 159.92 |  | 0 | 19/07/2021 | 2 | 241.24 | 79.96 | MVS
9 | PURULIA | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006311 | SM/07566 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-4 | 25/09/2020 | 3763 | 244.44 | Yes | 244.44 |  | 0 | 12/04/2021 | 17 | 204.46 | 231.69 | MVS
10 | PURULIA | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006314 | SM/07567 | Retrofitting | Purulia Sadar Sub-Division | Assistant Engineer |  | 25/09/2020 | 3823 | 168.98 | Yes | 168.98 | 27/01/2023 | 0 | 12/04/2021 | 27 | 124.47 | 122.94 | MVS
11 | PURULIA | Piped Water Supply Scheme from Marble Lake to adjoining areas. | TSM/005481 | SM/07764 | New | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 17/07/2020 | 2122 | 759.01 | Yes | 759.01 | 29/10/2024 | 56.95 | 08/06/2021 | 31 | 710.6 | 406.75 | MVS
12 | PURULIA | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006757 | SM/07836 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-3 | 04/12/2020 | 1072 | 91.65 | Yes | 91.65 |  | 0 | 19/07/2021 | 6 | 88.98 | 75.28 | MVS
13 | PURULIA | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006758 | SM/07837 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-3 | 04/12/2020 | 1801 | 224.29 | Yes | 224.29 | 26/09/2024 | 0 | 28/03/2022 | 12 | 152.19 | 100.3 | MVS
14 | PURULIA | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006759 | SM/07838 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-3 | 04/12/2020 | 1218 | 73.08 | Yes | 73.08 |  | 0 | 22/03/2021 | 7 | 117.64 | 64.56 | MVS
15 | PURULIA | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006760 | SM/07839 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-4 | 04/12/2020 | 2932 | 175.07 | Yes | 175.07 |  | 0 | 12/04/2021 | 12 | 157.43 | 143.46 | MVS
16 | PURULIA | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006761 | SM/07840 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-4 | 04/12/2020 | 171 | 10.75 | Yes | 10.75 | 05/09/2024 | 0 | 06/07/2021 | 2 | 9.2 | 6.44 | MVS
17 | PURULIA | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006762 | SM/07841 | Retrofitting | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-3 | 04/12/2020 | 1864 | 120.54 | Yes | 120.54 |  | 0 | 16/02/2022 | 4 | 73.8 | 72.48 | MVS
18 | PURULIA | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006315 | SM/08584 | Retrofitting | Purulia Sadar Sub-Division | Assistant Engineer |  | 25/09/2020 | 2623 | 474.74 | Yes | 474.74 | 27/01/2023 | 0 | 10/02/2021 | 12 | 488.14 | 457.78 | MVS
19 | PURULIA | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008391 | SM/09036 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 2888 | 965.77 | Yes | 965.77 | 29/10/2024 | 178.66 | 28/04/2022 | 54 | 953.39 | 476.47 | MVS
20 | PURULIA | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008388 | SM/09037 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 2031 | 684.31 | Yes | 684.31 | 29/10/2024 | 125.95 | 30/03/2022 | 40 | 642.92 | 349.83 | MVS
21 | PURULIA | Augmentation of Satra Water Supply Scheme | TSM/008387 | SM/09038 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 3823 | 389.21 | Yes | 389.21 | 28/10/2024 | 125.74 | 09/03/2022 | 33 | 373.44 | 244.17 | MVS
22 | PURULIA | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008431 | SM/09209 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 2359 | 590.04 | Yes | 590.04 | 28/10/2024 | 121.69 | 28/03/2022 | 32 | 580.25 | 329.22 | MVS
23 | PURULIA | Augmentation of Sonathali W/S Scheme | TSM/008397 | SM/09210 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 08/09/2021 | 1218 | 401.87 | Yes | 401.87 | 10/11/2023 | 143.05 | 28/02/2022 | 24 | 361.25 | 191.7 | MVS
24 | PURULIA | Augmentation of Bathanbari W/S Scheme | TSM/008398 | SM/09211 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 08/09/2021 | 988 | 167.09 | Yes | 167.09 | 28/10/2024 | 97.38 | 09/03/2022 | 26 | 192.65 | 134.12 | MVS
25 | PURULIA | Augmentation of Lachhyara Piped Water Supply Scheme | TSM/008395 | SM/09212 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 08/09/2021 | 768 | 354.91 | Yes | 354.91 | 28/08/2024 | 121.5 | 28/03/2022 | 20 | 439.49 | 193.4 | MVS
26 | PURULIA | Augmentation of Baram Water Supply Scheme | TSM/008385 | SM/09213 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 1241 | 195.46 | Yes | 195.46 | 26/09/2024 | 106.6 | 20/05/2022 | 26 | 202.58 | 116.59 | MVS
27 | PURULIA | Augmentation of Balitora & its adjoining mouzas water supply scheme | TSM/008393 | SM/09214 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | 08/09/2021 | 2672 | 463.76 | Yes | 463.76 | 26/09/2024 | 93.39 | 28/02/2022 | 47 | 510.7 | 194.17 | MVS
28 | PURULIA | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008392 | SM/09215 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 2135 | 514.62 | Yes | 514.62 | 29/10/2024 | 136.01 | 28/03/2022 | 31 | 635.17 | 354 | MVS
29 | PURULIA | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008390 | SM/09216 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 1140 | 424.22 | Yes | 424.22 | 28/08/2024 | 154.33 | 29/03/2022 | 29 | 460.75 | 251.07 | MVS
30 | PURULIA | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | TSM/008389 | SM/09217 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 271 | 386.08 | Yes | 386.08 | 28/10/2024 | 127.23 | 28/03/2022 | 30 | 412.92 | 251.24 | MVS
31 | PURULIA | Augmentation of Beldi Water Supply Scheme | TSM/008386 | SM/09218 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 1849 | 128.6 | Yes | 128.6 | 26/06/2024 | 67.9 | 07/03/2022 | 12 | 119.68 | 75.19 | MVS
32 | PURULIA | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | TSM/009010 | SM/09577 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/10/2021 | 3531 | 791.71 | Yes | 791.71 | 29/10/2024 | 139.94 | 22/03/2022 | 38 | 907.55 | 535.78 | MVS
33 | PURULIA | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008379 | SM/09578 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/10/2021 | 4309 | 785.53 | Yes | 785.53 | 28/08/2024 | 143.56 | 25/02/2022 | 37 | 937.2 | 480.2 | MVS
34 | PURULIA | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | TSM/009009 | SM/09579 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 08/10/2021 | 1450 | 463.03 | Yes | 463.03 | 30/07/2024 | 194.8 | 16/07/2022 | 35 | 514.48 | 332.82 | MVS
35 | PURULIA | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | TSM/009008 | SM/09580 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | 08/10/2021 | 860 | 504.47 | Yes | 504.47 | 29/10/2024 | 226.28 | 28/03/2022 | 50 | 496.63 | 307.16 | MVS
36 | PURULIA | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | TSM/009005 | SM/09581 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 08/10/2021 | 81 | 288.49 | Yes | 288.49 | 29/10/2024 | 109.16 | 22/03/2022 | 46 | 333.96 | 232.39 | MVS
37 | PURULIA | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | TSM/009002 | SM/09582 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | 08/10/2021 | 237 | 203.85 | Yes | 203.85 | 26/09/2024 | 108.37 | 29/03/2022 | 24 | 210.83 | 139.14 | MVS
38 | PURULIA | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | TSM/009000 | SM/09583 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 08/10/2021 | 1857 | 103.56 | Yes | 103.56 | 14/06/2024 | 70.6 | 28/02/2023 | 19 | 112.99 | 52.33 | MVS
39 | PURULIA | Augmentation of Manguria-Lalpur W/S Scheme | TSM/008396 | SM/09943 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 22/11/2021 | 800 | 371.08 | Yes | 371.08 | 26/09/2024 | 113.64 | 16/02/2022 | 32 | 459.76 | 273.97 | MVS
40 | PURULIA | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | TSM/008462 | SM/10045 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | 08/09/2021 | 47 | 1577.26 | Yes | 1577.26 | 29/10/2024 | 264.99 | 29/03/2022 | 37 | 1585.6 | 993.43 | MVS
41 | PURULIA | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008456 | SM/10046 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 13173 | 2330.93 | Yes | 2330.93 | 29/10/2024 | 326.53 | 02/05/2022 | 54 | 2311.65 | 861.7 | MVS
42 | PURULIA | Augmentation of Kashipur Piped Water Supply Scheme | TSM/008394 | SM/10047 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | 08/09/2021 | 4032 | 1088.37 | Yes | 1088.37 | 29/10/2024 | 149.38 | 23/02/2022 | 34 | 1027.14 | 633.87 | MVS
43 | PURULIA | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008384 | SM/10048 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/09/2021 | 4501 | 1477.06 | Yes | 1477.06 | 28/10/2024 | 245 | 13/04/2022 | 46 | 1733.72 | 800.19 | MVS
44 | PURULIA | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/009014 | SM/10198 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 22/11/2021 | 4421 | 1455.54 | Yes | 1455.54 | 29/10/2024 | 260 | 25/07/2022 | 52 | 1724.46 | 750.57 | MVS
45 | PURULIA | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008455 | SM/10347 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 27/01/2022 | 3104 | 940.26 | Yes | 940.26 | 28/08/2024 | 173.29 | 19/10/2022 | 24 | 786.27 | 348.76 | MVS
46 | PURULIA | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008461 | SM/10395 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 27/01/2022 | 5991 | 1949.9 | Yes | 1949.9 | 26/09/2024 | 239.76 | 19/10/2022 | 52 | 1623.2 | 365.28 | MVS
47 | PURULIA | Providing FHTC under Arsha Water Supply Scheme | TSM/010923 | SM/10544 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 16/03/2022 | 0 | 317.07 | Yes | 317.07 | 05/09/2024 | 0 | 22/11/2022 | 13 | 275.04 | 82.81 | MVS
48 | PURULIA | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | TSM/009015 | SM/10718 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | 08/10/2021 | 6702 | 1670.03 | Yes | 1670.03 | 29/10/2024 | 135.86 | 03/08/2022 | 38 | 1524.6 | 994.79 | MVS
49 | PURULIA | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/009013 | SM/10719 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/10/2021 | 5016 | 1569.58 | Yes | 1569.58 | 26/09/2024 | 201.76 | 11/11/2022 | 35 | 1660.62 | 690.53 | MVS
50 | PURULIA | Sarbari Piped Water Supply Scheme to Accommodate FHTC | TSM/009012 | SM/10720 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 08/10/2021 | 3650 | 1231.07 | Yes | 1231.07 | 28/08/2024 | 161.87 | 19/07/2022 | 35 | 1206.34 | 525.76 | MVS
51 | PURULIA | Augmentation of Saltore-Hijuli Water Supply Scheme | TSM/009011 | SM/10721 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | 08/10/2021 | 3676 | 1045.37 | Yes | 1045.37 | 28/08/2024 | 173.58 | 19/07/2022 | 33 | 1115.15 | 498.83 | MVS
52 | PURULIA | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | TSM/009004 | SM/10722 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/10/2021 | 7881 | 2195.7 | Yes | 2195.7 | 05/09/2024 | 247.24 | 16/07/2022 | 67 | 2181.49 | 848.24 | MVS
53 | PURULIA | Augmentation of Kotshila Water Supply Scheme. | TSM/009003 | SM/10723 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 08/10/2021 | 8268 | 2091.4 | Yes | 2091.4 | 08/02/2024 | 187.93 | 19/07/2022 | 74 | 3045.13 | 1333.08 | MVS
54 | PURULIA | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | TSM/008399 | SM/11453 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | 16/03/2022 | 6896 | 2367.56 | Yes | 2367.56 | 28/10/2024 | 205.87 | 05/09/2022 | 47 | 2249.5 | 1003.02 | MVS
55 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | TSM/016041 | SM/14022 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 26/09/2022 | 3393 | 559.47 | Yes | 559.47 | 29/10/2024 | 0 | 17/01/2023 | 12 | 469.18 | 41.74 | MVS
56 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | TSM/016044 | SM/14023 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 26/09/2022 | 3400 | 721.23 | Yes | 721.23 | 26/09/2024 | 21.57 | 17/01/2023 | 19 | 551.1 | 134.26 | MVS
57 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | TSM/016037 | SM/14024 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 26/09/2022 | 3031 | 782.25 | Yes | 782.25 | 29/10/2024 | 21.6 | 17/01/2023 | 19 | 676.49 | 293.55 | MVS
58 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | TSM/016038 | SM/14025 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 26/09/2022 | 2868 | 538.41 | Yes | 538.41 | 29/10/2024 | 0 | 06/01/2023 | 13 | 412.38 | 212.11 | MVS
59 | PURULIA | MINI PIPED WATER SUPPLY SCHEME FOR BAMANDIHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MANBAZAR-I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013873 | SM/14251 | New | Purulia Division | Assistant Engineer(HQ) |  | 26/09/2022 | 22 | 29.24 | Yes | 29.24 |  | 0 | 24/02/2023 | 1 | 4.69 | 4.33 | MVS
60 | PURULIA | Augmentation of Santuri Pipe Water Supply Scheme PWSS | TSM/016080 | SM/14459 | Augmentation | Purulia Mechanical Sub-Division (Drilling) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | 26/09/2022 | 658 | 363.94 | Yes | 363.94 | 29/10/2024 | 73.75 | 16/03/2023 | 16 | 377.87 | 155.77 | MVS
61 | PURULIA | Augmentation of Dubra Pipe Water Supply Scheme PWSS | TSM/016045 | SM/14460 | Augmentation | Raghunathpur Sub-Division | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | 26/09/2022 | 2424 | 660.04 | Yes | 660.04 | 08/02/2024 | 76.7 | 22/11/2022 | 16 | 638.95 | 379.82 | MVS
62 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | TSM/016035 | SM/14669 | Augmentation | Purulia Division | Assistant Engineer(HQ) |  | 26/09/2022 | 0 | 969.41 | Yes | 969.41 | 29/10/2024 | 23 | 17/01/2023 | 13 | 769.86 | 217.73 | MVS
63 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | TSM/016039 | SM/14670 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-1 | 26/09/2022 | 3183 | 984.33 | Yes | 984.33 | 07/08/2024 | 24.97 | 17/01/2023 | 14 | 968.35 | 356.87 | MVS
64 | PURULIA | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | TSM/019808 | SM/15039 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer | Junior Engineer-1 | 16/11/2022 | 0 | 512.38 | Yes | 512.38 | 28/08/2024 | 26.98 | 05/09/2023 | 8 | 360.18 | 114.56 | MVS
65 | PURULIA | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | TSM/019805 | SM/15040 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 16/11/2022 | 0 | 396.97 | Yes | 396.97 | 30/07/2024 | 58.65 | 19/06/2024 | 8 | 385.56 | 54.8 | MVS
66 | PURULIA | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | TSM/019807 | SM/15041 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 16/11/2022 | 0 | 298.83 | Yes | 298.83 | 28/08/2024 | 43.24 | 10/04/2023 | 9 | 280.09 | 67.74 | MVS
67 | PURULIA | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | TSM/019806 | SM/15336 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 28/12/2022 | 0 | 363.16 | Yes | 363.16 | 28/08/2024 | 16.64 | 19/07/2023 | 5 | 312.16 | 41.6 | MVS
68 | PURULIA | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013606 | SM/15380 | New | Purulia Division | Assistant Engineer(HQ) |  | 26/09/2022 | 44 | 32.84 | Yes | 32.84 |  | 0 | 08/02/2023 | 1 | 3.49 | 3.49 | MVS
69 | PURULIA | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | TSM/010889 | SM/15936 | Augmentation | Purulia Sadar Sub-Division | Assistant Engineer |  | 28/12/2022 | 3421 | 999.41 | Yes | 999.41 | 29/10/2024 | 0 | 11/04/2023 | 15 | 1100.2 | 488.29 | MVS
70 | PURULIA | MINI PIPED WATER SUPPLY SCHEME FOR ANKDUAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER JAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013718 | SM/16091 | New | Purulia Division | Assistant Engineer(HQ) |  | 28/12/2022 | 97 | 37.39 | Yes | 37.39 | 02/08/2022 | 0 | 24/02/2023 | 1 | 2.97 | 2.84 | MVS
71 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | TSM/016042 | SM/16379 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | 16/11/2022 | 1951 | 814.73 | Yes | 814.73 | 07/08/2024 | 21.86 | 17/01/2023 | 6 | 740.25 | 326.6 | MVS
72 | PURULIA | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. | TSM/019726 | SM/16414 | Augmentation | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 16/11/2022 | 0 | 717.4 | Yes | 717.4 | 28/08/2024 | 414.24 | 22/06/2023 | 19 | 414.24 | 267.34 | MVS
73 | PURULIA | MINI PIPED WATER SUPPLY SCHEME FOR BAMNI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ARSHA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013556 | SM/16570 | New | Purulia Division | Assistant Engineer(HQ) |  | 30/09/2022 | 50 | 30.31 | Yes | 30.31 |  | 0 | 10/02/2023 | 1 | 3.07 | 2.28 | MVS
74 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | TSM/016036 | SM/18250 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 26/09/2022 | 3798 | 1077.99 | Yes | 1077.99 | 29/10/2024 | 24.71 | 17/01/2023 | 9 | 837.62 | 128.75 | MVS
75 | PURULIA | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | TSM/016040 | SM/18306 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 26/09/2022 | 4471 | 1014.74 | Yes | 1014.74 | 29/10/2024 | 24.71 | 17/01/2023 | 8 | 947.45 | 111.47 | MVS
76 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme | TSM/011442 | SM/18319 | New | Project Management Unit,WBPWSP,Purulia | Assistant Engineer-I(C),Assistant Engineer-I(M/E),Assistant Engineer-II(M/E) | JE-I Civil,JE-II Civil,Junior Engineer (M/E),Sub Assistant Engineer-I (M/E),Sub Assistant Engineer-II (M/E) | 25/04/2022 | 14878 | 6135.38 | Yes | 6135.38 | 13/07/2023 | 0 | 12/07/2022 | 27 | 7255.27 | 163.19 | MVS
77 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | TSM/011448 | SM/18333 | New | Purulia Mechanical Sub-Division(W/S) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 20/05/2022 | 74419 | 10279.85 | Yes | 10279.85 | 11/09/2024 | 0 | 09/01/2024 | 2 | 9822.85 | 0 | MVS
78 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | TSM/012586 | SM/18528 | New | Purulia Sadar Sub-Division | Assistant Engineer |  | 20/05/2022 | 286151 | 27591.27 | Yes | 27591.27 | 19/01/2024 | 0 | 12/04/2023 | 6 | 26270.44 | 716.4 | MVS
79 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | TSM/016015 | SM/18641 | New | Purulia Sadar Sub-Division | Assistant Engineer |  | 30/09/2022 | 0 | 60986.55 | Yes | 60986.55 | 05/09/2024 | 1070.89 | 17/08/2023 | 38 | 49247.81 | 1863.13 | MVS
80 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | TSM/018257 | SM/18653 | New | Purulia Sadar Sub-Division | Assistant Engineer |  | 16/11/2022 | 0 | 16409.28 | Yes | 16409.28 | 07/03/2024 | 0 | 14/08/2023 | 15 | 5433.63 | 22.65 | MVS
81 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | TSM/017881 | SM/18654 | New | Purulia Sadar Sub-Division | Assistant Engineer |  | 16/11/2022 | 0 | 65922.47 | Yes | 65922.47 | 29/10/2024 | 0 | 14/08/2023 | 134 | 56752.07 | 1253.2 | MVS
82 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | TSM/015985 | SM/18731 | New | Purulia Sadar Sub-Division | Assistant Engineer |  | 10/03/2023 | 0 | 161758.31 | Yes | 161758.31 | 29/10/2024 | 5917.72 | 17/08/2023 | 156 | 89845.99 | 9577.79 | MVS
83 | PURULIA | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | TSM/017383 | SM/18779 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 30/09/2022 | 1038 | 4685.1 | Yes | 4685.1 | 29/10/2024 | 714.11 | 17/01/2023 | 27 | 2735.53 | 86.4 | MVS
84 | PURULIA | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | TSM/012987 | SM/18915 | Augmentation | Raghunathpur Sub-Division | Assistant Engineer |  | 10/03/2023 | 0 | 666.74 | Yes | 666.74 | 28/10/2024 | 372.98 | 17/11/2023 | 23 | 508.8 | 56.6 | MVS
Total | [9 empty] | 560540 | 402054.8 |  | 402054.8 |  |  | 14684.0954 | 2187 | 295230.85 | 35784.42