## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Scheme | TSM Code | SM Code | Scheme Type | Sub Division | Name of AE entrusted | Name of JE entrusted | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Resource Material | Date of first Work order | No. of Work Orders issued | Work Value | Payment | Scheme coverage type
1 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | TSM/005582 | SM/06827 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-III | 28/08/2020 | 1989 | 79.24 | Yes | 79.24 | 22/03/2023 | 0 | 26/03/2021 | 14 | 80.12 | 66.18 | MVS
2 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 5 Nos. P.W.S.S. within Binpur - I & 1 No. P.W.S.S. within Binpur - II | TSM/005669 | SM/06828 | Retrofitting | Jhargram Sub-Division |  | Junior Engineer-III | 28/08/2020 | 1720 | 98.98 | Yes | 98.98 | 22/02/2024 | 0 | 26/11/2020 | 8 | 66.7 | 71.01 | MVS
3 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I & 3 No. P.W.S.S. within Binpur - II | TSM/005670 | SM/06829 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-III | 28/08/2020 | 2031 | 98.99 | Yes | 98.99 |  | 0 | 25/02/2022 | 5 | 74.85 | 81.65 | MVS
4 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | TSM/005671 | SM/06830 | Retrofitting | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer-II | 28/08/2020 | 1771 | 91.19 | Yes | 91.19 |  | 0 | 12/02/2021 | 11 | 108.58 | 82.61 | MVS
5 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II | TSM/005672 | SM/06831 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-III | 28/08/2020 | 1818 | 97.11 | Yes | 97.11 |  | 0 | 02/08/2021 | 4 | 85.2 | 87.69 | MVS
6 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Jamboni , 2 Nos. P.W.S.S. within Jhargram & 3 Nos. P.W.S.S within Nayagram | TSM/005673 | SM/06832 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-II | 28/08/2020 | 1635 | 84.05 | Yes | 84.05 |  | 0 | 24/03/2021 | 9 | 54.74 | 66.23 | MVS
7 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Sankrail | TSM/005674 | SM/06833 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer Sankrail block | 28/08/2020 | 1319 | 67.61 | Yes | 67.61 |  | 0 | 02/08/2021 | 3 | 52.14 | 52.14 | MVS
8 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) Piped Water Supply Scheme. | TSM/005583 | SM/06834 | Retrofitting |  |  |  | 28/08/2020 | 2218 | 85.93 | Yes | 85.93 | 10/09/2024 | 0 | 26/03/2021 | 9 | 14.12 | 84.12 | MVS
9 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Barasukjore (Zone-II) Piped Water Supply Scheme. | TSM/005584 | SM/06835 | Retrofitting |  |  |  | 28/08/2020 | 1641 | 81.41 | Yes | 81.41 |  | 0 | 12/02/2021 | 8 | 23.59 | 78.88 | MVS
10 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 3 Nos. P.W.S.S. within Binpur - I, 2 Nos. P.W.S.S. within Binpur - II Block , 2 Nos. P.W.S.S. within Gopiballavpur - I Block, 1 No. P.W.S.S. within Gopiballavpur - II Block, 1 No. P.W.S.S. within Nayagram Blo | TSM/006753 | SM/07875 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer-II | 04/12/2020 | 816 | 39.75 | Yes | 39.75 | 21/08/2024 | 0 | 22/02/2022 | 13 | 48.68 | 38.59 | MVS
11 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in 45 Nos. Mini PWSS at different left out vulnerable Drought affected areas in different Blocks of Jhargram District. | TSM/006531 | SM/08029 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | 04/12/2020 | 4581 | 337.45 | Yes | 337.45 | 04/12/2023 | 0 | 25/02/2021 | 82 | 339.58 | 273.27 | MVS
12 | JHARGRAM | Cost of Land, Soil Investigation at OHR/CWR Locations, exploratory cum production tubewells for Sub-Surface Water Based Piped Water Supply Schemes and sinking of tubewells for Ground Water Based Schemes under Drinking Water Mitigation Master Plan. | TSM/006371 | SM/08081 | New |  |  |  | 04/12/2020 | 36 | 3498 | Yes | 3498 | 05/08/2024 | 0 | 13/01/2022 | 41 | 191.76 | 128.81 | MVS
13 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Bahadurpur P.W.S.S. (Phase-II) within Binpur-I Block | TSM/007031 | SM/08173 | Retrofitting |  |  |  | 08/01/2021 | 69 | 4.66 | Yes | 4.66 |  | 0 | 22/02/2021 | 1 | 7.46 | 3.73 | MVS
14 | JHARGRAM | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Dhamro P.W.S.S. Within Binpur I Block Under Jhargram Division, P.H.E. Dte | TSM/007486 | SM/08733 | Retrofitting | Jhargram Sub-Division |  | Junior Engineer-III | 19/02/2021 | 559 | 52.37 | Yes | 52.37 |  | 0 | 13/07/2021 | 6 | 51.46 | 45.72 | MVS
15 | JHARGRAM | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Laudaha P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | TSM/007487 | SM/08734 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer Sankrail block | 19/02/2021 | 541 | 50.87 | Yes | 50.87 | 22/12/2022 | 11.39 | 13/09/2021 | 6 | 42.78 | 41.97 | MVS
16 | JHARGRAM | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Rohini P.W.S.S. Within Sankrail Block Under Jhargram Division, P.H.E. | TSM/007488 | SM/08735 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer Sankrail block | 19/02/2021 | 1849 | 187.73 | Yes | 187.73 | 21/12/2022 | 16.79 | 18/06/2021 | 15 | 262.17 | 114.95 | MVS
17 | JHARGRAM | Retrofitting to Accommodate F.H.T.C. Under J.J.M. in Sasarah P.W.S.S. Within Gopiballavpur I Block Under Jhargram Division, P.H.E. | TSM/007489 | SM/08736 | Retrofitting | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | 19/02/2021 | 804 | 67.82 | Yes | 67.82 | 27/01/2024 | 12.41 | 17/09/2021 | 4 | 58.85 | 58.31 | MVS
18 | JHARGRAM | Augmentation of Ground Water Based Water supply scheme Chandal Bandh PWSS to Accommodate FHTC in Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008611 | SM/09372 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 29/09/2021 | 26 | 118.7 | Yes | 118.7 | 30/10/2024 | 13.66 | 22/02/2022 | 9 | 92.66 | 27.29 | MVS
19 | JHARGRAM | Augmentation of Ground Water Based Water supply scheme Lalgarh PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008609 | SM/09373 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 29/09/2021 | 2490 | 485.2 | Yes | 485.2 | 21/08/2024 | 27.74 | 12/08/2021 | 14 | 648.21 | 413.48 | MVS
20 | JHARGRAM | Augmentation of Ground Water Based Water Supply Scheme for Gidhni PWSS to Accommodate FHTC in Jamboni Block, Jhargram District. | TSM/008608 | SM/09374 | Augmentation | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 29/09/2021 | 2314 | 401.09 | Yes | 401.09 | 22/02/2024 | 20.34 | 08/03/2022 | 17 | 453.57 | 257.32 | MVS
21 | JHARGRAM | Augmentation of Ground Water Based Water Supply Scheme for Odalchua PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | TSM/008606 | SM/09375 | Augmentation |  |  |  | 29/09/2021 | 375 | 133.96 | Yes | 133.96 | 10/09/2024 | 16.19 | 23/02/2022 | 15 | 112.28 | 70.54 | MVS
22 | JHARGRAM | Rejuvenation of Ground Water Based Naupara PWSS to Accommodate FHTC in Gopiballavpur-II Block, Jhargram District. | TSM/008605 | SM/09376 | Augmentation | Jhargram Sub-Division | Assistant Engineer | JE (M),Junior Engineer-III | 29/09/2021 | 89 | 131.31 | Yes | 131.31 | 10/01/2024 | 13.96 | 15/03/2022 | 9 | 190.05 | 68.7 | MVS
23 | JHARGRAM | Augmentation of Ground Water Based Water Supply Scheme for Pakuria PWSS to Accommodate FHTC in Jhargram Block, Jhargram District | TSM/008603 | SM/09377 | Augmentation | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 29/09/2021 | 520 | 187.46 | Yes | 187.46 | 03/08/2023 | 19.2 | 12/08/2021 | 15 | 239.11 | 137.19 | MVS
24 | JHARGRAM | Augmentation of Ground Water Based Water Supply Scheme for Tamajuri PWSS to Accommodate FHTC in Binpur-II Block, Jhargram District. | TSM/008602 | SM/09378 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 29/09/2021 | 390 | 134.9 | Yes | 134.9 | 20/11/2024 | 1.11 | 23/02/2022 | 9 | 59.74 | 8.06 | MVS
25 | JHARGRAM | Augmentation of Ground Water Based Water supply scheme Belaberya PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008600 | SM/09379 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 29/09/2021 | 1187 | 304.18 | Yes | 304.18 | 20/11/2024 | 16.55 | 11/03/2022 | 10 | 280.69 | 171.87 | MVS
26 | JHARGRAM | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Kechenda Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008551 | SM/09380 | Augmentation |  |  |  | 29/09/2021 | 65 | 25.11 | Yes | 25.11 | 27/09/2024 | 5.94 | 23/02/2022 | 6 | 12.13 | 9.62 | MVS
27 | JHARGRAM | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Banspahari Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008548 | SM/09381 | Augmentation | Jhargram Sub-Division |  | Junior Engineer-II | 29/09/2021 | 100 | 41.53 | Yes | 41.53 | 28/12/2022 | 8.35 | 23/02/2022 | 9 | 68.1 | 31.14 | MVS
28 | JHARGRAM | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008547 | SM/09382 | Augmentation | Jhargram Sub-Division |  | Junior Engineer-II | 29/09/2021 | 194 | 37.85 | Yes | 37.85 | 07/08/2023 | 12.66 | 23/02/2022 | 9 | 41.76 | 25.09 | MVS
29 | JHARGRAM | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008527 | SM/09383 | Augmentation | Jhargram Sub-Division |  | Junior Engineer-III | 29/09/2021 | 2232 | 141.62 | Yes | 141.62 | 21/12/2022 | 29.68 | 22/07/2021 | 11 | 163.04 | 121.64 | MVS
30 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Nayagram Block (Part) PWSS. | TSM/008672 | SM/09384 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-II | 29/09/2021 | 17796 | 919.72 | Yes | 919.72 | 29/10/2024 | 0 | 12/08/2022 | 12 | 1020.01 | 518.59 | MVS
31 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. | TSM/008669 | SM/09385 | Retrofitting | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 29/09/2021 | 150 | 8.38 | Yes | 8.38 |  | 0 | 15/02/2022 | 2 | 6.43 | 6.11 | MVS
32 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Kuldiha PWSS under Nayagram Block. | TSM/008668 | SM/09386 | Retrofitting | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-III | 29/09/2021 | 603 | 32.56 | Yes | 32.56 | 11/06/2024 | 0 | 01/03/2023 | 3 | 17.3 | 14.63 | MVS
33 | JHARGRAM | Agumentation of Ground Water Based Birkarnar Water Supply scheme in Binpur-I Block within Jhargram District i.c.w. providing FHTC under Jhargram Division, PHE Dte. | TSM/007452 | SM/09434 | Augmentation | Jhargram Sub-Division |  | Junior Engineer-III | 19/02/2021 | 0 | 25.96 | Yes | 25.96 | 20/11/2024 | 0 | 02/08/2022 | 6 | 14.51 | 8.17 | MVS
34 | JHARGRAM | Augmentation of ground water based water supply scheme for Khasjungle ICW FHTC work. | TSM/007710 | SM/09881 | Augmentation |  |  |  | 22/11/2021 | 0 | 32.05 | Yes | 32.05 | 21/08/2024 | 4.18 | 23/02/2022 | 3 | 10.73 | 8.64 | MVS
35 | JHARGRAM | Augmentation of ground water based Chichira water supply scheme ICW providing FHTC. | TSM/007709 | SM/09882 | Augmentation | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-II | 22/11/2021 | 0 | 40.96 | Yes | 40.96 | 23/02/2024 | 9.71 | 22/02/2022 | 8 | 32.97 | 15.87 | MVS
36 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | TSM/008120 | SM/09915 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | 19/08/2021 | 23843 | 9931.41 | Yes | 9931.41 | 12/09/2024 | 1776.98 | 13/05/2022 | 619 | 9430.9 | 4970.05 | MVS
37 | JHARGRAM | Augmentation of Ground Water Based Water Supply Scheme for Gopiballavpur to Accommodate FHTC in Block-Gopiballavpur-I, District - Jhargram | TSM/009129 | SM/10064 | Augmentation | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/11/2021 | 4792 | 1060.66 | Yes | 1060.66 | 24/06/2024 | 48.84 | 03/08/2022 | 21 | 1424.82 | 830.1 | MVS
38 | JHARGRAM | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. | TSM/010186 | SM/10439 | Retrofitting |  |  |  | 17/02/2022 | 90 | 6.76 | Yes | 6.76 | 13/06/2024 | 0 | 04/04/2022 | 2 | 5.65 | 3.8 | MVS
39 | JHARGRAM | Rejuvenation of Ground Water Based Jhitka PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008540 | SM/10483 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/03/2022 | 15 | 29.32 | Yes | 29.32 | 19/11/2024 | 15.92 | 02/08/2022 | 8 | 29.2 | 23.15 | MVS
40 | JHARGRAM | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008541 | SM/10485 | Augmentation | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-I | 16/03/2022 | 303 | 100.61 | Yes | 100.61 | 07/08/2023 | 0 | 05/08/2022 | 2 | 9.18 | 4.37 | MVS
41 | JHARGRAM | Rejuvenation of Ground Water Based Netai PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008544 | SM/10488 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/03/2022 | 22 | 34.89 | Yes | 34.89 | 22/03/2023 | 0 | 02/08/2022 | 1 | 1.8 | 0 | MVS
42 | JHARGRAM | Rejuvenation of Ground Water Based Ragra PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008545 | SM/10489 | Augmentation | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer Sankrail block | 16/03/2022 | 45 | 81.98 | Yes | 81.98 |  | 0 | 04/06/2022 | 3 | 87.77 | 11.53 | MVS
43 | JHARGRAM | Augmentation of Ground Water Based Manikpara PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008539 | SM/10490 | Augmentation | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/03/2022 | 1755 | 353.34 | Yes | 353.34 | 07/06/2024 | 23.23 | 16/08/2022 | 16 | 380.98 | 309.86 | MVS
44 | JHARGRAM | Augmentation of Ground Water Based Water supply scheme Kultikri PWSS to Accommodate FHTC in Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/008550 | SM/10491 | Augmentation | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 16/03/2022 | 1752 | 344.86 | Yes | 344.86 | 01/11/2023 | 0 | 18/06/2021 | 6 | 316.34 | 199.57 | MVS
45 | JHARGRAM | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | TSM/008543 | SM/10492 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/03/2022 | 1768 | 214.93 | Yes | 214.93 | 19/02/2024 | 19.23 | 25/06/2021 | 8 | 175.26 | 89 | MVS
46 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | TSM/010656 | SM/11475 | New | Jhargram Division | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 30/03/2022 | 542 | 995 | Yes | 995 | 24/07/2024 | 8.19 | 05/09/2023 | 19 | 833.61 | 261.81 | MVS
47 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. | TSM/010652 | SM/11476 | New | Jhargram Division | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | 30/03/2022 | 887 | 993 | Yes | 993 | 24/07/2024 | 12.13 | 05/09/2023 | 11 | 913.34 | 248.48 | MVS
48 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | TSM/010659 | SM/11477 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | 30/03/2022 | 882 | 985 | Yes | 985 | 24/07/2024 | 34.82 | 05/09/2023 | 17 | 1044.42 | 301.9 | MVS
49 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | TSM/010660 | SM/11478 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 30/03/2022 | 1167 | 982 | Yes | 982 | 24/07/2024 | 4.79 | 05/09/2023 | 9 | 973.46 | 160.07 | MVS
50 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | TSM/010661 | SM/11479 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | 30/03/2022 | 515 | 967 | Yes | 967 | 24/07/2024 | 14.56 | 05/09/2023 | 10 | 842.26 | 4.91 | MVS
51 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | TSM/010662 | SM/11480 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | 30/03/2022 | 1218 | 974 | Yes | 974 | 20/05/2022 | 3.57 | 05/09/2023 | 9 | 926.76 | 314.47 | MVS
52 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | TSM/010663 | SM/11481 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block,Junior Engineer Sankrail block | 30/03/2022 | 360 | 485 | Yes | 485 | 20/05/2022 | 1.47 | 05/09/2023 | 7 | 500.2 | 1.47 | MVS
53 | JHARGRAM | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | TSM/013108 | SM/12324 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1053 | 464.32 | Yes | 464.32 | 22/07/2024 | 26.98 | 24/08/2023 | 6 | 456.33 | 181.35 | MVS
54 | JHARGRAM | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | TSM/013140 | SM/12325 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 936 | 343.02 | Yes | 343.02 | 13/03/2024 | 39.07 | 29/08/2023 | 9 | 355.31 | 128.76 | MVS
55 | JHARGRAM | SIMLI AND IT'S ADJOINING MOJAS PWS at Jhargram Block. | TSM/013125 | SM/12326 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1110 | 469.77 | Yes | 469.77 | 01/03/2024 | 20.82 | 26/05/2023 | 3 | 426.82 | 4.84 | MVS
56 | JHARGRAM | URANSAOL AND ADJOINING MOUJAS PWSS at Jhargram Block. | TSM/013123 | SM/12327 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1451 | 455.43 | Yes | 455.43 | 29/08/2023 | 28.85 | 26/05/2023 | 6 | 417.82 | 59.56 | MVS
57 | JHARGRAM | BURIMOL AND IT'S ADJOINING MOJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/013150 | SM/12328 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1663 | 562.67 | Yes | 562.67 | 16/03/2023 | 27.6 | 29/04/2024 | 5 | 536.14 | 40.15 | MVS
58 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | TSM/013103 | SM/12329 | New | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 1079 | 487.29 | Yes | 487.29 | 27/08/2024 | 43.11 | 27/07/2023 | 10 | 525.48 | 85.65 | MVS
59 | JHARGRAM | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | TSM/013100 | SM/12330 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1193 | 478.38 | Yes | 478.38 | 17/01/2024 | 24.43 | 08/09/2023 | 7 | 517.06 | 103.33 | MVS
60 | JHARGRAM | RAMCHANDRAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/013153 | SM/12332 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1020 | 397.66 | Yes | 397.66 | 16/03/2023 | 28.3 | 14/06/2024 | 4 | 371.1 | 7.72 | MVS
61 | JHARGRAM | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/012786 | SM/12333 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | 05/07/2022 | 1532 | 513.84 | Yes | 513.84 | 13/03/2024 | 37.76 | 26/05/2023 | 15 | 506.89 | 112.14 | MVS
62 | JHARGRAM | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | TSM/013071 | SM/12334 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 2225 | 717.22 | Yes | 717.22 | 15/03/2024 | 27.6 | 20/11/2023 | 6 | 714.59 | 254.98 | MVS
63 | JHARGRAM | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | TSM/013201 | SM/12336 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1416 | 446.27 | Yes | 446.27 | 13/03/2024 | 29.73 | 22/08/2023 | 10 | 440.8 | 150.18 | MVS
64 | JHARGRAM | MURAKATI AND ADJOINING MOUJAS PWSS | TSM/013502 | SM/12339 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1111 | 411.75 | Yes | 411.75 | 01/02/2024 | 29.01 | 24/08/2023 | 5 | 389.31 | 7.68 | MVS
65 | JHARGRAM | GOHALMARA AND ADJOINING MOUJAS PWSS | TSM/011775 | SM/12340 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 613 | 442.07 | Yes | 442.07 | 07/03/2024 | 25.91 | 07/09/2023 | 6 | 449.65 | 16.2 | MVS
66 | JHARGRAM | TENTULIA AND ADJOINING MOUJAS PWSS | TSM/011773 | SM/12341 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 1398 | 438.2 | Yes | 438.2 | 07/03/2024 | 33.69 | 07/09/2023 | 7 | 417.02 | 11.52 | MVS
67 | JHARGRAM | JUNSOLA AND ADJOINING MOUJAS PWSS | TSM/011772 | SM/12342 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 592 | 311.62 | Yes | 311.62 | 02/09/2024 | 28.46 | 26/05/2023 | 5 | 342.95 | 0 | MVS
68 | JHARGRAM | SIMLADANGA AND ADJOINING MOUJAS PWSS | TSM/011762 | SM/12343 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 20/05/2022 | 1993 | 830.61 | Yes | 830.61 | 07/03/2024 | 33.7 | 07/09/2023 | 6 | 856.98 | 4.5 | MVS
69 | JHARGRAM | JAKUA AND ADJOINING MOUJAS PWSS | TSM/011756 | SM/12344 | New | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 20/05/2022 | 764 | 345.73 | Yes | 345.73 | 21/02/2024 | 24.04 | 27/07/2023 | 8 | 367.46 | 82.33 | MVS
70 | JHARGRAM | SHONA KONIA AND ADJOINING MOUJAS PWSS | TSM/011748 | SM/12345 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 1021 | 292.84 | Yes | 292.84 | 07/03/2024 | 24.62 | 08/05/2024 | 5 | 266.92 | 6.07 | MVS
71 | JHARGRAM | KENDANA AND ADJOINING MOUJAS PWSS | TSM/011745 | SM/12346 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 1308 | 496.74 | Yes | 496.74 | 07/03/2024 | 26.62 | 08/05/2024 | 5 | 466.73 | 4.06 | MVS
72 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS | TSM/011740 | SM/12347 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 1091 | 403.45 | Yes | 403.45 | 02/09/2024 | 26.8 | 26/05/2023 | 8 | 417.21 | 12.67 | MVS
73 | JHARGRAM | TIAKITPUR ANAD AJOINING MOUJAS PWSS | TSM/013092 | SM/12349 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1683 | 415.83 | Yes | 415.83 | 22/07/2024 | 28.29 | 01/02/2024 | 6 | 412.96 | 55.64 | MVS
74 | JHARGRAM | Chorchita Adjoining Moujas Piped Water supply Scheme block-Gopiballavpur-II, Dist-Jhargram | TSM/010230 | SM/12350 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 05/07/2022 | 1079 | 363.72 | Yes | 363.72 | 07/03/2024 | 25.96 | 29/04/2024 | 4 | 325.45 | 3.73 | MVS
75 | JHARGRAM | BANKATI AND IT'S ADJOINING MOUJAS | TSM/013495 | SM/12351 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 05/07/2022 | 1278 | 604.79 | Yes | 604.79 | 15/03/2024 | 37.97 | 06/09/2023 | 6 | 657.72 | 255.9 | MVS
76 | JHARGRAM | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS | TSM/012711 | SM/12352 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 2020 | 668.4 | Yes | 668.4 | 10/01/2024 | 18.5 | 05/09/2023 | 4 | 651.51 | 227.76 | MVS
77 | JHARGRAM | BHAUDI AND ADJOINING MOUJAS PWSS | TSM/013161 | SM/12353 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1365 | 484.38 | Yes | 484.38 | 01/03/2024 | 26.1 | 30/03/2024 | 4 | 457.69 | 3.77 | MVS
78 | JHARGRAM | PETBINDHI AND ADJOINING MOUJAS PWSS | TSM/011771 | SM/12354 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 1862 | 522.37 | Yes | 522.37 | 02/09/2024 | 30.35 | 26/05/2023 | 7 | 536.17 | 17.33 | MVS
79 | JHARGRAM | PITHAPURA AND ADJOINING MOUJAS PWSS | TSM/011776 | SM/12355 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 20/05/2022 | 927 | 323.12 | Yes | 323.12 | 20/07/2023 | 32.26 | 30/08/2023 | 9 | 327.21 | 48.34 | MVS
80 | JHARGRAM | CHAKKUA AND ADJOINING MOUJAS PWSS | TSM/013175 | SM/12356 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 861 | 451.72 | Yes | 451.72 | 29/08/2023 | 33.4 | 07/09/2023 | 8 | 479.17 | 108.81 | MVS
81 | JHARGRAM | DALKATI AND ADJOINING MOUJAS PWSS | TSM/013203 | SM/12357 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 05/07/2022 | 1148 | 416.55 | Yes | 416.55 | 13/03/2024 | 33.82 | 26/05/2023 | 13 | 365.66 | 57.15 | MVS
82 | JHARGRAM | DARUKULI AND ADJOINING MOUJAS PWSS | TSM/013081 | SM/12358 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 869 | 417.84 | Yes | 417.84 | 27/02/2023 | 15.64 | 03/08/2023 | 3 | 354.34 | 0 | MVS
83 | JHARGRAM | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | TSM/012784 | SM/12359 | New | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 1798 | 587.48 | Yes | 587.48 | 27/08/2024 | 34.22 | 27/07/2023 | 5 | 573.05 | 289.44 | MVS
84 | JHARGRAM | Chingra And Adjoining Moujas PWSS | TSM/013079 | SM/12385 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1216 | 519.22 | Yes | 519.22 | 07/03/2024 | 24.72 | 29/12/2023 | 5 | 480.74 | 5.82 | MVS
85 | JHARGRAM | Mahapal PWSS Block-Gopiballavpur-II, Dist-Jhargram | TSM/010231 | SM/12386 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 05/07/2022 | 891 | 311.48 | Yes | 311.48 | 07/03/2024 | 29.73 | 26/05/2023 | 7 | 284.01 | 3.51 | MVS
86 | JHARGRAM | CHAMPASOL AND ADJOINING MOUJAS PWSS | TSM/013507 | SM/12387 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1160 | 504.16 | Yes | 504.16 | 01/03/2024 | 24.34 | 14/06/2024 | 4 | 462.9 | 5.79 | MVS
87 | JHARGRAM | BALISHIRA AND ADJOINING MOUJAS PWSS | TSM/013504 | SM/12388 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 05/07/2022 | 1736 | 534.67 | Yes | 534.67 | 07/03/2024 | 26.76 | 07/09/2023 | 6 | 594.44 | 26.05 | MVS
88 | JHARGRAM | SUSHNI AND ADJOINING MOUJAS PWSS | TSM/013506 | SM/12389 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1536 | 605.9 | Yes | 605.9 | 01/02/2024 | 38.16 | 24/08/2023 | 5 | 478.97 | 3.04 | MVS
89 | JHARGRAM | BAKRA AND ITS ADJOINING MOUJAS PWSS | TSM/013058 | SM/12390 | New | Gopiballavpur Sub Division | Assistant Engineer | Junior Engineer-II | 05/07/2022 | 1897 | 637.82 | Yes | 637.82 | 27/08/2024 | 39.1 | 27/07/2023 | 9 | 663.3 | 238.14 | MVS
90 | JHARGRAM | BHALUKASOL AND ADJOINING MOUJAS PWSS | TSM/012773 | SM/12391 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1260 | 613.27 | Yes | 613.27 | 01/03/2024 | 23.38 | 01/02/2024 | 6 | 611.15 | 88.73 | MVS
91 | JHARGRAM | BRAHMANDANA AND ADJOINING MOUJAS PWSS | TSM/013085 | SM/12392 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1459 | 492.42 | Yes | 492.42 | 16/03/2023 | 28.67 | 30/03/2024 | 4 | 463.86 | 5.08 | MVS
92 | JHARGRAM | GHORA PINCHA AND ADJOINING MOJAS PWSS | TSM/013094 | SM/12408 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 881 | 405.39 | Yes | 405.39 | 22/07/2024 | 28.67 | 08/09/2023 | 9 | 394.56 | 75.56 | MVS
93 | JHARGRAM | HARIPURBIRUA AND AJOINING MOUJAS PWSS | TSM/013110 | SM/12409 | New | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 2752 | 836.25 | Yes | 836.25 | 27/08/2024 | 27.06 | 08/11/2023 | 7 | 937.62 | 209.32 | MVS
94 | JHARGRAM | CHANDABILA AND ADJOINING MOPUJAS PWSS | TSM/014185 | SM/12435 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1219 | 374.55 | Yes | 374.55 | 01/02/2024 | 25.04 | 07/09/2023 | 6 | 371.79 | 133.22 | MVS
95 | JHARGRAM | HARDA AND ADJOINING MOUJAS PWSS | TSM/014182 | SM/12436 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 15/07/2022 | 2827 | 817.7 | Yes | 817.7 | 07/03/2024 | 35.86 | 06/09/2023 | 5 | 965.47 | 290.72 | MVS
96 | JHARGRAM | METIAL AND ADJOINING MOUJAS PWSS | TSM/014181 | SM/12437 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 1356 | 491.35 | Yes | 491.35 | 28/02/2024 | 30.23 | 30/03/2024 | 5 | 452.14 | 5.86 | MVS
97 | JHARGRAM | DOMAHANI AND ADJOINING MOUJAS PWSS | TSM/014171 | SM/12438 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block,JE (M) | 15/07/2022 | 1160 | 469.57 | Yes | 469.57 | 16/03/2023 | 18.55 | 08/09/2023 | 4 | 444.28 | 1.4 | MVS
98 | JHARGRAM | KHAS JANGAL AND ADJOINING MOUJAS PWSS | TSM/014166 | SM/12439 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 617 | 408.33 | Yes | 408.33 | 27/02/2023 | 20.78 | 26/05/2023 | 3 | 372.95 | 0 | MVS
99 | JHARGRAM | MURABANI AND ADJOINING MOUJAS PWSS | TSM/014158 | SM/12440 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 15/07/2022 | 1367 | 411.12 | Yes | 411.12 | 13/03/2024 | 27.19 | 26/05/2023 | 10 | 367.8 | 70.52 | MVS
100 | JHARGRAM | BAHIR GRAM AND ADJOINING MOUJAS PWSS | TSM/014154 | SM/12441 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1204 | 563.95 | Yes | 563.95 | 01/02/2024 | 32.06 | 25/08/2023 | 5 | 428.15 | 10.73 | MVS
101 | JHARGRAM | BANDARBANI AND ADJONING MOUJAS PWSS | TSM/014153 | SM/12442 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 15/07/2022 | 1931 | 648.02 | Yes | 648.02 | 07/03/2024 | 27.11 | 06/09/2023 | 6 | 707.33 | 2.8 | MVS
102 | JHARGRAM | BELIA AND ADJOINING MOUJAS PWSS | TSM/014152 | SM/12444 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1409 | 523.17 | Yes | 523.17 | 01/02/2024 | 30.67 | 25/08/2023 | 6 | 420.21 | 181.22 | MVS
103 | JHARGRAM | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | TSM/014139 | SM/12445 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | 15/07/2022 | 1646 | 533.24 | Yes | 533.24 | 13/03/2024 | 26.24 | 08/09/2023 | 8 | 463.4 | 136.91 | MVS
104 | JHARGRAM | KHAMARPARA AND ADJOINING MOUJAS PWSS | TSM/014136 | SM/12446 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1200 | 420.68 | Yes | 420.68 | 01/02/2024 | 29.05 | 07/09/2023 | 6 | 457.67 | 98.63 | MVS
105 | JHARGRAM | ANKRO AND ADJOINING MOUJAS PWSS | TSM/014135 | SM/12447 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 15/07/2022 | 1175 | 599.18 | Yes | 599.18 | 07/03/2024 | 18.5 | 06/09/2023 | 4 | 424.19 | 0 | MVS
106 | JHARGRAM | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | TSM/014131 | SM/12448 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1264 | 421.06 | Yes | 421.06 | 17/01/2024 | 20.62 | 01/02/2024 | 5 | 405.94 | 4.2 | MVS
107 | JHARGRAM | TENTULIA AND ADJOINING MOUJAS PWSS | TSM/014122 | SM/12449 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 963 | 416.02 | Yes | 416.02 | 16/03/2023 | 18.55 | 08/09/2023 | 3 | 401.6 | 0 | MVS
108 | JHARGRAM | PINDRAKULI AND ADJOINING MOUJAS PWSS | TSM/014117 | SM/12450 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 871 | 376.23 | Yes | 376.23 | 27/02/2023 | 20.71 | 26/05/2023 | 3 | 313.05 | 0 | MVS
109 | JHARGRAM | BELDA AND ADJOINING MOUJAS PWSS | TSM/014115 | SM/12451 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 15/07/2022 | 911 | 423.84 | Yes | 423.84 | 26/07/2024 | 28.4 | 24/08/2023 | 6 | 410.73 | 169.3 | MVS
110 | JHARGRAM | BHILA AND ADJOINING MOUJAS PWSS | TSM/013116 | SM/12452 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | 15/07/2022 | 1197 | 488.63 | Yes | 488.63 | 22/07/2024 | 25.37 | 11/03/2024 | 11 | 436.51 | 112.65 | MVS
111 | JHARGRAM | THAKURPARA AND ADJOINING MOUJAS PWSS | TSM/014250 | SM/12453 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 15/07/2022 | 2198 | 688.86 | Yes | 688.86 | 11/06/2024 | 36.21 | 07/09/2023 | 8 | 735.79 | 8.46 | MVS
112 | JHARGRAM | KAPGARI AND IT'S ADJOINING MOUJAS PWSS | TSM/014249 | SM/12454 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 935 | 387.68 | Yes | 387.68 | 01/02/2024 | 24.33 | 10/11/2023 | 4 | 303.24 | 2.99 | MVS
113 | JHARGRAM | PARIHATI AND ADJOINING MOUJAS PWSS | TSM/014138 | SM/12455 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 15/07/2022 | 1365 | 487.27 | Yes | 487.27 | 01/02/2024 | 24.59 | 07/09/2023 | 5 | 443.77 | 3.25 | MVS
114 | JHARGRAM | SIJUA AND ADJOINING MOUJAS PWSS | TSM/013233 | SM/12519 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 05/07/2022 | 1135 | 508.92 | Yes | 508.92 | 07/03/2024 | 28.82 | 06/09/2023 | 6 | 405.81 | 19.71 | MVS
115 | JHARGRAM | SHALUKA AND ADJOINING MOUJAS PWSS | TSM/013489 | SM/12520 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 05/07/2022 | 662 | 316.15 | Yes | 316.15 | 07/03/2024 | 20.01 | 07/09/2023 | 5 | 264.27 | 1.46 | MVS
116 | JHARGRAM | MAHISAMURA & ADJOINING MOUJAS PWSS | TSM/013478 | SM/12521 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1012 | 396.51 | Yes | 396.51 | 01/02/2024 | 23.98 | 07/09/2023 | 5 | 323.58 | 5.66 | MVS
117 | JHARGRAM | BAGMURI AND ADJOINING MOUJAS PWSS | TSM/013131 | SM/12523 | New | Jhargram Division | Assistant Engineer Headquarter | Junior Engineer-II | 05/07/2022 | 992 | 389.63 | Yes | 389.63 | 27/02/2023 | 20.76 | 26/05/2023 | 4 | 388.17 | 0 | MVS
118 | JHARGRAM | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS | TSM/013054 | SM/12524 | New | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 1457 | 474.81 | Yes | 474.81 | 11/06/2024 | 42.77 | 27/07/2023 | 8 | 500.83 | 206.23 | MVS
119 | JHARGRAM | MANTIPA & IT'S ADJOINING MOJAS PWSS | TSM/013189 | SM/12525 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 622 | 401.24 | Yes | 401.24 | 01/03/2024 | 29.14 | 31/05/2024 | 4 | 375.51 | 5.29 | MVS
120 | JHARGRAM | NOAGOAN AND ADJOINING MOUJAS PWSS | TSM/013102 | SM/12526 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 2019 | 591.31 | Yes | 591.31 | 11/06/2024 | 38.73 | 22/06/2023 | 8 | 623.84 | 247.04 | MVS
121 | JHARGRAM | PATHARNALA AND ADJOINING MOUJAS PWSS | TSM/013218 | SM/12527 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 05/07/2022 | 1207 | 568.25 | Yes | 568.25 | 01/03/2024 | 25.37 | 29/08/2023 | 5 | 560.31 | 258.49 | MVS
122 | JHARGRAM | SUMITRAPUR AND ADJOINING MOJAS PWSS | TSM/013091 | SM/12528 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1725 | 534.56 | Yes | 534.56 | 01/03/2024 | 26.62 | 01/02/2024 | 6 | 535.57 | 72.84 | MVS
123 | JHARGRAM | TILABANI AND ADJOINING MOUJAS PWSS | TSM/014285 | SM/12530 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 15/07/2022 | 2339 | 723 | Yes | 723 | 07/03/2024 | 43.25 | 06/09/2023 | 6 | 807.36 | 5.62 | MVS
124 | JHARGRAM | PARSHULI AND ADJOINING MOUJAS PWSS | TSM/014282 | SM/12531 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1115 | 463.62 | Yes | 463.62 | 01/02/2024 | 30.2 | 28/09/2022 | 7 | 403.63 | 216.19 | MVS
125 | JHARGRAM | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | TSM/014248 | SM/12532 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 751 | 338.87 | Yes | 338.87 | 22/02/2024 | 20.79 | 26/05/2023 | 3 | 285.23 | 0 | MVS
126 | JHARGRAM | JIRAPARA AND ADJOINING MOUJAS PWSS | TSM/014214 | SM/12533 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 15/07/2022 | 1616 | 677.48 | Yes | 677.48 | 01/02/2024 | 22.54 | 09/08/2023 | 13 | 583.38 | 0 | MVS
127 | JHARGRAM | MAHULBANI AND ADJOINING MOUJAS PWSS | TSM/014193 | SM/12534 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1020 | 613.77 | Yes | 613.77 | 22/07/2024 | 34.24 | 11/03/2024 | 6 | 590.42 | 7.53 | MVS
128 | JHARGRAM | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | TSM/014191 | SM/12535 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 15/07/2022 | 1191 | 652.02 | Yes | 652.02 | 26/07/2024 | 27.61 | 08/08/2023 | 5 | 567.72 | 306.58 | MVS
129 | JHARGRAM | PALASHBANI AND ADJOINING MOUJAS PWSS | TSM/014218 | SM/12711 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 673 | 441.75 | Yes | 441.75 | 01/02/2024 | 33.51 | 05/09/2023 | 6 | 411.44 | 202.89 | MVS
130 | JHARGRAM | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | TSM/014215 | SM/12713 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 15/07/2022 | 1927 | 742.21 | Yes | 742.21 | 14/11/2024 | 32.62 | 06/09/2023 | 6 | 712.11 | 3.2 | MVS
131 | JHARGRAM | CHANDRI AND ADJOINING MOUJAS PWSS | TSM/014162 | SM/12715 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 15/07/2022 | 2066 | 545.91 | Yes | 545.91 | 01/03/2024 | 26.63 | 26/05/2023 | 12 | 497.69 | 116.31 | MVS
132 | JHARGRAM | BARABARI AND ADJOINING MOUJAS PWSS | TSM/013236 | SM/12722 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 883 | 537.44 | Yes | 537.44 | 14/11/2024 | 27.25 | 08/09/2023 | 6 | 477.41 | 237.52 | MVS
133 | JHARGRAM | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | TSM/014335 | SM/12723 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 22/08/2022 | 1326 | 601.69 | Yes | 601.69 | 13/03/2024 | 30.2 | 26/05/2023 | 9 | 447.42 | 20.4 | MVS
134 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS | TSM/014314 | SM/12724 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 22/08/2022 | 1289 | 460.54 | Yes | 460.54 | 07/03/2024 | 27.77 | 07/09/2023 | 6 | 462.41 | 4.63 | MVS
135 | JHARGRAM | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS | TSM/014556 | SM/12725 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 1400 | 562.67 | Yes | 562.67 | 29/08/2023 | 35.15 | 07/09/2023 | 7 | 544.5 | 149.69 | MVS
136 | JHARGRAM | JANGALKHAS AND ADJOINING MOUJAS PWSS | TSM/014319 | SM/12775 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 22/08/2022 | 1336 | 665.38 | Yes | 665.38 | 07/03/2024 | 31.56 | 07/09/2023 | 6 | 507.44 | 68.14 | MVS
137 | JHARGRAM | NEPURA AND ADJOINING MOUJAS PWSS | TSM/014401 | SM/12776 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 22/08/2022 | 2184 | 824.12 | Yes | 824.12 | 11/06/2024 | 31.24 | 07/09/2023 | 4 | 742.81 | 4.95 | MVS
138 | JHARGRAM | RADHANAGAR AND ADJOINING MOUJAS PWSS | TSM/013239 | SM/12777 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 1591 | 566.07 | Yes | 566.07 | 13/03/2024 | 35.38 | 29/08/2023 | 12 | 498.02 | 168.95 | MVS
139 | JHARGRAM | RAJBAND AND ADJOINING MOUJAS PWSS | TSM/013139 | SM/12842 | New | Jhargram Division | Assistant Engineer Headquarter | Junior Engineer-II | 05/07/2022 | 786 | 344.49 | Yes | 344.49 | 16/03/2023 | 18.55 | 25/07/2024 | 3 | 307.91 | 0 | MVS
140 | JHARGRAM | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS | TSM/013075 | SM/12845 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1075 | 508.1 | Yes | 508.1 | 17/01/2024 | 25.55 | 07/09/2023 | 6 | 517.72 | 5.64 | MVS
141 | JHARGRAM | RAMPURA AND ADJOINING MOUJAS | TSM/011770 | SM/12880 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 20/05/2022 | 1248 | 406.33 | Yes | 406.33 | 10/01/2024 | 31.85 | 22/06/2023 | 6 | 438.08 | 11.42 | MVS
142 | JHARGRAM | NOHARIA AND ADJOINING MOUJAS | TSM/013498 | SM/12885 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1592 | 433.66 | Yes | 433.66 | 01/02/2024 | 25.71 | 07/09/2023 | 5 | 481.57 | 4.37 | MVS
143 | JHARGRAM | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/009315 | SM/13678 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 16/12/2021 | 270 | 46.29 | Yes | 46.29 | 10/09/2024 | 19.81 | 12/08/2021 | 8 | 48.19 | 25.27 | MVS
144 | JHARGRAM | BARBARIA AND ITS ADJOINING MOUJAS PWSS | TSM/013520 | SM/14133 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-II block | 15/07/2022 | 3050 | 1067.06 | Yes | 1067.06 | 07/02/2023 | 31.73 | 26/05/2023 | 3 | 1081.14 | 78.9 | MVS
145 | JHARGRAM | RAJABASA AND ADJOINING MOUJAS PWSS | TSM/014217 | SM/14184 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 15/07/2022 | 3502 | 1292.08 | Yes | 1292.08 | 27/02/2023 | 45.92 | 26/05/2023 | 4 | 1125.65 | 4.38 | MVS
146 | JHARGRAM | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS | TSM/017880 | SM/16675 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 28/12/2022 | 1017 | 652.47 | Yes | 652.47 | 21/07/2023 | 50.21 | 02/08/2023 | 2 | 552.21 | 0 | MVS
147 | JHARGRAM | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | TSM/015441 | SM/16934 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 26/09/2022 | 1389 | 661.95 | Yes | 661.95 | 21/08/2024 | 25.67 | 08/09/2023 | 4 | 525.63 | 210.62 | MVS
148 | JHARGRAM | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | TSM/015762 | SM/16982 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 26/09/2022 | 905 | 362.71 | Yes | 362.71 | 20/08/2024 | 21.03 | 10/08/2023 | 3 | 351.19 | 0 | MVS
149 | JHARGRAM | ANDHARI AND ADJOINING MOUJAS PWSS | TSM/013042 | SM/16991 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 26/09/2022 | 1064 | 334.36 | Yes | 334.36 | 11/06/2024 | 27.48 | 17/08/2023 | 7 | 374.5 | 53.25 | MVS
150 | JHARGRAM | DHADANGIRI AND ADJOINING MOUJAS | TSM/011764 | SM/16992 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 26/09/2022 | 1997 | 611.94 | Yes | 611.94 | 07/03/2024 | 24.01 | 16/08/2023 | 6 | 556.66 | 1.93 | MVS
151 | JHARGRAM | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | TSM/015922 | SM/16993 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer RWS, Binpur-II Devlopment Block.,JE (M) | 26/09/2022 | 1504 | 885.79 | Yes | 885.79 | 16/03/2023 | 21.04 | 10/08/2023 | 3 | 582.47 | 0 | MVS
152 | JHARGRAM | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS | TSM/015452 | SM/16994 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 26/09/2022 | 1645 | 540.88 | Yes | 540.88 | 16/03/2023 | 30.67 | 10/08/2023 | 3 | 596.97 | 0 | MVS
153 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | TSM/020266 | SM/17039 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | 28/12/2022 | 895 | 539.48 | Yes | 539.48 | 22/02/2024 | 0 | 21/09/2023 | 67 | 384.37 | 34.03 | MVS
154 | JHARGRAM | RAGRA AND ADJOINING MOUJAS PWSS | TSM/013093 | SM/17174 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 1318 | 428.5 | Yes | 428.5 | 27/08/2024 | 35.12 | 22/06/2023 | 8 | 473.21 | 204.13 | MVS
155 | JHARGRAM | BHAMAL AND ADOINING MOUJAS PWSS | TSM/011783 | SM/17417 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 20/05/2022 | 1300 | 313.06 | Yes | 313.06 | 07/03/2024 | 28.02 | 26/05/2023 | 8 | 304.64 | 4.56 | MVS
156 | JHARGRAM | DHOBA KURYA AND ADJOINING MOUJAS PWSS | TSM/013483 | SM/17570 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 819 | 380.58 | Yes | 380.58 | 01/02/2024 | 24.39 | 08/09/2023 | 5 | 393.29 | 84.53 | MVS
157 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS | TSM/013205 | SM/17571 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | 05/07/2022 | 1343 | 463.29 | Yes | 463.29 | 13/03/2024 | 35.49 | 26/05/2023 | 11 | 455.03 | 140.69 | MVS
158 | JHARGRAM | SAFTALDIHA AND ADJOINING MOUJAS PWSS | TSM/013222 | SM/17580 | New | Jhargram Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 05/07/2022 | 1498 | 516.78 | Yes | 516.78 | 13/03/2024 | 27.71 | 08/09/2023 | 24 | 495.65 | 162.13 | MVS
159 | JHARGRAM | DHANSOL AND ADJOINING MOUJAS PWSS | TSM/013095 | SM/17581 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 1361 | 453.32 | Yes | 453.32 | 11/06/2024 | 28.09 | 27/07/2023 | 8 | 450.53 | 57.33 | MVS
160 | JHARGRAM | BHATAN DIA AND ADJOINING MOUJAS PWSS | TSM/013097 | SM/17582 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1164 | 374.62 | Yes | 374.62 | 17/01/2024 | 18.55 | 13/03/2024 | 3 | 394.95 | 0 | MVS
161 | JHARGRAM | ANANDAPUR AND ADJOINING MOUJAS PWSS | TSM/013053 | SM/17583 | New | Jhargram RWS Sub Division | Assistant Engineer | JE (M),Junior Engineer-II | 05/07/2022 | 1073 | 373.73 | Yes | 373.73 | 11/06/2024 | 28.3 | 17/08/2023 | 8 | 362.21 | 181.43 | MVS
162 | JHARGRAM | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | TSM/012754 | SM/17584 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1908 | 513.68 | Yes | 513.68 | 17/01/2024 | 25.16 | 11/03/2024 | 5 | 482.88 | 3.33 | MVS
163 | JHARGRAM | GOHAL BURA AND ADJOINING MOUJAS PWSS | TSM/012735 | SM/17585 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 05/07/2022 | 1718 | 542.43 | Yes | 542.43 | 22/07/2024 | 29.67 | 08/09/2023 | 12 | 492.87 | 170.51 | MVS
164 | JHARGRAM | AMARDA AND ADJOINING MOUJAS PWSS | TSM/012757 | SM/17586 | New | Gopiballavpur Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | 05/07/2022 | 1630 | 519.04 | Yes | 519.04 | 17/01/2024 | 22.27 | 11/03/2024 | 5 | 492.71 | 1.88 | MVS
165 | JHARGRAM | KULIANA AND ADJOINING MOUJAS PWSS | TSM/011774 | SM/17587 | New | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 20/05/2022 | 1241 | 310.7 | Yes | 310.7 | 07/03/2024 | 25.35 | 29/04/2024 | 5 | 315.8 | 3.4 | MVS
166 | JHARGRAM | GAJPATHAR AND ADJOINING MOUJAS PWSS | TSM/014453 | SM/17590 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 841 | 450.65 | Yes | 450.65 | 05/03/2024 | 1.47 | 27/10/2023 | 14 | 282.02 | 31.99 | MVS
167 | JHARGRAM | SHIYARBINDA AND ADJOINING MOUJAS PWSS | TSM/014447 | SM/17591 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 636 | 432.68 | Yes | 432.68 | 27/02/2024 | 0 | 27/10/2023 | 10 | 226.85 | 36.8 | MVS
168 | JHARGRAM | KHARIYARATA AND ADJOINING MOUJAS PWSS | TSM/014387 | SM/17592 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 713 | 443.46 | Yes | 443.46 | 01/08/2023 | 0 | 21/09/2023 | 6 | 152.52 | 37.1 | MVS
169 | JHARGRAM | BIRMADAL AND ADJOINING MOUJAS PWSS | TSM/014477 | SM/17593 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 634 | 452.34 | Yes | 452.34 | 05/03/2024 | 0 | 27/10/2023 | 14 | 215.42 | 1.47 | MVS
170 | JHARGRAM | HIJLA AND ADJOINING MOUJAS PWSS | TSM/014334 | SM/17594 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 22/08/2022 | 1257 | 463.44 | Yes | 463.44 | 01/03/2024 | 69.41 | 01/09/2023 | 21 | 381.44 | 34.77 | MVS
171 | JHARGRAM | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | TSM/013231 | SM/17595 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 695 | 437.57 | Yes | 437.57 | 27/02/2024 | 0.21 | 27/10/2023 | 12 | 247.85 | 1.26 | MVS
172 | JHARGRAM | CHAKADOBA AND ADJOINING MOUJAS PWSS | TSM/014382 | SM/17596 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 1434 | 589.96 | Yes | 589.96 | 01/08/2023 | 0 | 21/09/2023 | 6 | 305.91 | 14.31 | MVS
173 | JHARGRAM | KALADABAR AND ADJOINING MOUJAS PWSS | TSM/014482 | SM/17597 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 22/08/2022 | 505 | 380.65 | Yes | 380.65 | 01/08/2023 | 0 | 21/09/2023 | 5 | 108.21 | 0.21 | MVS
174 | JHARGRAM | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | TSM/015892 | SM/17924 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 26/09/2022 | 978 | 522.61 | Yes | 522.61 | 28/02/2024 | 145.76 | 26/12/2023 | 25 | 483.47 | 85.9 | MVS
175 | JHARGRAM | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | TSM/015919 | SM/17925 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 30/09/2022 | 1663 | 639.18 | Yes | 639.18 | 01/10/2024 | 113.45 | 19/12/2023 | 7 | 514.43 | 105.93 | MVS
176 | JHARGRAM | GIDIGHATI AND ADJOINING MOUJAS PWSS | TSM/015912 | SM/17926 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 30/09/2022 | 694 | 436.42 | Yes | 436.42 | 27/02/2024 | 0 | 27/10/2023 | 12 | 248.32 | 1.26 | MVS
177 | JHARGRAM | DAKAI AND ADJOINING MOUJAS PWSS | TSM/015911 | SM/17927 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 30/09/2022 | 727 | 456.15 | Yes | 456.15 | 05/03/2024 | 0 | 27/10/2023 | 9 | 240.89 | 5.01 | MVS
178 | JHARGRAM | BURIJHOR AND ADJOINING MOUJAS PWSS | TSM/015888 | SM/17928 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 30/09/2022 | 681 | 472.21 | Yes | 472.21 | 05/03/2024 | 0 | 27/10/2023 | 12 | 228.21 | 1.26 | MVS
179 | JHARGRAM | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | TSM/015873 | SM/17929 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 30/09/2022 | 1420 | 522.47 | Yes | 522.47 | 07/03/2024 | 127.9 | 11/01/2024 | 13 | 556.31 | 42.93 | MVS
180 | JHARGRAM | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | TSM/015763 | SM/17930 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 30/09/2022 | 1639 | 730.76 | Yes | 730.76 | 01/10/2024 | 103.48 | 29/12/2023 | 5 | 665.7 | 51.11 | MVS
181 | JHARGRAM | BANKSOL AND ADJOINING MOUJAS PWSS | TSM/015563 | SM/17931 | New | Midnapur Mechanical (Drill.) Sub-Division | DIC(D)_MMSD(D) | JE (M) | 30/09/2022 | 1008 | 480.2 | Yes | 480.2 | 06/06/2024 | 55.35 | 12/09/2023 | 9 | 300.56 | 12.55 | MVS
182 | JHARGRAM | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | TSM/015456 | SM/17932 | New | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 30/09/2022 | 874 | 497.89 | Yes | 497.89 | 27/02/2024 | 0 | 27/10/2023 | 16 | 313.12 | 1.68 | MVS
183 | JHARGRAM | Retrofitting(Phase-III) to accomodate FHTC under JJM in Balibandh PWSS within Jamboni Block, Jhargram District under Jhargram Division, PHE Dte. | TSM/017857 | SM/17945 | Augmentation | Jhargram RWS Sub Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 16/11/2022 | 0 | 36.98 | Yes | 36.98 | 13/03/2023 | 10.33 | 11/05/2023 | 3 | 23.19 | 15.34 | MVS
184 | JHARGRAM | Installation of Iron Elemination Plant(IEP) and related works in different schemes(Barajharia PWSS, Lalgarh PWSS, Baratilaboni PWSS) within Nayagram and Binpur-I Blocks in Jhargram District under Jhargram Division, PHE Dte. | TSM/017862 | SM/17948 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Nayagram block | 16/11/2022 | 0 | 85.96 | Yes | 85.96 | 30/07/2024 | 0 | 14/07/2023 | 1 | 54.17 | 27.34 | MVS
185 | JHARGRAM | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | TSM/017859 | SM/17950 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | 16/11/2022 | 0 | 70.53 | Yes | 70.53 | 05/02/2024 | 7.04 | 03/01/2023 | 11 | 38.17 | 4.36 | MVS
186 | JHARGRAM | Augmentation of Pond Water Based Silda Pipe Water Supply Scheme under Jhargram Division, Block : Binpur-II, District : Jhargram | TSM/018036 | SM/17953 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | 16/11/2022 | 1880 | 576.13 | Yes | 576.13 | 02/08/2023 | 0 | 09/01/2024 | 1 | 369 | 0 | MVS
187 | JHARGRAM | Rejuvenation of Ground Water Based Rohini PWSS to Accommodate FHTC under JJM at Sankrail Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017855 | SM/17956 | Augmentation | Gopiballavpur Sub Division | Assistant Engineer | JE (M),Junior Engineer Sankrail block | 16/11/2022 | 0 | 73.08 | Yes | 73.08 | 19/05/2023 | 19.76 | 29/09/2023 | 2 | 50.63 | 0 | MVS
188 | JHARGRAM | Rejuvenation of Ground Water Based Dhamro Water Supply Scheme to Accommodate FHTC under JJM at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017849 | SM/17959 | Augmentation | Jhargram Sub-Division | Assistant Engineer | Junior Engineer Binpur-I block | 16/11/2022 | 194 | 41.56 | Yes | 41.56 | 28/12/2022 | 0 | 18/08/2023 | 2 | 33.74 | 11.1 | MVS
189 | JHARGRAM | Retrofitting incl. Augmentation of Source(Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte | TSM/017850 | SM/17964 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/11/2022 | 150 | 188.03 | Yes | 188.03 | 10/09/2024 | 0 | 08/06/2023 | 4 | 121.8 | 9.19 | MVS
190 | JHARGRAM | Retrofitting incl. Augmentation of Source (Phase-II) and Installation of IEP & related works to Accommodate FHTC under JJM in Ground Water based Lakat Water Supply Scheme at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017848 | SM/17965 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/11/2022 | 0 | 46.72 | Yes | 46.72 | 17/05/2023 | 9.56 | 08/06/2023 | 4 | 36.85 | 15.23 | MVS
191 | JHARGRAM | Rejuvenation(Phase-II) of Ground Water Based Chandal Bandh PWSS and Installation of IEP & related works to Accommodate FHTC at Nayagram Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017853 | SM/17966 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | 16/11/2022 | 25 | 59.97 | Yes | 59.97 | 28/12/2022 | 0 | 14/09/2023 | 2 | 33.95 | 5.72 | MVS
192 | JHARGRAM | Rejuvenation of Ground Water Based Kantapahari PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017846 | SM/18002 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 16/11/2022 | 50 | 67.65 | Yes | 67.65 | 20/11/2024 | 9.62 | 25/07/2023 | 6 | 63.52 | 19.71 | MVS
193 | JHARGRAM | Rejuvenation (Phase-II) of Ground Water Based Netai PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017845 | SM/18007 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/11/2022 | 10 | 115.77 | Yes | 115.77 | 19/05/2023 | 9.62 | 08/09/2023 | 2 | 100.37 | 23.95 | MVS
194 | JHARGRAM | Rejuvenation (Phase-II) of Ground Water Based Jhitka PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017844 | SM/18008 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 16/11/2022 | 10 | 57.02 | Yes | 57.02 | 28/12/2022 | 0 | 11/12/2020 | 3 | 43.13 | 24.47 | MVS
195 | JHARGRAM | Rejuvenation(Phase-II) of Ground Water Based Naupara PWSS and Installation of IEP & related works to Accommodate FHTC at Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017851 | SM/18010 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-II block | 16/11/2022 | 30 | 53.1 | Yes | 53.1 | 17/05/2023 | 0 | 08/06/2023 | 4 | 60.85 | 29.49 | MVS
196 | JHARGRAM | Rejuvenation (Phase-II) of Ground Water Based Birkanar PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017847 | SM/18012 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | 16/11/2022 | 10 | 50.5 | Yes | 50.5 | 28/12/2022 | 0 | 04/05/2023 | 2 | 42.24 | 23.2 | MVS
197 | JHARGRAM | Rejuvenation(Phase-II) of Ground Water Based Ramgarh PWSS(Zone-I & II) PWSS and Installation of IEP & related works to Accommodate FHTC at Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | TSM/017843 | SM/18014 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | 16/11/2022 | 50 | 163.98 | Yes | 163.98 | 08/08/2023 | 9.61 | 08/06/2023 | 5 | 160.31 | 67.34 | MVS
198 | JHARGRAM | Retrofitting(Phase-III) to accomodate FHTC under JJM in Junsola PWSS within Gopiballavpur-II Block, Jhargram District under Jhargram Division, PHE Dte. | TSM/017852 | SM/18190 | Augmentation | Jhargram Sub-Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-II block | 16/11/2022 | 294 | 46.68 | Yes | 46.68 | 19/05/2023 | 9.41 | 03/08/2023 | 4 | 34.98 | 8.02 | MVS
199 | JHARGRAM | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCK WITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | TSM/018706 | SM/18428 | Augmentation | Jhargram Sub-Division | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | 28/12/2022 | 7292 | 4219.65 | Yes | 4219.65 | 14/11/2024 | 0 | 10/11/2023 | 7 | 1128.08 | 222.04 | MVS
200 | JHARGRAM | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | TSM/020327 | SM/18435 | Augmentation | Jhargram Sub-Division | Assistant Engineer | Junior Engineer-II | 28/12/2022 | 0 | 2052.61 | Yes | 2052.61 | 11/11/2024 | 0 | 10/08/2023 | 9 | 1714.72 | 72.62 | MVS
201 | JHARGRAM | CHIANBERA ZONE-IV (MALABATI) AND IT'S ADJOINING MOUJAS PWSS | TSM/018025 | SM/18604 | New | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer-II | 28/12/2022 | 1843 | 1025.14 | Yes | 1025.14 | 21/07/2023 | 62.3 | 10/08/2023 | 3 | 854.62 | 0 | MVS
202 | JHARGRAM | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | TSM/015566 | SM/18746 | New | Jhargram RWS Sub Division | Assistant Engineer | Junior Engineer-II | 26/09/2022 | 2017 | 789.66 | Yes | 789.66 | 01/10/2024 | 238 | 29/12/2023 | 17 | 840.82 | 38.09 | MVS
Total | [9 empty] | 277050 | 102446.11 |  | 102446.11 |  |  | 6393.5735 | 2239 | 88834.36 | 20115.65