## JJM Schemes Financial Status (C
JJM Schemes Financial Status (COOCHBEHAR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | COOCHBEHAR | SM/17439 | AUGMENTATION OF BALABHUT PIPED WATER SUPPLY SCHEME | TSM/019951 | 40049296 | Augmentation | SVS | GO2223017010PH | 18/03/2023 | 194.04 | 24.05 | 218.09 | Coochbehar Division | Northern Mechanical Division II | 128 | 13.95 | 0 | 0 | 141.95 | 128 | 13.95 | 0 | 0 | 141.95 | 65.09 | 70
2 | COOCHBEHAR | SM/15931 | AUGMENTATION OF BARA GADAIKHORAPIPED WATER SUPPLY SCHEME | TSM/019962 | 40048674 | Augmentation | MVS | GO2223014685PH | 22/02/2023 | 289.66 | 24.05 | 313.71 | Coochbehar Division | Northern Mechanical Division II | 35.68 | 1.6 | 71.35 | 0 | 108.63 | 35.68 | 1.6 | 71.35 | 0 | 108.63 | 34.63 | 68
3 | COOCHBEHAR | SM/15932 | AUGMENTATION OF KHARIKABARIPIPED WATER SUPPLY SCHEME | TSM/019938 | 40048507 | Augmentation | MVS | GO2223014684PH | 22/02/2023 | 433.43 | 24.05 | 457.49 | Coochbehar Division | Northern Mechanical Division II | 166.07 | 7.62 | 151.32 | 0 | 325.01 | 166.07 | 7.62 | 151.32 | 0 | 325.01 | 71.04 | 79
4 | COOCHBEHAR | SM/16516 | AGUMENTATION OF BASRAJA PRATHAM KHANDA PWSS | TSM/019998 | 40062675 | Augmentation | SVS | GO2223015224PH | 03/03/2023 | 482.58 | 41.41 | 523.99 | Coochbehar Division | Northern Mechanical Division II | 136.41 | 6.18 | 0 | 0 | 142.59 | 135.57 | 6.18 | 0 | 0 | 141.75 | 27.05 | 72
5 | COOCHBEHAR | SM/13378 | Augmentatin of Bajejama Chilakhana Zone-III PWSS Accomodate FHTC in TFG-I BLOCK | TSM/015357 | 40064067 | Augmentation | SVS | GO2223008930PH | 19/10/2022 | 470.08 | 26.1 | 496.18 | Coochbehar Division | Northern Mechanical Division II | 272.87 | 18.39 | 0 | 0 | 291.27 | 260.35 | 18.39 | 0 | 0 | 278.74 | 56.18 | 80
6 | COOCHBEHAR | SM/11983 | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | TSM/009868 | 40023862 | Augmentation | MVS | GO2223006901PH | 01/09/2022 | 1101.69 | 19.65 | 1121.34 | Coochbehar Division | Northern Mechanical Division II | 984.11 | 0 | 5.95 | 0 | 990.06 | 961.49 | 0 | 5.95 | 0 | 967.44 | 86.28 | 85
7 | COOCHBEHAR | SM/10161 | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | TSM/009774 | 40003737 | Augmentation | MVS | GO2122009650PH | 11/02/2022 | 486.78 | 38.01 | 524.8 | Coochbehar Division | Northern Mechanical Division II | 327.95 | 30.43 | 0 | 0 | 358.38 | 327.95 | 30.43 | 0 | 0 | 358.38 | 68.29 | 87
8 | COOCHBEHAR | SM/10163 | Augmentation of NIJTARAF Piped water supply schemes | TSM/009754 | 40003698 | Augmentation | MVS | GO2122009637PH | 11/02/2022 | 402.28 | 18.46 | 420.74 | Coochbehar Division | Northern Mechanical Division II | 304.34 | 14.14 | 87.83 | 0 | 406.3 | 304.34 | 12.63 | 87.83 | 0 | 404.79 | 96.21 | 94
9 | COOCHBEHAR | SM/16350 | Augmentation OF AMBARI PIPED WATER SUPPLY SCHEME | TSM/010882 | 40063168 | Augmentation | SVS | GO2223014964PH | 28/02/2023 | 576.74 | 58.34 | 635.08 | Coochbehar Division | Northern Mechanical Division II | 486.56 | 35.66 | 0 | 0 | 522.22 | 486.56 | 35.66 | 0 | 0 | 522.22 | 82.23 | 83
10 | COOCHBEHAR | SM/10049 | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | TSM/009056 | 40014381 | Augmentation | SVS | GO2122008623PH | 24/01/2022 | 1098.59 | 107.97 | 1206.57 | Coochbehar Division | Northern Mechanical Division II | 1004.99 | 48.5 | 0 | 0 | 1053.48 | 1004.99 | 48.5 | 0 | 0 | 1053.48 | 87.31 | 92
11 | COOCHBEHAR | SM/16931 | Augmentation of Bajejama Chilakhana ZONE-I PWSS | TSM/015355 | 40034826 | Augmentation | MVS | GO2223016565PH | 16/03/2023 | 366.51 | 26.1 | 392.61 | Coochbehar Division | Northern Mechanical Division II | 114.36 | 0 | 16.29 | 0 | 130.65 | 114.36 | 0 | 16.29 | 0 | 130.65 | 33.28 | 90
12 | COOCHBEHAR | SM/13386 | Augmentation of bajejama chilakhana zone-II PWSS | TSM/015356 | 40035463 | Augmentation | MVS | GO2223008932PH | 19/10/2022 | 435.66 | 26.1 | 461.75 | Coochbehar Division | Northern Mechanical Division II | 223.79 | 20.98 | 16.59 | 0 | 261.36 | 223.79 | 20.98 | 16.59 | 0 | 261.36 | 56.6 | 75
13 | COOCHBEHAR | SM/10050 | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | TSM/009092 | 40014512 | Augmentation | MVS | GO2122008623PH | 24/01/2022 | 1906.85 | 128.21 | 2035.06 | Coochbehar Division | Northern Mechanical Division II | 1346.23 | 25.68 | 49.95 | 0 | 1421.86 | 1328.21 | 25.55 | 49.95 | 0 | 1403.71 | 68.98 | 92
14 | COOCHBEHAR | SM/10152 | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | TSM/009086 | 40009245 | Augmentation | MVS | GO2122009597PH | 10/02/2022 | 1750.36 | 135.02 | 1885.38 | Coochbehar Division | Northern Mechanical Division II | 1389.61 | 90.99 | 309.77 | 0 | 1790.36 | 1389.61 | 90.99 | 309.77 | 0 | 1790.36 | 94.96 | 92
15 | COOCHBEHAR | SM/10142 | Augmentation of BARA KAIMARI Piped Water Supply Scheme | TSM/009895 | 40004000 | Augmentation | MVS | GO2122009586PH | 09/02/2022 | 547.06 | 17.19 | 564.24 | Coochbehar Division | Northern Mechanical Division II | 424.77 | 11.92 | 110.24 | 0 | 546.93 | 424.77 | 11.92 | 110.24 | 0 | 546.93 | 96.93 | 97
16 | COOCHBEHAR | SM/13182 | AUGMENTATION OF BARA KODALI ZONE-II PWSS | TSM/014617 | 40035138 | Augmentation | MVS | GO2223008625PH | 12/10/2022 | 461.82 | 26.1 | 487.92 | Coochbehar Division | Northern Mechanical Division II | 268.55 | 15.31 | 0 | 0 | 283.86 | 268.55 | 15.31 | 0 | 0 | 283.86 | 58.18 | 99
17 | COOCHBEHAR | SM/16156 | AUGMENTATION OF BILSI PIPED WATER SUPPLY SCHEME | TSM/019961 | 40054721 | Augmentation | MVS | GO2223014598PH | 22/02/2023 | 96.31 | 24.05 | 120.36 | Coochbehar Division | Northern Mechanical Division II | 80.42 | 0 | 0 | 0 | 80.42 | 52.8 | 0 | 0 | 0 | 52.8 | 43.86 | 79
18 | COOCHBEHAR | SM/09302 | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | TSM/009087 | 40009251 | Augmentation | SVS | GO2122005328PH | 09/11/2021 | 551.28 | 47.65 | 598.93 | Coochbehar Division | Northern Mechanical Division II | 483.49 | 20.87 | 2.88 | 0 | 507.24 | 483.49 | 20.87 | 2.88 | 0 | 507.24 | 84.69 | 99
19 | COOCHBEHAR | SM/12371 | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | TSM/010877 | 40027453 | Augmentation | MVS | GO2223007580PH | 13/09/2022 | 1580.75 | 108.35 | 1689.1 | Coochbehar Division | Northern Mechanical Division II | 899.94 | 73.96 | 267.28 | 0 | 1241.18 | 879.42 | 73.96 | 267.28 | 0 | 1220.66 | 72.27 | 85
20 | COOCHBEHAR | SM/17443 | AUGMENTATION OF Chhota Godaikhora Pwss | TSM/019912 | 40048497 | Augmentation | MVS | GO2223017014PH | 18/03/2023 | 171.47 | 24.05 | 195.52 | Coochbehar Division | Northern Mechanical Division II | 102.16 | 5.27 | 0 | 0 | 107.43 | 102.16 | 5.27 | 0 | 0 | 107.43 | 54.95 | 93
21 | COOCHBEHAR | SM/09296 | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | TSM/009091 | 40012602 | Augmentation | MVS | GO2122005325PH | 09/11/2021 | 459.84 | 36.49 | 496.33 | Coochbehar Division | Northern Mechanical Division II | 423.35 | 12.04 | 8.62 | 0 | 444.01 | 423.35 | 12.04 | 8.62 | 0 | 444.01 | 89.46 | 85
22 | COOCHBEHAR | SM/10148 | Augmentation of Chilakhana piped water supply scheme. | TSM/008564 | 40009254 | Augmentation | MVS | GO2122009595PH | 10/02/2022 | 1093.86 | 34.37 | 1128.23 | Coochbehar Division | Northern Mechanical Division II | 707.13 | 18.39 | 179.23 | 0 | 904.75 | 707.13 | 18.39 | 179.23 | 0 | 904.75 | 80.19 | 96
23 | COOCHBEHAR | SM/09807 | Augmentation of Dakshin Bajejama Water Supply Scheme. | TSM/008969 | 40013412 | Augmentation | MVS | GO2122006290PH | 01/12/2021 | 318.9 | 18.46 | 337.36 | Coochbehar Division | Northern Mechanical Division II | 208.88 | 11.61 | 4.39 | 0 | 224.88 | 175.63 | 11.61 | 4.39 | 0 | 191.63 | 56.8 | 78
24 | COOCHBEHAR | SM/09297 | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | TSM/009089 | 40015653 | Augmentation | SVS | GO2122005325PH | 09/11/2021 | 374.91 | 37.97 | 412.88 | Coochbehar Division | Northern Mechanical Division II | 324.45 | 10.77 | 0 | 0 | 335.22 | 303.87 | 10.77 | 0 | 0 | 314.64 | 76.21 | 84
25 | COOCHBEHAR | SM/09303 | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | TSM/009085 | 40014380 | Augmentation | SVS | GO2122005329PH | 09/11/2021 | 621.28 | 33.75 | 655.03 | Coochbehar Division | Northern Mechanical Division II | 459.62 | 23.88 | 82.8 | 0 | 566.29 | 459.6 | 23.84 | 82.8 | 0 | 566.23 | 86.44 | 87
26 | COOCHBEHAR | SM/09822 | Augmentation of dhaluabari water supply scheme | TSM/008970 | 40014378 | Augmentation | MVS | GO2122006289PH | 01/12/2021 | 619.61 | 17.24 | 636.85 | Coochbehar Division | Northern Mechanical Division II | 490.93 | 11.62 | 32.21 | 0 | 534.75 | 490.93 | 11.62 | 32.21 | 0 | 534.75 | 83.97 | 98
27 | COOCHBEHAR | SM/11977 | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | TSM/010124 | 40019721 | Augmentation | MVS | GO2223006841PH | 31/08/2022 | 1980.98 | 96.68 | 2077.66 | Coochbehar Division | Northern Mechanical Division II | 959.86 | 16.99 | 48.24 | 0 | 1025.1 | 959.86 | 16.99 | 48.24 | 0 | 1025.1 | 49.34 | 58
28 | COOCHBEHAR | SM/16531 | Augmentation of GHUGHUMARI Piped Water Supply Scheme | TSM/009896 | 40034141 | Augmentation | MVS | GO2223015530PH | 10/03/2023 | 1459.86 | 87.7 | 1547.57 | Coochbehar Division | Northern Mechanical Division II | 870.79 | 69.54 | 66.93 | 0 | 1007.26 | 851.12 | 69.54 | 66.93 | 0 | 987.6 | 63.82 | 84
29 | COOCHBEHAR | SM/10150 | Augmentation of Gosanimari piped water supply scheme. | TSM/008560 | 40009255 | Augmentation | MVS | GO2122009595PH | 10/02/2022 | 1713.31 | 51.66 | 1764.97 | Coochbehar Division | Northern Mechanical Division II | 1475.71 | 49.11 | 129.84 | 0 | 1654.66 | 1475.71 | 49.11 | 129.84 | 0 | 1654.66 | 93.75 | 88
30 | COOCHBEHAR | SM/13380 | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | TSM/015366 | 40035441 | Augmentation | MVS | GO2223008935PH | 19/10/2022 | 846.5 | 52.2 | 898.7 | Coochbehar Division | Northern Mechanical Division II | 339.83 | 11.61 | 37.62 | 0 | 389.06 | 303.16 | 11.61 | 37.62 | 0 | 352.39 | 39.21 | 67
31 | COOCHBEHAR | SM/13148 | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | TSM/014609 | 40029011 | Augmentation | MVS | GO2223008621PH | 12/10/2022 | 462.25 | 26.1 | 488.35 | Coochbehar Division | Northern Mechanical Division II | 204.42 | 0 | 15.76 | 0 | 220.18 | 204.42 | 0 | 15.76 | 0 | 220.18 | 45.09 | 54
32 | COOCHBEHAR | SM/16518 | AUGMENTATION OF GROUND WATER BASED PHULBARI PART A PWSS | TSM/018468 | 40062681 | Augmentation | SVS | GO2223015228PH | 03/03/2023 | 517.29 | 47.27 | 564.56 | Coochbehar Division | Northern Mechanical Division II | 312.62 | 0 | 0 | 0 | 312.62 | 302.37 | 0 | 0 | 0 | 302.37 | 53.56 | 45
33 | COOCHBEHAR | SM/14932 | AUGMENTATION OF GROUND WATER BASED ALOKJHARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION | TSM/016304 | 40034728 | Augmentation | MVS | GO2223012963PH | 03/02/2023 | 323.01 | 21.09 | 344.1 | Coochbehar Division | Northern Mechanical Division II | 156.32 | 20.47 | 0 | 0 | 176.8 | 156.32 | 20.47 | 0 | 0 | 176.8 | 51.38 | 88
34 | COOCHBEHAR | SM/16139 | AUGMENTATION OF GROUND WATER BASED BAJRAPUR PWSS TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/018080 | 40048826 | Augmentation | MVS | GO2223014688PH | 22/02/2023 | 500.29 | 42.98 | 543.27 | Coochbehar Division | Northern Mechanical Division II | 256.13 | 19.33 | 0 | 0 | 275.46 | 232.23 | 19.33 | 0 | 0 | 251.56 | 46.31 | 70
35 | COOCHBEHAR | SM/14928 | AUGMENTATION OF GROUND WATER BASED BARA PHALIMARI PWSS DINHATA -I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/016314 | 40034742 | Augmentation | MVS | GO2223012967PH | 03/02/2023 | 441.03 | 20.71 | 461.74 | Coochbehar Division | Northern Mechanical Division II | 90.16 | 5.65 | 0 | 0 | 95.81 | 78.75 | 5.65 | 0 | 0 | 84.4 | 18.28 | 75
36 | COOCHBEHAR | SM/13860 | AUGMENTATION OF GROUND WATER BASED BARAIBARI PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016279 | 40034993 | Augmentation | MVS | GO2223010068PH | 25/11/2022 | 453.33 | 20.45 | 473.77 | Coochbehar Division | Northern Mechanical Division II | 257.89 | 17.67 | 0 | 0 | 275.56 | 257.89 | 17.67 | 0 | 0 | 275.56 | 58.16 | 84
37 | COOCHBEHAR | SM/13181 | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/013269 | 40029490 | Augmentation | MVS | GO2223008624PH | 12/10/2022 | 490.92 | 26.1 | 517.02 | Coochbehar Division | Northern Mechanical Division II | 459.52 | 21.56 | 16.89 | 0 | 497.97 | 459.52 | 21.56 | 16.89 | 0 | 497.97 | 96.32 | 78
38 | COOCHBEHAR | SM/16519 | AUGMENTATION OF GROUND WATER BASED BARASOLMARI-SINGIJANI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/017376 | 40062700 | Augmentation | SVS | GO2223015226PH | 03/03/2023 | 517.72 | 21.49 | 539.21 | Coochbehar Division | Northern Mechanical Division II | 277.36 | 7.21 | 0 | 0 | 284.57 | 277.36 | 7.21 | 0 | 0 | 284.57 | 52.78 | 78
39 | COOCHBEHAR | SM/13222 | AUGMENTATION OF GROUND WATER BASED BASKOTAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/013275 | 40036747 | Augmentation | SVS | GO2223008684PH | 13/10/2022 | 256.29 | 38.16 | 294.45 | Coochbehar Division | Northern Mechanical Division II | 122.19 | 10.65 | 13.27 | 0 | 146.11 | 82.39 | 10.65 | 13.27 | 0 | 106.32 | 36.11 | 45
40 | COOCHBEHAR | SM/16140 | AUGMENTATION OF GROUND WATER BASED BHERBHERI PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/017362 | 40049358 | Augmentation | MVS | GO2223014690PH | 22/02/2023 | 532.26 | 42.98 | 575.24 | Coochbehar Division | Northern Mechanical Division II | 241.85 | 15.76 | 0 | 0 | 257.61 | 241.85 | 15.76 | 0 | 0 | 257.61 | 44.78 | 65
41 | COOCHBEHAR | SM/13223 | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/013273 | 40029492 | Augmentation | SVS | GO2223008685PH | 13/10/2022 | 397.79 | 38.16 | 435.95 | Coochbehar Division | Northern Mechanical Division II | 99.66 | 17.28 | 0 | 0 | 116.94 | 99.66 | 17.28 | 0 | 0 | 116.94 | 26.82 | 68
42 | COOCHBEHAR | SM/13859 | AUGMENTATION OF GROUND WATER BASED BHURKUSH PWSS TAFANGANJ-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016277 | 40034530 | Augmentation | MVS | GO2223010067PH | 25/11/2022 | 250.56 | 26.1 | 276.66 | Coochbehar Division | Northern Mechanical Division II | 160.94 | 0 | 61.6 | 0 | 222.54 | 160.94 | 0 | 61.6 | 0 | 222.54 | 80.44 | 85
43 | COOCHBEHAR | SM/14904 | AUGMENTATION OF GROUND WATER BASED CHARALJANI Piped Water Supply Scheme TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | TSM/016199 | 40034870 | Augmentation | SVS | GO2223012965PH | 03/02/2023 | 560.09 | 42.96 | 603.05 | Coochbehar Division | Northern Mechanical Division II | 332.98 | 27.46 | 40.58 | 0 | 401.02 | 227.07 | 27.46 | 40.58 | 0 | 295.11 | 48.94 | 61
44 | COOCHBEHAR | SM/16520 | AUGMENTATION OF GROUND WATER BASED CHHAT RAMPUR PWSS TUFANGANJ I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | TSM/018467 | 40054756 | Augmentation | MVS | GO2223015227PH | 03/03/2023 | 450.62 | 42.98 | 493.6 | Coochbehar Division | Northern Mechanical Division II | 342.02 | 15.31 | 0 | 0 | 357.33 | 340.47 | 15.31 | 0 | 0 | 355.79 | 72.08 | 76
45 | COOCHBEHAR | SM/14935 | AUGMENTATION OF GROUND WATER BASED CHIKLIGURI PIPED WATER SUPPLY SCHEME TUFANGANJ - I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | TSM/016200 | 40034967 | Augmentation | SVS | GO2223012966PH | 03/02/2023 | 131.35 | 26.1 | 157.45 | Coochbehar Division | Northern Mechanical Division II | 51.06 | 5.52 | 0 | 0 | 56.59 | 47.68 | 5.52 | 0 | 0 | 53.21 | 33.79 | 74
46 | COOCHBEHAR | SM/13229 | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. | TSM/014611 | 40033816 | Augmentation | SVS | GO2223008691PH | 13/10/2022 | 608.58 | 38.16 | 646.74 | Coochbehar Division | Northern Mechanical Division II | 235.99 | 25.62 | 0 | 0 | 261.62 | 235.99 | 25.62 | 0 | 0 | 261.62 | 40.45 | 74
47 | COOCHBEHAR | SM/13230 | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | TSM/014608 | 40027582 | Augmentation | MVS | GO2223008692PH | 13/10/2022 | 450.06 | 26.1 | 476.16 | Coochbehar Division | Northern Mechanical Division II | 203.2 | 0 | 15.4 | 0 | 218.6 | 203.2 | 0 | 15.4 | 0 | 218.6 | 45.91 | 82
48 | COOCHBEHAR | SM/13152 | Augmentation of Ground Water Based Dakshin Basrajbala Zone-II PWSS (Haldibari Block) | TSM/014610 | 40027583 | Augmentation | MVS | GO2223008667PH | 12/10/2022 | 422.44 | 26.1 | 448.54 | Coochbehar Division | Northern Mechanical Division II | 10.03 | 7.95 | 8.59 | 0 | 26.57 | 10 | 7.95 | 8.59 | 0 | 26.54 | 5.92 | 37
49 | COOCHBEHAR | SM/16521 | AUGMENTATION OF GROUND WATER BASED DALUA DASGIR PWSS COOCHBEHAR - I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/017369 | 40054819 | Augmentation | MVS | GO2223015225PH | 03/03/2023 | 444.99 | 42.98 | 487.98 | Coochbehar Division | Northern Mechanical Division II | 162.37 | 24.98 | 30.98 | 0 | 218.33 | 162.37 | 24.98 | 30.98 | 0 | 218.33 | 44.74 | 45
50 | COOCHBEHAR | SM/16165 | AUGMENTATION OF GROUND WATER BASED DHALDIBARI PIPED WATER SUPPLY SCHEME OF TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/017373 | 40062718 | Augmentation | SVS | GO2223014601PH | 22/02/2023 | 508.82 | 42.98 | 551.8 | Coochbehar Division | Northern Mechanical Division II | 294.12 | 20.76 | 26.13 | 0 | 341.01 | 289.85 | 20.76 | 26.13 | 0 | 336.74 | 61.03 | 84
51 | COOCHBEHAR | SM/14933 | AUGMENTATION OF GROUND WATER BASED GAJENDRAPUR CHOWRANGEE PWSS HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016283 | 40035055 | Augmentation | SVS | GO2223012968PH | 03/02/2023 | 923.54 | 62.13 | 985.67 | Coochbehar Division | Northern Mechanical Division II | 297.97 | 7.39 | 87.54 | 0 | 392.9 | 297.88 | 7.39 | 87.54 | 0 | 392.81 | 39.85 | 53
52 | COOCHBEHAR | SM/16522 | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -I PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/018083 | 40054842 | Augmentation | MVS | GO2223015220PH | 03/03/2023 | 261.92 | 44.24 | 306.15 | Coochbehar Division | Northern Mechanical Division II | 6.84 | 17.54 | 2.07 | 0 | 26.46 | 6.84 | 17.54 | 2.07 | 0 | 26.46 | 8.64 | 81
53 | COOCHBEHAR | SM/16523 | AUGMENTATION OF GROUND WATER BASED GHARGHARIA ZONE -II PWSS COOCHBEHAR I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/018084 | 40054161 | Augmentation | SVS | GO2223015066PH | 03/03/2023 | 196.12 | 44.24 | 240.36 | Coochbehar Division | Northern Mechanical Division II | 43.97 | 0 | 2.93 | 0 | 46.9 | 43.97 | 0 | 2.93 | 0 | 46.9 | 19.51 | 72
54 | COOCHBEHAR | SM/16146 | AUGMENTATION OF GROUND WATER BASED GOPALPUR PWSS COOCH BEHAR-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016282 | 40049351 | Augmentation | MVS | GO2223014692PH | 22/02/2023 | 896.48 | 64.67 | 961.15 | Coochbehar Division | Northern Mechanical Division II | 298.28 | 16.57 | 110.3 | 0 | 425.15 | 296.21 | 16.57 | 110.3 | 0 | 423.08 | 44.02 | 65
55 | COOCHBEHAR | SM/16147 | AUGMENTATION OF GROUND WATER BASED HEMKUMARI PIPED WATER SUPPLY SCHEME ZONE-I (PART-B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION, PHED. | TSM/016051 | 40049371 | Augmentation | MVS | GO2223014691PH | 22/02/2023 | 141.87 | 0 | 141.87 | Coochbehar Division |  | 9.12 | 0 | 18.53 | 0 | 27.65 | 9.12 | 0 | 18.53 | 0 | 27.65 | 19.49 | 76
56 | COOCHBEHAR | SM/13224 | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/013272 | 40029491 | Augmentation | MVS | GO2223008686PH | 13/10/2022 | 456.8 | 26.1 | 482.9 | Coochbehar Division | Northern Mechanical Division II | 145.24 | 0 | 18.26 | 0 | 163.5 | 145.24 | 0 | 18.26 | 0 | 163.5 | 33.86 | 45
57 | COOCHBEHAR | SM/13153 | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | TSM/014614 | 40036723 | Augmentation | MVS | GO2223008668PH | 12/10/2022 | 550.41 | 26.1 | 576.51 | Coochbehar Division | Northern Mechanical Division II | 106.64 | 16.82 | 74.87 | 0 | 198.33 | 106.64 | 16.82 | 74.87 | 0 | 198.33 | 34.4 | 60
58 | COOCHBEHAR | SM/16148 | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-I PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/018176 | 40048814 | Augmentation | MVS | GO2223014693PH | 22/02/2023 | 854.2 | 85.97 | 940.17 | Coochbehar Division | Northern Mechanical Division II | 176.83 | 14.21 | 0 | 0 | 191.05 | 173.71 | 14.21 | 0 | 0 | 187.92 | 19.99 | 45
59 | COOCHBEHAR | SM/16515 | AUGMENTATION OF GROUND WATER BASED KONACHATRA ZONE-II PIPED WATER SUPPLY SCHEME OF SITAI BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/018196 | 40048735 | Augmentation | MVS | GO2223015199PH | 03/03/2023 | 537.2 | 42.98 | 580.19 | Coochbehar Division | Northern Mechanical Division II | 61.58 | 22.68 | 5.06 | 0 | 89.33 | 61.58 | 22.68 | 5.06 | 0 | 89.33 | 15.4 | 48
60 | COOCHBEHAR | SM/13154 | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | TSM/014622 | 40036726 | Augmentation | MVS | GO2223008669PH | 12/10/2022 | 457.52 | 39.15 | 496.67 | Coochbehar Division | Northern Mechanical Division II | 174.05 | 0.09 | 0 | 0 | 174.14 | 174.05 | 0.09 | 0 | 0 | 174.14 | 35.06 | 80
61 | COOCHBEHAR | SM/13225 | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | TSM/014621 | 40027269 | Augmentation | MVS | GO2223008687PH | 13/10/2022 | 591.08 | 39.15 | 630.23 | Coochbehar Division | Northern Mechanical Division II | 291.59 | 23.19 | 0 | 0 | 314.78 | 291.59 | 23.19 | 0 | 0 | 314.78 | 49.95 | 65
62 | COOCHBEHAR | SM/16149 | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-I PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/018219 | 40048701 | Augmentation | MVS | GO2223014687PH | 22/02/2023 | 530.79 | 64.48 | 595.27 | Coochbehar Division | Northern Mechanical Division II | 258.57 | 40.02 | 25.25 | 0 | 323.85 | 239.12 | 40.02 | 25.25 | 0 | 304.39 | 51.14 | 70
63 | COOCHBEHAR | SM/16166 | AUGMENTATION OF GROUND WATER BASED MAHISHKUCHI ZONE-II PIPED WATER SUPPLY SCHEME OF TUFANGUNJ-II BLOCK WITHIN COOCHBEHAR DISTRICT | TSM/018233 | 40062728 | Augmentation | SVS | GO2223014587PH | 22/02/2023 | 286.44 | 42.98 | 329.42 | Coochbehar Division | Northern Mechanical Division II | 111.31 | 26.5 | 0 | 0 | 137.82 | 92.25 | 26.5 | 0 | 0 | 118.75 | 36.05 | 81
64 | COOCHBEHAR | SM/16517 | AUGMENTATION OF GROUND WATER BASED MANTANI PWSS TUFANGANJ - IIBLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/017374 | 40054744 | Augmentation | MVS | GO2223015229PH | 03/03/2023 | 300.29 | 21.49 | 321.78 | Coochbehar Division | Northern Mechanical Division II | 196.89 | 15.62 | 2.67 | 0 | 215.18 | 196.89 | 15.62 | 2.67 | 0 | 215.18 | 66.87 | 88
65 | COOCHBEHAR | SM/16473 | AUGMENTATION OF GROUND WATER BASED MUKUL DANGA PWSS MATHABHANGA - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/018081 | 40049483 | Augmentation | MVS | GO2223015198PH | 02/03/2023 | 532.53 | 21.49 | 554.02 | Coochbehar Division | Northern Mechanical Division II | 187.99 | 7.97 | 0 | 0 | 195.95 | 187.99 | 7.97 | 0 | 0 | 195.95 | 35.37 | 45
66 | COOCHBEHAR | SM/15981 | AUGMENTATION OF GROUND WATER BASED NAJIRAN DEUTIKATA PWSS TAFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016281 | 40049344 | Augmentation | MVS | GO2223014683PH | 22/02/2023 | 434.39 | 20.7 | 455.1 | Coochbehar Division | Northern Mechanical Division II | 253.93 | 8.28 | 2.76 | 0 | 264.96 | 253.93 | 8.28 | 2.76 | 0 | 264.96 | 58.22 | 75
67 | COOCHBEHAR | SM/16150 | AUGMENTATION OF GROUND WATER BASED NAJIRGANJ PWSS DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016278 | 40049369 | Augmentation | MVS | GO2223014695PH | 22/02/2023 | 504.55 | 21.09 | 525.64 | Coochbehar Division | Northern Mechanical Division II | 263.83 | 14.02 | 40.91 | 0 | 318.75 | 263.77 | 14.02 | 40.91 | 0 | 318.7 | 60.63 | 70
68 | COOCHBEHAR | SM/14934 | AUGMENTATION OF GROUND WATER BASED NAKKATI PWSS COOCH BEHAR-I BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/016280 | 40034533 | Augmentation | MVS | GO2223012964PH | 03/02/2023 | 446.98 | 41.44 | 488.42 | Coochbehar Division | Northern Mechanical Division II | 102.18 | 22.26 | 0 | 0 | 124.44 | 83.88 | 22.26 | 0 | 0 | 106.13 | 21.73 | 61
69 | COOCHBEHAR | SM/16151 | AUGMENTATION OF GROUND WATER BASED NAKKATIGACHHI PIPED WATER SUPPLY SCHEME TUFANGANJ - I BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. Dte. | TSM/016198 | 40049362 | Augmentation | MVS | GO2223014682PH | 22/02/2023 | 372.78 | 42.22 | 415 | Coochbehar Division | Northern Mechanical Division II | 174.73 | 9.33 | 6.78 | 0 | 190.84 | 174.73 | 9.33 | 6.78 | 0 | 190.84 | 45.99 | 74
70 | COOCHBEHAR | SM/13155 | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | TSM/014623 | 40036730 | Augmentation | MVS | GO2223008670PH | 12/10/2022 | 758.98 | 39.15 | 798.13 | Coochbehar Division | Northern Mechanical Division II | 140.38 | 0 | 25.92 | 0 | 166.3 | 140.38 | 0 | 25.92 | 0 | 166.3 | 20.84 | 79
71 | COOCHBEHAR | SM/13156 | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | TSM/014620 | 40064065 | Augmentation | MVS | GO2223008671PH | 12/10/2022 | 880.63 | 52.2 | 932.83 | Coochbehar Division | Northern Mechanical Division II | 338.07 | 38.7 | 59.25 | 0 | 436.02 | 265.87 | 38.7 | 59.25 | 0 | 363.82 | 39 | 65
72 | COOCHBEHAR | SM/13381 | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | TSM/015360 | 40029009 | Augmentation | MVS | GO2223008939PH | 19/10/2022 | 665.08 | 39.15 | 704.23 | Coochbehar Division | Northern Mechanical Division II | 266.09 | 35.93 | 42.81 | 0 | 344.83 | 215.83 | 35.93 | 42.81 | 0 | 294.57 | 41.83 | 86
73 | COOCHBEHAR | SM/16167 | AUGMENTATION OF GROUND WATER BASED SHILGHAGRI PWSS TUFANGANJ - II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/018082 | 40062732 | Augmentation | SVS | GO2223014593PH | 22/02/2023 | 263.26 | 21.49 | 284.75 | Coochbehar Division | Northern Mechanical Division II | 168.74 | 15.53 | 2.76 | 0 | 187.03 | 168.74 | 15.53 | 2.76 | 0 | 187.03 | 65.68 | 78
74 | COOCHBEHAR | SM/13316 | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | TSM/015369 | 40064068 | Augmentation | SVS | GO2223008806PH | 17/10/2022 | 947.55 | 52.2 | 999.75 | Coochbehar Division | Northern Mechanical Division II | 432.57 | 0 | 24.06 | 0 | 456.64 | 432.07 | 0 | 24.06 | 0 | 456.13 | 45.62 | 78
75 | COOCHBEHAR | SM/13379 | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | TSM/015368 | 40035450 | Augmentation | MVS | GO2223008945PH | 19/10/2022 | 811.71 | 39.15 | 850.86 | Coochbehar Division | Northern Mechanical Division II | 352.6 | 20.51 | 49.11 | 0 | 422.22 | 316.95 | 20.51 | 49.11 | 0 | 386.57 | 45.43 | 84
76 | COOCHBEHAR | SM/13684 | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | TSM/015367 | 40035071 | Augmentation | MVS | GO2223009718PH | 14/11/2022 | 944.77 | 52.2 | 996.96 | Coochbehar Division | Northern Mechanical Division II | 331.17 | 10.43 | 48.4 | 0 | 390 | 331.17 | 10.43 | 48.4 | 0 | 390 | 39.12 | 68
77 | COOCHBEHAR | SM/13289 | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | TSM/015348 | 40035434 | Augmentation | MVS | GO2223008804PH | 17/10/2022 | 942.52 | 52.2 | 994.72 | Coochbehar Division | Northern Mechanical Division II | 195.97 | 0 | 34.07 | 0 | 230.03 | 190.53 | 0 | 34.07 | 0 | 224.59 | 22.58 | 59
78 | COOCHBEHAR | SM/13226 | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | TSM/013274 | 40033772 | Augmentation | MVS | GO2223008688PH | 13/10/2022 | 518.78 | 26.1 | 544.88 | Coochbehar Division | Northern Mechanical Division II | 318.29 | 0 | 20.69 | 0 | 338.98 | 310.25 | 0 | 20.69 | 0 | 330.94 | 60.74 | 85
79 | COOCHBEHAR | SM/13159 | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | TSM/014607 | 40036935 | Augmentation | MVS | GO2223008673PH | 12/10/2022 | 596.73 | 26.1 | 622.83 | Coochbehar Division | Northern Mechanical Division II | 389.16 | 9.38 | 16.31 | 0 | 414.85 | 375.5 | 9.38 | 16.31 | 0 | 401.19 | 64.41 | 86
80 | COOCHBEHAR | SM/13157 | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | TSM/014665 | 40030519 | Augmentation | MVS | GO2223008672PH | 12/10/2022 | 909.19 | 39.15 | 948.34 | Coochbehar Division | Northern Mechanical Division II | 497.9 | 4.54 | 0 | 0 | 502.44 | 475.31 | 4.54 | 0 | 0 | 479.85 | 50.6 | 60
81 | COOCHBEHAR | SM/13227 | AUGMENTATION OF GROUND WATER BASED UPENCHAUKIKUCHLIBARI PIPED WATER SUPPLY SCHEME | TSM/014618 | 40027584 | Augmentation | MVS | GO2223008689PH | 13/10/2022 | 397.82 | 39.15 | 436.97 | Coochbehar Division | Northern Mechanical Division II | 210.09 | 0 | 0 | 0 | 210.09 | 210.09 | 0 | 0 | 0 | 210.09 | 48.08 | 74
82 | COOCHBEHAR | SM/18122 | AUGMENTATION OF GROUND WATER HEMKUMARI ZONE-I ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | TSM/014612 | 40035117 | Augmentation | MVS | GO2223017948PH | 29/03/2023 | 462.25 | 26.1 | 488.35 | Coochbehar Division | Northern Mechanical Division II | 228.3 | 0 | 0 | 0 | 228.3 | 222.35 | 0 | 0 | 0 | 222.35 | 45.53 | 67
83 | COOCHBEHAR | SM/13149 | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | TSM/014613 | 40030522 | Augmentation | MVS | GO2223008623PH | 12/10/2022 | 435.49 | 26.1 | 461.59 | Coochbehar Division | Northern Mechanical Division II | 189.25 | 0 | 15.71 | 0 | 204.96 | 189.25 | 0 | 15.71 | 0 | 204.96 | 44.4 | 83
84 | COOCHBEHAR | SM/09298 | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | TSM/009088 | 40024450 | Augmentation | SVS | GO2122005323PH | 09/11/2021 | 342.72 | 32.4 | 375.12 | Coochbehar Division | Northern Mechanical Division II | 232.73 | 0 | 59.03 | 0 | 291.76 | 232.73 | 0 | 59.03 | 0 | 291.76 | 77.78 | 93
85 | COOCHBEHAR | SM/18297 | Augmentation of Guriahati Pwss | TSM/019982 | 40049418 | Augmentation | SVS | 1668/PHE-28011/125/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 1300.02 | 141.77 | 1441.79 | Coochbehar Division | Northern Mechanical Division II | 392.99 | 33.48 | 9.83 | 0 | 436.3 | 384.82 | 33.48 | 9.83 | 0 | 428.13 | 29.69 | 85
86 | COOCHBEHAR | SM/13150 | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | TSM/014615 | 40064066 | Augmentation | MVS | GO2223008626PH | 12/10/2022 | 588.5 | 26.1 | 614.6 | Coochbehar Division | Northern Mechanical Division II | 220.68 | 3.73 | 15.76 | 0 | 240.17 | 122.96 | 3.73 | 15.76 | 0 | 142.45 | 23.18 | 49
87 | COOCHBEHAR | SM/10220 | Augmentation of JHAUKUTHI Piped Water Supply Scheme | TSM/009775 | 40003380 | Augmentation | SVS | GO2122009806PH | 24/02/2022 | 308.94 | 18.97 | 327.91 | Coochbehar Division | Northern Mechanical Division II | 263.98 | 14.63 | 0 | 0 | 278.61 | 263.83 | 14.63 | 0 | 0 | 278.46 | 84.92 | 97
88 | COOCHBEHAR | SM/13151 | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | TSM/014616 | 40030521 | Augmentation | MVS | GO2223008622PH | 12/10/2022 | 447.84 | 26.1 | 473.94 | Coochbehar Division | Northern Mechanical Division II | 323.46 | 16.09 | 0 | 0 | 339.55 | 323.46 | 16.09 | 0 | 0 | 339.55 | 71.64 | 98
89 | COOCHBEHAR | SM/14183 | AUGMENTATION OF KALARAYERKUTHI PIPED WATER SUPPLY SCHEME | TSM/010601 | 40034363 | Augmentation | MVS | GO2223011536PH | 02/01/2023 | 1783.81 | 111.6 | 1895.41 | Coochbehar Division | Northern Mechanical Division II | 1082.43 | 71.66 | 54.85 | 0 | 1208.93 | 1057.42 | 71.66 | 54.85 | 0 | 1183.93 | 62.46 | 79
90 | COOCHBEHAR | SM/09810 | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | TSM/009132 | 40009252 | Augmentation | MVS | GO2122006286PH | 01/12/2021 | 686.23 | 57.13 | 743.36 | Coochbehar Division | Northern Mechanical Division II | 619.62 | 20.92 | 0 | 0 | 640.55 | 619.62 | 20.92 | 0 | 0 | 640.55 | 86.17 | 85
91 | COOCHBEHAR | SM/09808 | Augmentation of Kauardara Water Supply Scheme | TSM/008968 | 40016239 | Augmentation | MVS | GO2122006290PH | 01/12/2021 | 398.77 | 18.46 | 417.23 | Coochbehar Division | Northern Mechanical Division II | 248.73 | 11.66 | 149.97 | 0 | 410.37 | 248.73 | 11.66 | 149.97 | 0 | 410.37 | 98.36 | 99
92 | COOCHBEHAR | SM/13403 | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | TSM/010170 | 40029008 | Augmentation | MVS | GO2223009062PH | 21/10/2022 | 2379.5 | 148 | 2527.51 | Coochbehar Division | Northern Mechanical Division II | 1016.17 | 16.32 | 61.6 | 0 | 1094.09 | 1016.17 | 16.32 | 61.6 | 0 | 1094.09 | 43.29 | 59
93 | COOCHBEHAR | SM/18788 | AUGMENTATION OF KHOLTA PIPED WATER SUPPLY SCHEME | TSM/010885 | 40034268 | Augmentation | SVS | 2629/PHE-28011/108/2022-ESTT CELL-Dept. of PHE | 31/08/2023 | 1007 | 59.01 | 1066.01 | Coochbehar Division | Northern Mechanical Division II | 547.77 | 4.74 | 32.5 | 0 | 585.01 | 547.77 | 4.74 | 32.5 | 0 | 585.01 | 54.88 | 57
94 | COOCHBEHAR | SM/16472 | AUGMENTATION OF KRISHNAPUR PIPED WATER SUPPLY SCHEME | TSM/020152 | 40048455 | Augmentation | MVS | GO2223015197PH | 02/03/2023 | 247.18 | 24.05 | 271.23 | Coochbehar Division | Northern Mechanical Division II | 115.35 | 22.54 | 0 | 0 | 137.89 | 115.35 | 22.54 | 0 | 0 | 137.89 | 50.84 | 81
95 | COOCHBEHAR | SM/14112 | Augmentation of MARADANGA Piped Water Supply Scheme | TSM/009898 | 40004092 | Augmentation | MVS | GO2223010906PH | 15/12/2022 | 1588.85 | 51.66 | 1640.51 | Coochbehar Division | Northern Mechanical Division II | 929.37 | 36.88 | 95.18 | 0 | 1061.44 | 777.68 | 36.88 | 95.18 | 0 | 909.74 | 55.45 | 85
96 | COOCHBEHAR | SM/11486 | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | TSM/010971 | 40037411 | Augmentation | SVS | GO2223005063PH | 14/07/2022 | 463.55 | 42.22 | 505.77 | Coochbehar Division | Northern Mechanical Division II | 385.96 | 31.56 | 14.63 | 0 | 432.15 | 385.96 | 31.56 | 14.63 | 0 | 432.15 | 85.44 | 96
97 | COOCHBEHAR | SM/15935 | Augmentation of Natabari Pwss | TSM/019963 | 40048684 | Augmentation | MVS | GO2223014699PH | 22/02/2023 | 677.63 | 0 | 677.63 | Coochbehar Division | Northern Mechanical Division II | 229.17 | 0 | 0 | 0 | 229.17 | 141.39 | 0 | 0 | 0 | 141.39 | 20.87 | 68
98 | COOCHBEHAR | SM/13402 | AUGMENTATION OF NIGAMNAGAR PIPED WATER SUPPLY SCHEME COB Division PHED. | TSM/010175 | 40034216 | Augmentation | MVS | GO2223009061PH | 21/10/2022 | 2422.33 | 89.38 | 2511.71 | Coochbehar Division | Northern Mechanical Division II | 1050.5 | 41.59 | 32.48 | 0 | 1124.57 | 897.74 | 41.59 | 32.48 | 0 | 971.81 | 38.69 | 68
99 | COOCHBEHAR | SM/16526 | Augmentation of Panisala PWSS. | TSM/019999 | 40054857 | Augmentation | MVS | GO2223015219PH | 03/03/2023 | 109.12 | 24.05 | 133.17 | Coochbehar Division | Northern Mechanical Division II | 84.3 | 11.42 | 16.39 | 0 | 112.1 | 84.3 | 11.42 | 16.39 | 0 | 112.1 | 84.18 | 83
100 | COOCHBEHAR | SM/10162 | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | TSM/009752 | 40003705 | Augmentation | MVS | GO2122009637PH | 11/02/2022 | 466.91 | 18.46 | 485.38 | Coochbehar Division | Northern Mechanical Division II | 361.35 | 6.05 | 36.1 | 0 | 403.5 | 361.35 | 6.05 | 36.1 | 0 | 403.5 | 83.13 | 87
101 | COOCHBEHAR | SM/09299 | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | TSM/009090 | 40009253 | Augmentation | SVS | GO2122005323PH | 09/11/2021 | 380.05 | 43.68 | 423.73 | Coochbehar Division | Northern Mechanical Division II | 347.71 | 16.71 | 12.04 | 0 | 376.46 | 344.47 | 16.71 | 12.04 | 0 | 373.22 | 88.08 | 90
102 | COOCHBEHAR | SM/11272 | Augmentation of RAMPUR Piped Water Supply Scheme | TSM/009773 | 40003668 | Augmentation | MVS | GO2223004457PH | 24/06/2022 | 1657.6 | 38.88 | 1696.48 | Coochbehar Division | Northern Mechanical Division II | 1193.17 | 25.28 | 0 | 0 | 1218.45 | 1193.17 | 25.28 | 0 | 0 | 1218.45 | 71.82 | 87
103 | COOCHBEHAR | SM/09300 | Augmentation of Rasikbil piped water supply scheme. | TSM/008565 | 40009306 | Augmentation | MVS | GO2122005327PH | 09/11/2021 | 849.46 | 34.12 | 883.58 | Coochbehar Division | Northern Mechanical Division II | 746.04 | 20.49 | 40.64 | 0 | 807.16 | 746.04 | 20.49 | 40.64 | 0 | 807.16 | 91.35 | 90
104 | COOCHBEHAR | SM/10164 | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | TSM/009751 | 40004003 | Augmentation | MVS | GO2122009646PH | 11/02/2022 | 420.64 | 18.46 | 439.11 | Coochbehar Division | Northern Mechanical Division II | 321.41 | 11.21 | 75.34 | 0 | 407.95 | 309.87 | 11.21 | 75.34 | 0 | 396.41 | 90.28 | 95
105 | COOCHBEHAR | SM/13385 | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | TSM/015358 | 40035466 | Augmentation | MVS | GO2223008936PH | 19/10/2022 | 442.22 | 26.1 | 468.31 | Coochbehar Division | Northern Mechanical Division II | 208.65 | 23.12 | 18.07 | 0 | 249.85 | 201.13 | 23.12 | 18.07 | 0 | 242.32 | 51.74 | 64
106 | COOCHBEHAR | SM/13382 | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | TSM/015359 | 40035456 | Augmentation | MVS | GO2223008933PH | 19/10/2022 | 414.86 | 26.1 | 440.96 | Coochbehar Division | Northern Mechanical Division II | 229.21 | 14.75 | 4.2 | 0 | 248.17 | 229.21 | 14.75 | 4.2 | 0 | 248.17 | 56.28 | 85
107 | COOCHBEHAR | SM/18757 | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME | TSM/010440 | 40034414 | Augmentation | MVS | 2483/PHE-28011/107/2022-ESTT CELL-Dept. of PHE | 21/08/2023 | 1619.49 | 74.07 | 1693.56 | Coochbehar Division | Northern Mechanical Division II | 944.77 | 26.45 | 37.98 | 0 | 1009.2 | 940.52 | 26.45 | 37.98 | 0 | 1004.95 | 59.34 | 65
108 | COOCHBEHAR | SM/10149 | Augmentation of Singimari Bhetaguri piped water supply scheme. | TSM/008562 | 40009320 | Augmentation | MVS | GO2122009595PH | 10/02/2022 | 1339.21 | 34.24 | 1373.45 | Coochbehar Division | Northern Mechanical Division II | 996.91 | 25.9 | 138.55 | 0 | 1161.37 | 996.91 | 25.9 | 138.55 | 0 | 1161.37 | 84.56 | 92
109 | COOCHBEHAR | SM/10147 | Augmentation of Sitai piped water supply scheme. | TSM/008563 | 40009409 | Augmentation | MVS | GO2122009595PH | 10/02/2022 | 1666.02 | 68.91 | 1734.93 | Coochbehar Division | Northern Mechanical Division II | 1076.02 | 41.68 | 150.76 | 0 | 1268.46 | 1076.02 | 41.68 | 150.76 | 0 | 1268.46 | 73.11 | 93
110 | COOCHBEHAR | SM/09301 | Augmentation of Takagach piped water supply scheme. | TSM/008558 | 40012582 | Augmentation | SVS | GO2122005326PH | 09/11/2021 | 598.04 | 18.07 | 616.11 | Coochbehar Division | Northern Mechanical Division II | 539.11 | 10.93 | 31.01 | 0 | 581.06 | 539.11 | 10.93 | 31.01 | 0 | 581.06 | 94.31 | 85
111 | COOCHBEHAR | SM/15930 | Augmentation of Tutiarkuthi Piped Water Supply Scheme. | TSM/019901 | 40048360 | Augmentation | MVS | GO2223014686PH | 22/02/2023 | 592.6 | 24.05 | 616.66 | Coochbehar Division | Northern Mechanical Division II | 353.42 | 7.02 | 0 | 0 | 360.44 | 353.42 | 7.02 | 0 | 0 | 360.43 | 58.45 | 71
112 | COOCHBEHAR | SM/13228 | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | TSM/014619 | 40029010 | Augmentation | MVS | GO2223008690PH | 13/10/2022 | 796.4 | 39.15 | 835.55 | Coochbehar Division | Northern Mechanical Division II | 456.83 | 23.01 | 0 | 0 | 479.84 | 453.8 | 23.01 | 0 | 0 | 476.81 | 57.06 | 85
113 | COOCHBEHAR | SM/10221 | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | TSM/009753 | 40003322 | Augmentation | MVS | GO2122009807PH | 24/02/2022 | 751.87 | 18.46 | 770.33 | Coochbehar Division | Northern Mechanical Division II | 369.91 | 13.77 | 303.2 | 0 | 686.88 | 369.88 | 12.12 | 303.2 | 0 | 685.19 | 88.95 | 89
114 | COOCHBEHAR | SM/10157 | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of SOULMARI Piped water supply schemes. | TSM/009756 | 40003298 | Augmentation | MVS | GO2122009653PH | 11/02/2022 | 347.65 | 18.46 | 366.11 | Coochbehar Division | Northern Mechanical Division II | 248.7 | 17.6 | 86.38 | 0 | 352.68 | 248.7 | 17.6 | 86.38 | 0 | 352.68 | 96.33 | 95
115 | COOCHBEHAR | SM/10158 | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | TSM/009750 | 40014537 | Augmentation | MVS | GO2122009653PH | 11/02/2022 | 280.15 | 25.21 | 305.36 | Coochbehar Division | Northern Mechanical Division II | 233.88 | 11.87 | 41.32 | 0 | 287.07 | 233.86 | 11.87 | 41.32 | 0 | 287.05 | 94 | 85
116 | COOCHBEHAR | SM/10141 | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | TSM/009897 | 40003324 | Augmentation | MVS | GO2122009566PH | 09/02/2022 | 601.85 | 18.07 | 619.92 | Coochbehar Division | Northern Mechanical Division II | 319.48 | 11.57 | 17.48 | 0 | 348.53 | 314.98 | 11.57 | 17.48 | 0 | 344.03 | 55.5 | 92
117 | COOCHBEHAR | SM/10159 | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | TSM/009894 | 40003392 | Augmentation | MVS | GO2122009652PH | 11/02/2022 | 848.69 | 34.47 | 883.16 | Coochbehar Division | Northern Mechanical Division II | 294.64 | 17.57 | 189.01 | 0 | 501.22 | 273.44 | 17.57 | 189.01 | 0 | 480.02 | 54.35 | 83
118 | COOCHBEHAR | SM/16527 | AUGUMENTATION OF GROUND WATER BASED BARAI BARI PWSS MATHABHANGA II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | TSM/018355 | 40062739 | Augmentation | SVS | GO2223015223PH | 03/03/2023 | 478.45 | 42.98 | 521.44 | Coochbehar Division | Northern Mechanical Division II | 236.47 | 17.48 | 0 | 0 | 253.95 | 72.09 | 17.48 | 0 | 0 | 89.57 | 17.18 | 50
119 | COOCHBEHAR | SM/15934 | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE I PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | TSM/018337 | 40048746 | Augmentation | MVS | GO2223014697PH | 22/02/2023 | 864.44 | 21.49 | 885.93 | Coochbehar Division | Northern Mechanical Division II | 416.68 | 8.6 | 106.66 | 0 | 531.94 | 415.07 | 8.6 | 106.66 | 0 | 530.33 | 59.86 | 55
120 | COOCHBEHAR | SM/18093 | AUGUMENTATION OF GROUND WATER BASED CHAKCHAKA ZONE II PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | TSM/018339 | 40048750 | Augmentation | MVS | GO2223017756PH | 27/03/2023 | 287.01 | 42.98 | 329.99 | Coochbehar Division | Northern Mechanical Division II | 200 | 31.17 | 13.25 | 0 | 244.43 | 200 | 31.17 | 13.25 | 0 | 244.43 | 74.07 | 90
121 | COOCHBEHAR | SM/15933 | AUGUMENTATION OF GROUND WATER BASED HARINCHAOWRA PWSS COOCHBEHAR 1 BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION, PHE DTE | TSM/018336 | 40048742 | Augmentation | MVS | GO2223014696PH | 22/02/2023 | 400.79 | 44.24 | 445.03 | Coochbehar Division | Northern Mechanical Division II | 143.06 | 18.58 | 31.67 | 0 | 193.3 | 117.49 | 18.58 | 31.67 | 0 | 167.74 | 37.69 | 55
122 | COOCHBEHAR | SM/16153 | AUGUMENTATION OF GROUND WATER BASED MARANADIRKUTHI PWSS COOCHBEHAR II BLOCK WITHIN COOCHBEHAR DISTRICT UNDER COOCHBEHAR DIVISION , PHE DTE | TSM/018340 | 40048481 | Augmentation | MVS | GO2223014694PH | 22/02/2023 | 296.43 | 20.72 | 317.15 | Coochbehar Division | Northern Mechanical Division II | 123.11 | 8.35 | 0 | 0 | 131.45 | 122.87 | 8.35 | 0 | 0 | 131.22 | 41.37 | 66
123 | COOCHBEHAR | SM/09823 | Augumentation of Nalangibari Water Supply scheme | TSM/008965 | 40009235 | Augmentation | MVS | GO2122006296PH | 01/12/2021 | 398.33 | 36.93 | 435.26 | Coochbehar Division | Northern Mechanical Division II | 352.18 | 21.17 | 45.29 | 0 | 418.65 | 352.16 | 21.17 | 45.29 | 0 | 418.62 | 96.18 | 86
124 | COOCHBEHAR | SM/09295 | Augumentation of Petla Water Supply Scheme. | TSM/008957 | 40000036 | Augmentation | SVS | GO2122005324PH | 09/11/2021 | 342.26 | 19.45 | 361.71 | Coochbehar Division | Northern Mechanical Division II | 292.1 | 10.39 | 26.7 | 0 | 329.19 | 292.1 | 10.39 | 26.7 | 0 | 329.19 | 91.01 | 98
125 | COOCHBEHAR | SM/16525 | GROUND WATER BASED PRAN MAJUMDER PIPED WATER SUPPLY AUGMENTATION SCHEME | TSM/020431 | 40054883 | Augmentation | MVS | GO2223015221PH | 03/03/2023 | 495.73 | 45.18 | 540.91 | Coochbehar Division | Northern Mechanical Division II | 414.83 | 5.23 | 0 | 0 | 420.05 | 399.04 | 5.23 | 0 | 0 | 404.26 | 74.74 | 88
126 | COOCHBEHAR | SM/11258 | Rejuvenation of BARO PINJARERJHAR Water Supply Scheme | TSM/010254 | 40037438 | Augmentation | SVS | GO2223004384PH | 23/06/2022 | 118.06 | 0 | 118.06 | Coochbehar Division |  | 47.86 | 0 | 14.82 | 0 | 62.69 | 47.86 | 0 | 14.82 | 0 | 62.69 | 53.1 | 80
127 | COOCHBEHAR | SM/10365 | Rejuvenation of BHANDIJALAS Water Supply Scheme | TSM/010037 | 40016491 | Augmentation | SVS | GO2122010920PH | 16/03/2022 | 41.47 | 18.76 | 60.23 | Coochbehar Division | Northern Mechanical Division II | 40.27 | 11.25 | 0 | 0 | 51.51 | 40.27 | 11.25 | 0 | 0 | 51.51 | 85.53 | 85
128 | COOCHBEHAR | SM/10712 | Rejuvenation of BHANGA MORE Water Supply Scheme | TSM/010251 | 40002949 | Augmentation | SVS | GO2223001528PH | 12/05/2022 | 164.53 | 15.58 | 180.12 | Coochbehar Division | Northern Mechanical Division II | 89.72 | 9.92 | 0 | 0 | 99.64 | 89.72 | 9.92 | 0 | 0 | 99.64 | 55.32 | 80
129 | COOCHBEHAR | SM/10361 | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | TSM/010040 | 40048020 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 80.8 | 18.76 | 99.56 | Coochbehar Division | Northern Mechanical Division II | 48.61 | 5 | 0 | 0 | 53.61 | 48.61 | 5 | 0 | 0 | 53.61 | 53.85 | 80
130 | COOCHBEHAR | SM/10366 | Rejuvenation of CHHAGALBER Water Supply Scheme | TSM/010039 | 40033523 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 91.71 | 19.01 | 110.72 | Coochbehar Division | Northern Mechanical Division II | 91.53 | 11.63 | 0 | 0 | 103.16 | 91.49 | 11.63 | 0 | 0 | 103.12 | 93.14 | 99
131 | COOCHBEHAR | SM/10711 | Rejuvenation of CHUNGERKHATA KHAGRIBARI Water Supply Scheme | TSM/010252 | 40022831 | Augmentation | SVS | GO2223001528PH | 12/05/2022 | 99.98 | 0 | 99.98 | Coochbehar Division | Northern Mechanical Division II | 62.79 | 0 | 0 | 0 | 62.79 | 62.79 | 0 | 0 | 0 | 62.79 | 62.8 | 88
132 | COOCHBEHAR | SM/10364 | Rejuvenation of DEOCHARAI Water Supply Scheme | TSM/010035 | 40007628 | Augmentation | SVS | GO2122010920PH | 16/03/2022 | 54.59 | 18.84 | 73.44 | Coochbehar Division | Northern Mechanical Division II | 14.83 | 0 | 0 | 0 | 14.83 | 16.35 | 0 | 0 | 0 | 16.35 | 22.26 | 54
133 | COOCHBEHAR | SM/10709 | Rejuvenation of JAMALDAH HAT Water Supply Scheme | TSM/010256 | 40030520 | Augmentation | MVS | GO2223001528PH | 12/05/2022 | 153.08 | 15.58 | 168.66 | Coochbehar Division | Northern Mechanical Division II | 148.62 | 11.32 | 0 | 0 | 159.94 | 148.62 | 11.32 | 0 | 0 | 159.94 | 94.83 | 95
134 | COOCHBEHAR | SM/10359 | Rejuvenation of KALAPANI Water Supply Scheme | TSM/010043 | 40020102 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 38.31 | 19.01 | 57.32 | Coochbehar Division | Northern Mechanical Division II | 37.2 | 12.13 | 0 | 0 | 49.33 | 37.2 | 12.13 | 0 | 0 | 49.33 | 86.06 | 92
135 | COOCHBEHAR | SM/10363 | Rejuvenation of KHAPAIDANGA Water Supply Scheme | TSM/010036 | 40020115 | Augmentation | SVS | GO2122010920PH | 16/03/2022 | 81.19 | 18.84 | 100.03 | Coochbehar Division | Northern Mechanical Division II | 48.51 | 9.32 | 0 | 0 | 57.83 | 39.06 | 9.32 | 0 | 0 | 48.38 | 48.37 | 84
136 | COOCHBEHAR | SM/10360 | Rejuvenation of KUMIRGHAT Water Supply Scheme | TSM/010042 | 40036707 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 62.51 | 19.41 | 81.91 | Coochbehar Division | Northern Mechanical Division II | 60.69 | 12.05 | 0 | 0 | 72.74 | 60.68 | 12.05 | 0 | 0 | 72.73 | 88.78 | 84
137 | COOCHBEHAR | SM/10231 | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | TSM/009780 | 40004084 | Augmentation | MVS | GO2122009808PH | 24/02/2022 | 552.73 | 38.84 | 591.57 | Coochbehar Division | Northern Mechanical Division II | 301.46 | 23.44 | 42.43 | 0 | 367.33 | 290.4 | 23.44 | 42.43 | 0 | 356.27 | 60.22 | 92
138 | COOCHBEHAR | SM/10713 | Rejuvenation of LOTAPOTA Water Supply Scheme | TSM/010250 | 40034182 | Augmentation | MVS | GO2223001528PH | 12/05/2022 | 78.18 | 15.58 | 93.77 | Coochbehar Division | Northern Mechanical Division II | 23.06 | 15.13 | 0 | 0 | 38.19 | 23.06 | 15.13 | 0 | 0 | 38.19 | 40.73 | 64
139 | COOCHBEHAR | SM/10369 | Rejuvenation of MARICHBARI Water Supply Scheme | TSM/010041 | 40006627 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 77.24 | 19.41 | 96.65 | Coochbehar Division | Northern Mechanical Division II | 63.95 | 11.51 | 0 | 0 | 75.46 | 63.95 | 11.51 | 0 | 0 | 75.46 | 78.07 | 92
140 | COOCHBEHAR | SM/10707 | Rejuvenation of PAKHIHAGA Water Supply Scheme | TSM/010255 | 6904446 | Augmentation | MVS | GO2223001528PH | 12/05/2022 | 112.74 | 15.58 | 128.32 | Coochbehar Division | Northern Mechanical Division II | 76.32 | 11.58 | 0 | 0 | 87.9 | 76.32 | 11.58 | 0 | 0 | 87.9 | 68.5 | 100
141 | COOCHBEHAR | SM/10368 | Rejuvenation of PANISALA Water Supply Scheme | TSM/010034 | 40018508 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 85.23 | 18.84 | 104.08 | Coochbehar Division | Northern Mechanical Division II | 82.75 | 14.02 | 0 | 0 | 96.78 | 82.75 | 14.02 | 0 | 0 | 96.78 | 92.98 | 92
142 | COOCHBEHAR | SM/10367 | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme | TSM/010033 | 40027585 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 51.94 | 18.84 | 70.79 | Coochbehar Division | Northern Mechanical Division II | 50.43 | 11.78 | 0 | 0 | 62.2 | 50.43 | 11.78 | 0 | 0 | 62.2 | 87.88 | 98
143 | COOCHBEHAR | SM/10710 | Rejuvenation of RAMTHANGA Water Supply Scheme | TSM/010253 | 40015590 | Augmentation | MVS | GO2223001528PH | 12/05/2022 | 154.36 | 15.58 | 169.95 | Coochbehar Division | Northern Mechanical Division II | 52.87 | 11 | 97.15 | 0 | 161.03 | 52.87 | 11 | 97.15 | 0 | 161.03 | 94.75 | 95
144 | COOCHBEHAR | SM/10362 | Rejuvenation of SINGIMARI PASCHIMPAR Water Supply Scheme | TSM/010038 | 40036731 | Augmentation | MVS | GO2122010920PH | 16/03/2022 | 114.91 | 19.95 | 134.86 | Coochbehar Division | Northern Mechanical Division II | 60.15 | 11.45 | 0 | 0 | 71.6 | 60.15 | 11.45 | 0 | 0 | 71.6 | 53.09 | 75
145 | COOCHBEHAR | SM/10708 | Rejuvenation of UTTAR FULKARDABRI Water Supply Scheme | TSM/010249 | 40028610 | Augmentation | MVS | GO2223001528PH | 12/05/2022 | 138.76 | 15.58 | 154.34 | Coochbehar Division | Northern Mechanical Division II | 122.03 | 0 | 0 | 0 | 122.03 | 122.03 | 0 | 0 | 0 | 122.03 | 79.07 | 83
146 | COOCHBEHAR | SM/18299 | REJUVENATION OF BARA ATIABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | TSM/010886 | 40035108 | Augmentation | MVS | 1666/PHE-28011/110/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 1016.36 | 60.06 | 1076.42 | Coochbehar Division | Northern Mechanical Division II | 717.58 | 26.54 | 31.16 | 0 | 775.28 | 717.58 | 26.54 | 31.16 | 0 | 775.28 | 72.02 | 83
147 | COOCHBEHAR | SM/10160 | Rejuvenation of HARI BHANGA Piped Water Supply Scheme | TSM/009776 | 40003731 | Augmentation | MVS | GO2122009650PH | 11/02/2022 | 190.47 | 19.37 | 209.84 | Coochbehar Division | Northern Mechanical Division II | 76.5 | 0 | 17.82 | 0 | 94.32 | 76.5 | 0 | 17.82 | 0 | 94.32 | 44.95 | 80
148 | COOCHBEHAR | SM/10219 | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | TSM/009781 | 40003383 | Augmentation | MVS | GO2122009806PH | 24/02/2022 | 471.32 | 38.9 | 510.22 | Coochbehar Division | Northern Mechanical Division II | 196.67 | 26.77 | 42.45 | 0 | 265.89 | 179.48 | 26.77 | 42.45 | 0 | 248.7 | 48.74 | 88
149 | COOCHBEHAR | SM/09824 | Rejuvenation of Payamari Water Supply Scheme | TSM/008971 | 40015591 | Augmentation | SVS | GO2122006296PH | 01/12/2021 | 340.66 | 18.07 | 358.73 | Coochbehar Division | Northern Mechanical Division II | 108.76 | 3.88 | 18.45 | 0 | 131.09 | 108.74 | 3.88 | 18.45 | 0 | 131.07 | 36.54 | 78
150 | COOCHBEHAR | SM/09820 | Rejuvenation of Salmara water supply scheme | TSM/008972 | 40017412 | Augmentation | MVS | GO2122006287PH | 01/12/2021 | 502.09 | 18.07 | 520.16 | Coochbehar Division | Northern Mechanical Division II | 415.98 | 11.56 | 79.22 | 0 | 506.77 | 415.98 | 11.56 | 79.22 | 0 | 506.77 | 97.42 | 97
151 | COOCHBEHAR | SM/13160 | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | TSM/010884 | 40029007 | Augmentation | MVS | GO2223008666PH | 12/10/2022 | 475.78 | 60.06 | 535.85 | Coochbehar Division | Northern Mechanical Division II | 298.25 | 3.72 | 13.11 | 0 | 315.07 | 298.25 | 3.72 | 13.11 | 0 | 315.07 | 58.8 | 86
152 | COOCHBEHAR | SM/09293 | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | TSM/008833 | 40009223 | Augmentation | SVS | GO2122005324PH | 09/11/2021 | 164.7 | 19.35 | 184.05 | Coochbehar Division | Northern Mechanical Division II | 142.13 | 11.24 | 6.83 | 0 | 160.21 | 127.81 | 11.24 | 6.83 | 0 | 145.88 | 79.26 | 72
153 | COOCHBEHAR | SM/09819 | Rejuvination of Chhatoa water supply scheme | TSM/008831 | 40023112 | Augmentation | MVS | GO2122006287PH | 01/12/2021 | 121.53 | 18.84 | 140.37 | Coochbehar Division | Northern Mechanical Division II | 59.01 | 12.31 | 51.1 | 0 | 122.42 | 59.01 | 12.31 | 51.1 | 0 | 122.42 | 87.21 | 88
154 | COOCHBEHAR | SM/09809 | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | TSM/008834 | 40008646 | Augmentation | MVS | GO2122006286PH | 01/12/2021 | 173.18 | 19.32 | 192.5 | Coochbehar Division | Northern Mechanical Division II | 155.64 | 11.33 | 12.49 | 0 | 179.47 | 155.64 | 11.33 | 12.49 | 0 | 179.47 | 93.23 | 88
155 | COOCHBEHAR | SM/09292 | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | TSM/008958 | 40033980 | Augmentation | MVS | GO2122005324PH | 09/11/2021 | 129.6 | 19.37 | 148.97 | Coochbehar Division | Northern Mechanical Division II | 70.89 | 1.06 | 54.91 | 0 | 126.86 | 70.89 | 1.06 | 54.91 | 0 | 126.86 | 85.16 | 98
156 | COOCHBEHAR | SM/09818 | Rejuvination of Salbari Water Supply Scheme | TSM/008954 | 40012601 | Augmentation | MVS | GO2122006287PH | 01/12/2021 | 165.51 | 19.77 | 185.28 | Coochbehar Division | Northern Mechanical Division II | 148.79 | 11.12 | 0 | 0 | 159.91 | 148.79 | 11.12 | 0 | 0 | 159.91 | 86.3 | 95
157 | COOCHBEHAR | SM/09821 | Rejuvination of Sathbhandari water supply scheme | TSM/008808 | 40002465 | Augmentation | MVS | GO2122006289PH | 01/12/2021 | 143.44 | 19.32 | 162.76 | Coochbehar Division | Northern Mechanical Division II | 94.73 | 10.76 | 2.42 | 0 | 107.91 | 94.56 | 10.76 | 2.42 | 0 | 107.74 | 66.2 | 95
158 | COOCHBEHAR | SM/09294 | Rejuvination of Takoamari water supply scheme | TSM/008829 | 40014536 | Augmentation | SVS | GO2122005324PH | 09/11/2021 | 85.28 | 18.86 | 104.14 | Coochbehar Division | Northern Mechanical Division II | 33.46 | 10 | 0 | 0 | 43.46 | 33.46 | 10 | 0 | 0 | 43.46 | 41.73 | 86
Total | [9 empty] | 89144.76 | 5767.69 | 94912.45 |  |  | 50136.74 | 2453.69 | 5077.77 | 0 | 57668.2 | 48610.47 | 2450.36 | 5077.77 | 0 | 56138.6 | 59.15