## JJM Schemes Financial Status (C
JJM Schemes Financial Status (COOCHBEHAR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | COOCHBEHAR | SM/07156 | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | TSM/006225 | 6858836 | Retrofitting | MVS | GO2021002921PH | 01/12/2020 | 87.4 | 0 | 87.4 | Coochbehar Division |  | 84.79 | 0 | 0 | 0 | 84.79 | 84.79 | 0 | 0 | 0 | 84.79 | 97.01 | 100
2 | COOCHBEHAR | SM/09832 | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | TSM/006227 | 40012600 | Retrofitting | MVS | GO2122006347PH | 02/12/2021 | 847.71 | 0 | 847.71 | Coochbehar Division |  | 741.36 | 0 | 96.08 | 0 | 837.44 | 741.36 | 0 | 96.08 | 0 | 837.44 | 98.79 | 98
3 | COOCHBEHAR | SM/07160 | Retrofitting cum Rejuvenation of Kalapani Piped Water Suply Scheme | TSM/006230 | 8132393 | Retrofitting | MVS | GO2021002925PH | 01/12/2020 | 95.99 | 0 | 95.99 | Coochbehar Division |  | 93.19 | 0 | 0.77 | 0 | 93.96 | 93.19 | 0 | 0.77 | 0 | 93.96 | 97.89 | 100
4 | COOCHBEHAR | SM/07161 | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | TSM/006231 | 40035991 | Retrofitting | SVS | GO2021002926PH | 01/12/2020 | 99.21 | 0 | 99.21 | Coochbehar Division |  | 96.32 | 0 | 0 | 0 | 96.32 | 91.89 | 0 | 0 | 0 | 91.89 | 92.62 | 95
5 | COOCHBEHAR | SM/07158 | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | TSM/006226 | 8129975 | Retrofitting | MVS | GO2021002920PH | 01/12/2020 | 95.27 | 0 | 95.27 | Coochbehar Division |  | 92.49 | 0 | 0 | 0 | 92.49 | 92.49 | 0 | 0 | 0 | 92.49 | 97.09 | 95
6 | COOCHBEHAR | SM/07159 | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | TSM/006229 | 6904423 | Retrofitting | MVS | GO2021002924PH | 01/12/2020 | 97.31 | 0 | 97.31 | Coochbehar Division |  | 97.31 | 0 | 0 | 0 | 97.31 | 97.31 | 0 | 0 | 0 | 97.31 | 100 | 100
7 | COOCHBEHAR | SM/07147 | Retrofitting of existing Basraja Pratham Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006235 | 6858845 | Retrofitting | SVS | GO2021002889PH | 01/12/2020 | 97.91 | 0 | 97.91 | Coochbehar Division |  | 97.91 | 0 | 0 | 0 | 97.91 | 97.91 | 0 | 0 | 0 | 97.91 | 100 | 100
8 | COOCHBEHAR | SM/07167 | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006239 | 8130303 | Retrofitting | SVS | GO2021002930PH | 01/12/2020 | 96.01 | 0 | 96.01 | Coochbehar Division |  | 91.6 | 0 | 4.4 | 0 | 96 | 91.6 | 0 | 4.4 | 0 | 96 | 99.99 | 97
9 | COOCHBEHAR | SM/07166 | Retrofitting of existing Bhurkush Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006238 | 6762118 | Retrofitting | MVS | GO2021002932PH | 01/12/2020 | 94.92 | 0 | 94.92 | Coochbehar Division |  | 91.58 | 0 | 3.35 | 0 | 94.92 | 91.58 | 0 | 3.35 | 0 | 94.92 | 100 | 100
10 | COOCHBEHAR | SM/07165 | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006236 | 7368960 | Retrofitting | MVS | GO2021002931PH | 01/12/2020 | 98.97 | 0 | 98.97 | Coochbehar Division |  | 92.65 | 0 | 2.75 | 0 | 95.4 | 92.65 | 0 | 2.75 | 0 | 95.4 | 96.4 | 100
11 | COOCHBEHAR | SM/07164 | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006234 | 6762111 | Retrofitting | SVS | GO2021002928PH | 01/12/2020 | 79.55 | 0 | 79.55 | Coochbehar Division |  | 73.57 | 0 | 0.55 | 0 | 74.11 | 73.57 | 0 | 0.55 | 0 | 74.11 | 93.17 | 100
12 | COOCHBEHAR | SM/07162 | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | TSM/006232 | 8130340 | Retrofitting | SVS | GO2021002927PH | 01/12/2020 | 97.26 | 0 | 97.26 | Coochbehar Division |  | 94.43 | 0 | 0 | 0 | 94.43 | 94.43 | 0 | 0 | 0 | 94.43 | 97.09 | 95
13 | COOCHBEHAR | SM/07163 | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006233 | 8130297 | Retrofitting | MVS | GO2021002929PH | 01/12/2020 | 96.35 | 0 | 96.35 | Coochbehar Division |  | 90.27 | 0 | 0 | 0 | 90.27 | 82.45 | 0 | 0 | 0 | 82.45 | 85.57 | 95
14 | COOCHBEHAR | SM/07148 | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | TSM/006237 | 40037050 | Retrofitting | MVS | GO2021002890PH | 01/12/2020 | 99.38 | 0 | 99.38 | Coochbehar Division |  | 86.45 | 0 | 2.06 | 0 | 88.51 | 86.45 | 0 | 2.06 | 0 | 88.51 | 89.06 | 90
15 | COOCHBEHAR | SM/07157 | Retrofitting of existing Singimari Paschimpar Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Singimari Paschimpar Piped Water Supply Scheme | TSM/006228 | 6904425 | Retrofitting | MVS | GO2021002922PH | 01/12/2020 | 98.83 | 0 | 98.83 | Coochbehar Division |  | 90.44 | 0 | 0 | 0 | 90.44 | 90.44 | 0 | 0 | 0 | 90.44 | 91.51 | 100
16 | COOCHBEHAR | SM/08152 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | TSM/006951 | 8228192 | Retrofitting | MVS | GO2021006545PH | 08/02/2021 | 98.54 | 0 | 98.54 | Coochbehar Division |  | 90.33 | 0 | 0 | 0 | 90.33 | 88.51 | 0 | 0 | 0 | 88.51 | 89.82 | 97
17 | COOCHBEHAR | SM/08158 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | TSM/006939 | 40012623 | Retrofitting | MVS | GO2021006645PH | 09/02/2021 | 58.94 | 0 | 58.94 | Coochbehar Division |  | 57.22 | 0 | 0 | 0 | 57.22 | 57.22 | 0 | 0 | 0 | 57.22 | 97.09 | 95
18 | COOCHBEHAR | SM/08144 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bara Soulmari Water Supply Scheme | TSM/006938 | 6858867 | Retrofitting | MVS | GO2021006542PH | 08/02/2021 | 99.27 | 0 | 99.27 | Coochbehar Division |  | 90.29 | 0 | 6.59 | 0 | 96.88 | 90.27 | 0 | 6.59 | 0 | 96.86 | 97.58 | 100
19 | COOCHBEHAR | SM/08165 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | TSM/006947 | 40037046 | Retrofitting | SVS | GO2021006629PH | 09/02/2021 | 93.89 | 0 | 93.89 | Coochbehar Division |  | 72.17 | 0 | 0 | 0 | 72.17 | 72.17 | 0 | 0 | 0 | 72.17 | 76.87 | 95
20 | COOCHBEHAR | SM/08148 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | TSM/006944 | 40016306 | Retrofitting | SVS | GO2021006550PH | 08/02/2021 | 99.39 | 0 | 99.39 | Coochbehar Division |  | 73.75 | 0 | 3.58 | 0 | 77.32 | 73.73 | 0 | 3.58 | 0 | 77.31 | 77.78 | 90
21 | COOCHBEHAR | SM/08154 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | TSM/006953 | 6858860 | Retrofitting | MVS | GO2021006543PH | 08/02/2021 | 99.54 | 0 | 99.54 | Coochbehar Division |  | 88.53 | 0 | 7.03 | 0 | 95.57 | 88.53 | 0 | 7.03 | 0 | 95.57 | 96.01 | 88
22 | COOCHBEHAR | SM/08159 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | TSM/006940 | 8228147 | Retrofitting | MVS | GO2021006639PH | 09/02/2021 | 97.85 | 0 | 97.85 | Coochbehar Division |  | 95 | 0 | 0 | 0 | 95 | 95 | 0 | 0 | 0 | 95 | 97.09 | 96
23 | COOCHBEHAR | SM/08153 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | TSM/006952 | 8228175 | Retrofitting | MVS | GO2021006544PH | 08/02/2021 | 82.63 | 0 | 82.63 | Coochbehar Division |  | 80.22 | 0 | 0 | 0 | 80.22 | 78.41 | 0 | 0 | 0 | 78.41 | 94.9 | 95
24 | COOCHBEHAR | SM/08157 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | TSM/006942 | 8227113 | Retrofitting | MVS | GO2021006642PH | 09/02/2021 | 97.91 | 0 | 97.91 | Coochbehar Division |  | 92.2 | 0 | 0 | 0 | 92.2 | 92.2 | 0 | 0 | 0 | 92.2 | 94.16 | 98
25 | COOCHBEHAR | SM/08149 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | TSM/006948 | 8282265 | Retrofitting | SVS | GO2021006549PH | 08/02/2021 | 77.36 | 0 | 77.36 | Coochbehar Division |  | 75.11 | 0 | 0 | 0 | 75.11 | 75.11 | 0 | 0 | 0 | 75.11 | 97.09 | 98
26 | COOCHBEHAR | SM/08164 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | TSM/006946 | 8227029 | Retrofitting | SVS | GO2021006631PH | 09/02/2021 | 86.77 | 0 | 86.77 | Coochbehar Division |  | 84.24 | 0 | 0 | 0 | 84.24 | 84.24 | 0 | 0 | 0 | 84.24 | 97.09 | 95
27 | COOCHBEHAR | SM/08143 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ekmukha Water Supply Scheme | TSM/006936 | 6858862 | Retrofitting | MVS | GO2021006540PH | 08/02/2021 | 99.02 | 0 | 99.02 | Coochbehar Division |  | 99.02 | 0 | 0 | 0 | 99.02 | 99.02 | 0 | 0 | 0 | 99.02 | 100 | 100
28 | COOCHBEHAR | SM/08156 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | TSM/006941 | 8228160 | Retrofitting | MVS | GO2021006640PH | 09/02/2021 | 97.67 | 0 | 97.67 | Coochbehar Division |  | 94.82 | 0 | 1.37 | 0 | 96.19 | 93 | 0 | 1.37 | 0 | 94.37 | 96.62 | 95
29 | COOCHBEHAR | SM/08163 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | TSM/006945 | 8282127 | Retrofitting | MVS | GO2021006632PH | 09/02/2021 | 206.7 | 0 | 206.7 | Coochbehar Division |  | 200.68 | 0 | 0 | 0 | 200.68 | 200.68 | 0 | 0 | 0 | 200.68 | 97.09 | 95
30 | COOCHBEHAR | SM/08146 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kharimala Khagrabari(CT) Water Supply Scheme | TSM/006937 | 6904436 | Retrofitting | SVS | GO2021006541PH | 08/02/2021 | 91.07 | 0 | 91.07 | Coochbehar Division |  | 73.39 | 0 | 0.55 | 0 | 73.94 | 72.41 | 0 | 0.55 | 0 | 72.95 | 80.11 | 98
31 | COOCHBEHAR | SM/08155 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | TSM/006929 | 8281387 | Retrofitting | MVS | GO2021006627PH | 09/02/2021 | 87.78 | 0 | 87.78 | Coochbehar Division |  | 62.98 | 0 | 21.91 | 0 | 84.89 | 62.98 | 0 | 21.91 | 0 | 84.89 | 96.71 | 95
32 | COOCHBEHAR | SM/08161 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | TSM/006932 | 8376745 | Retrofitting | MVS | GO2021006636PH | 09/02/2021 | 99.78 | 0 | 99.78 | Coochbehar Division |  | 92.95 | 0 | 1.65 | 0 | 94.59 | 92.94 | 0 | 1.65 | 0 | 94.59 | 94.79 | 95
33 | COOCHBEHAR | SM/08147 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najiran Deutikhata Water Supply Scheme | TSM/006934 | 8281446 | Retrofitting | MVS | GO2021006538PH | 08/02/2021 | 90.78 | 0 | 90.78 | Coochbehar Division |  | 86.04 | 0 | 4.74 | 0 | 90.78 | 86.04 | 0 | 4.74 | 0 | 90.78 | 100 | 100
34 | COOCHBEHAR | SM/08160 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | TSM/006943 | 7350380 | Retrofitting | MVS | GO2021006644PH | 09/02/2021 | 99.93 | 0 | 99.93 | Coochbehar Division |  | 97.02 | 0 | 0 | 0 | 97.02 | 97.02 | 0 | 0 | 0 | 97.02 | 97.09 | 95
35 | COOCHBEHAR | SM/09831 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | TSM/006933 | 40012597 | Retrofitting | MVS | GO2122006346PH | 02/12/2021 | 743.04 | 0 | 743.04 | Coochbehar Division |  | 710.4 | 0 | 12.65 | 0 | 723.05 | 710.39 | 0 | 12.65 | 0 | 723.03 | 97.31 | 100
36 | COOCHBEHAR | SM/08150 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Pakhihaga Water Supply Scheme | TSM/006949 | 6904446 | Retrofitting | MVS | GO2021006547PH | 08/02/2021 | 99.72 | 0 | 99.72 | Coochbehar Division |  | 93.39 | 0 | 0 | 0 | 93.39 | 93.39 | 0 | 0 | 0 | 93.39 | 93.65 | 100
37 | COOCHBEHAR | SM/08162 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | TSM/006931 | 8227143 | Retrofitting | MVS | GO2021006637PH | 09/02/2021 | 95.45 | 0 | 95.45 | Coochbehar Division |  | 95.41 | 0 | 0 | 0 | 95.41 | 93.17 | 0 | 0 | 0 | 93.17 | 97.61 | 100
38 | COOCHBEHAR | SM/08145 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | TSM/006935 | 8384783 | Retrofitting | MVS | GO2021006539PH | 08/02/2021 | 98.31 | 0 | 98.31 | Coochbehar Division |  | 94.21 | 0 | 0 | 0 | 94.21 | 94.21 | 0 | 0 | 0 | 94.21 | 95.84 | 94
39 | COOCHBEHAR | SM/08151 | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | TSM/006950 | 6934397 | Retrofitting | MVS | GO2021006546PH | 08/02/2021 | 97.72 | 0 | 97.72 | Coochbehar Division |  | 94.87 | 0 | 0 | 0 | 94.87 | 94.87 | 0 | 0 | 0 | 94.87 | 97.09 | 100
40 | COOCHBEHAR | SM/10006 | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | TSM/006930 | 40012599 | Retrofitting | MVS | GO2122007092PH | 22/12/2021 | 1719.81 | 0 | 1719.81 | Coochbehar Division |  | 1428.36 | 0 | 24.71 | 0 | 1453.07 | 1428.36 | 0 | 24.71 | 0 | 1453.07 | 84.49 | 95
Total | [9 empty] | 6900.93 | 0 | 6900.93 |  |  | 6236.98 | 0 | 194.73 | 0 | 6431.71 | 6216 | 0 | 194.73 | 0 | 6410.73 | 92.9