## JJM Schemes Financial Status (U
JJM Schemes Financial Status (UTTAR DINAJPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | UTTAR DINAJPUR | SM/18828 | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | TSM/005420 | 40061007 | Augmentation | MVS | 2761/PHE/IV/W-612/23 | 12/09/2023 | 214.61 | 0 | 214.61 | Raiganj Division |  | 5.4 | 0 | 0 | 0 | 5.4 | 5.4 | 0 | 0 | 0 | 5.4 | 2.52 | 100
2 | UTTAR DINAJPUR | SM/15124 | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME | TSM/011426 | 40043420 | Augmentation | MVS | GO2223013178PH | 04/02/2023 | 725.05 | 51.07 | 776.11 | Raiganj Division | Malda Mechanical Division | 241.48 | 27.23 | 19.17 | 0 | 287.88 | 241.48 | 27.23 | 19.17 | 0 | 287.88 | 37.09 | 55
3 | UTTAR DINAJPUR | SM/09989 | Augmentation Dilwarpur Piped Water Supply Scheme. | TSM/009096 | 40001228 | Augmentation | SVS | GO2122006949PH | 16/12/2021 | 409.03 | 20.49 | 429.52 | Raiganj Division | Malda Mechanical Division | 184.33 | 15.52 | 8.14 | 0 | 208 | 184.33 | 15.52 | 8.14 | 0 | 208 | 48.43 | 73
4 | UTTAR DINAJPUR | SM/11796 | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME | TSM/011409 | 40027050 | Augmentation | MVS | GO2223006096PH | 05/08/2022 | 707.23 | 34.64 | 741.87 | Raiganj Division | Malda Mechanical Division | 214.52 | 28.53 | 15.13 | 0 | 258.18 | 214.52 | 28.53 | 15.13 | 0 | 258.18 | 34.8 | 61
5 | UTTAR DINAJPUR | SM/11726 | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME | TSM/011422 | 40027506 | Augmentation | MVS | GO2223006018PH | 03/08/2022 | 759.58 | 31.48 | 791.06 | Raiganj Division | Malda Mechanical Division | 368.44 | 19.11 | 16.54 | 0 | 404.09 | 368.44 | 19.11 | 16.54 | 0 | 404.09 | 51.08 | 72
6 | UTTAR DINAJPUR | SM/11196 | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME | TSM/009723 | 40027370 | Augmentation | MVS | GO2223003814PH | 03/06/2022 | 755.85 | 42.84 | 798.69 | Raiganj Division | Malda Mechanical Division | 220.3 | 36.41 | 70.14 | 0 | 326.85 | 220.3 | 36.41 | 70.14 | 0 | 326.85 | 40.92 | 82
7 | UTTAR DINAJPUR | SM/10129 | Augmentation of Chopra Water Supply Scheme. | TSM/009083 | 40002670 | Augmentation | MVS | GO2122009277PH | 08/02/2022 | 1338.82 | 43.29 | 1382.11 | Raiganj Division | Malda Mechanical Division | 209.87 | 36 | 138.29 | 0 | 384.17 | 209.87 | 36 | 138.29 | 0 | 384.17 | 27.8 | 82
8 | UTTAR DINAJPUR | SM/12393 | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | TSM/013310 | 40028355 | Augmentation | MVS | GO2223007527PH | 13/09/2022 | 742.2 | 36.59 | 778.79 | Raiganj Division | Malda Mechanical Division | 159.81 | 0 | 33.81 | 0 | 193.62 | 159.81 | 0 | 33.81 | 0 | 193.62 | 24.86 | 76
9 | UTTAR DINAJPUR | SM/12394 | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | TSM/013311 | 40028368 | Augmentation | MVS | GO2223007529PH | 13/09/2022 | 863.45 | 36.59 | 900.04 | Raiganj Division | Malda Mechanical Division | 224.26 | 20.25 | 40.21 | 0 | 284.73 | 224.26 | 20.25 | 40.21 | 0 | 284.73 | 31.64 | 64
10 | UTTAR DINAJPUR | SM/10548 | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME | TSM/009724 | 40027041 | Augmentation | SVS | GO2223000376PH | 18/04/2022 | 358.85 | 21.76 | 380.61 | Raiganj Division | Malda Mechanical Division | 102.05 | 20.25 | 9.85 | 0 | 132.14 | 102.05 | 20.25 | 9.85 | 0 | 132.14 | 34.72 | 52
11 | UTTAR DINAJPUR | SM/11799 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | TSM/011652 | 40027044 | Augmentation | MVS | GO2223006098PH | 05/08/2022 | 987 | 34.76 | 1021.76 | Raiganj Division | Malda Mechanical Division | 280.08 | 22.84 | 69.61 | 0 | 372.52 | 280.08 | 22.84 | 69.61 | 0 | 372.52 | 36.46 | 80
12 | UTTAR DINAJPUR | SM/11727 | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | TSM/011655 | 40027045 | Augmentation | MVS | GO2223006008PH | 03/08/2022 | 1007.37 | 49.75 | 1057.12 | Raiganj Division | Malda Mechanical Division | 155.4 | 28.04 | 24.78 | 0 | 208.22 | 155.4 | 28.04 | 24.78 | 0 | 208.22 | 19.7 | 52
13 | UTTAR DINAJPUR | SM/11721 | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | TSM/011651 | 40027480 | Augmentation | MVS | GO2223005999PH | 03/08/2022 | 988.43 | 41.24 | 1029.67 | Raiganj Division | Malda Mechanical Division | 259.9 | 23.85 | 72.11 | 0 | 355.86 | 259.9 | 23.85 | 72.11 | 0 | 355.86 | 34.56 | 51
14 | UTTAR DINAJPUR | SM/11794 | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | TSM/011647 | 40028518 | Augmentation | MVS | GO2223006082PH | 05/08/2022 | 727.5 | 40.18 | 767.67 | Raiganj Division | Malda Mechanical Division | 189.9 | 20.98 | 112.34 | 0 | 323.22 | 189.9 | 20.98 | 112.34 | 0 | 323.22 | 42.1 | 62
15 | UTTAR DINAJPUR | SM/11800 | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur | TSM/011666 | 40027426 | Augmentation | MVS | GO2223006099PH | 05/08/2022 | 816.99 | 49.76 | 866.75 | Raiganj Division | Malda Mechanical Division | 233.75 | 36.41 | 109.68 | 0 | 379.85 | 233.68 | 36.41 | 109.68 | 0 | 379.78 | 43.82 | 90
16 | UTTAR DINAJPUR | SM/11801 | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | TSM/011660 | 40027432 | Augmentation | MVS | GO2223006100PH | 05/08/2022 | 999.16 | 38.37 | 1037.52 | Raiganj Division | Malda Mechanical Division | 255.88 | 27.57 | 47.35 | 0 | 330.8 | 255.88 | 27.57 | 47.35 | 0 | 330.8 | 31.88 | 84
17 | UTTAR DINAJPUR | SM/11728 | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | TSM/011648 | 40027378 | Augmentation | SVS | GO2223006015PH | 03/08/2022 | 653.35 | 54.61 | 707.96 | Raiganj Division | Malda Mechanical Division | 186.79 | 38.25 | 9.79 | 0 | 234.83 | 186.79 | 38.25 | 9.79 | 0 | 234.83 | 33.17 | 61
18 | UTTAR DINAJPUR | SM/13115 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | TSM/011646 | 40028756 | Augmentation | MVS | GO2223008576PH | 10/10/2022 | 1461.21 | 58.44 | 1519.65 | Raiganj Division | Malda Mechanical Division | 155.53 | 28.92 | 119.13 | 0 | 303.58 | 155.53 | 28.92 | 119.13 | 0 | 303.58 | 19.98 | 59
19 | UTTAR DINAJPUR | SM/11802 | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | TSM/011644 | 40027507 | Augmentation | MVS | GO2223006093PH | 05/08/2022 | 843.81 | 50.24 | 894.05 | Raiganj Division | Malda Mechanical Division | 197.33 | 35.07 | 34.83 | 0 | 267.23 | 196.39 | 35.07 | 34.83 | 0 | 266.29 | 29.78 | 89
20 | UTTAR DINAJPUR | SM/11798 | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | TSM/011645 | 40027051 | Augmentation | SVS | GO2223006089PH | 05/08/2022 | 647.25 | 48.13 | 695.38 | Raiganj Division | Malda Mechanical Division | 192.84 | 19.44 | 1.75 | 0 | 214.02 | 192.84 | 19.44 | 1.75 | 0 | 214.02 | 30.78 | 76
21 | UTTAR DINAJPUR | SM/18295 | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | TSM/018165 | 40043597 | Augmentation | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1177.81 | 70.64 | 1248.45 | Raiganj Division | Malda Mechanical Division | 34.68 | 0 | 287.93 | 0 | 322.62 | 34.68 | 0 | 287.93 | 0 | 322.62 | 25.84 | 23
22 | UTTAR DINAJPUR | SM/18290 | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. | TSM/018223 | 40044489 | Augmentation | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1370.36 | 55.19 | 1425.54 | Raiganj Division | Malda Mechanical Division | 17.96 | 0 | 113.89 | 0 | 131.85 | 17.96 | 0 | 113.89 | 0 | 131.85 | 9.25 | 15
23 | UTTAR DINAJPUR | SM/12395 | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. | TSM/013312 | 40028674 | Augmentation | SVS | GO2223007528PH | 13/09/2022 | 580.41 | 50.9 | 631.31 | Raiganj Division | Malda Mechanical Division | 113.33 | 29.65 | 32.64 | 0 | 175.62 | 113.33 | 29.65 | 32.64 | 0 | 175.62 | 27.82 | 56
24 | UTTAR DINAJPUR | SM/17740 | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. | TSM/018636 | 40060377 | Augmentation | SVS | GO2223016801PH | 17/03/2023 | 170.93 | 10.49 | 181.42 | Raiganj Division | Malda Mechanical Division | 10.19 | 5.83 | 6.39 | 0 | 22.42 | 10.19 | 5.83 | 6.39 | 0 | 22.42 | 12.36 | 38
25 | UTTAR DINAJPUR | SM/17741 | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. | TSM/018631 | 40060372 | Augmentation | SVS | GO2223016807PH | 17/03/2023 | 158.64 | 10.49 | 169.13 | Raiganj Division | Malda Mechanical Division | 1.04 | 0 | 4.43 | 0 | 5.47 | 1.04 | 0 | 4.43 | 0 | 5.47 | 3.24 | 20
26 | UTTAR DINAJPUR | SM/09985 | Augmentation of Kanki Matiari Piped Water Supply Scheme. | TSM/009094 | 40002477 | Augmentation | MVS | GO2122006955PH | 16/12/2021 | 319.88 | 20.39 | 340.27 | Raiganj Division | Malda Mechanical Division | 170.7 | 18.49 | 7.14 | 0 | 196.33 | 170.62 | 18.49 | 7.14 | 0 | 196.25 | 57.67 | 93
27 | UTTAR DINAJPUR | SM/11797 | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME | TSM/011425 | 40027048 | Augmentation | MVS | GO2223006097PH | 05/08/2022 | 675.54 | 48.3 | 723.84 | Raiganj Division | Malda Mechanical Division | 233.66 | 33.69 | 9.71 | 0 | 277.07 | 233.66 | 33.69 | 9.71 | 0 | 277.07 | 38.28 | 67
28 | UTTAR DINAJPUR | SM/15125 | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME | TSM/011435 | 40043591 | Augmentation | MVS | GO2223013172PH | 04/02/2023 | 570.22 | 32.76 | 602.98 | Raiganj Division | Malda Mechanical Division | 81.88 | 31.8 | 15.08 | 0 | 128.76 | 81.88 | 31.8 | 15.08 | 0 | 128.76 | 21.35 | 38
29 | UTTAR DINAJPUR | SM/11795 | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME | TSM/011433 | 40027047 | Augmentation | MVS | GO2223006092PH | 05/08/2022 | 652.8 | 25.28 | 678.08 | Raiganj Division | Malda Mechanical Division | 325.77 | 11.39 | 17.19 | 0 | 354.35 | 325.77 | 11.39 | 17.19 | 0 | 354.35 | 52.26 | 62
30 | UTTAR DINAJPUR | SM/11724 | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME | TSM/011434 | 40027413 | Augmentation | SVS | GO2223006016PH | 03/08/2022 | 582.97 | 40.86 | 623.82 | Raiganj Division | Malda Mechanical Division | 224.06 | 24.96 | 26.51 | 0 | 275.52 | 224.06 | 24.96 | 26.51 | 0 | 275.52 | 44.17 | 82
31 | UTTAR DINAJPUR | SM/11725 | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME | TSM/011419 | 40027049 | Augmentation | MVS | GO2223006012PH | 03/08/2022 | 832.6 | 51.07 | 883.67 | Raiganj Division | Malda Mechanical Division | 182.19 | 22.03 | 55.85 | 0 | 260.07 | 182.19 | 22.03 | 55.85 | 0 | 260.07 | 29.43 | 46
32 | UTTAR DINAJPUR | SM/17743 | Augmentation of Nalbithi Madhabpur Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. | TSM/018652 | 40060483 | Augmentation | SVS | GO2223016799PH | 17/03/2023 | 144.75 | 10.49 | 155.24 | Raiganj Division | Malda Mechanical Division | 9.67 | 0 | 3.77 | 0 | 13.44 | 9.67 | 0 | 3.77 | 0 | 13.44 | 8.66 | 56
33 | UTTAR DINAJPUR | SM/10040 | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME | TSM/009722 | 40002417 | Augmentation | SVS | GO2122008402PH | 19/01/2022 | 360.96 | 20.49 | 381.45 | Raiganj Division | Malda Mechanical Division | 169.9 | 11.95 | 7.54 | 0 | 189.39 | 169.9 | 11.95 | 7.54 | 0 | 189.39 | 49.65 | 49
34 | UTTAR DINAJPUR | SM/17742 | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. | TSM/018651 | 40060362 | Augmentation | SVS | GO2223016803PH | 17/03/2023 | 192.93 | 10.49 | 203.43 | Raiganj Division | Malda Mechanical Division | 1.24 | 9.57 | 3.56 | 0 | 14.37 | 1.24 | 9.57 | 3.56 | 0 | 14.37 | 7.06 | 70
35 | UTTAR DINAJPUR | SM/09990 | Augmentation of Sitalgaon Piped Water Supply Scheme. | TSM/009075 | 40002556 | Augmentation | SVS | GO2122006949PH | 16/12/2021 | 514.39 | 20.77 | 535.16 | Raiganj Division | Malda Mechanical Division | 181.11 | 18.47 | 6.61 | 0 | 206.2 | 181.11 | 18.47 | 6.61 | 0 | 206.2 | 38.53 | 88
36 | UTTAR DINAJPUR | SM/12638 | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015258 | 40041723 | Augmentation | SVS | GO2223007870PH | 19/09/2022 | 36.72 | 19.65 | 56.37 | Raiganj Division | Malda Mechanical Division | 0 | 9.09 | 0.52 | 0 | 9.62 | 0 | 9.09 | 0.52 | 0 | 9.62 | 17.06 | 10
37 | UTTAR DINAJPUR | SM/10545 | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. | TSM/010497 | 40020263 | Augmentation | MVS | GO2223000358PH | 18/04/2022 | 283.68 | 0 | 283.68 | Raiganj Division |  | 269.31 | 0 | 0 | 0 | 269.31 | 269.3 | 0 | 0 | 0 | 269.3 | 94.93 | 63
38 | UTTAR DINAJPUR | SM/18227 | Replacement T/W for 4 Nos. water supply scheme. | TSM/005422 | 40063954 | Augmentation | SVS | GO2223016586PH | 16/03/2023 | 137.5 | 0 | 137.5 | Raiganj Division |  | 24.85 | 0 | 0 | 0 | 24.85 | 24.85 | 0 | 0 | 0 | 24.85 | 18.08 | 36
39 | UTTAR DINAJPUR | SM/12639 | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015280 | 40037930 | Augmentation | SVS | GO2223007862PH | 19/09/2022 | 39.49 | 19.65 | 59.14 | Raiganj Division | Malda Mechanical Division | 16.99 | 15.72 | 0 | 0 | 32.71 | 16.99 | 15.72 | 0 | 0 | 32.71 | 55.31 | 52
40 | UTTAR DINAJPUR | SM/14225 | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016481 | 40060206 | Augmentation | SVS | GO2223011811PH | 10/01/2023 | 31.1 | 18.65 | 49.75 | Raiganj Division | Malda Mechanical Division | 0 | 9.18 | 1.7 | 0 | 10.88 | 0 | 9.18 | 1.7 | 0 | 10.88 | 21.87 | 13
41 | UTTAR DINAJPUR | SM/12641 | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015272 | 40037464 | Augmentation | SVS | GO2223007843PH | 19/09/2022 | 29.91 | 19.65 | 49.56 | Raiganj Division | Malda Mechanical Division | 16.02 | 5.93 | 0 | 0 | 21.95 | 16.02 | 5.33 | 0 | 0 | 21.35 | 43.08 | 32
42 | UTTAR DINAJPUR | SM/12648 | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015253 | 40037491 | Augmentation | SVS | GO2223007872PH | 19/09/2022 | 36.72 | 19.65 | 56.37 | Raiganj Division | Malda Mechanical Division | 0 | 14.76 | 2.61 | 0 | 17.37 | 0 | 14.76 | 2.61 | 0 | 17.37 | 30.82 | 21
43 | UTTAR DINAJPUR | SM/12650 | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015257 | 40038205 | Augmentation | SVS | GO2223007858PH | 19/09/2022 | 33.32 | 19.65 | 52.98 | Raiganj Division | Malda Mechanical Division | 0 | 15.04 | 0 | 0 | 15.04 | 0 | 15.04 | 0 | 0 | 15.04 | 28.39 | 30
44 | UTTAR DINAJPUR | SM/13021 | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015274 | 40038173 | Augmentation | SVS | GO2223008384PH | 28/09/2022 | 38.84 | 19.65 | 58.49 | Raiganj Division | Malda Mechanical Division | 12.89 | 14 | 0 | 0 | 26.89 | 12.89 | 14 | 0 | 0 | 26.89 | 45.97 | 68
45 | UTTAR DINAJPUR | SM/12643 | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015259 | 40038281 | Augmentation | SVS | GO2223007846PH | 19/09/2022 | 34.77 | 19.72 | 54.48 | Raiganj Division | Malda Mechanical Division | 12.59 | 18.33 | 0 | 0 | 30.91 | 12.59 | 18.33 | 0 | 0 | 30.91 | 56.74 | 24
46 | UTTAR DINAJPUR | SM/12649 | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015265 | 40037485 | Augmentation | SVS | GO2223007863PH | 19/09/2022 | 36.72 | 19.65 | 56.37 | Raiganj Division | Malda Mechanical Division | 0 | 9.12 | 2.61 | 0 | 11.73 | 0 | 9.12 | 2.61 | 0 | 11.73 | 20.81 | 16
47 | UTTAR DINAJPUR | SM/14229 | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016478 | 40060215 | Augmentation | SVS | GO2223011813PH | 10/01/2023 | 30.89 | 18.65 | 49.54 | Raiganj Division | Malda Mechanical Division | 26.86 | 9.14 | 2.4 | 0 | 38.41 | 26.86 | 9.14 | 2.4 | 0 | 38.41 | 77.53 | 24
48 | UTTAR DINAJPUR | SM/13020 | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015282 | 40041562 | Augmentation | SVS | GO2223008382PH | 28/09/2022 | 36.72 | 19.65 | 56.37 | Raiganj Division | Malda Mechanical Division | 10.42 | 13.52 | 2.61 | 0 | 26.55 | 10.42 | 13.52 | 2.61 | 0 | 26.55 | 47.1 | 13
49 | UTTAR DINAJPUR | SM/12640 | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015281 | 40039129 | Augmentation | SVS | GO2223007850PH | 19/09/2022 | 44.79 | 19.65 | 64.44 | Raiganj Division | Malda Mechanical Division | 16.23 | 15.83 | 0 | 0 | 32.06 | 16.23 | 15.83 | 0 | 0 | 32.06 | 49.75 | 45
50 | UTTAR DINAJPUR | SM/12647 | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015286 | 40041508 | Augmentation | SVS | GO2223007871PH | 19/09/2022 | 36.72 | 19.65 | 56.37 | Raiganj Division | Malda Mechanical Division | 0 | 9.18 | 2.61 | 0 | 11.79 | 0 | 9.18 | 2.61 | 0 | 11.79 | 20.92 | 12
51 | UTTAR DINAJPUR | SM/12655 | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015267 | 40060127 | Augmentation | SVS | GO2223007868PH | 19/09/2022 | 36.88 | 19.65 | 56.53 | Raiganj Division | Malda Mechanical Division | 9.79 | 4.01 | 2.61 | 0 | 16.41 | 9.79 | 4.01 | 2.61 | 0 | 16.41 | 29.03 | 17
52 | UTTAR DINAJPUR | SM/14228 | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016494 | 40060197 | Augmentation | SVS | GO2223011808PH | 10/01/2023 | 31 | 18.65 | 49.66 | Raiganj Division | Malda Mechanical Division | 21.44 | 13.09 | 2.4 | 0 | 36.94 | 21.44 | 13.09 | 2.4 | 0 | 36.94 | 74.39 | 47
53 | UTTAR DINAJPUR | SM/12642 | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015275 | 40039178 | Augmentation | MVS | GO2223007840PH | 19/09/2022 | 44.21 | 19.65 | 63.86 | Raiganj Division | Malda Mechanical Division | 16.49 | 3.62 | 0 | 0 | 20.11 | 16.49 | 3.62 | 0 | 0 | 20.11 | 31.5 | 47
54 | UTTAR DINAJPUR | SM/12652 | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015252 | 40040649 | Augmentation | SVS | GO2223007852PH | 19/09/2022 | 36.72 | 19.65 | 56.37 | Raiganj Division | Malda Mechanical Division | 10.59 | 13.32 | 2.61 | 0 | 26.52 | 10.59 | 13.32 | 2.61 | 0 | 26.52 | 47.06 | 10
55 | UTTAR DINAJPUR | SM/12651 | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015244 | 40037474 | Augmentation | SVS | GO2223007865PH | 19/09/2022 | 38.88 | 19.65 | 58.53 | Raiganj Division | Malda Mechanical Division | 18.64 | 13.54 | 0 | 0 | 32.18 | 18.64 | 13.54 | 0 | 0 | 32.18 | 54.98 | 23
56 | UTTAR DINAJPUR | SM/12654 | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015247 | 40040541 | Augmentation | SVS | GO2223007854PH | 19/09/2022 | 38.88 | 19.65 | 58.53 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
57 | UTTAR DINAJPUR | SM/14232 | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016477 | 40060216 | Augmentation | SVS | GO2223011814PH | 10/01/2023 | 30.89 | 18.65 | 49.54 | Raiganj Division | Malda Mechanical Division | 10.54 | 16.04 | 2.4 | 0 | 28.99 | 10.54 | 16.04 | 2.4 | 0 | 28.99 | 58.51 | 5
58 | UTTAR DINAJPUR | SM/14230 | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016480 | 40060212 | Augmentation | SVS | GO2223011807PH | 10/01/2023 | 30.89 | 18.65 | 49.54 | Raiganj Division | Malda Mechanical Division | 21.9 | 12.82 | 2.4 | 0 | 37.13 | 21.9 | 12.82 | 2.4 | 0 | 37.13 | 74.96 | 17
59 | UTTAR DINAJPUR | SM/12653 | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015268 | 40040636 | Augmentation | SVS | GO2223007866PH | 19/09/2022 | 35.33 | 19.65 | 54.98 | Raiganj Division | Malda Mechanical Division | 16.66 | 17.93 | 0 | 0 | 34.6 | 16.66 | 17.93 | 0 | 0 | 34.6 | 62.93 | 44
60 | UTTAR DINAJPUR | SM/14231 | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016476 | 40060217 | Augmentation | SVS | GO2223011809PH | 10/01/2023 | 31.1 | 18.65 | 49.75 | Raiganj Division | Malda Mechanical Division | 0 | 9.17 | 2.4 | 0 | 11.58 | 0 | 9.17 | 2.4 | 0 | 11.58 | 23.27 | 3
61 | UTTAR DINAJPUR | SM/12646 | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015246 | 40040615 | Augmentation | SVS | GO2223007855PH | 19/09/2022 | 29.46 | 19.65 | 49.11 | Raiganj Division | Malda Mechanical Division | 16.01 | 17.77 | 0 | 0 | 33.78 | 16.01 | 17.77 | 0 | 0 | 33.78 | 68.77 | 53
62 | UTTAR DINAJPUR | SM/14226 | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016497 | 40060176 | Augmentation | SVS | GO2223011812PH | 10/01/2023 | 30.89 | 18.65 | 49.54 | Raiganj Division | Malda Mechanical Division | 0 | 14.28 | 2.38 | 0 | 16.66 | 0 | 14.28 | 2.38 | 0 | 16.66 | 33.62 | 21
63 | UTTAR DINAJPUR | SM/13015 | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015245 | 40040602 | Augmentation | SVS | GO2223008385PH | 28/09/2022 | 33.52 | 19.65 | 53.17 | Raiganj Division | Malda Mechanical Division | 17.02 | 13.24 | 0 | 0 | 30.26 | 17.02 | 13.24 | 0 | 0 | 30.25 | 56.9 | 52
64 | UTTAR DINAJPUR | SM/14227 | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | TSM/016479 | 40060213 | Augmentation | SVS | GO2223011810PH | 10/01/2023 | 30.89 | 18.65 | 49.54 | Raiganj Division | Malda Mechanical Division | 10.62 | 13.35 | 2.4 | 0 | 26.38 | 10.62 | 13.35 | 2.4 | 0 | 26.38 | 53.25 | 17
65 | UTTAR DINAJPUR | SM/12644 | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015290 | 40040583 | Augmentation | SVS | GO2223007851PH | 19/09/2022 | 35.33 | 19.65 | 54.98 | Raiganj Division | Malda Mechanical Division | 16.8 | 13.39 | 0 | 0 | 30.19 | 16.8 | 13.39 | 0 | 0 | 30.19 | 54.9 | 13
66 | UTTAR DINAJPUR | SM/12645 | Source Augmentation for Surun Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | TSM/015248 | 40040572 | Augmentation | SVS | GO2223007860PH | 19/09/2022 | 37 | 19.65 | 56.65 | Raiganj Division | Malda Mechanical Division | 10.33 | 13.51 | 0 | 0 | 23.84 | 10.33 | 8.37 | 0 | 0 | 18.7 | 33 | 18
Total | [9 empty] | 25751.62 | 1824.81 | 27576.43 |  |  | 6398.28 | 1050.48 | 1585.58 | 0 | 9034.35 | 6397.18 | 1044.74 | 1585.58 | 0 | 9027.5 | 32.74