## JJM Schemes Financial Status (U
JJM Schemes Financial Status (UTTAR DINAJPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | UTTAR DINAJPUR | SM/18629 | BHABANIPUR PWSS | TSM/018353 | 40042999 | New | MVS | 2165/PHE-28011/67/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1295.93 | 76.89 | 1372.82 | Raiganj Division | Malda Mechanical Division | 394.05 | 20.72 | 69.69 | 0 | 484.46 | 394.05 | 20.72 | 69.69 | 0 | 484.46 | 35.29 | 26
2 | UTTAR DINAJPUR | SM/12108 | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | TSM/012052 | 40028122 | New | MVS | GO2223006969PH | 02/09/2022 | 533 | 47.75 | 580.75 | Raiganj Division | Malda Mechanical Division | 246.17 | 30.02 | 10.59 | 0 | 286.77 | 246.17 | 30.02 | 10.59 | 0 | 286.77 | 49.38 | 66
3 | UTTAR DINAJPUR | SM/12091 | AGDIMTI Piped Water Supply Scheme at Islampur Block | TSM/013515 | 40028305 | New | MVS | GO2223006986PH | 02/09/2022 | 699.81 | 42.14 | 741.95 | Raiganj Division | Malda Mechanical Division | 290.02 | 15.48 | 44.03 | 0 | 349.53 | 290.02 | 15.48 | 44.03 | 0 | 349.53 | 47.11 | 41
4 | UTTAR DINAJPUR | SM/13456 | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | TSM/015320 | 40028538 | New | MVS | GO2223009195PH | 02/11/2022 | 667.16 | 43.15 | 710.31 | Raiganj Division | Malda Mechanical Division | 214.73 | 27.85 | 31.73 | 0 | 274.31 | 214.73 | 27.85 | 31.73 | 0 | 274.31 | 38.62 | 48
5 | UTTAR DINAJPUR | SM/14164 | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/017531 | 40033994 | New | MVS | GO2223011639PH | 05/01/2023 | 624.85 | 42.31 | 667.17 | Raiganj Division | Malda Mechanical Division | 45.91 | 9.38 | 47.16 | 0 | 102.45 | 45.91 | 9.38 | 47.16 | 0 | 102.45 | 15.36 | 67
6 | UTTAR DINAJPUR | SM/12090 | ALIGANJ Piped Water Supply Scheme at Islampur Block | TSM/013513 | 40028306 | New | MVS | GO2223006981PH | 02/09/2022 | 987.74 | 42.14 | 1029.88 | Raiganj Division | Malda Mechanical Division | 139.18 | 22.34 | 127.36 | 0 | 288.88 | 139.18 | 22.34 | 127.36 | 0 | 288.88 | 28.05 | 89
7 | UTTAR DINAJPUR | SM/12707 | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | TSM/014458 | 40028415 | New | MVS | GO2223007998PH | 20/09/2022 | 446.86 | 40.73 | 487.59 | Raiganj Division | Malda Mechanical Division | 159.8 | 32.63 | 29.46 | 0 | 221.89 | 159.8 | 32.63 | 29.46 | 0 | 221.89 | 45.51 | 45
8 | UTTAR DINAJPUR | SM/13796 | ATGHARA PIPED WATER SUPPLY SCHEME | TSM/012590 | 40028146 | New | MVS | GO2223009931PH | 22/11/2022 | 1231.54 | 66.69 | 1298.23 | Raiganj Division | Malda Mechanical Division | 640.21 | 62.36 | 68.87 | 0 | 771.45 | 639.81 | 62.36 | 68.87 | 0 | 771.05 | 59.39 | 94
9 | UTTAR DINAJPUR | SM/15215 | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018130 | 40042885 | New | MVS | GO2223013482PH | 07/02/2023 | 855.03 | 42.31 | 897.34 | Raiganj Division | Malda Mechanical Division | 367.17 | 34.01 | 13.47 | 0 | 414.66 | 367.17 | 34.01 | 13.47 | 0 | 414.66 | 46.21 | 40
10 | UTTAR DINAJPUR | SM/12778 | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014486 | 40028502 | New | MVS | GO2223007997PH | 20/09/2022 | 652.52 | 40.95 | 693.47 | Raiganj Division | Malda Mechanical Division | 131.97 | 36.96 | 41.03 | 0 | 209.95 | 131.97 | 36.96 | 41.03 | 0 | 209.95 | 30.28 | 42
11 | UTTAR DINAJPUR | SM/16536 | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | TSM/015098 | 40028495 | New | MVS | GO2223015529PH | 10/03/2023 | 1318.41 | 108.97 | 1427.38 | Raiganj Division | Malda Mechanical Division | 190.3 | 89.2 | 250.16 | 0 | 529.67 | 190.3 | 89.2 | 250.16 | 0 | 529.67 | 37.11 | 56
12 | UTTAR DINAJPUR | SM/11643 | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | TSM/011707 | 40028089 | New | MVS | GO2223005654PH | 27/07/2022 | 381.66 | 44.16 | 425.83 | Raiganj Division | Malda Mechanical Division | 188.18 | 27.32 | 12.84 | 0 | 228.33 | 188.18 | 27.32 | 12.84 | 0 | 228.33 | 53.62 | 70
13 | UTTAR DINAJPUR | SM/16222 | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018495 | 40053566 | New | MVS | GO2223014824PH | 23/02/2023 | 578.1 | 46.42 | 624.52 | Raiganj Division | Malda Mechanical Division | 158.61 | 35.1 | 20.99 | 0 | 214.7 | 158.22 | 35.1 | 20.99 | 0 | 214.31 | 34.32 | 33
14 | UTTAR DINAJPUR | SM/16223 | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018496 | 40053623 | New | MVS | GO2223014823PH | 23/02/2023 | 628.52 | 46.42 | 674.95 | Raiganj Division | Malda Mechanical Division | 139.87 | 25.55 | 23.59 | 0 | 189.01 | 139.5 | 25.55 | 23.59 | 0 | 188.64 | 27.95 | 52
15 | UTTAR DINAJPUR | SM/14146 | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | TSM/017738 | 40034177 | New | MVS | GO2223011526PH | 02/01/2023 | 668.98 | 50.43 | 719.4 | Raiganj Division | Malda Mechanical Division | 165.38 | 27.98 | 28.05 | 0 | 221.4 | 165.38 | 27.98 | 28.05 | 0 | 221.4 | 30.78 | 75
16 | UTTAR DINAJPUR | SM/18626 | BAJARGAON PWSS | TSM/018347 | 40042036 | New | MVS | 2165/PHE-28011/67/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1223.09 | 67.54 | 1290.63 | Raiganj Division | Malda Mechanical Division | 39.56 | 34.45 | 71.31 | 0 | 145.32 | 39.56 | 34.45 | 71.31 | 0 | 145.32 | 11.26 | 41
17 | UTTAR DINAJPUR | SM/11644 | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | TSM/011708 | 40028102 | New | MVS | GO2223005658PH | 27/07/2022 | 611.56 | 42.65 | 654.21 | Raiganj Division | Malda Mechanical Division | 271.6 | 22.69 | 18.63 | 0 | 312.93 | 271.6 | 22.69 | 18.63 | 0 | 312.93 | 47.83 | 85
18 | UTTAR DINAJPUR | SM/13520 | BALARAMPUR PIPED WATER SUPPLY SCHEME | TSM/015266 | 40028558 | New | MVS | GO2223009358PH | 04/11/2022 | 391.31 | 40.95 | 432.26 | Raiganj Division | Malda Mechanical Division | 145.94 | 32.95 | 9.11 | 0 | 188 | 145.94 | 32.95 | 9.11 | 0 | 188 | 43.49 | 23
19 | UTTAR DINAJPUR | SM/12107 | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/012635 | 40028331 | New | MVS | GO2223006966PH | 02/09/2022 | 529.01 | 44.5 | 573.51 | Raiganj Division | Malda Mechanical Division | 230.17 | 25.2 | 9.46 | 0 | 264.82 | 230.17 | 25.2 | 9.46 | 0 | 264.82 | 46.18 | 72
20 | UTTAR DINAJPUR | SM/13234 | BALDIABASA Piped Water Supply Scheme | TSM/015377 | 40028571 | New | MVS | GO2223008695PH | 13/10/2022 | 353.6 | 42.91 | 396.51 | Raiganj Division | Malda Mechanical Division | 150.02 | 20.07 | 16.07 | 0 | 186.16 | 123.56 | 20.07 | 16.07 | 0 | 159.7 | 40.28 | 42
21 | UTTAR DINAJPUR | SM/18493 | Balia Piped Water Supply Scheme. | TSM/004007 | 40034191 | New | MVS | PHE/IV/2005/W-598/23 | 24/07/2023 | 675.21 | 37.87 | 713.08 | Raiganj Division | Malda Mechanical Division | 17.34 | 13.54 | 19.38 | 0 | 50.27 | 17.34 | 13.54 | 19.38 | 0 | 50.27 | 7.05 | 40
22 | UTTAR DINAJPUR | SM/17631 | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | TSM/003985 | 40034199 | New | MVS | GO2223017474PH | 22/03/2023 | 508.09 | 37.91 | 546 | Raiganj Division | Malda Mechanical Division | 19.4 | 0 | 25.27 | 0 | 44.67 | 19.4 | 0 | 25.27 | 0 | 44.67 | 8.18 | 26
23 | UTTAR DINAJPUR | SM/17256 | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/020259 | 40034013 | New | MVS | GO2223016240PH | 15/03/2023 | 177.21 | 8.49 | 185.7 | Raiganj Division | Malda Mechanical Division | 48.73 | 5.83 | 6.25 | 0 | 60.8 | 48.73 | 5.83 | 6.25 | 0 | 60.8 | 32.74 | 53
24 | UTTAR DINAJPUR | SM/16505 | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/016905 | 40034017 | New | SVS | GO2223015183PH | 02/03/2023 | 124.19 | 8.49 | 132.68 | Raiganj Division | Malda Mechanical Division | 42.39 | 7.26 | 2.6 | 0 | 52.25 | 42.39 | 7.26 | 2.6 | 0 | 52.25 | 39.38 | 58
25 | UTTAR DINAJPUR | SM/11825 | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | TSM/011913 | 40028133 | New | MVS | GO2223006313PH | 16/08/2022 | 795.54 | 45.02 | 840.56 | Raiganj Division | Malda Mechanical Division | 295.37 | 38.42 | 21.33 | 0 | 355.12 | 295.37 | 38.42 | 21.33 | 0 | 355.12 | 42.25 | 72
26 | UTTAR DINAJPUR | SM/16471 | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | TSM/015388 | 40033916 | New | MVS | GO2223015188PH | 02/03/2023 | 352.96 | 40.95 | 393.91 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 6.18 | 0 | 6.18 | 0 | 0 | 6.18 | 0 | 6.18 | 1.57 | 6
27 | UTTAR DINAJPUR | SM/12522 | BANIKANER ALISA RAHATPUR PWSS | TSM/014361 | 40028437 | New | MVS | GO2223007531PH | 13/09/2022 | 370.27 | 43.84 | 414.11 | Raiganj Division | Malda Mechanical Division | 79.78 | 36.6 | 25.61 | 0 | 141.99 | 79.78 | 36.6 | 25.61 | 0 | 141.99 | 34.29 | 66
28 | UTTAR DINAJPUR | SM/18167 | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020973 | 40066211 | New | SVS | GO2223017985PH | 29/03/2023 | 115.23 | 18.36 | 133.59 | Raiganj Division | Malda Mechanical Division | 30.28 | 9.87 | 6.5 | 0 | 46.65 | 30.28 | 9.87 | 6.5 | 0 | 46.65 | 34.92 | 56
29 | UTTAR DINAJPUR | SM/12396 | BARA DOPAHARU Piped Water Supply Scheme | TSM/014803 | 40028507 | New | MVS | GO2223007533PH | 13/09/2022 | 418.51 | 42.14 | 460.65 | Raiganj Division | Malda Mechanical Division | 110.72 | 39.66 | 26.09 | 0 | 176.47 | 110.72 | 39.66 | 26.09 | 0 | 176.47 | 38.31 | 28
30 | UTTAR DINAJPUR | SM/12397 | BARA MIRCHA Piped Water Supply Scheme | TSM/014689 | 40028506 | New | MVS | GO2223007532PH | 13/09/2022 | 285.91 | 42.83 | 328.74 | Raiganj Division | Malda Mechanical Division | 112.98 | 33.88 | 14.78 | 0 | 161.64 | 112.98 | 33.88 | 14.78 | 0 | 161.64 | 49.17 | 25
31 | UTTAR DINAJPUR | SM/12529 | BARA SINGHANATH Piped Water Supply Scheme | TSM/014476 | 40028443 | New | MVS | GO2223007530PH | 13/09/2022 | 879.39 | 43.11 | 922.51 | Raiganj Division | Malda Mechanical Division | 274.73 | 9.66 | 35.68 | 0 | 320.08 | 274.73 | 9.66 | 35.68 | 0 | 320.08 | 34.7 | 44
32 | UTTAR DINAJPUR | SM/12093 | BARAKHANTI Piped Water Supply Scheme at Islampur Block | TSM/013549 | 40028307 | New | SVS | GO2223006980PH | 02/09/2022 | 851.78 | 42.14 | 893.92 | Raiganj Division | Malda Mechanical Division | 132.04 | 31.82 | 48.33 | 0 | 212.2 | 132.04 | 31.82 | 48.33 | 0 | 212.2 | 23.74 | 46
33 | UTTAR DINAJPUR | SM/12443 | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | TSM/014694 | 40028516 | New | MVS | GO2223007526PH | 13/09/2022 | 307.1 | 40.71 | 347.81 | Raiganj Division | Malda Mechanical Division | 73.35 | 39.39 | 27.17 | 0 | 139.91 | 73.35 | 39.39 | 27.17 | 0 | 139.91 | 40.23 | 30
34 | UTTAR DINAJPUR | SM/16226 | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | TSM/017556 | 40053600 | New | MVS | GO2223014821PH | 23/02/2023 | 316.42 | 42.02 | 358.44 | Raiganj Division | Malda Mechanical Division | 31.93 | 9.6 | 21.94 | 0 | 63.46 | 31.93 | 9.6 | 21.94 | 0 | 63.46 | 17.71 | 33
35 | UTTAR DINAJPUR | SM/12779 | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | TSM/014865 | 40028501 | New | MVS | GO2223007909PH | 20/09/2022 | 507.99 | 49.77 | 557.76 | Raiganj Division | Malda Mechanical Division | 102.92 | 47.96 | 9.78 | 0 | 160.66 | 102.92 | 47.96 | 9.78 | 0 | 160.66 | 28.8 | 68
36 | UTTAR DINAJPUR | SM/11961 | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | TSM/011690 | 40028119 | New | MVS | GO2223006710PH | 25/08/2022 | 644.89 | 42.83 | 687.72 | Raiganj Division | Malda Mechanical Division | 285.65 | 13.62 | 9.72 | 0 | 309 | 285.65 | 12.85 | 9.72 | 0 | 308.23 | 44.82 | 88
37 | UTTAR DINAJPUR | SM/15129 | BASATPUT Piped Water Supply Scheme | TSM/016384 | 40034296 | New | MVS | GO2223013116PH | 04/02/2023 | 875.13 | 58.49 | 933.62 | Raiganj Division | Malda Mechanical Division | 242.49 | 28.54 | 22.89 | 0 | 293.92 | 213.95 | 28.54 | 22.89 | 0 | 265.38 | 28.43 | 41
38 | UTTAR DINAJPUR | SM/14642 | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | TSM/016824 | 40034010 | New | MVS | GO2223012709PH | 31/01/2023 | 796.68 | 50.65 | 847.33 | Raiganj Division | Malda Mechanical Division | 112.52 | 27.86 | 39.17 | 0 | 179.54 | 112.52 | 27.86 | 39.17 | 0 | 179.54 | 21.19 | 46
39 | UTTAR DINAJPUR | SM/14182 | BASUDEBPUR Piped Water Supply Scheme | TSM/017263 | 40033049 | New | MVS | GO2223011743PH | 09/01/2023 | 767.37 | 42.31 | 809.69 | Raiganj Division | Malda Mechanical Division | 208.67 | 5.06 | 36.14 | 0 | 249.88 | 208.66 | 5.06 | 36.14 | 0 | 249.87 | 30.86 | 42
40 | UTTAR DINAJPUR | SM/15904 | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | TSM/017356 | 40033986 | New | MVS | GO2223014284PH | 20/02/2023 | 862.41 | 51.17 | 913.58 | Raiganj Division | Malda Mechanical Division | 306.1 | 43.61 | 26.03 | 0 | 375.74 | 306.1 | 43.61 | 26.03 | 0 | 375.74 | 41.13 | 67
41 | UTTAR DINAJPUR | SM/13233 | BELAN Piped Water Supply Scheme | TSM/015468 | 40028609 | New | MVS | GO2223008696PH | 13/10/2022 | 732.97 | 40.95 | 773.92 | Raiganj Division | Malda Mechanical Division | 202.31 | 10.65 | 17.35 | 0 | 230.3 | 192.16 | 10.65 | 17.35 | 0 | 220.16 | 28.45 | 31
42 | UTTAR DINAJPUR | SM/12104 | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/012758 | 40028336 | New | MVS | GO2223006985PH | 02/09/2022 | 362.67 | 40.74 | 403.41 | Raiganj Division | Malda Mechanical Division | 147.76 | 30.8 | 23.1 | 0 | 201.67 | 146.97 | 30.8 | 23.1 | 0 | 200.88 | 49.79 | 95
43 | UTTAR DINAJPUR | SM/18170 | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020865 | 40066221 | New | SVS | GO2223017888PH | 29/03/2023 | 147.97 | 20.59 | 168.56 | Raiganj Division | Malda Mechanical Division | 48.19 | 11.33 | 5.08 | 0 | 64.59 | 47.8 | 11.33 | 5.08 | 0 | 64.2 | 38.09 | 30
44 | UTTAR DINAJPUR | SM/14163 | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018205 | 40034123 | New | MVS | GO2223011638PH | 05/01/2023 | 910.06 | 64.56 | 974.62 | Raiganj Division | Malda Mechanical Division | 130.36 | 15.91 | 45.74 | 0 | 192.01 | 130.36 | 15.91 | 45.74 | 0 | 192.01 | 19.7 | 56
45 | UTTAR DINAJPUR | SM/18628 | BHIKHANPUR PWSS | TSM/018357 | 40042932 | New | MVS | 2165/PHE-28011/67/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1094.03 | 62.14 | 1156.17 | Raiganj Division | Malda Mechanical Division | 223.79 | 53.26 | 140.61 | 0 | 417.66 | 223.79 | 52.51 | 140.61 | 0 | 416.91 | 36.06 | 42
46 | UTTAR DINAJPUR | SM/12106 | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | TSM/012695 | 40028222 | New | MVS | GO2223006970PH | 02/09/2022 | 737.34 | 44.02 | 781.36 | Raiganj Division | Malda Mechanical Division | 90.7 | 17.32 | 16.58 | 0 | 124.59 | 90.7 | 17.32 | 16.58 | 0 | 124.59 | 15.95 | 30
47 | UTTAR DINAJPUR | SM/18627 | BHOMRA PWSS | TSM/018346 | 40042216 | New | MVS | 2165/PHE-28011/67/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1239.81 | 62.14 | 1301.95 | Raiganj Division | Malda Mechanical Division | 198.87 | 35.58 | 27.97 | 0 | 262.42 | 198.87 | 35.58 | 27.97 | 0 | 262.42 | 20.16 | 44
48 | UTTAR DINAJPUR | SM/14239 | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | TSM/015735 | 40028655 | New | MVS | GO2223012002PH | 16/01/2023 | 1307.08 | 62.03 | 1369.11 | Raiganj Division | Malda Mechanical Division | 21.19 | 51.44 | 25.53 | 0 | 98.16 | 21.19 | 51.44 | 25.53 | 0 | 98.16 | 7.17 | 26
49 | UTTAR DINAJPUR | SM/15147 | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | TSM/018418 | 40042218 | New | MVS | GO2223013489PH | 07/02/2023 | 708.76 | 43.56 | 752.32 | Raiganj Division | Malda Mechanical Division | 178.11 | 33.71 | 18.1 | 0 | 229.92 | 178.11 | 33.71 | 18.1 | 0 | 229.92 | 30.56 | 65
50 | UTTAR DINAJPUR | SM/16563 | BILASPUR Piped Water Supply Scheme | TSM/018367 | 40053558 | New | MVS | GO2223015488PH | 10/03/2023 | 598.68 | 43.56 | 642.24 | Raiganj Division | Malda Mechanical Division | 0 | 20.74 | 15.94 | 0 | 36.68 | 0 | 20.74 | 15.94 | 0 | 36.68 | 5.71 | 42
51 | UTTAR DINAJPUR | SM/18165 | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020936 | 40066210 | New | SVS | GO2223017887PH | 29/03/2023 | 84.78 | 8.75 | 93.53 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 2.52 | 0 | 2.52 | 0 | 0 | 2.52 | 0 | 2.52 | 2.7 | 15
52 | UTTAR DINAJPUR | SM/12110 | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | TSM/011862 | 40028126 | New | MVS | GO2223006960PH | 02/09/2022 | 767.44 | 47.08 | 814.52 | Raiganj Division | Malda Mechanical Division | 49.62 | 0 | 19.09 | 0 | 68.7 | 49.62 | 0 | 19.09 | 0 | 68.7 | 8.43 | 36
53 | UTTAR DINAJPUR | SM/18166 | BIRSINGGACHH MINI PIPED WATER SUPPLY SCHEME IN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020866 | 40066219 | New | SVS | GO2223017983PH | 29/03/2023 | 63.47 | 8.75 | 72.22 | Raiganj Division | Malda Mechanical Division | 28.46 | 0 | 0.79 | 0 | 29.26 | 28.46 | 0 | 0.79 | 0 | 29.26 | 40.51 | 45
54 | UTTAR DINAJPUR | SM/14144 | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018229 | 40032820 | New | MVS | GO2223011507PH | 02/01/2023 | 647.95 | 42.23 | 690.18 | Raiganj Division | Malda Mechanical Division | 171.63 | 3.74 | 37.28 | 0 | 212.65 | 171.63 | 3.74 | 37.28 | 0 | 212.65 | 30.81 | 31
55 | UTTAR DINAJPUR | SM/19012 | BUDHRA PWSS | TSM/018370 | 40043359 | New | MVS | PHE/IV/3274/W-709/23 | 27/10/2023 | 544.81 | 42.08 | 586.89 | Raiganj Division | Malda Mechanical Division | 0.69 | 29.71 | 14.4 | 0 | 44.79 | 0.69 | 29.71 | 14.4 | 0 | 44.79 | 7.63 | 43
56 | UTTAR DINAJPUR | SM/12112 | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | TSM/012813 | 40028340 | New | MVS | GO2223006973PH | 02/09/2022 | 610.14 | 40.66 | 650.8 | Raiganj Division | Malda Mechanical Division | 306.59 | 29.46 | 67.15 | 0 | 403.2 | 306.59 | 29.46 | 67.15 | 0 | 403.2 | 61.95 | 86
57 | UTTAR DINAJPUR | SM/16258 | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | TSM/017839 | 40034262 | New | MVS | GO2223014885PH | 24/02/2023 | 870.85 | 50.78 | 921.63 | Raiganj Division | Malda Mechanical Division | 284.86 | 28.51 | 42.27 | 0 | 355.64 | 284.86 | 28.51 | 42.27 | 0 | 355.64 | 38.59 | 82
58 | UTTAR DINAJPUR | SM/12094 | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | TSM/012812 | 40028274 | New | MVS | GO2223006965PH | 02/09/2022 | 908.61 | 43.94 | 952.55 | Raiganj Division | Malda Mechanical Division | 292.91 | 30.87 | 16.32 | 0 | 340.1 | 292.91 | 30.87 | 16.32 | 0 | 340.1 | 35.7 | 77
59 | UTTAR DINAJPUR | SM/14641 | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | TSM/016709 | 40034021 | New | MVS | GO2223012707PH | 31/01/2023 | 835.27 | 50.65 | 885.92 | Raiganj Division | Malda Mechanical Division | 163.14 | 23.44 | 39.92 | 0 | 226.5 | 163.14 | 23.44 | 39.92 | 0 | 226.5 | 25.57 | 67
60 | UTTAR DINAJPUR | SM/12102 | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/012771 | 40028275 | New | MVS | GO2223006984PH | 02/09/2022 | 418.24 | 40.65 | 458.89 | Raiganj Division | Malda Mechanical Division | 144.37 | 31.85 | 22.14 | 0 | 198.36 | 144.37 | 31.85 | 22.14 | 0 | 198.36 | 43.23 | 79
61 | UTTAR DINAJPUR | SM/12095 | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | TSM/012816 | 40028276 | New | MVS | GO2223006976PH | 02/09/2022 | 824.2 | 50.01 | 874.21 | Raiganj Division | Malda Mechanical Division | 351.04 | 35.23 | 33.64 | 0 | 419.91 | 351.04 | 35.23 | 33.64 | 0 | 419.91 | 48.03 | 56
62 | UTTAR DINAJPUR | SM/15146 | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | TSM/018241 | 40042215 | New | MVS | GO2223013485PH | 07/02/2023 | 672.09 | 42.08 | 714.17 | Raiganj Division | Malda Mechanical Division | 125.18 | 35.56 | 31.98 | 0 | 192.72 | 124.78 | 35.56 | 31.98 | 0 | 192.32 | 26.93 | 66
63 | UTTAR DINAJPUR | SM/16647 | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018401 | 40042126 | New | MVS | GO2223015938PH | 14/03/2023 | 609.53 | 42.08 | 651.61 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 24.35 | 0 | 24.35 | 0 | 0 | 24.35 | 0 | 24.35 | 3.74 | 6
64 | UTTAR DINAJPUR | SM/11863 | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | TSM/011704 | 40028095 | New | MVS | GO2223006412PH | 17/08/2022 | 420.29 | 41.32 | 461.61 | Raiganj Division | Malda Mechanical Division | 186.31 | 27.43 | 7.64 | 0 | 221.39 | 185.92 | 27.43 | 7.64 | 0 | 221 | 47.88 | 80
65 | UTTAR DINAJPUR | SM/18450 | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District | TSM/018690 | 40065967 | New | MVS | 1960/PHE-28011/132/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 1069.38 | 57.89 | 1127.27 | Raiganj Division | Malda Mechanical Division | 227.72 | 14.56 | 132.77 | 0 | 375.05 | 226.54 | 14.56 | 132.77 | 0 | 373.87 | 33.17 | 46
66 | UTTAR DINAJPUR | SM/12780 | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014398 | 40028450 | New | MVS | GO2223007898PH | 20/09/2022 | 550.39 | 50.25 | 600.64 | Raiganj Division | Malda Mechanical Division | 136.75 | 22.79 | 34.47 | 0 | 194.01 | 136.75 | 22.79 | 34.47 | 0 | 194.01 | 32.3 | 39
67 | UTTAR DINAJPUR | SM/16228 | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | TSM/018400 | 40053604 | New | SVS | GO2223014819PH | 23/02/2023 | 998.61 | 43.56 | 1042.17 | Raiganj Division | Malda Mechanical Division | 260.86 | 37.76 | 44.07 | 0 | 342.69 | 260.86 | 30.62 | 44.07 | 0 | 335.54 | 32.2 | 27
68 | UTTAR DINAJPUR | SM/14167 | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/016571 | 40032951 | New | MVS | GO2223011635PH | 05/01/2023 | 795.4 | 45.53 | 840.92 | Raiganj Division | Malda Mechanical Division | 343.17 | 35.29 | 40.27 | 0 | 418.73 | 330.15 | 35.29 | 40.27 | 0 | 405.71 | 48.25 | 62
69 | UTTAR DINAJPUR | SM/15304 | CHOUKAI Pipe Water Supply Scheme | TSM/018404 | 40042212 | New | MVS | GO2223013661PH | 09/02/2023 | 724.64 | 42.08 | 766.71 | Raiganj Division | Malda Mechanical Division | 24.61 | 20.07 | 12.5 | 0 | 57.18 | 0 | 20.07 | 12.5 | 0 | 32.57 | 4.25 | 18
70 | UTTAR DINAJPUR | SM/15305 | DAKSHIN ARIAGAON Pipe Water Supply Scheme | TSM/018381 | 40042925 | New | MVS | GO2223013660PH | 09/02/2023 | 627.93 | 42.3 | 670.23 | Raiganj Division | Malda Mechanical Division | 0 | 4.88 | 12.92 | 0 | 17.81 | 0 | 4.88 | 12.92 | 0 | 17.81 | 2.66
71 | UTTAR DINAJPUR | SM/12089 | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | TSM/013508 | 40028308 | New | MVS | GO2223006959PH | 02/09/2022 | 357.16 | 43.15 | 400.31 | Raiganj Division | Malda Mechanical Division | 111.39 | 12.13 | 17.21 | 0 | 140.73 | 111.39 | 12.13 | 17.21 | 0 | 140.73 | 35.16 | 40
72 | UTTAR DINAJPUR | SM/18149 | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. | TSM/020855 | 40066227 | New | SVS | GO2223017982PH | 29/03/2023 | 159.66 | 18.64 | 178.3 | Raiganj Division | Malda Mechanical Division | 0 | 11.74 | 6.3 | 0 | 18.04 | 0 | 11.74 | 6.3 | 0 | 18.04 | 10.12 | 16
73 | UTTAR DINAJPUR | SM/14145 | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018225 | 40034329 | New | MVS | GO2223011505PH | 02/01/2023 | 964.76 | 42.31 | 1007.08 | Raiganj Division | Malda Mechanical Division | 28.5 | 0 | 41.15 | 0 | 69.66 | 5.64 | 0 | 41.15 | 0 | 46.79 | 4.65 | 39
74 | UTTAR DINAJPUR | SM/12781 | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | TSM/014440 | 40028478 | New | MVS | GO2223007930PH | 20/09/2022 | 375.03 | 42.14 | 417.17 | Raiganj Division | Malda Mechanical Division | 85.51 | 29.62 | 16.8 | 0 | 131.92 | 85.51 | 29.62 | 16.8 | 0 | 131.92 | 31.62 | 32
75 | UTTAR DINAJPUR | SM/16495 | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/016150 | 40034008 | New | MVS | GO2223015182PH | 02/03/2023 | 564.81 | 42.93 | 607.74 | Raiganj Division | Malda Mechanical Division | 188.39 | 35.6 | 22.36 | 0 | 246.35 | 188.39 | 35.6 | 22.36 | 0 | 246.35 | 40.53 | 56
76 | UTTAR DINAJPUR | SM/16491 | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015935 | 40033889 | New | MVS | GO2223015187PH | 02/03/2023 | 497.31 | 40.73 | 538.04 | Raiganj Division | Malda Mechanical Division | 108.16 | 29.94 | 12.25 | 0 | 150.35 | 108.16 | 29.94 | 12.25 | 0 | 150.35 | 27.94 | 33
77 | UTTAR DINAJPUR | SM/13232 | DAKSHIN RAMPUR Piped Water Supply Scheme | TSM/015519 | 40028579 | New | MVS | GO2223008694PH | 13/10/2022 | 551.84 | 40.95 | 592.79 | Raiganj Division | Malda Mechanical Division | 230.3 | 28.52 | 16.35 | 0 | 275.17 | 225.62 | 28.52 | 16.35 | 0 | 270.49 | 45.63 | 50
78 | UTTAR DINAJPUR | SM/12782 | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014427 | 40028451 | New | MVS | GO2223007899PH | 20/09/2022 | 518.2 | 43.15 | 561.35 | Raiganj Division | Malda Mechanical Division | 121 | 10.26 | 23.06 | 0 | 154.32 | 121 | 10.26 | 23.06 | 0 | 154.32 | 27.49 | 44
79 | UTTAR DINAJPUR | SM/18148 | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020903 | 40066225 | New | MVS | GO2223017903PH | 29/03/2023 | 357.91 | 19.89 | 377.79 | Raiganj Division | Malda Mechanical Division | 74.82 | 0 | 16.13 | 0 | 90.95 | 74.82 | 0 | 16.13 | 0 | 90.95 | 24.07 | 42
80 | UTTAR DINAJPUR | SM/18168 | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020863 | 40066216 | New | SVS | GO2223017969PH | 29/03/2023 | 249.22 | 19.2 | 268.43 | Raiganj Division | Malda Mechanical Division | 71.91 | 9.76 | 11.71 | 0 | 93.37 | 71.51 | 9.76 | 11.71 | 0 | 92.98 | 34.64 | 32
81 | UTTAR DINAJPUR | SM/13236 | DAMODARKHURI Piped Water Supply Scheme | TSM/015341 | 40028544 | New | MVS | GO2223008697PH | 13/10/2022 | 561.28 | 40.95 | 602.24 | Raiganj Division | Malda Mechanical Division | 0 | 19.12 | 29.29 | 0 | 48.41 | 0 | 19.12 | 29.29 | 0 | 48.41 | 8.04 | 10
82 | UTTAR DINAJPUR | SM/14168 | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/016572 | 40032988 | New | MVS | GO2223011637PH | 05/01/2023 | 678.86 | 47.44 | 726.29 | Raiganj Division | Malda Mechanical Division | 113.7 | 30.66 | 9.34 | 0 | 153.69 | 113.7 | 30.66 | 9.34 | 0 | 153.69 | 21.16 | 26
83 | UTTAR DINAJPUR | SM/18169 | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020919 | 40066213 | New | SVS | GO2223017896PH | 29/03/2023 | 86.25 | 10.48 | 96.73 | Raiganj Division | Malda Mechanical Division | 49.09 | 8.76 | 2.58 | 0 | 60.43 | 49.09 | 8.76 | 2.58 | 0 | 60.43 | 62.48 | 95
84 | UTTAR DINAJPUR | SM/14639 | Dhamdhol Piped Water Supply Scheme. | TSM/016124 | 40033947 | New | MVS | GO2223012700PH | 31/01/2023 | 655.82 | 50.45 | 706.27 | Raiganj Division | Malda Mechanical Division | 156.87 | 28.03 | 29.84 | 0 | 214.75 | 156.47 | 28.03 | 29.84 | 0 | 214.35 | 30.35 | 60
85 | UTTAR DINAJPUR | SM/13717 | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/014170 | 40028375 | New | MVS | GO2223009857PH | 17/11/2022 | 1109.41 | 62.03 | 1171.44 | Raiganj Division | Malda Mechanical Division | 71.61 | 44.34 | 91.5 | 0 | 207.45 | 71.61 | 36.93 | 91.5 | 0 | 200.04 | 17.08 | 55
86 | UTTAR DINAJPUR | SM/15213 | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018375 | 40043525 | New | MVS | GO2223013483PH | 07/02/2023 | 890.63 | 37.2 | 927.83 | Raiganj Division | Malda Mechanical Division | 144.11 | 15.46 | 20.22 | 0 | 179.78 | 144.11 | 15.46 | 20.22 | 0 | 179.78 | 19.38 | 43
87 | UTTAR DINAJPUR | SM/15212 | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018369 | 40042214 | New | MVS | GO2223013484PH | 07/02/2023 | 658.42 | 42.08 | 700.5 | Raiganj Division | Malda Mechanical Division | 170.75 | 33.26 | 37.22 | 0 | 241.23 | 170.75 | 33.26 | 37.22 | 0 | 241.23 | 34.44 | 55
88 | UTTAR DINAJPUR | SM/18298 | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | TSM/017842 | 40047319 | New | MVS | 1667/PHE-28011/60/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 1017.69 | 50.78 | 1068.47 | Raiganj Division | Malda Mechanical Division | 157.45 | 21.53 | 30.84 | 0 | 209.83 | 157.45 | 21.53 | 30.84 | 0 | 209.83 | 19.64 | 30
89 | UTTAR DINAJPUR | SM/14827 | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | TSM/017861 | 40047320 | New | SVS | GO2223012979PH | 03/02/2023 | 114.13 | 8.49 | 122.62 | Raiganj Division | Malda Mechanical Division | 34.93 | 7.3 | 4.41 | 0 | 46.64 | 34.93 | 7.3 | 4.41 | 0 | 46.64 | 38.04 | 45
90 | UTTAR DINAJPUR | SM/18292 | DIGHALGAON PWSS | TSM/018378 | 40042221 | New | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 992.49 | 64.1 | 1056.59 | Raiganj Division | Malda Mechanical Division | 69.82 | 14.37 | 24.79 | 0 | 108.98 | 69.82 | 14.37 | 24.79 | 0 | 108.98 | 10.31 | 35
91 | UTTAR DINAJPUR | SM/18304 | DOHASO PWSS | TSM/015576 | 40028650 | New | MVS | 1660PHE-28011/186/2023-SCHM CELL-Dept. of PHE | 26/06/2023 | 1698.41 | 68.72 | 1767.14 | Raiganj Division | Malda Mechanical Division | 795.41 | 26.14 | 94.18 | 0 | 915.74 | 795.41 | 26.14 | 94.18 | 0 | 915.74 | 51.82 | 78
92 | UTTAR DINAJPUR | SM/18293 | DULEPUR PWSS | TSM/018374 | 40041993 | New | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1001.78 | 62.14 | 1063.92 | Raiganj Division | Malda Mechanical Division | 34.7 | 25.69 | 32.33 | 0 | 92.72 | 34.7 | 24.73 | 32.33 | 0 | 91.76 | 8.62 | 51
93 | UTTAR DINAJPUR | SM/12087 | DURGAPUR Piped Water Supply Scheme at Islampur Block | TSM/014156 | 40028389 | New | MVS | GO2223007005PH | 02/09/2022 | 517.85 | 40.73 | 558.58 | Raiganj Division | Malda Mechanical Division | 132.16 | 12.54 | 19.16 | 0 | 163.86 | 132.16 | 12.54 | 19.16 | 0 | 163.86 | 29.33 | 60
94 | UTTAR DINAJPUR | SM/18180 | Dwipnagar Piped Water Supply Scheme. | TSM/004005 | 40034222 | New | MVS | GO2223018089PH | 30/03/2023 | 493.98 | 37.78 | 531.76 | Raiganj Division | Malda Mechanical Division | 66.25 | 24.09 | 132.51 | 0 | 222.85 | 66.25 | 24.09 | 132.51 | 0 | 222.85 | 41.91 | 80
95 | UTTAR DINAJPUR | SM/14129 | FASHIA DIATION PIPED WATER SUPPLY SCHEME | TSM/016516 | 40032863 | New | MVS | GO2223011508PH | 02/01/2023 | 564.79 | 42.31 | 607.1 | Raiganj Division | Malda Mechanical Division | 0 | 8.08 | 14.25 | 0 | 22.34 | 0 | 8.08 | 14.25 | 0 | 22.34 | 3.68 | 5
96 | UTTAR DINAJPUR | SM/13012 | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | TSM/015104 | 40028515 | New | MVS | GO2223008314PH | 28/09/2022 | 923 | 56.94 | 979.94 | Raiganj Division | Malda Mechanical Division | 119.03 | 41.2 | 83.37 | 0 | 243.6 | 119.03 | 41.2 | 83.37 | 0 | 243.6 | 24.86 | 53
97 | UTTAR DINAJPUR | SM/12092 | GAISAL Piped Water Supply Scheme at Islampur Block | TSM/013516 | 40028309 | New | MVS | GO2223006979PH | 02/09/2022 | 774.29 | 47.38 | 821.68 | Raiganj Division | Malda Mechanical Division | 273.92 | 39.76 | 49.01 | 0 | 362.69 | 273.92 | 39.76 | 49.01 | 0 | 362.69 | 44.14 | 70
98 | UTTAR DINAJPUR | SM/12783 | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | TSM/014815 | 40028520 | New | SVS | GO2223007917PH | 20/09/2022 | 270.46 | 41.46 | 311.92 | Raiganj Division | Malda Mechanical Division | 82.04 | 28.22 | 3.09 | 0 | 113.35 | 82.04 | 28.22 | 3.09 | 0 | 113.35 | 36.34 | 45
99 | UTTAR DINAJPUR | SM/12784 | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014474 | 40028493 | New | SVS | GO2223007903PH | 20/09/2022 | 549.5 | 44.83 | 594.32 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 11.1 | 0 | 11.1 | 0 | 0 | 11.1 | 0 | 11.1 | 1.87 | 5
100 | UTTAR DINAJPUR | SM/15128 | GODASAMAL Piped Water Supply Scheme | TSM/016367 | 40032839 | New | MVS | GO2223013120PH | 04/02/2023 | 942.88 | 62.14 | 1005.02 | Raiganj Division | Malda Mechanical Division | 295.67 | 31.51 | 24.81 | 0 | 352 | 280.21 | 30.75 | 24.81 | 0 | 335.76 | 33.41 | 40
101 | UTTAR DINAJPUR | SM/12785 | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | TSM/014866 | 40028513 | New | MVS | GO2223007926PH | 20/09/2022 | 873.66 | 56.53 | 930.19 | Raiganj Division | Malda Mechanical Division | 294.81 | 31.74 | 26.83 | 0 | 353.38 | 294.81 | 31.74 | 26.83 | 0 | 353.38 | 37.99 | 70
102 | UTTAR DINAJPUR | SM/14640 | Gorahar Piped Water Supply Scheme. | TSM/016130 | 40033960 | New | SVS | GO2223012699PH | 31/01/2023 | 543.99 | 50.45 | 594.44 | Raiganj Division | Malda Mechanical Division | 108.54 | 35.77 | 24.76 | 0 | 169.07 | 108.54 | 35.77 | 24.76 | 0 | 169.07 | 28.44 | 32
103 | UTTAR DINAJPUR | SM/11642 | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | TSM/011695 | 40028105 | New | MVS | GO2223005653PH | 27/07/2022 | 856.23 | 42.57 | 898.8 | Raiganj Division | Malda Mechanical Division | 392.12 | 25.04 | 25.2 | 0 | 442.36 | 392.12 | 25.04 | 25.2 | 0 | 442.36 | 49.22 | 62
104 | UTTAR DINAJPUR | SM/18296 | GUNJARIA PWSS | TSM/016520 | 40042213 | New | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 983.51 | 48.91 | 1032.42 | Raiganj Division | Malda Mechanical Division | 140.14 | 10.56 | 84.41 | 0 | 235.11 | 140.14 | 10.56 | 84.41 | 0 | 235.11 | 22.77 | 45
105 | UTTAR DINAJPUR | SM/16219 | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | TSM/018695 | 40053567 | New | MVS | GO2223014817PH | 23/02/2023 | 660.18 | 46.42 | 706.61 | Raiganj Division | Malda Mechanical Division | 216.89 | 22.68 | 52.98 | 0 | 292.55 | 216.89 | 22.68 | 52.98 | 0 | 292.55 | 41.4 | 53
106 | UTTAR DINAJPUR | SM/16220 | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | TSM/018697 | 40053570 | New | MVS | GO2223014820PH | 23/02/2023 | 524.97 | 46.42 | 571.4 | Raiganj Division | Malda Mechanical Division | 189.18 | 41.78 | 19.87 | 0 | 250.83 | 189.18 | 41.78 | 19.87 | 0 | 250.83 | 43.9 | 86
107 | UTTAR DINAJPUR | SM/18160 | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR | TSM/020862 | 40066229 | New | SVS | GO2223017987PH | 29/03/2023 | 350.92 | 28.06 | 378.98 | Raiganj Division | Malda Mechanical Division | 71.82 | 4.21 | 15.06 | 0 | 91.1 | 71.82 | 4.21 | 15.06 | 0 | 91.1 | 24.04 | 44
108 | UTTAR DINAJPUR | SM/14180 | HEMENPUR Piped Water Supply Scheme | TSM/017332 | 40033055 | New | MVS | GO2223011739PH | 09/01/2023 | 522.07 | 42.08 | 564.15 | Raiganj Division | Malda Mechanical Division | 156.16 | 34.21 | 36.61 | 0 | 226.97 | 156.16 | 34.21 | 36.61 | 0 | 226.97 | 40.23 | 60
109 | UTTAR DINAJPUR | SM/18294 | IKARCHALA PWSS | TSM/014639 | 40042175 | New | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1115.79 | 84.37 | 1200.16 | Raiganj Division | Malda Mechanical Division | 380.13 | 59.82 | 53.97 | 0 | 493.91 | 380.13 | 59.82 | 53.97 | 0 | 493.91 | 41.15 | 75
110 | UTTAR DINAJPUR | SM/18449 | ILLUABARI PWSS | TSM/018454 | 40065958 | New | MVS | 1960/PHE-28011/132/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 1826.72 | 84.37 | 1911.1 | Raiganj Division | Malda Mechanical Division | 480.54 | 52.93 | 15.71 | 0 | 549.18 | 480.54 | 52.93 | 15.71 | 0 | 549.18 | 28.74 | 42
111 | UTTAR DINAJPUR | SM/13795 | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | TSM/013510 | 40028352 | New | MVS | GO2223009941PH | 22/11/2022 | 1249.15 | 62.03 | 1311.18 | Raiganj Division | Malda Mechanical Division | 599.49 | 48.87 | 80.54 | 0 | 728.9 | 598.99 | 48.87 | 80.54 | 0 | 728.4 | 55.55 | 77
112 | UTTAR DINAJPUR | SM/18287 | JAGDISHPUR PWSS | TSM/012027 | 40028149 | New | MVS | 1620/PHE-28011/175/2023-SCHM CELL-Dept. of PHE | 23/06/2023 | 1001.26 | 66.16 | 1067.42 | Raiganj Division | Malda Mechanical Division | 272.65 | 13.55 | 117.05 | 0 | 403.25 | 272.65 | 13.55 | 117.05 | 0 | 403.25 | 37.78 | 58
113 | UTTAR DINAJPUR | SM/14179 | JAMIRA Piped Water Supply Scheme | TSM/017295 | 40033964 | New | MVS | GO2223011737PH | 09/01/2023 | 745.01 | 43.99 | 789 | Raiganj Division | Malda Mechanical Division | 227.03 | 41.67 | 22.89 | 0 | 291.59 | 216.84 | 41.67 | 22.89 | 0 | 281.4 | 35.67 | 38
114 | UTTAR DINAJPUR | SM/12786 | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014422 | 40028440 | New | MVS | GO2223007929PH | 20/09/2022 | 560.29 | 43.15 | 603.43 | Raiganj Division | Malda Mechanical Division | 116.33 | 6.69 | 34.85 | 0 | 157.87 | 116.33 | 6.69 | 34.85 | 0 | 157.87 | 26.16 | 41
115 | UTTAR DINAJPUR | SM/18476 | JHITKAI PWSS | TSM/018220 | 40034292 | New | MVS | 1996/PHE-28011/168/2023-SCHM CELL-Dept. of PHE | 24/07/2023 | 1121.21 | 62.14 | 1183.35 | Raiganj Division | Malda Mechanical Division | 309.54 | 17.04 | 69.88 | 0 | 396.46 | 309.54 | 17.04 | 69.88 | 0 | 396.46 | 33.5 | 55
116 | UTTAR DINAJPUR | SM/13738 | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015618 | 40028568 | New | MVS | GO2223009813PH | 17/11/2022 | 777.62 | 42.14 | 819.76 | Raiganj Division | Malda Mechanical Division | 138.6 | 24.98 | 36.99 | 0 | 200.56 | 138.6 | 24.98 | 36.99 | 0 | 200.56 | 24.47 | 24
117 | UTTAR DINAJPUR | SM/13235 | KABUTARKHOPI Piped Water Supply Scheme | TSM/015529 | 40028601 | New | MVS | GO2223008693PH | 13/10/2022 | 579.24 | 48.36 | 627.6 | Raiganj Division | Malda Mechanical Division | 251.31 | 21.17 | 16.03 | 0 | 288.51 | 243.16 | 21.17 | 16.03 | 0 | 280.35 | 44.67 | 53
118 | UTTAR DINAJPUR | SM/13013 | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | TSM/015107 | 40028504 | New | MVS | GO2223008315PH | 28/09/2022 | 695.53 | 51.82 | 747.35 | Raiganj Division | Malda Mechanical Division | 107.64 | 42.42 | 77.2 | 0 | 227.26 | 107.64 | 42.42 | 77.2 | 0 | 227.26 | 30.41 | 75
119 | UTTAR DINAJPUR | SM/15307 | KADERGANJ Pipe Water Supply Scheme | TSM/018390 | 40044986 | New | MVS | GO2223013662PH | 09/02/2023 | 666.22 | 42.31 | 708.54 | Raiganj Division | Malda Mechanical Division | 0 | 25.21 | 20.71 | 0 | 45.93 | 0 | 25.21 | 20.71 | 0 | 45.93 | 6.48 | 11
120 | UTTAR DINAJPUR | SM/18451 | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018393 | 40053560 | New | MVS | 1960/PHE-28011/132/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 1244.31 | 108.51 | 1352.83 | Raiganj Division | Malda Mechanical Division | 265.91 | 27.8 | 99.1 | 0 | 392.81 | 265.91 | 27.8 | 99.1 | 0 | 392.81 | 29.04 | 71
121 | UTTAR DINAJPUR | SM/12787 | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014417 | 40028445 | New | MVS | GO2223007924PH | 20/09/2022 | 296.37 | 42.91 | 339.28 | Raiganj Division | Malda Mechanical Division | 83.75 | 35.2 | 23.11 | 0 | 142.06 | 83.75 | 35.2 | 23.11 | 0 | 142.06 | 41.87 | 40
122 | UTTAR DINAJPUR | SM/12788 | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | TSM/014738 | 40028514 | New | MVS | GO2223007911PH | 20/09/2022 | 695.58 | 40.97 | 736.56 | Raiganj Division | Malda Mechanical Division | 129.53 | 4.28 | 11.48 | 0 | 145.29 | 129.53 | 4.28 | 11.48 | 0 | 145.29 | 19.73 | 46
123 | UTTAR DINAJPUR | SM/18341 | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | TSM/016713 | 40034018 | New | MVS | 1749/PHE-28011/55/2023-SCHM CELL-Dept. of PHE | 04/07/2023 | 2165.23 | 92.3 | 2257.53 | Raiganj Division | Malda Mechanical Division | 228.8 | 54.73 | 122.87 | 0 | 406.4 | 227.62 | 47.41 | 122.87 | 0 | 397.9 | 17.63 | 36
124 | UTTAR DINAJPUR | SM/18182 | Kashimpur Piped Water Supply Scheme. | TSM/003990 | 40034250 | New | MVS | GO2223018121PH | 31/03/2023 | 526.08 | 37.93 | 564.01 | Raiganj Division | Malda Mechanical Division | 92.62 | 16.12 | 33.7 | 0 | 142.44 | 92.62 | 16.12 | 33.7 | 0 | 142.44 | 25.25 | 62
125 | UTTAR DINAJPUR | SM/12082 | KATAGAON Piped Water Supply Scheme at Chopra Block | TSM/014301 | 40028360 | New | MVS | GO2223007007PH | 02/09/2022 | 340.91 | 40.95 | 381.86 | Raiganj Division | Malda Mechanical Division | 90.11 | 39.18 | 24.5 | 0 | 153.79 | 90.11 | 39.18 | 24.5 | 0 | 153.79 | 40.27 | 36
126 | UTTAR DINAJPUR | SM/13739 | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015710 | 40028577 | New | MVS | GO2223009814PH | 17/11/2022 | 744.55 | 42.35 | 786.9 | Raiganj Division | Malda Mechanical Division | 143.39 | 26.42 | 16.02 | 0 | 185.83 | 143.39 | 26.42 | 16.02 | 0 | 185.83 | 23.62 | 45
127 | UTTAR DINAJPUR | SM/18179 | Khalsi Piped Water Supply Scheme. | TSM/004009 | 40034297 | New | MVS | GO2223018119PH | 31/03/2023 | 472.81 | 39.5 | 512.31 | Raiganj Division | Malda Mechanical Division | 105.28 | 15.83 | 40.46 | 0 | 161.57 | 105.28 | 15.83 | 40.46 | 0 | 161.57 | 31.54 | 60
128 | UTTAR DINAJPUR | SM/12103 | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/012769 | 40028279 | New | MVS | GO2223006958PH | 02/09/2022 | 692.38 | 40.82 | 733.2 | Raiganj Division | Malda Mechanical Division | 262.94 | 23.83 | 29.71 | 0 | 316.49 | 262.94 | 23.83 | 29.71 | 0 | 316.49 | 43.17 | 80
129 | UTTAR DINAJPUR | SM/12789 | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014974 | 40028449 | New | MVS | GO2223007905PH | 20/09/2022 | 493.92 | 42.91 | 536.84 | Raiganj Division | Malda Mechanical Division | 163.64 | 34.38 | 24.96 | 0 | 222.98 | 163.64 | 34.38 | 24.96 | 0 | 222.98 | 41.54 | 40
130 | UTTAR DINAJPUR | SM/14175 | KOKRA Piped Water Supply Scheme | TSM/018226 | 40034271 | New | MVS | GO2223011729PH | 09/01/2023 | 434.11 | 42.31 | 476.42 | Raiganj Division | Malda Mechanical Division | 114.7 | 20.38 | 8.41 | 0 | 143.48 | 114.7 | 20.38 | 8.41 | 0 | 143.48 | 30.12 | 55
131 | UTTAR DINAJPUR | SM/14166 | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/017365 | 40034149 | New | MVS | GO2223011598PH | 05/01/2023 | 862.48 | 43.56 | 906.05 | Raiganj Division | Malda Mechanical Division | 221.99 | 17.99 | 18.82 | 0 | 258.81 | 221.99 | 17.99 | 18.82 | 0 | 258.81 | 28.56 | 45
132 | UTTAR DINAJPUR | SM/16227 | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | TSM/018271 | 40053571 | New | MVS | GO2223014818PH | 24/02/2023 | 683.73 | 40.95 | 724.68 | Raiganj Division | Malda Mechanical Division | 0 | 14.77 | 39.42 | 0 | 54.19 | 0 | 14.77 | 39.42 | 0 | 54.19 | 7.48 | 20
133 | UTTAR DINAJPUR | SM/18164 | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020850 | 40066231 | New | MVS | GO2223017980PH | 29/03/2023 | 254.45 | 17.5 | 271.95 | Raiganj Division | Malda Mechanical Division | 26.17 | 19.31 | 12.4 | 0 | 57.87 | 26.17 | 19.31 | 12.4 | 0 | 57.87 | 21.28 | 60
134 | UTTAR DINAJPUR | SM/18325 | KUCHILA PWSS | TSM/016546 | 40032917 | New | MVS | 1687/PHE-28011/44/2023-SCHM CELL-Dept. of PHE | 27/06/2023 | 1057.09 | 43.99 | 1101.08 | Raiganj Division | Malda Mechanical Division | 246.49 | 0 | 24.65 | 0 | 271.14 | 246.49 | 0 | 24.65 | 0 | 271.14 | 24.63 | 35
135 | UTTAR DINAJPUR | SM/11821 | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | TSM/011943 | 40028111 | New | MVS | GO2223006277PH | 16/08/2022 | 562.84 | 42.64 | 605.48 | Raiganj Division | Malda Mechanical Division | 158.23 | 34.79 | 71.2 | 0 | 264.22 | 157.95 | 34.79 | 71.2 | 0 | 263.94 | 43.59 | 46
136 | UTTAR DINAJPUR | SM/12086 | KUNDARGAON Piped Water Supply Scheme at Islampur Block | TSM/014258 | 40028392 | New | MVS | GO2223007004PH | 02/09/2022 | 503.73 | 42.14 | 545.87 | Raiganj Division | Malda Mechanical Division | 128.38 | 27.05 | 8 | 0 | 163.43 | 128.38 | 27.05 | 8 | 0 | 163.43 | 29.94 | 66
137 | UTTAR DINAJPUR | SM/14165 | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/017508 | 40033987 | New | MVS | GO2223011632PH | 05/01/2023 | 637.52 | 51.8 | 689.32 | Raiganj Division | Malda Mechanical Division | 74.3 | 31.35 | 32.83 | 0 | 138.49 | 73.9 | 31.35 | 32.83 | 0 | 138.09 | 20.03 | 23
138 | UTTAR DINAJPUR | SM/11897 | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | TSM/011694 | 40028115 | New | SVS | GO2223006514PH | 18/08/2022 | 460.84 | 42.73 | 503.57 | Raiganj Division | Malda Mechanical Division | 207.27 | 19 | 32.68 | 0 | 258.94 | 207.27 | 19 | 32.68 | 0 | 258.94 | 51.42 | 58
139 | UTTAR DINAJPUR | SM/12115 | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | TSM/013047 | 40028284 | New | MVS | GO2223006972PH | 02/09/2022 | 796.6 | 40.66 | 837.26 | Raiganj Division | Malda Mechanical Division | 392.27 | 33.32 | 16.04 | 0 | 441.62 | 392.27 | 33.32 | 16.04 | 0 | 441.62 | 52.75 | 87
140 | UTTAR DINAJPUR | SM/18159 | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020859 | 40066228 | New | SVS | GO2223017988PH | 29/03/2023 | 257.12 | 19.25 | 276.37 | Raiganj Division | Malda Mechanical Division | 76.16 | 16.48 | 11.35 | 0 | 103.98 | 76.16 | 16.48 | 11.35 | 0 | 103.98 | 37.62 | 33
141 | UTTAR DINAJPUR | SM/18289 | MACHHALI PWSS | TSM/018359 | 40042084 | New | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1167.02 | 62.14 | 1229.16 | Raiganj Division | Malda Mechanical Division | 243.71 | 57.45 | 68.83 | 0 | 369.99 | 243.71 | 57.45 | 68.83 | 0 | 369.99 | 30.1 | 64
142 | UTTAR DINAJPUR | SM/12101 | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/013032 | 40028406 | New | MVS | GO2223006982PH | 02/09/2022 | 519.42 | 42.86 | 562.28 | Raiganj Division | Malda Mechanical Division | 210.08 | 24.25 | 11.49 | 0 | 245.83 | 210.08 | 24.25 | 11.49 | 0 | 245.83 | 43.72 | 80
143 | UTTAR DINAJPUR | SM/18155 | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020924 | 40066208 | New | SVS | GO2223017966PH | 29/03/2023 | 57 | 8.75 | 65.75 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 5.66 | 0 | 5.66 | 0 | 0 | 5.66 | 0 | 5.66 | 8.61 | 16
144 | UTTAR DINAJPUR | SM/15214 | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018311 | 40042217 | New | MVS | GO2223013487PH | 07/02/2023 | 928.41 | 42.31 | 970.73 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 18.98 | 0 | 18.98 | 0 | 0 | 18.98 | 0 | 18.98 | 1.96 | 29
145 | UTTAR DINAJPUR | SM/15516 | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | TSM/015895 | 40028644 | New | MVS | GO2223014009PH | 16/02/2023 | 1224.48 | 73.41 | 1297.89 | Raiganj Division | Malda Mechanical Division | 283.66 | 33.64 | 24.16 | 0 | 341.45 | 283.66 | 33.64 | 24.16 | 0 | 341.45 | 26.31 | 45
146 | UTTAR DINAJPUR | SM/11865 | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | TSM/011908 | 40028107 | New | MVS | GO2223006443PH | 17/08/2022 | 709.48 | 41.38 | 750.86 | Raiganj Division | Malda Mechanical Division | 296.98 | 19.23 | 55.06 | 0 | 371.27 | 296.98 | 19.23 | 55.06 | 0 | 371.27 | 49.45 | 82
147 | UTTAR DINAJPUR | SM/11824 | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | TSM/011914 | 40028128 | New | MVS | GO2223006290PH | 16/08/2022 | 1133.46 | 44.77 | 1178.23 | Raiganj Division | Malda Mechanical Division | 327.34 | 22.2 | 114.35 | 0 | 463.89 | 327.34 | 22.2 | 114.35 | 0 | 463.89 | 39.37 | 56
148 | UTTAR DINAJPUR | SM/13502 | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015800 | 40028603 | New | MVS | GO2223009196PH | 02/11/2022 | 597.12 | 40.95 | 638.08 | Raiganj Division | Malda Mechanical Division | 205.68 | 31.3 | 17.72 | 0 | 254.7 | 197.58 | 31.3 | 17.72 | 0 | 246.6 | 38.65 | 57
149 | UTTAR DINAJPUR | SM/15303 | MALKOT Pipe Water Supply Scheme | TSM/018415 | 40042219 | New | MVS | GO2223013656PH | 09/02/2023 | 721.9 | 42.17 | 764.07 | Raiganj Division | Malda Mechanical Division | 130.53 | 37.93 | 13.92 | 0 | 182.38 | 130.15 | 37.93 | 13.92 | 0 | 182 | 23.82 | 41
150 | UTTAR DINAJPUR | SM/12084 | MANIKPUR Piped Water Supply Scheme at Islampur Block | TSM/014295 | 40028356 | New | MVS | GO2223007009PH | 02/09/2022 | 685.76 | 47.61 | 733.37 | Raiganj Division | Malda Mechanical Division | 383.73 | 42.73 | 23.15 | 0 | 449.6 | 383.34 | 42.73 | 23.15 | 0 | 449.22 | 61.25 | 80
151 | UTTAR DINAJPUR | SM/13014 | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | TSM/015108 | 40028485 | New | MVS | GO2223008316PH | 28/09/2022 | 731.13 | 50.19 | 781.32 | Raiganj Division | Malda Mechanical Division | 144.32 | 36.04 | 21.92 | 0 | 202.28 | 144.32 | 36.04 | 21.92 | 0 | 202.28 | 25.89 | 61
152 | UTTAR DINAJPUR | SM/15126 | MANORA Piped Water Supply Scheme | TSM/015952 | 40032899 | New | MVS | GO2223013124PH | 04/02/2023 | 938.14 | 62.14 | 1000.28 | Raiganj Division | Malda Mechanical Division | 98.21 | 0 | 23.61 | 0 | 121.82 | 98.21 | 0 | 23.61 | 0 | 121.82 | 12.18 | 32
153 | UTTAR DINAJPUR | SM/11520 | Mini Piped Water Supply Scheme for the Blocks of Chopra and Goalpokhar-II in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | TSM/010099 | 40060621 | New | MVS | GO2223005217PH | 19/07/2022 | 977.22 | 0 | 977.22 | Raiganj Division | Malda Mechanical Division | 15.82 | 0 | 0 | 0 | 15.82 | 15.82 | 0 | 0 | 0 | 15.82 | 1.62 | 40
154 | UTTAR DINAJPUR | SM/11516 | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | TSM/010058 | 40060579 | New | MVS | GO2223005213PH | 19/07/2022 | 969.86 | 0 | 969.86 | Raiganj Division | Malda Mechanical Division | 7.38 | 0 | 0 | 0 | 7.38 | 7.38 | 0 | 0 | 0 | 7.38 | 0.76 | 40
155 | UTTAR DINAJPUR | SM/11517 | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. | TSM/010111 | 40060578 | New | MVS | GO2223005220PH | 19/07/2022 | 975.54 | 0 | 975.54 | Raiganj Division | Malda Mechanical Division | 9.81 | 0 | 0 | 0 | 9.81 | 9.81 | 0 | 0 | 0 | 9.81 | 1.01 | 40
156 | UTTAR DINAJPUR | SM/11518 | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | TSM/010110 | 40060558 | New | MVS | GO2223005219PH | 19/07/2022 | 978.29 | 0 | 978.29 | Raiganj Division | Malda Mechanical Division | 31.04 | 0 | 0 | 0 | 31.04 | 31.04 | 0 | 0 | 0 | 31.04 | 3.17 | 40
157 | UTTAR DINAJPUR | SM/11519 | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | TSM/010109 | 40060608 | New | MVS | GO2223005222PH | 19/07/2022 | 976.8 | 0 | 976.8 | Raiganj Division | Malda Mechanical Division | 40.99 | 0 | 0 | 0 | 40.99 | 40.99 | 0 | 0 | 0 | 40.99 | 4.2 | 40
158 | UTTAR DINAJPUR | SM/11521 | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. | TSM/010098 | 40060538 | New | MVS | GO2223005223PH | 19/07/2022 | 565.81 | 0 | 565.81 | Raiganj Division | Malda Mechanical Division | 14.16 | 0 | 0 | 0 | 14.16 | 14.16 | 0 | 0 | 0 | 14.16 | 2.5 | 40
159 | UTTAR DINAJPUR | SM/14627 | MIRJADPUR Piped Water Supply Scheme | TSM/016582 | 40032939 | New | MVS | GO2223012723PH | 31/01/2023 | 584.42 | 42.31 | 626.74 | Raiganj Division | Malda Mechanical Division | 0 | 0 | 14.1 | 0 | 14.1 | 0 | 0 | 14.1 | 0 | 14.1 | 2.25 | 5
160 | UTTAR DINAJPUR | SM/17199 | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018892 | 40053586 | New | MVS | GO2223016238PH | 15/03/2023 | 709.55 | 46.42 | 755.97 | Raiganj Division | Malda Mechanical Division | 184.21 | 32.03 | 127.78 | 0 | 344.02 | 184.21 | 32.03 | 127.78 | 0 | 344.02 | 45.51 | 62
161 | UTTAR DINAJPUR | SM/16225 | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | TSM/018406 | 40053559 | New | MVS | GO2223014822PH | 23/02/2023 | 438.58 | 42.31 | 480.89 | Raiganj Division | Malda Mechanical Division | 87.29 | 5.04 | 5.74 | 0 | 98.07 | 87.29 | 5.04 | 5.74 | 0 | 98.07 | 20.39 | 35
162 | UTTAR DINAJPUR | SM/16490 | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015931 | 40033855 | New | MVS | GO2223015185PH | 02/03/2023 | 477.67 | 42 | 519.67 | Raiganj Division | Malda Mechanical Division | 126.27 | 34.68 | 12.58 | 0 | 173.53 | 125.88 | 34.68 | 12.58 | 0 | 173.13 | 33.32 | 48
163 | UTTAR DINAJPUR | SM/15148 | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | TSM/018893 | 40042226 | New | MVS | GO2223013488PH | 07/02/2023 | 722.53 | 48.42 | 770.95 | Raiganj Division | Malda Mechanical Division | 126.56 | 32.38 | 130.86 | 0 | 289.79 | 126.56 | 32.38 | 130.86 | 0 | 289.79 | 37.59 | 59
164 | UTTAR DINAJPUR | SM/16199 | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | TSM/016131 | 40060925 | New | SVS | GO2223014884PH | 24/02/2023 | 127.58 | 11.06 | 138.64 | Raiganj Division | Malda Mechanical Division | 38.13 | 10.66 | 3.11 | 0 | 51.9 | 38.13 | 10.66 | 3.11 | 0 | 51.9 | 37.44 | 90
165 | UTTAR DINAJPUR | SM/18181 | Palaibari Piped Water Supply Scheme. | TSM/003994 | 40034308 | New | MVS | GO2223018118PH | 31/03/2023 | 757.34 | 55.68 | 813.02 | Raiganj Division | Malda Mechanical Division | 171.33 | 42.66 | 43.59 | 0 | 257.58 | 171.33 | 42.66 | 43.59 | 0 | 257.58 | 31.68 | 59
166 | UTTAR DINAJPUR | SM/12099 | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/013030 | 40028293 | New | MVS | GO2223006964PH | 02/09/2022 | 695.24 | 45.85 | 741.1 | Raiganj Division | Malda Mechanical Division | 322.65 | 27.98 | 29.26 | 0 | 379.89 | 322.65 | 27.98 | 29.26 | 0 | 379.89 | 51.26 | 73
167 | UTTAR DINAJPUR | SM/13542 | PANDITPOTA PIPED WATER SUPPLY SCHEME | TSM/015533 | 40028559 | New | MVS | GO2223009380PH | 04/11/2022 | 498.73 | 42.14 | 540.87 | Raiganj Division | Malda Mechanical Division | 98.78 | 32.35 | 10.26 | 0 | 141.39 | 98.78 | 32.35 | 10.26 | 0 | 141.39 | 26.14 | 65
168 | UTTAR DINAJPUR | SM/16494 | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/016133 | 40033965 | New | MVS | GO2223015184PH | 02/03/2023 | 829.15 | 50.78 | 879.93 | Raiganj Division | Malda Mechanical Division | 145.5 | 20.33 | 27.33 | 0 | 193.17 | 145.5 | 20.33 | 27.33 | 0 | 193.17 | 21.95 | 64
169 | UTTAR DINAJPUR | SM/12083 | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block | TSM/014313 | 40028390 | New | MVS | GO2223007008PH | 02/09/2022 | 337.64 | 40.95 | 378.6 | Raiganj Division | Malda Mechanical Division | 126 | 25.24 | 5.96 | 0 | 157.19 | 126 | 25.24 | 5.96 | 0 | 157.19 | 41.52 | 40
170 | UTTAR DINAJPUR | SM/12085 | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block | TSM/014265 | 40028395 | New | SVS | GO2223007010PH | 02/09/2022 | 719.8 | 43.15 | 762.95 | Raiganj Division | Malda Mechanical Division | 0 | 9.93 | 13.39 | 0 | 23.31 | 0 | 5.18 | 13.39 | 0 | 18.56 | 2.43 | 21
171 | UTTAR DINAJPUR | SM/18147 | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020864 | 40066222 | New | SVS | GO2223017984PH | 29/03/2023 | 90.66 | 9.39 | 100.04 | Raiganj Division | Malda Mechanical Division | 30.28 | 7.28 | 2.56 | 0 | 40.13 | 30.28 | 7.28 | 2.56 | 0 | 40.13 | 40.11 | 63
172 | UTTAR DINAJPUR | SM/11820 | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | TSM/011936 | 40028113 | New | MVS | GO2223006307PH | 16/08/2022 | 709.06 | 42.77 | 751.83 | Raiganj Division | Malda Mechanical Division | 350.85 | 31.25 | 18.27 | 0 | 400.37 | 350.85 | 31.25 | 18.27 | 0 | 400.37 | 53.25 | 70
173 | UTTAR DINAJPUR | SM/12790 | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014703 | 40028512 | New | SVS | GO2223007915PH | 20/09/2022 | 64.72 | 19.14 | 83.86 | Raiganj Division | Malda Mechanical Division | 47.85 | 28.15 | 1.88 | 0 | 77.88 | 47.85 | 28.15 | 1.88 | 0 | 77.88 | 92.87 | 95
174 | UTTAR DINAJPUR | SM/12088 | POTHIA Piped Water Supply Scheme at Islampur Block | TSM/014140 | 40028396 | New | MVS | GO2223007006PH | 02/09/2022 | 682.41 | 49.44 | 731.84 | Raiganj Division | Malda Mechanical Division | 277.53 | 36.83 | 19.38 | 0 | 333.74 | 277.34 | 36.83 | 19.38 | 0 | 333.55 | 45.58 | 63
175 | UTTAR DINAJPUR | SM/14128 | PRATAPPUR PIPED WATER SUPPLY SCHEME | TSM/016739 | 40032967 | New | MVS | GO2223011509PH | 02/01/2023 | 568.39 | 44.62 | 613.01 | Raiganj Division | Malda Mechanical Division | 201.37 | 37.29 | 34.43 | 0 | 273.09 | 201.37 | 37.29 | 34.43 | 0 | 273.09 | 44.55 | 44
176 | UTTAR DINAJPUR | SM/16229 | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | TSM/018405 | 40053602 | New | SVS | GO2223014816PH | 23/02/2023 | 424.53 | 46.46 | 470.99 | Raiganj Division | Malda Mechanical Division | 113.3 | 36.91 | 4.87 | 0 | 155.07 | 113.3 | 36.91 | 4.87 | 0 | 155.07 | 32.93 | 74
177 | UTTAR DINAJPUR | SM/13550 | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015845 | 40028622 | New | MVS | GO2223009359PH | 04/11/2022 | 786.85 | 44.83 | 831.68 | Raiganj Division | Malda Mechanical Division | 262.19 | 31.02 | 18.03 | 0 | 311.24 | 262.19 | 31.02 | 18.03 | 0 | 311.24 | 37.42 | 45
178 | UTTAR DINAJPUR | SM/12791 | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | TSM/014442 | 40028469 | New | MVS | GO2223007913PH | 20/09/2022 | 676.42 | 40.95 | 717.37 | Raiganj Division | Malda Mechanical Division | 97.66 | 21.01 | 14.59 | 0 | 133.26 | 97.66 | 21.01 | 14.59 | 0 | 133.26 | 18.58 | 43
179 | UTTAR DINAJPUR | SM/18448 | PURBBA GOMAIDIGHI PWSS | TSM/016371 | 40053598 | New | SVS | 1960/PHE-28011/132/2023-SCHM CELL-Dept. of PHE | 20/07/2023 | 963.58 | 48.71 | 1012.28 | Raiganj Division | Malda Mechanical Division | 303.91 | 41.39 | 38.98 | 0 | 384.29 | 303.91 | 41.39 | 38.98 | 0 | 384.29 | 37.96 | 53
180 | UTTAR DINAJPUR | SM/12097 | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/013010 | 40028295 | New | MVS | GO2223006977PH | 02/09/2022 | 532.38 | 44.5 | 576.88 | Raiganj Division | Malda Mechanical Division | 233.24 | 28.68 | 11.09 | 0 | 273.01 | 233.24 | 28.68 | 11.09 | 0 | 273.01 | 47.33 | 93
181 | UTTAR DINAJPUR | SM/12105 | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | TSM/012698 | 40028298 | New | MVS | GO2223006974PH | 02/09/2022 | 854.46 | 41.34 | 895.79 | Raiganj Division | Malda Mechanical Division | 205.04 | 16.53 | 47.81 | 0 | 269.39 | 205.04 | 16.53 | 47.81 | 0 | 269.39 | 30.07 | 60
182 | UTTAR DINAJPUR | SM/14181 | RANIGANJ Piped Water Supply Scheme | TSM/017338 | 40033977 | New | MVS | GO2223011744PH | 09/01/2023 | 770.93 | 62.14 | 833.07 | Raiganj Division | Malda Mechanical Division | 144.48 | 50.18 | 64.9 | 0 | 259.56 | 144.48 | 50.18 | 64.9 | 0 | 259.56 | 31.16 | 56
183 | UTTAR DINAJPUR | SM/15306 | RAUTARA Pipe Water Supply Scheme | TSM/018384 | 40041829 | New | MVS | GO2223013659PH | 09/02/2023 | 710.72 | 42.31 | 753.03 | Raiganj Division | Malda Mechanical Division | 186.75 | 21.07 | 21.21 | 0 | 229.02 | 186.75 | 21.07 | 21.21 | 0 | 229.02 | 30.41 | 34
184 | UTTAR DINAJPUR | SM/18161 | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | TSM/020854 | 40066230 | New | SVS | GO2223017964PH | 29/03/2023 | 82.55 | 9.34 | 91.89 | Raiganj Division | Malda Mechanical Division | 0 | 9.05 | 4.2 | 0 | 13.25 | 0 | 9.05 | 4.2 | 0 | 13.25 | 14.42 | 62
185 | UTTAR DINAJPUR | SM/12792 | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | TSM/014488 | 40028460 | New | MVS | GO2223007907PH | 20/09/2022 | 819.55 | 50.7 | 870.25 | Raiganj Division | Malda Mechanical Division | 385.77 | 45.81 | 16.03 | 0 | 447.61 | 385.77 | 45.81 | 16.03 | 0 | 447.61 | 51.44 | 60
186 | UTTAR DINAJPUR | SM/12109 | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | TSM/012037 | 40028141 | New | MVS | GO2223006968PH | 02/09/2022 | 691.31 | 40.79 | 732.1 | Raiganj Division | Malda Mechanical Division | 156.47 | 33.29 | 53.86 | 0 | 243.63 | 156.47 | 33.29 | 53.86 | 0 | 243.63 | 33.28 | 78
187 | UTTAR DINAJPUR | SM/18994 | SADIPUR PWSS | TSM/018395 | 40043119 | New | MVS | PHE/IV/3207/W-697/23 | 17/10/2023 | 871.49 | 43.56 | 915.05 | Raiganj Division | Malda Mechanical Division | 300.71 | 9.59 | 16.11 | 0 | 326.41 | 300.71 | 9.1 | 16.11 | 0 | 325.92 | 35.62 | 67
188 | UTTAR DINAJPUR | SM/16493 | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/016128 | 40034005 | New | MVS | GO2223015186PH | 02/03/2023 | 444.65 | 51.51 | 496.17 | Raiganj Division | Malda Mechanical Division | 184.08 | 45.65 | 9.65 | 0 | 239.38 | 183.69 | 45.65 | 9.65 | 0 | 239 | 48.17 | 72
189 | UTTAR DINAJPUR | SM/17255 | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/019160 | 40053625 | New | MVS | GO2223016242PH | 15/03/2023 | 658.04 | 46.42 | 704.46 | Raiganj Division | Malda Mechanical Division | 225.82 | 8.81 | 28.71 | 0 | 263.35 | 225.82 | 8.81 | 28.71 | 0 | 263.35 | 37.38 | 69
190 | UTTAR DINAJPUR | SM/15127 | SARJAPUR Piped Water Supply Scheme | TSM/015948 | 40032874 | New | MVS | GO2223013112PH | 04/02/2023 | 889.36 | 42.17 | 931.52 | Raiganj Division | Malda Mechanical Division | 10.07 | 20.95 | 24.61 | 0 | 55.63 | 0 | 20.95 | 24.61 | 0 | 45.56 | 4.89 | 6
191 | UTTAR DINAJPUR | SM/13231 | Sathaur Piped Water Supply Scheme | TSM/015526 | 40028607 | New | MVS | GO2223008698PH | 13/10/2022 | 404.93 | 40.73 | 445.66 | Raiganj Division | Malda Mechanical Division | 142.36 | 30.51 | 22.93 | 0 | 195.8 | 142.36 | 30.51 | 22.93 | 0 | 195.8 | 43.93 | 65
192 | UTTAR DINAJPUR | SM/12793 | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | TSM/014404 | 40028452 | New | MVS | GO2223007928PH | 20/09/2022 | 707.6 | 44.74 | 752.34 | Raiganj Division | Malda Mechanical Division | 209.74 | 35.35 | 49.12 | 0 | 294.21 | 209.74 | 35.35 | 49.12 | 0 | 294.21 | 39.11 | 48
193 | UTTAR DINAJPUR | SM/15211 | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/018397 | 40041911 | New | MVS | GO2223013490PH | 07/02/2023 | 502.56 | 43.56 | 546.12 | Raiganj Division | Malda Mechanical Division | 137.48 | 9.02 | 7.93 | 0 | 154.43 | 137.48 | 8.28 | 7.93 | 0 | 153.69 | 28.14 | 51
194 | UTTAR DINAJPUR | SM/12100 | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/012780 | 40028303 | New | MVS | GO2223006975PH | 02/09/2022 | 615.3 | 40.74 | 656.05 | Raiganj Division | Malda Mechanical Division | 251.5 | 26.74 | 31.13 | 0 | 309.37 | 251.5 | 26.74 | 31.13 | 0 | 309.37 | 47.16 | 75
195 | UTTAR DINAJPUR | SM/16221 | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | TSM/018891 | 40053588 | New | MVS | GO2223014825PH | 23/02/2023 | 659.19 | 46.42 | 705.61 | Raiganj Division | Malda Mechanical Division | 209.11 | 19.4 | 20.75 | 0 | 249.26 | 209.11 | 19.4 | 20.75 | 0 | 249.26 | 35.33 | 60
196 | UTTAR DINAJPUR | SM/17226 | Sripur Piped Water Supply Scheme | TSM/016135 | 40034000 | New | SVS | GO2223016355PH | 15/03/2023 | 117.72 | 8.49 | 126.21 | Raiganj Division | Malda Mechanical Division | 10.2 | 5.66 | 6.57 | 0 | 22.42 | 10.2 | 5.66 | 6.57 | 0 | 22.42 | 17.76 | 25
197 | UTTAR DINAJPUR | SM/16224 | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018409 | 40065970 | New | MVS | GO2223014815PH | 23/02/2023 | 767.97 | 44.44 | 812.41 | Raiganj Division | Malda Mechanical Division | 286.46 | 28.19 | 29.47 | 0 | 344.11 | 286.44 | 28.19 | 29.47 | 0 | 344.09 | 42.35 | 85
198 | UTTAR DINAJPUR | SM/17436 | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018492 | 40053561 | New | MVS | GO2223017209PH | 18/03/2023 | 577.06 | 48.83 | 625.89 | Raiganj Division | Malda Mechanical Division | 131.75 | 42.6 | 24.97 | 0 | 199.33 | 131.75 | 42.6 | 24.97 | 0 | 199.33 | 31.85 | 61
199 | UTTAR DINAJPUR | SM/17437 | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | TSM/018494 | 40053605 | New | MVS | GO2223017210PH | 18/03/2023 | 403.86 | 8.49 | 412.36 | Raiganj Division | Malda Mechanical Division | 83.57 | 7.28 | 12.3 | 0 | 103.15 | 83.57 | 7.28 | 12.3 | 0 | 103.15 | 25.02 | 62
200 | UTTAR DINAJPUR | SM/13503 | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | TSM/015620 | 40028615 | New | MVS | GO2223009197PH | 02/11/2022 | 571.84 | 41.08 | 612.92 | Raiganj Division | Malda Mechanical Division | 220.76 | 33.7 | 22.75 | 0 | 277.21 | 198.98 | 33.7 | 22.75 | 0 | 255.43 | 41.67 | 46
201 | UTTAR DINAJPUR | SM/11819 | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | TSM/011957 | 40028109 | New | MVS | GO2223006320PH | 16/08/2022 | 424.39 | 42.73 | 467.12 | Raiganj Division | Malda Mechanical Division | 269.37 | 23.88 | 3.36 | 0 | 296.6 | 269.37 | 23.88 | 3.36 | 0 | 296.6 | 63.5 | 90
202 | UTTAR DINAJPUR | SM/18243 | TOPAMARI PWSS | TSM/014297 | 40028369 | New | MVS | 1555/PHE-28011/72/2023-ESTT CELL-Dept. of PHE | 16/06/2023 | 1052.59 | 59.97 | 1112.55 | Raiganj Division | Malda Mechanical Division | 288.94 | 44.27 | 25.37 | 0 | 358.59 | 288.94 | 44.27 | 25.37 | 0 | 358.59 | 32.23 | 57
203 | UTTAR DINAJPUR | SM/18291 | TUNIBHITA PWSS | TSM/018453 | 40043016 | New | MVS | 1669/PHE-28011/68/2023-ESTT CELL-Dept. of PHE | 26/06/2023 | 1161.76 | 64.65 | 1226.41 | Raiganj Division | Malda Mechanical Division | 201.96 | 47.85 | 22.13 | 0 | 271.94 | 201.96 | 47.85 | 22.13 | 0 | 271.94 | 22.17 | 35
204 | UTTAR DINAJPUR | SM/12794 | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | TSM/014632 | 40028481 | New | MVS | GO2223007996PH | 20/09/2022 | 519.57 | 40.73 | 560.31 | Raiganj Division | Malda Mechanical Division | 40.31 | 31.34 | 29.76 | 0 | 101.41 | 40.31 | 31.34 | 29.76 | 0 | 101.41 | 18.1 | 21
205 | UTTAR DINAJPUR | SM/12795 | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | TSM/014469 | 40028476 | New | MVS | GO2223007994PH | 20/09/2022 | 382.12 | 40.95 | 423.08 | Raiganj Division | Malda Mechanical Division | 0 | 20.16 | 47.85 | 0 | 68 | 0 | 20.16 | 47.85 | 0 | 68 | 16.07
206 | UTTAR DINAJPUR | SM/12098 | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | TSM/013025 | 40028346 | New | MVS | GO2223006983PH | 02/09/2022 | 365.61 | 39.29 | 404.9 | Raiganj Division | Malda Mechanical Division | 138.07 | 31.15 | 24.74 | 0 | 193.96 | 138.07 | 31.15 | 24.74 | 0 | 193.96 | 47.9 | 91
207 | UTTAR DINAJPUR | SM/12096 | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | TSM/012989 | 40028304 | New | MVS | GO2223006978PH | 02/09/2022 | 441.9 | 42.92 | 484.82 | Raiganj Division | Malda Mechanical Division | 174.7 | 28.61 | 29.61 | 0 | 232.92 | 174.7 | 28.61 | 29.61 | 0 | 232.92 | 48.04 | 84
208 | UTTAR DINAJPUR | SM/12796 | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | TSM/014503 | 40028479 | New | MVS | GO2223007995PH | 20/09/2022 | 263.03 | 40.73 | 303.76 | Raiganj Division | Malda Mechanical Division | 39.38 | 22.38 | 16.49 | 0 | 78.26 | 39.38 | 22.38 | 16.49 | 0 | 78.26 | 25.76 | 25
209 | UTTAR DINAJPUR | SM/18475 | UTTAR SHAHAPUR PWSS | TSM/016451 | 40036117 | New | MVS | 1996/PHE-28011/168/2023-SCHM CELL-Dept. of PHE | 24/07/2023 | 1068.86 | 62.14 | 1131 | Raiganj Division | Malda Mechanical Division | 377.61 | 52.08 | 24.96 | 0 | 454.65 | 377.61 | 52.08 | 24.96 | 0 | 454.65 | 40.2 | 80
Total | [9 empty] | 140183.35 | 9039.15 | 149222.5 |  |  | 33428.55 | 5145.51 | 6533.52 | 0 | 45107.58 | 33215.24 | 5114.41 | 6533.52 | 0 | 44863.17 | 30.06