## JJM Schemes Financial Status (D
JJM Schemes Financial Status (DAKSHIN DINAJPUR) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | DAKSHIN DINAJPUR | SM/09796 | Providing Functional House Hold Tap Connection by Retrofitting of 05 nos Zones under Tapan Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | TSM/009130 | 6704577 | Retrofitting | MVS | GO2122006294PH | 01/12/2021 | 379.42 | 0 | 379.42 | Balurghat Division |  | 222.78 | 0 | 40.35 | 0 | 263.13 | 222.78 | 0 | 40.35 | 0 | 263.13 | 69.35 | 85
2 | DAKSHIN DINAJPUR | SM/10516 | Providing Functional House Hold Tap Connection by Retrofitting of 10 nos Zones of Tapan Eastern Sector Under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur | TSM/010050 | 6704577 | Retrofitting | MVS | GO2223000247PH | 13/04/2022 | 999.3 | 0 | 999.3 | Balurghat Division |  | 4.08 | 0 | 0 | 0 | 4.08 | 4.08 | 0 | 0 | 0 | 4.08 | 0.41 | 85
3 | DAKSHIN DINAJPUR | SM/10024 | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | TSM/009226 | 6329112 | Retrofitting | MVS | GO2122007940PH | 05/01/2022 | 1780.97 | 0 | 1780.97 | Balurghat Division |  | 779.2 | 0 | 210.25 | 0 | 989.45 | 779.2 | 0 | 210.25 | 0 | 989.45 | 55.56 | 90
4 | DAKSHIN DINAJPUR | SM/10458 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Buniadpur Piped Water Supply Scheme at Bansihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | TSM/010669 | 40018340 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 20.16 | 0 | 20.16 | Balurghat Division |  | 3.58 | 0 | 0 | 0 | 3.58 | 3.58 | 0 | 0 | 0 | 3.58 | 17.73
5 | DAKSHIN DINAJPUR | SM/10452 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering D | TSM/010682 | 40018308 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 22.98 | 0 | 22.98 | Balurghat Division |  | 6.87 | 0 | 0 | 0 | 6.87 | 6.87 | 0 | 0 | 0 | 6.87 | 29.89 | 30
6 | DAKSHIN DINAJPUR | SM/10457 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | TSM/010672 | 40018314 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 29.13 | 0 | 29.13 | Balurghat Division |  | 7.73 | 0 | 0 | 0 | 7.73 | 7.73 | 0 | 0 | 0 | 7.73 | 26.52 | 40
7 | DAKSHIN DINAJPUR | SM/10453 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | TSM/010680 | 40018320 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 13.77 | 0 | 13.77 | Balurghat Division |  | 3.04 | 0 | 0 | 0 | 3.04 | 3.04 | 0 | 0 | 0 | 3.04 | 22.09 | 90
8 | DAKSHIN DINAJPUR | SM/10454 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kamarpara Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | TSM/010679 | 40018336 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 27.07 | 0 | 27.07 | Balurghat Division |  | 19.42 | 0 | 4.77 | 0 | 24.2 | 19.42 | 0 | 4.77 | 0 | 24.2 | 89.39 | 75
9 | DAKSHIN DINAJPUR | SM/10455 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | TSM/010676 | 40018312 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 18.45 | 0 | 18.45 | Balurghat Division |  | 7.82 | 0 | 0 | 0 | 7.82 | 7.82 | 0 | 0 | 0 | 7.82 | 42.39 | 60
10 | DAKSHIN DINAJPUR | SM/10456 | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | TSM/010674 | 40018338 | Retrofitting | MVS | GO2223000205PH | 13/04/2022 | 29.45 | 0 | 29.45 | Balurghat Division |  | 8.72 | 0 | 0 | 0 | 8.72 | 8.72 | 0 | 0 | 0 | 8.72 | 29.62 | 30
11 | DAKSHIN DINAJPUR | SM/07092 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Alipur Piped Water Supply Scheme at Balurghat Block | TSM/005966 | 8136190 | Retrofitting | MVS | GO2021002874PH | 27/11/2020 | 59.06 | 0 | 59.06 | Balurghat Division |  | 50.65 | 0 | 0 | 0 | 50.65 | 50.65 | 0 | 0 | 0 | 50.65 | 85.76 | 100
12 | DAKSHIN DINAJPUR | SM/08166 | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Anantapur Zone - I Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | TSM/007013 | 7734877 | Retrofitting | MVS | GO2021006692PH | 09/02/2021 | 25.6 | 0 | 25.6 | Balurghat Division |  | 16.92 | 0 | 5.49 | 0 | 22.41 | 16.92 | 0 | 5.49 | 0 | 22.41 | 87.54 | 95
13 | DAKSHIN DINAJPUR | SM/07083 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Badmulukkismat Piped Water Supply Scheme at Balurghat Block | TSM/005949 | 8136153 | Retrofitting | MVS | GO2021002868PH | 27/11/2020 | 73.5 | 0 | 73.5 | Balurghat Division |  | 57.64 | 0 | 0 | 0 | 57.64 | 53.95 | 0 | 0 | 0 | 53.95 | 73.41 | 100
14 | DAKSHIN DINAJPUR | SM/07089 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | TSM/005981 | 8136197 | Retrofitting | MVS | GO2021002877PH | 27/11/2020 | 82.29 | 0 | 82.29 | Balurghat Division |  | 77.29 | 0 | 0 | 0 | 77.29 | 68.92 | 0 | 0 | 0 | 68.92 | 83.75 | 100
15 | DAKSHIN DINAJPUR | SM/08167 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bilbarail piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur(PHASE - II) | TSM/007014 | 7734875 | Retrofitting | MVS | GO2021006691PH | 09/02/2021 | 43.32 | 0 | 43.32 | Balurghat Division |  | 38.82 | 0 | 0 | 0 | 38.82 | 38.82 | 0 | 0 | 0 | 38.82 | 89.63 | 100
16 | DAKSHIN DINAJPUR | SM/07173 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | TSM/005979 | 8136099 | Retrofitting | MVS | GO2021003055PH | 04/12/2020 | 63.61 | 0 | 63.61 | Balurghat Division |  | 60.49 | 0 | 0 | 0 | 60.49 | 51.58 | 0 | 0 | 0 | 51.58 | 81.09 | 100
17 | DAKSHIN DINAJPUR | SM/07081 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dangram Piped Water Supply Scheme at Harirampur Block | TSM/005951 | 8136168 | Retrofitting | MVS | GO2021002870PH | 27/11/2020 | 89.01 | 0 | 89.01 | Balurghat Division |  | 75 | 0 | 0 | 0 | 75 | 74.64 | 0 | 0 | 0 | 74.64 | 83.85 | 90
18 | DAKSHIN DINAJPUR | SM/08168 | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Deulbari Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | TSM/007015 | 7734873 | Retrofitting | MVS | GO2021006689PH | 09/02/2021 | 23.49 | 0 | 23.49 | Balurghat Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
19 | DAKSHIN DINAJPUR | SM/07090 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhalpara Piped Water Supply Scheme at Hilli Block | TSM/005978 | 6174521 | Retrofitting | MVS | GO2021002876PH | 27/11/2020 | 57.62 | 0 | 57.62 | Balurghat Division |  | 54.61 | 0 | 0 | 0 | 54.61 | 53.92 | 0 | 0 | 0 | 53.92 | 93.57 | 100
20 | DAKSHIN DINAJPUR | SM/07078 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block | TSM/005950 | 7362703 | Retrofitting | MVS | GO2021002869PH | 27/11/2020 | 19.21 | 0 | 19.21 | Balurghat Division |  | 18.45 | 0 | 0 | 0 | 18.45 | 18.44 | 0 | 0 | 0 | 18.44 | 95.97 | 100
21 | DAKSHIN DINAJPUR | SM/07086 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Goalgaon Piped Water Supply Scheme at Kushmandi Block | TSM/005953 | 5342438 | Retrofitting | MVS | GO2021002872PH | 27/11/2020 | 90.56 | 0 | 90.56 | Balurghat Division |  | 86.14 | 0 | 0 | 0 | 86.14 | 78.79 | 0 | 0 | 0 | 78.79 | 87 | 100
22 | DAKSHIN DINAJPUR | SM/07091 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | TSM/005968 | 5342475 | Retrofitting | MVS | GO2021002875PH | 27/11/2020 | 53.14 | 0 | 53.14 | Balurghat Division |  | 51.6 | 0 | 0 | 0 | 51.6 | 51.6 | 0 | 0 | 0 | 51.6 | 97.09 | 100
23 | DAKSHIN DINAJPUR | SM/07080 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Harigaon Piped Water Supply Scheme at Balurghat Block | TSM/005945 | 8136131 | Retrofitting | MVS | GO2021002863PH | 27/11/2020 | 60.87 | 0 | 60.87 | Balurghat Division |  | 50 | 0 | 0 | 0 | 50 | 41.75 | 0 | 0 | 0 | 41.75 | 68.58 | 85
24 | DAKSHIN DINAJPUR | SM/07171 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Jabaripur Piped Water Supply Scheme | TSM/005977 | 6171074 | Retrofitting | MVS | GO2021003053PH | 04/12/2020 | 31.82 | 0 | 31.82 | Balurghat Division |  | 28 | 0 | 0 | 0 | 28 | 27.64 | 0 | 0 | 0 | 27.64 | 86.88 | 100
25 | DAKSHIN DINAJPUR | SM/07082 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Kalibari Piped Water Supply Scheme at Balurghat Block | TSM/005943 | 6173971 | Retrofitting | MVS | GO2021002861PH | 27/11/2020 | 77.55 | 0 | 77.55 | Balurghat Division |  | 66.62 | 0 | 0 | 0 | 66.62 | 54.16 | 0 | 0 | 0 | 54.16 | 69.84 | 100
26 | DAKSHIN DINAJPUR | SM/08170 | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | TSM/007017 | 7734874 | Retrofitting | MVS | GO2021006685PH | 09/02/2021 | 85.05 | 0 | 85.05 | Balurghat Division |  | 67.46 | 0 | 8.24 | 0 | 75.7 | 67.46 | 0 | 8.24 | 0 | 75.7 | 89.01 | 90
27 | DAKSHIN DINAJPUR | SM/08169 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur (PHASE - II) | TSM/007016 | 7734868 | Retrofitting | MVS | GO2021006688PH | 09/02/2021 | 45.08 | 0 | 45.08 | Balurghat Division |  | 39.13 | 0 | 2.75 | 0 | 41.88 | 39.13 | 0 | 2.75 | 0 | 41.88 | 92.9 | 100
28 | DAKSHIN DINAJPUR | SM/07087 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Khidirpur Piped Water Supply Scheme at Balurghat Block | TSM/005946 | 8136143 | Retrofitting | MVS | GO2021002865PH | 27/11/2020 | 91.37 | 0 | 91.37 | Balurghat Division |  | 82.45 | 0 | 0 | 0 | 82.45 | 82.42 | 0 | 0 | 0 | 82.42 | 90.21 | 100
29 | DAKSHIN DINAJPUR | SM/07172 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | TSM/005964 | 4721048 | Retrofitting | MVS | GO2021003054PH | 04/12/2020 | 98.62 | 0 | 98.62 | Balurghat Division |  | 84.75 | 0 | 11 | 0 | 95.75 | 84.75 | 0 | 11 | 0 | 95.75 | 97.09 | 100
30 | DAKSHIN DINAJPUR | SM/07079 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nunail Piped Water Supply Scheme at Balurghat Block | TSM/005948 | 5476096 | Retrofitting | MVS | GO2021002867PH | 27/11/2020 | 72.69 | 0 | 72.69 | Balurghat Division |  | 62.65 | 0 | 0 | 0 | 62.65 | 58.82 | 0 | 0 | 0 | 58.82 | 80.92 | 85
31 | DAKSHIN DINAJPUR | SM/07085 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Panjul Piped Water Supply Scheme at Hili Block | TSM/005957 | 6174545 | Retrofitting | MVS | GO2021002873PH | 27/11/2020 | 90.12 | 0 | 90.12 | Balurghat Division |  | 87.44 | 0 | 0 | 0 | 87.44 | 87.36 | 0 | 0 | 0 | 87.36 | 96.94 | 100
32 | DAKSHIN DINAJPUR | SM/07394 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | TSM/005962 | 8346396 | Retrofitting | MVS | GO2021003788PH | 29/12/2020 | 259.01 | 0 | 259.01 | Balurghat Division |  | 211.44 | 0 | 2.85 | 0 | 214.3 | 211.44 | 0 | 2.85 | 0 | 214.3 | 82.74 | 80
33 | DAKSHIN DINAJPUR | SM/07170 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Purba Hariharpur Piped Water Supply Scheme | TSM/005976 | 8136116 | Retrofitting | SVS | GO2021003052PH | 04/12/2020 | 15.8 | 0 | 15.8 | Balurghat Division |  | 14.62 | 0 | 0 | 0 | 14.62 | 8.48 | 0 | 0 | 0 | 8.48 | 53.66 | 100
34 | DAKSHIN DINAJPUR | SM/07084 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Salgaon Piped Water Supply Scheme at Balurghat Block | TSM/005947 | 5476599 | Retrofitting | MVS | GO2021002866PH | 27/11/2020 | 67.26 | 0 | 67.26 | Balurghat Division |  | 59.6 | 0 | 0 | 0 | 59.6 | 59.6 | 0 | 0 | 0 | 59.6 | 88.61 | 100
35 | DAKSHIN DINAJPUR | SM/07088 | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Siala Piped Water Supply Scheme at Balurghat Block | TSM/005952 | 6189279 | Retrofitting | MVS | GO2021002871PH | 27/11/2020 | 98.96 | 0 | 98.96 | Balurghat Division |  | 95.43 | 0 | 0 | 0 | 95.43 | 93.6 | 0 | 0 | 0 | 93.6 | 94.58 | 100
36 | DAKSHIN DINAJPUR | SM/13018 | Retrofitting of Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-III] | TSM/014672 | 40060986 | Retrofitting | MVS | GO2223008379PH | 28/09/2022 | 26.55 | 0 | 26.55 | Balurghat Division |  | 11.69 | 0 | 1.44 | 0 | 13.13 | 11.69 | 0 | 1.44 | 0 | 13.13 | 49.44 | 100
37 | DAKSHIN DINAJPUR | SM/13019 | Retrofitting of Pundari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-II] | TSM/014652 | 40061001 | Retrofitting | MVS | GO2223008376PH | 28/09/2022 | 43.3 | 0 | 43.3 | Balurghat Division |  | 17.91 | 0 | 2.4 | 0 | 20.31 | 17.91 | 0 | 2.4 | 0 | 20.31 | 46.91 | 75
Total | [9 empty] | 5165.18 | 0 | 5165.18 |  |  | 2630.03 | 0 | 289.55 | 0 | 2919.58 | 2567.66 | 0 | 289.55 | 0 | 2857.21 | 55.32