## JJM Schemes Financial Status (M
JJM Schemes Financial Status (MALDAH) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | MALDAH | SM/14098 | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011269 | 40035007 | New | MVS | GO2223011018PH | 15/12/2022 | 1519.66 | 58.44 | 1578.1 | Malda Division | Malda Mechanical Division | 371.28 | 33.93 | 73.25 | 0 | 478.46 | 371.28 | 33.93 | 73.25 | 0 | 478.46 | 30.32 | 52
2 | MALDAH | SM/12762 | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda | TSM/014864 | 40026212 | Augmentation | MVS | GO2223007977PH | 20/09/2022 | 130.13 | 19.65 | 149.78 | Malda Division | Malda Mechanical Division | 51.84 | 15.41 | 0 | 0 | 67.25 | 51.84 | 15.41 | 0 | 0 | 67.25 | 44.9 | 81
3 | MALDAH | SM/19225 | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani | TSM/020265 | 40061721 | Augmentation | MVS | 1973/PHE-28011/246/2023-ESTT CELL-Dept. of PHE | 25/07/2024 | 0 | 2769.31 | 2769.31 |  | Malda Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MALDAH | SM/15960 | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | TSM/017385 | 40066040 | New | SVS | GO2223014621PH | 22/02/2023 | 40.78 | 8.75 | 49.53 | Malda Division | Malda Mechanical Division | 19.89 | 7.73 | 0.65 | 0 | 28.27 | 19.89 | 7.73 | 0.65 | 0 | 28.27 | 57.08 | 90
5 | MALDAH | SM/12075 | Alal Zone-I Piped Water Supply Scheme | TSM/011887 | 40028430 | New | MVS | GO2223007012PH | 02/09/2022 | 681.49 | 51.27 | 732.76 | Malda Division | Malda Mechanical Division | 182.71 | 25.8 | 48.64 | 0 | 257.15 | 182.71 | 25.8 | 48.64 | 0 | 257.15 | 35.09 | 53
6 | MALDAH | SM/12877 | Alal Zone-II Piped Water Supply Scheme | TSM/011886 | 40028431 | New | MVS | GO2223008157PH | 23/09/2022 | 547.49 | 48.7 | 596.19 | Malda Division | Malda Mechanical Division | 115.11 | 22.39 | 18.14 | 0 | 155.64 | 115.11 | 22.39 | 18.14 | 0 | 155.64 | 26.11 | 48
7 | MALDAH | SM/13431 | ALINAGAR Piped Water Supply Scheme | TSM/015847 | 40033888 | New | MVS | GO2223009242PH | 02/11/2022 | 679.7 | 44.62 | 724.32 | Malda Division | Malda Mechanical Division | 361.23 | 32.81 | 15.42 | 0 | 409.47 | 361.23 | 32.81 | 15.42 | 0 | 409.47 | 56.53 | 74
8 | MALDAH | SM/15521 | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte | TSM/016030 | 40038795 | New | SVS | GO2223014011PH | 16/02/2023 | 1181.35 | 129.62 | 1310.98 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 118.38 | 14.43 | 2.25 | 0 | 135.07 | 118.38 | 14.43 | 2.25 | 0 | 135.07 | 10.3 | 30
9 | MALDAH | SM/13734 | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | TSM/013468 | 40034633 | New | MVS | GO2223009853PH | 17/11/2022 | 1344.41 | 44.62 | 1389.03 | Malda Division | Malda Mechanical Division | 740.62 | 13.43 | 27.67 | 0 | 781.73 | 739.27 | 13.43 | 27.67 | 0 | 780.38 | 56.18 | 68
10 | MALDAH | SM/15958 | Augmentation of Adina Zone-I Piped Water Supply Scheme | TSM/011889 | 40060336 | Augmentation | SVS | GO2223014624PH | 22/02/2023 | 503.4 | 40.05 | 543.44 | Malda Division | Malda Mechanical Division | 106.32 | 8.67 | 20.51 | 0 | 135.49 | 106.14 | 8.67 | 20.51 | 0 | 135.31 | 24.9 | 44
11 | MALDAH | SM/15956 | Augmentation of Adina Zone-II Piped Water Supply Scheme | TSM/011890 | 40060389 | Augmentation | SVS | GO2223014610PH | 22/02/2023 | 338.17 | 17.6 | 355.78 | Malda Division | Malda Mechanical Division | 143.03 | 15.11 | 6.02 | 0 | 164.17 | 143.03 | 15.11 | 6.02 | 0 | 164.17 | 46.14 | 60
12 | MALDAH | SM/15155 | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | TSM/017676 | 40046989 | Augmentation | SVS | GO2223013408PH | 07/02/2023 | 352.17 | 46.23 | 398.39 | Malda Division | Malda Mechanical Division | 196.61 | 0 | 8.85 | 0 | 205.46 | 196.61 | 0 | 8.85 | 0 | 205.46 | 51.57 | 53
13 | MALDAH | SM/15951 | Augmentation of Alal Zone-III Piped Water Supply Scheme | TSM/011885 | 40060303 | Augmentation | MVS | GO2223014608PH | 22/02/2023 | 381.31 | 43.94 | 425.25 | Malda Division | Malda Mechanical Division | 154.98 | 4.31 | 22.25 | 0 | 181.55 | 154.98 | 4.31 | 22.25 | 0 | 181.55 | 42.69 | 52
14 | MALDAH | SM/10181 | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME | TSM/008180 | 40011166 | Augmentation | MVS | GO2122009753PH | 17/02/2022 | 2031.18 | 95.21 | 2126.39 | Malda Division | Malda Mechanical Division | 846.59 | 35.61 | 158.71 | 0 | 1040.91 | 846.59 | 35.58 | 158.71 | 0 | 1040.88 | 48.95 | 62
15 | MALDAH | SM/14099 | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme | TSM/011899 | 40035086 | Augmentation | MVS | GO2223011013PH | 15/12/2022 | 2083.49 | 116.66 | 2200.14 | Malda Division | Malda Mechanical Division | 4.59 | 57.44 | 74.33 | 0 | 136.36 | 4.59 | 57.44 | 74.33 | 0 | 136.36 | 6.2 | 45
16 | MALDAH | SM/10138 | Augmentation of Bamongram piped water supply scheme. | TSM/008160 | 40002521 | Augmentation | MVS | GO2122009361PH | 08/02/2022 | 946.24 | 92.4 | 1038.64 | Malda Division | Malda Mechanical Division | 563.67 | 28.25 | 75.2 | 0 | 667.12 | 563.67 | 28.25 | 75.2 | 0 | 667.12 | 64.23 | 83
17 | MALDAH | SM/18910 | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/020578 | 40067381 | Augmentation | MVS | PHE/IV/3073/W-668/23 | 09/10/2023 | 133.47 | 0 | 133.47 | Malda Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
18 | MALDAH | SM/10137 | Augmentation of Bhaluka Fatepur Piped water supply scheme | TSM/009046 | 40002522 | Augmentation | MVS | GO2122009354PH | 08/02/2022 | 1038.94 | 38.31 | 1077.25 | Malda Division | Malda Mechanical Division | 317.78 | 31.98 | 86.11 | 0 | 435.88 | 317.78 | 31.98 | 86.11 | 0 | 435.88 | 40.46 | 87
19 | MALDAH | SM/15948 | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | TSM/017675 | 40060438 | Augmentation | SVS | GO2223014619PH | 22/02/2023 | 212.73 | 42.14 | 254.87 | Malda Division | Malda Mechanical Division | 62.58 | 8.07 | 13.39 | 0 | 84.04 | 62.58 | 8.07 | 13.39 | 0 | 84.04 | 32.97 | 71
20 | MALDAH | SM/09422 | Augmentation of Bulbulchandi PWSS. | TSM/008161 | 40001227 | Augmentation | MVS | GO2122005478PH | 17/11/2021 | 947.61 | 33.45 | 981.06 | Malda Division |  | 541.71 | 0 | 77.49 | 0 | 619.2 | 541.71 | 0 | 77.49 | 0 | 619.2 | 63.12 | 70
21 | MALDAH | SM/09986 | Augmentation of Deotala Water Supply Scheme | TSM/005108 | 40006366 | Augmentation | MVS | GO2122006954PH | 16/12/2021 | 792.45 | 49.61 | 842.06 | Malda Division | Malda Mechanical Division | 182.78 | 0 | 0 | 0 | 182.78 | 182.78 | 0 | 0 | 0 | 182.78 | 21.71 | 66
22 | MALDAH | SM/18558 | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017388 | 40046393 | Augmentation | MVS | 2140/PHE-28011/115/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 2893.33 | 192 | 3085.32 | Malda Division | Malda Mechanical Division | 329.7 | 56.22 | 149.94 | 0 | 535.86 | 329.7 | 56.22 | 149.94 | 0 | 535.86 | 17.37 | 38
23 | MALDAH | SM/12734 | Augmentation of Jatradanga Piped water supply scheme | TSM/010498 | 40016237 | Augmentation | SVS | GO2223007987PH | 20/09/2022 | 383.79 | 6.42 | 390.21 | Malda Division | Malda Mechanical Division | 76.91 | 0 | 21.46 | 0 | 98.37 | 76.91 | 0 | 21.46 | 0 | 98.37 | 25.21 | 42
24 | MALDAH | SM/14190 | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme | TSM/008179 | 40016240 | Augmentation | MVS | GO2223011796PH | 10/01/2023 | 505.92 | 40.65 | 546.57 | Malda Division | Malda Mechanical Division | 66.99 | 24.11 | 23.12 | 0 | 114.22 | 65.42 | 24.11 | 23.12 | 0 | 112.65 | 20.61 | 42
25 | MALDAH | SM/10397 | Augmentation of Khusida Piped Water Supply Scheme | TSM/008174 | 40002523 | Augmentation | MVS | GO2121011630PH | 31/03/2022 | 1165.03 | 57.96 | 1222.99 | Malda Division | Malda Mechanical Division | 431.33 | 33.14 | 61.91 | 0 | 526.38 | 431.33 | 33.14 | 61.91 | 0 | 526.38 | 43.04 | 52
26 | MALDAH | SM/12362 | Augmentation of Maheshpur piped water supply scheme | TSM/005106 | 40028434 | Augmentation | MVS | GO2223007584PH | 13/09/2022 | 1523.27 | 42.76 | 1566.03 | Malda Division | Malda Mechanical Division | 606.49 | 32.93 | 71.64 | 0 | 711.07 | 606.49 | 32.93 | 71.64 | 0 | 711.07 | 45.41 | 82
27 | MALDAH | SM/16383 | Augmentation of Mahishbathani Piped Water Supply Scheme | TSM/017802 | 40046986 | Augmentation | SVS | GO2223015020PH | 28/02/2023 | 283.65 | 44.4 | 328.05 | Malda Division | Malda Mechanical Division | 77.07 | 20.87 | 10.38 | 0 | 108.33 | 77.07 | 20.87 | 10.38 | 0 | 108.33 | 33.02 | 46
28 | MALDAH | SM/09987 | AUGMENTATION OF MALATIPUR PWSS | TSM/008173 | 40006363 | Augmentation | MVS | GO2122006953PH | 16/12/2021 | 645.04 | 54.38 | 699.42 | Malda Division | Malda Mechanical Division | 317.03 | 17.66 | 16.95 | 0 | 351.63 | 317.03 | 17.66 | 16.95 | 0 | 351.63 | 50.27 | 77
29 | MALDAH | SM/10317 | Augmentation of Mirzapur Piped Water Supply Scheme | TSM/009757 | 40006926 | Augmentation | MVS | GO2122010474PH | 04/03/2022 | 967.45 | 62.21 | 1029.67 | Malda Division | Malda Mechanical Division | 507.84 | 49.8 | 74.57 | 0 | 632.21 | 507.84 | 49.8 | 74.57 | 0 | 632.21 | 61.4 | 83
30 | MALDAH | SM/15952 | Augmentation of Nasipur Piped Water Supply Scheme | TSM/011880 | 40060504 | Augmentation | SVS | GO2223014622PH | 22/02/2023 | 739.14 | 129.68 | 868.83 | Malda Division | Malda Mechanical Division | 213.76 | 56.28 | 68.94 | 0 | 338.98 | 213.76 | 56.28 | 68.94 | 0 | 338.98 | 39.02 | 46
31 | MALDAH | SM/18447 | Augmentation of Samsi PWSS. | TSM/008164 | 40016238 | Augmentation | MVS | 1959/PHE-28011/7/2023-ESTT CELL-Dept. of PHE | 20/07/2023 | 2048.81 | 185.23 | 2234.04 | Malda Division | Malda Mechanical Division | 238.9 | 9.75 | 30.48 | 0 | 279.13 | 238.9 | 9.75 | 30.48 | 0 | 279.13 | 12.49 | 35
32 | MALDAH | SM/18660 | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) | TSM/019386 | 40049022 | Augmentation | MVS | 2233/PHE-28011/95/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 73902.66 | 6524.96 | 80427.62 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 11917.39 | 115.56 | 17819.69 | 0 | 29852.64 | 11917.39 | 64.24 | 17819.69 | 0 | 29801.32 | 26.7 | 45
33 | MALDAH | SM/09567 | Augmentation of Tilasan Piped water supply scheme | TSM/009047 | 40002169 | Augmentation | MVS | GO2122005685PH | 22/11/2021 | 311.27 | 20.58 | 331.85 | Malda Division | Malda Mechanical Division | 213.17 | 6.06 | 0 | 6.86 | 226.09 | 213.17 | 6.06 | 0 | 6.86 | 226.09 | 68.13 | 92
34 | MALDAH | SM/16053 | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019385 | 40060451 | Augmentation | SVS | GO2223014612PH | 22/02/2023 | 544.47 | 76.46 | 620.93 | Malda Division | Malda Mechanical Division | 139.05 | 41.56 | 82.87 | 0 | 263.48 | 137.46 | 41.56 | 82.87 | 0 | 261.89 | 42.18 | 60
35 | MALDAH | SM/16382 | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019387 | 40046992 | Augmentation | SVS | GO2223015021PH | 28/02/2023 | 942.47 | 88.52 | 1030.99 | Malda Division | Malda Mechanical Division | 0 | 10.01 | 108.07 | 0 | 118.07 | 0 | 10.01 | 108.07 | 0 | 118.07 | 11.45 | 43
36 | MALDAH | SM/15149 | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019388 | 40046993 | Augmentation | SVS | GO2223013330PH | 06/02/2023 | 800.18 | 80.98 | 881.16 | Malda Division | Malda Mechanical Division | 84.47 | 7.9 | 58.49 | 0 | 150.86 | 84.47 | 7.9 | 58.49 | 0 | 150.86 | 17.12 | 53
37 | MALDAH | SM/15308 | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019389 | 40046995 | Augmentation | SVS | GO2223013471PH | 10/02/2023 | 817.91 | 61.63 | 879.54 | Malda Division | Malda Mechanical Division | 87.27 | 18.9 | 28.05 | 0 | 134.22 | 87.27 | 18.9 | 28.05 | 0 | 134.22 | 15.26 | 55
38 | MALDAH | SM/15193 | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/019390 | 40046390 | Augmentation | MVS | GO2223013329PH | 06/02/2023 | 878.93 | 109.54 | 988.47 | Malda Division | Malda Mechanical Division | 125.29 | 8.28 | 41.31 | 0 | 174.89 | 125.29 | 8.28 | 41.31 | 0 | 174.89 | 17.69 | 56
39 | MALDAH | SM/10291 | Augmentation of Uttar Harishandropur piped water supply scheme. | TSM/008163 | 40011171 | Augmentation | MVS | GO2122010177PH | 28/02/2022 | 2090.96 | 132.76 | 2223.72 | Malda Division | Malda Mechanical Division | 642.61 | 52.04 | 106.62 | 0 | 801.27 | 642.38 | 52.04 | 106.62 | 0 | 801.04 | 36.02 | 60
40 | MALDAH | SM/15188 | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | TSM/017677 | 40046996 | Augmentation | SVS | GO2223013409PH | 07/02/2023 | 347.52 | 42.99 | 390.5 | Malda Division | Malda Mechanical Division | 132.99 | 23.08 | 10.51 | 0 | 166.58 | 132.99 | 23.08 | 10.51 | 0 | 166.58 | 42.66 | 58
41 | MALDAH | SM/18433 | BABUPUR PWSS | TSM/014434 | 40034236 | New | MVS | 1928/PHE-28011/188/2023-SCHM CELL-Dept. of PHE | 18/07/2023 | 1626.71 | 70.68 | 1697.39 | Malda Division | Malda Mechanical Division | 672.19 | 7.16 | 19.1 | 0 | 698.44 | 671.46 | 7.16 | 19.1 | 0 | 697.71 | 41.11 | 52
42 | MALDAH | SM/12743 | BAIRAT Piped Water Supply Scheme | TSM/014439 | 40027623 | New | MVS | GO2223007978PH | 20/09/2022 | 894.58 | 44.62 | 939.2 | Malda Division | Malda Mechanical Division | 593.95 | 37.77 | 41.11 | 0 | 672.82 | 593.95 | 37.77 | 41.11 | 0 | 672.82 | 71.64 | 93
43 | MALDAH | SM/15944 | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | TSM/017774 | 40055883 | New | SVS | GO2223014634PH | 22/02/2023 | 507.75 | 63.42 | 571.17 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 182.44 | 2.27 | 4.96 | 0 | 189.67 | 182.44 | 2.27 | 4.96 | 0 | 189.67 | 33.21 | 70
44 | MALDAH | SM/12193 | BANGRUA PWSS | TSM/013018 | 40027594 | New | SVS | GO2223007215PH | 07/09/2022 | 256.98 | 43.11 | 300.09 | Malda Division | Malda Mechanical Division | 8.87 | 29.59 | 14 | 0 | 52.46 | 8.87 | 29.59 | 14 | 0 | 52.46 | 17.48 | 74
45 | MALDAH | SM/12191 | BETAHAL Piped Water Supply Scheme | TSM/013024 | 40027592 | New | MVS | GO2223007227PH | 07/09/2022 | 483.91 | 43.08 | 526.99 | Malda Division | Malda Mechanical Division | 175.09 | 32.67 | 32.28 | 0 | 240.04 | 175.09 | 32.67 | 32.28 | 0 | 240.04 | 45.55 | 84
46 | MALDAH | SM/12768 | BHADAR Piped Water Supply Scheme | TSM/014278 | 40027628 | New | MVS | GO2223007979PH | 20/09/2022 | 617.43 | 42.96 | 660.39 | Malda Division | Malda Mechanical Division | 459.32 | 39.98 | 30.97 | 0 | 530.27 | 459.32 | 39.98 | 30.97 | 0 | 530.27 | 80.3 | 99
47 | MALDAH | SM/13507 | BISHANPUR PIPED WATER SUPPLY SCHEME | TSM/014466 | 40033760 | New | MVS | GO2223009206PH | 02/11/2022 | 639.63 | 43.14 | 682.77 | Malda Division | Malda Mechanical Division | 223.83 | 20.37 | 44.43 | 0 | 288.63 | 223.83 | 20.37 | 44.43 | 0 | 288.63 | 42.27 | 45
48 | MALDAH | SM/13719 | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | TSM/013215 | 40034160 | New | MVS | GO2223009858PH | 17/11/2022 | 1102.76 | 46.9 | 1149.66 | Malda Division | Malda Mechanical Division | 671.03 | 33.91 | 41.8 | 0 | 746.74 | 671.03 | 33.91 | 41.8 | 0 | 746.74 | 64.95 | 76
49 | MALDAH | SM/12632 | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | TSM/012833 | 40027621 | New | MVS | GO2223007805PH | 19/09/2022 | 293.29 | 42.02 | 335.31 | Malda Division | Malda Mechanical Division | 133.47 | 33.37 | 30.21 | 0 | 197.04 | 133.47 | 33.37 | 30.21 | 0 | 197.04 | 58.76 | 88
50 | MALDAH | SM/12076 | Choupaldanga pipe water Supply Scheme | TSM/011833 | 40022361 | New | MVS | GO2223007013PH | 02/09/2022 | 838.4 | 64.47 | 902.87 | Malda Division | Malda Mechanical Division | 312.05 | 17.7 | 64.02 | 0 | 393.77 | 312.05 | 17.7 | 64.02 | 0 | 393.77 | 43.61 | 77
51 | MALDAH | SM/15142 | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) | TSM/017446 | 40049066 | Augmentation | MVS | GO2223012949PH | 06/02/2023 | 204.02 | 418.74 | 622.76 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 198.59 | 367.7 | 0 | 0 | 566.29 | 172.71 | 366.93 | 0 | 0 | 539.64 | 86.65 | 91
52 | MALDAH | SM/18461 | DAHIL Piped Water Supply Scheme. | TSM/015609 | 40034651 | New | MVS | 1963/PHE-28011/35/2023-ESTT CELL-Dept. of PHE | 20/07/2023 | 1525.46 | 68.99 | 1594.44 | Malda Division | Malda Mechanical Division | 496.03 | 7.48 | 13.62 | 0 | 517.13 | 496.03 | 7.48 | 13.62 | 0 | 517.13 | 32.43 | 42
53 | MALDAH | SM/12186 | DAKSHIN BHAKURIA Piped Water Supply Scheme | TSM/013248 | 40022364 | New | MVS | GO2223007115PH | 06/09/2022 | 303.93 | 42.9 | 346.83 | Malda Division | Malda Mechanical Division | 93.8 | 27.5 | 13.12 | 0 | 134.41 | 93.8 | 27.5 | 13.12 | 0 | 134.41 | 38.76 | 71
54 | MALDAH | SM/12338 | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda | TSM/011680 | 40022690 | New | MVS | GO2223007475PH | 12/09/2022 | 661.54 | 49.1 | 710.64 | Malda Division | Malda Mechanical Division | 34.14 | 33.6 | 36.42 | 0 | 104.15 | 34.14 | 33.6 | 36.42 | 0 | 104.15 | 14.66 | 82
55 | MALDAH | SM/18232 | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | TSM/018102 | 40055906 | New | SVS | 1482/PHE-28011/171/2023-SCHM CELL-Dept. of PHE | 12/06/2023 | 1248.28 | 117.07 | 1365.35 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 253.97 | 16.09 | 154.14 | 0 | 424.2 | 253.97 | 16.09 | 154.14 | 0 | 424.2 | 31.07 | 70
56 | MALDAH | SM/15903 | DILALBATI Piped Water Supply Scheme. | TSM/014129 | 40034885 | New | SVS | GO2223014285PH | 20/02/2023 | 250.25 | 41.9 | 292.15 | Malda Division | Malda Mechanical Division | 88.64 | 40.65 | 9.79 | 0 | 139.08 | 88.64 | 40.65 | 9.79 | 0 | 139.08 | 47.61 | 99
57 | MALDAH | SM/13721 | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. | TSM/014431 | 40034322 | New | MVS | GO2223009854PH | 17/11/2022 | 1083.96 | 44.62 | 1128.57 | Malda Division | Malda Mechanical Division | 0 | 27.4 | 28.79 | 0 | 56.19 | 0 | 27.4 | 28.79 | 0 | 56.19 | 4.98 | 67
58 | MALDAH | SM/13720 | EMAMNAGAR PIPED WATER SUPPLY SCHEME. | TSM/014505 | 40034171 | New | MVS | GO2223009855PH | 17/11/2022 | 1437.85 | 46.69 | 1484.54 | Malda Division | Malda Mechanical Division | 634.24 | 7.2 | 121.37 | 0 | 762.81 | 634.24 | 7.2 | 121.37 | 0 | 762.81 | 51.38 | 58
59 | MALDAH | SM/14173 | FATEPUR Piped Water Supply Scheme | TSM/015785 | 40034658 | New | MVS | GO2223011641PH | 09/01/2023 | 1510.37 | 71.36 | 1581.73 | Malda Division | Malda Mechanical Division | 193.65 | 43.93 | 19.22 | 0 | 256.8 | 193.65 | 43.93 | 19.22 | 0 | 256.8 | 16.24 | 68
60 | MALDAH | SM/12079 | GAURIA Piped Water Supply Scheme. | TSM/011717 | 40022291 | New | MVS | GO2223007015PH | 02/09/2022 | 939.37 | 67.15 | 1006.53 | Malda Division | Malda Mechanical Division | 418.49 | 45.13 | 35.88 | 0 | 499.5 | 418.49 | 45.13 | 35.88 | 0 | 499.5 | 49.63 | 83
61 | MALDAH | SM/15947 | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | TSM/018180 | 40055901 | New | SVS | GO2223014638PH | 22/02/2023 | 774.44 | 100.95 | 875.39 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 67.87 | 7.72 | 0 | 0 | 75.59 | 67.87 | 7.72 | 0 | 0 | 75.59 | 8.63 | 15
62 | MALDAH | SM/12267 | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. | TSM/012594 | 40027599 | New | MVS | GO2223007209PH | 07/09/2022 | 707.78 | 45.67 | 753.45 | Malda Division | Malda Mechanical Division | 174.7 | 32.96 | 42.55 | 0 | 250.21 | 174.7 | 32.96 | 42.55 | 0 | 250.21 | 33.21 | 53
63 | MALDAH | SM/13792 | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme | TSM/011884 | 40035079 | Augmentation | MVS | GO2223009971PH | 22/11/2022 | 2771.16 | 221.65 | 2992.8 | Malda Division | Malda Mechanical Division | 76.16 | 57.68 | 225.66 | 0 | 359.5 | 76.16 | 53.03 | 225.66 | 0 | 354.85 | 11.86 | 32
64 | MALDAH | SM/15223 | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011258 | 40016168 | New | MVS | GO2223013361PH | 07/02/2023 | 2371.72 | 114.79 | 2486.52 | Malda Division | Malda Mechanical Division | 1105.64 | 51 | 199.93 | 0 | 1356.57 | 1105.64 | 51 | 199.93 | 0 | 1356.57 | 54.56 | 78
65 | MALDAH | SM/11588 | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011278 | 40016190 | New | MVS | GO2223005418PH | 22/07/2022 | 857.09 | 47.81 | 904.9 | Malda Division | Malda Mechanical Division | 150.45 | 29.93 | 83.21 | 0 | 263.59 | 150.45 | 29.93 | 83.21 | 0 | 263.59 | 29.13 | 66
66 | MALDAH | SM/11589 | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011264 | 40016192 | New | SVS | GO2223005409PH | 22/07/2022 | 586.3 | 32.15 | 618.45 | Malda Division | Malda Mechanical Division | 221.75 | 19.5 | 21.5 | 0 | 262.75 | 221.75 | 19.5 | 21.5 | 0 | 262.75 | 42.49 | 67
67 | MALDAH | SM/11590 | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011266 | 40016191 | New | MVS | GO2223005416PH | 22/07/2022 | 565.11 | 44.17 | 609.28 | Malda Division | Malda Mechanical Division | 176.8 | 21.01 | 32.79 | 0 | 230.6 | 176.8 | 21.01 | 32.79 | 0 | 230.6 | 37.85 | 52
68 | MALDAH | SM/11587 | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011277 | 40016199 | New | MVS | GO2223005408PH | 22/07/2022 | 562.92 | 19.22 | 582.14 | Malda Division | Malda Mechanical Division | 136.31 | 18.11 | 24.76 | 0 | 179.17 | 136.31 | 18.11 | 24.76 | 0 | 179.17 | 30.78 | 89
69 | MALDAH | SM/12709 | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED | TSM/014888 | 40038319 | New | SVS | GO2223007916PH | 20/09/2022 | 656.8 | 86.86 | 743.66 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 167.68 | 48.43 | 0 | 0 | 216.1 | 167.68 | 48.43 | 0 | 0 | 216.1 | 29.06 | 75
70 | MALDAH | SM/12078 | Hatinda Piped Water Supply Scheme. | TSM/011729 | 40015010 | New | MVS | GO2223007014PH | 02/09/2022 | 1021.52 | 73.84 | 1095.36 | Malda Division | Malda Mechanical Division | 368 | 34.25 | 69.57 | 0 | 471.83 | 368 | 34.25 | 69.57 | 0 | 471.83 | 43.08 | 54
71 | MALDAH | SM/18496 | HATNAGAR PIPED WATER SUPPLY SCHEME | TSM/020336 | 40057544 | New | MVS | 2035/PHE-28011/210/2023-ESTT CELL-Dept. of PHE | 26/07/2023 | 1180.59 | 52.17 | 1232.77 | Malda Division | Malda Mechanical Division | 399.56 | 7.91 | 8.25 | 0 | 415.71 | 399.56 | 7.91 | 8.25 | 0 | 415.71 | 33.72 | 42
72 | MALDAH | SM/13432 | HORGOA Piped Water Supply Scheme | TSM/015215 | 40033798 | New | MVS | GO2223009244PH | 02/11/2022 | 641.61 | 43.3 | 684.91 | Malda Division | Malda Mechanical Division | 254.46 | 33.08 | 20.76 | 0 | 308.3 | 254.46 | 33.08 | 20.76 | 0 | 308.3 | 45.01 | 79
73 | MALDAH | SM/13237 | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. | TSM/014262 | 40062167 | Augmentation | MVS | GO2223008731PH | 14/10/2022 | 0 | 123.52 | 123.52 |  | Malda Mechanical Division | 0 | 111.15 | 0 | 0 | 111.15 | 0 | 111.15 | 0 | 0 | 111.15 | 89.99 | 81
74 | MALDAH | SM/15143 | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED | TSM/018197 | 40049069 | Augmentation | MVS | GO2223013335PH | 06/02/2023 | 219.75 | 50.48 | 270.23 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 126.53 | 34.37 | 0 | 0 | 160.9 | 126.53 | 34.37 | 0 | 0 | 160.9 | 59.54 | 70
75 | MALDAH | SM/15145 | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED | TSM/018215 | 40049624 | Augmentation | SVS | GO2223013333PH | 06/02/2023 | 31.42 | 0 | 31.42 | Malda Arsenic Area W/S Division |  | 20.31 | 0 | 0 | 0 | 20.31 | 20.31 | 0 | 0 | 0 | 20.31 | 64.64 | 80
76 | MALDAH | SM/12879 | JAMALPUR Piped Water Supply Scheme. | TSM/013493 | 40027632 | New | MVS | GO2223008164PH | 23/09/2022 | 1002.54 | 44.64 | 1047.18 | Malda Division | Malda Mechanical Division | 373.86 | 17.61 | 26.63 | 0 | 418.1 | 373.86 | 17.61 | 26.63 | 0 | 418.1 | 39.93 | 44
77 | MALDAH | SM/12182 | JIBJALSAR Piped Water Supply Scheme | TSM/013490 | 40025737 | New | SVS | GO2223007179PH | 07/09/2022 | 52.96 | 20.1 | 73.06 | Malda Division | Malda Mechanical Division | 35.76 | 11.92 | 2.83 | 0 | 50.52 | 35.76 | 11.92 | 2.83 | 0 | 50.52 | 69.15 | 61
78 | MALDAH | SM/13430 | JIGIN Piped Water Supply Scheme | TSM/015837 | 40033792 | New | SVS | GO2223009237PH | 02/11/2022 | 190.7 | 43.47 | 234.18 | Malda Division | Malda Mechanical Division | 71.09 | 36.27 | 35.31 | 0 | 142.67 | 71.09 | 36.27 | 35.31 | 0 | 142.67 | 60.93 | 92
79 | MALDAH | SM/15946 | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED | TSM/017773 | 40055896 | New | SVS | GO2223014641PH | 22/02/2023 | 444.5 | 63.42 | 507.92 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 207.41 | 4.37 | 0 | 0 | 211.78 | 207.41 | 4.37 | 0 | 0 | 211.78 | 41.7 | 75
80 | MALDAH | SM/12708 | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED | TSM/014767 | 40038381 | New | SVS | GO2223007912PH | 20/09/2022 | 505.24 | 69.5 | 574.74 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 158.35 | 44.54 | 0 | 0 | 202.89 | 158.35 | 44.54 | 0 | 0 | 202.89 | 35.3 | 70
81 | MALDAH | SM/18427 | KALUARI PWSS | TSM/018421 | 40067330 | New | MVS | 1923/PHE-28011/146/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 1316.05 | 64.13 | 1380.18 | Malda Division | Malda Mechanical Division | 423.82 | 48.43 | 76.82 | 0 | 549.07 | 423.82 | 48.43 | 76.82 | 0 | 549.07 | 39.78 | 57
82 | MALDAH | SM/12304 | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte | TSM/013454 | 40027600 | New | MVS | GO2223007384PH | 09/09/2022 | 555.52 | 46.82 | 602.34 | Malda Division | Malda Mechanical Division | 274.25 | 36.36 | 14.15 | 0 | 324.76 | 274.25 | 36.36 | 14.15 | 0 | 324.76 | 53.92 | 59
83 | MALDAH | SM/12183 | KHARANGAPUR JABRA Piped Water Supply Scheme | TSM/013445 | 40027586 | New | SVS | GO2223007178PH | 07/09/2022 | 248.27 | 43.2 | 291.47 | Malda Division | Malda Mechanical Division | 96.95 | 26.61 | 15.97 | 0 | 139.54 | 96.95 | 26.61 | 15.97 | 0 | 139.54 | 47.87 | 83
84 | MALDAH | SM/13793 | KHARBA PIPED WATER SUPPLY SCHEME. | TSM/011882 | 40033932 | New | MVS | GO2223009962PH | 22/11/2022 | 1146.89 | 73.84 | 1220.74 | Malda Division | Malda Mechanical Division | 490.99 | 45.06 | 103.59 | 0 | 639.64 | 490.99 | 45.06 | 103.59 | 0 | 639.64 | 52.4 | 79
85 | MALDAH | SM/17177 | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. | TSM/015921 | 40038730 | New | SVS | GO2223016065PH | 15/03/2023 | 878.81 | 88.19 | 967 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 246.07 | 11.07 | 51.56 | 0 | 308.69 | 246.07 | 11.07 | 51.56 | 0 | 308.69 | 31.92 | 60
86 | MALDAH | SM/12190 | KISMAT BAROL Piped Water Supply Scheme | TSM/013044 | 40027591 | New | MVS | GO2223007223PH | 07/09/2022 | 628.92 | 43.08 | 672 | Malda Division | Malda Mechanical Division | 46.69 | 25.48 | 37.76 | 0 | 109.93 | 46.69 | 25.48 | 37.76 | 0 | 109.93 | 16.36 | 66
87 | MALDAH | SM/13746 | KRISHNAPUR PIPED WATER SUPPLY SCHEME. | TSM/013458 | 40034839 | New | MVS | GO2223009833PH | 17/11/2022 | 836.06 | 44.62 | 880.68 | Malda Division | Malda Mechanical Division | 508.35 | 15.63 | 13.01 | 0 | 536.99 | 508.35 | 15.63 | 13.01 | 0 | 536.99 | 60.97 | 67
88 | MALDAH | SM/15086 | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. | TSM/017205 | 40046564 | Augmentation | MVS | GO2223013162PH | 04/02/2023 | 116.57 | 0 | 116.57 | Malda Division |  | 93.75 | 0 | 0 | 0 | 93.75 | 93.75 | 0 | 0 | 0 | 93.75 | 80.42 | 87
89 | MALDAH | SM/15197 | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. | TSM/017379 | 40046499 | Augmentation | MVS | GO2223013325PH | 06/02/2023 | 164.65 | 0 | 164.65 | Malda Division |  | 134.36 | 0 | 0 | 0 | 134.36 | 134.36 | 0 | 0 | 0 | 134.36 | 81.6 | 87
90 | MALDAH | SM/17178 | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED | TSM/015930 | 40038753 | New | SVS | GO2223016062PH | 15/03/2023 | 749.32 | 106.39 | 855.71 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 147.59 | 34.99 | 26.7 | 0 | 209.28 | 147.59 | 34.99 | 26.7 | 0 | 209.28 | 24.46 | 60
91 | MALDAH | SM/12197 | MABARAKPUR PWSS | TSM/012922 | 40027598 | New | MVS | GO2223007221PH | 07/09/2022 | 659.09 | 45.12 | 704.22 | Malda Division | Malda Mechanical Division | 201.37 | 41.13 | 46.25 | 0 | 288.75 | 201.37 | 41.13 | 46.25 | 0 | 288.75 | 41 | 99
92 | MALDAH | SM/13733 | Mahil Piped Water Supply Scheme | TSM/014388 | 40034327 | New | MVS | GO2223009851PH | 17/11/2022 | 1824.91 | 70.59 | 1895.5 | Malda Division | Malda Mechanical Division | 526.12 | 52.31 | 116.35 | 0 | 694.78 | 526.12 | 52.31 | 116.35 | 0 | 694.78 | 36.65 | 78
93 | MALDAH | SM/12192 | MALIOR PWSS | TSM/013022 | 40027593 | New | MVS | GO2223007214PH | 07/09/2022 | 675.77 | 43.08 | 718.85 | Malda Division | Malda Mechanical Division | 212.57 | 26.39 | 45.29 | 0 | 284.25 | 212.57 | 26.39 | 45.29 | 0 | 284.25 | 39.54 | 74
94 | MALDAH | SM/13451 | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED | TSM/015617 | 40038386 | New | SVS | GO2223009250PH | 02/11/2022 | 744.43 | 92.6 | 837.04 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 194.99 | 9.14 | 7.7 | 0 | 211.82 | 194.99 | 9.14 | 7.7 | 0 | 211.82 | 25.31 | 60
95 | MALDAH | SM/15248 | MATHURAPUR PIPED WATER SUPPLY SCHEME | TSM/013453 | 40034904 | New | MVS | GO2223013452PH | 07/02/2023 | 534.39 | 42.16 | 576.55 | Malda Division | Malda Mechanical Division | 151.37 | 20.44 | 20.57 | 0 | 192.38 | 151.37 | 20.44 | 20.57 | 0 | 192.38 | 33.37 | 76
96 | MALDAH | SM/12769 | MATIHARPUR Piped Water Supply Scheme | TSM/013447 | 40027629 | New | MVS | GO2223007982PH | 20/09/2022 | 930.72 | 63.29 | 994.01 | Malda Division | Malda Mechanical Division | 258.96 | 32.65 | 64.72 | 0 | 356.33 | 258.96 | 32.65 | 64.72 | 0 | 356.33 | 35.85 | 78
97 | MALDAH | SM/15222 | MEHERPUR PIPED WATER SUPPLY SCHEME | TSM/011828 | 40033900 | New | MVS | GO2223013360PH | 06/02/2023 | 1191.26 | 73.25 | 1264.51 | Malda Division | Malda Mechanical Division | 581.19 | 27.61 | 3.57 | 0 | 612.38 | 581.19 | 27.61 | 3.57 | 0 | 612.38 | 48.43 | 78
98 | MALDAH | SM/18557 | MORGRAM PWSS | TSM/018419 | 40046438 | New | MVS | 2140/PHE-28011/115/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1033.89 | 65.08 | 1098.97 | Malda Division | Malda Mechanical Division | 389.27 | 46.4 | 16.12 | 0 | 451.8 | 389.27 | 46.4 | 16.12 | 0 | 451.8 | 41.11 | 55
99 | MALDAH | SM/12767 | NABAGRAM Piped Water Supply Scheme | TSM/013452 | 40027627 | New | MVS | GO2223007991PH | 20/09/2022 | 829.86 | 46.69 | 876.56 | Malda Division | Malda Mechanical Division | 285.08 | 41.63 | 40.24 | 0 | 366.94 | 285.08 | 41.63 | 40.24 | 0 | 366.94 | 41.86 | 95
100 | MALDAH | SM/15949 | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED | TSM/017551 | 40055865 | New | SVS | GO2223014631PH | 22/02/2023 | 650.54 | 83.49 | 734.03 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 126.25 | 50.05 | 12.24 | 0 | 188.54 | 126.25 | 50.05 | 12.24 | 0 | 188.54 | 25.69 | 40
101 | MALDAH | SM/13718 | OLTARA PIPED WATER SUPPLY SCHEME. | TSM/013242 | 40033946 | New | MVS | GO2223009859PH | 17/11/2022 | 1176.19 | 77.6 | 1253.79 | Malda Division | Malda Mechanical Division | 663.66 | 58.94 | 49.45 | 0 | 772.05 | 663.66 | 58.94 | 49.45 | 0 | 772.05 | 61.58 | 97
102 | MALDAH | SM/18432 | PARAHAR PWSS | TSM/014116 | 40034621 | New | MVS | 1927/PHE-28011/77/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 1312.89 | 43.2 | 1356.09 | Malda Division | Malda Mechanical Division | 658.47 | 12.27 | 14.56 | 0 | 685.3 | 658.47 | 12.27 | 14.56 | 0 | 685.3 | 50.53 | 58
103 | MALDAH | SM/18431 | PARAIL PWSS | TSM/014391 | 40034640 | New | MVS | 1927/PHE-28011/77/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 1225.42 | 50.71 | 1276.14 | Malda Division | Malda Mechanical Division | 539.53 | 22.02 | 7.35 | 0 | 568.9 | 539.53 | 22.02 | 7.35 | 0 | 568.9 | 44.58 | 51
104 | MALDAH | SM/12195 | PARO PWSS | TSM/012960 | 40027596 | New | MVS | GO2223007217PH | 07/09/2022 | 467.75 | 43 | 510.75 | Malda Division | Malda Mechanical Division | 166.44 | 15.59 | 26.53 | 0 | 208.56 | 166.44 | 15.59 | 26.53 | 0 | 208.56 | 40.83 | 76
105 | MALDAH | SM/12188 | PASCHIM BHAGABANPUR Piped Water Supply Scheme | TSM/013216 | 40027589 | New | MVS | GO2223007226PH | 07/09/2022 | 822.22 | 45.12 | 867.35 | Malda Division | Malda Mechanical Division | 400.46 | 36.55 | 33.43 | 0 | 470.44 | 400.46 | 36.55 | 33.43 | 0 | 470.44 | 54.24 | 84
106 | MALDAH | SM/18420 | PERAPUR PWSS | TSM/015903 | 40034871 | New | MVS | 1919/PHE-28011/109/2023-SCHM CELL-Dept. of PHE | 18/07/2023 | 1167.53 | 45.98 | 1213.51 | Malda Division | Malda Mechanical Division | 76.72 | 0 | 17.65 | 0 | 94.37 | 76.72 | 0 | 17.65 | 0 | 94.37 | 7.78 | 22
107 | MALDAH | SM/06850 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme | TSM/005681 | 8128270 | Retrofitting | MVS | GO2021001793PH | 07/10/2020 | 68.82 | 0 | 68.82 | Malda Division |  | 34.1 | 0 | 0 | 0 | 34.1 | 34.1 | 0 | 0 | 0 | 34.1 | 49.56 | 69
108 | MALDAH | SM/06851 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme | TSM/005679 | 8128247 | Retrofitting | MVS | GO2021001792PH | 07/10/2020 | 96.17 | 0 | 96.17 | Malda Division |  | 40.32 | 0 | 0 | 0 | 40.32 | 40.32 | 0 | 0 | 0 | 40.32 | 41.93 | 67
109 | MALDAH | SM/06852 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme | TSM/005680 | 8128272 | Retrofitting | MVS | GO2021001797PH | 07/10/2020 | 102.95 | 0 | 102.95 | Malda Division |  | 60.27 | 0 | 0 | 0 | 60.27 | 60.27 | 0 | 0 | 0 | 60.27 | 58.54 | 66
110 | MALDAH | SM/06853 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme | TSM/005682 | 8128274 | Retrofitting | MVS | GO2021001798PH | 07/10/2020 | 61.62 | 0 | 61.62 | Malda Division |  | 8.75 | 0 | 0 | 0 | 8.75 | 8.75 | 0 | 0 | 0 | 8.75 | 14.2 | 75
111 | MALDAH | SM/06854 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme | TSM/005683 | 8128280 | Retrofitting | MVS | GO2021001799PH | 07/10/2020 | 84.53 | 0 | 84.53 | Malda Division |  | 67.28 | 0 | 1.42 | 0 | 68.7 | 67.28 | 0 | 1.42 | 0 | 68.7 | 81.26 | 84
112 | MALDAH | SM/06855 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme | TSM/005684 | 8128312 | Retrofitting | MVS | GO2021001800PH | 07/10/2020 | 73.75 | 0 | 73.75 | Malda Division |  | 47.52 | 0 | 4 | 0 | 51.53 | 36.6 | 0 | 4 | 0 | 40.6 | 55.06 | 80
113 | MALDAH | SM/06856 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme | TSM/005685 | 8128314 | Retrofitting | MVS | GO2021001801PH | 07/10/2020 | 86.33 | 0 | 86.33 | Malda Division |  | 85.02 | 0 | 0 | 0 | 85.02 | 85.02 | 0 | 0 | 0 | 85.02 | 98.48 | 99
114 | MALDAH | SM/07007 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme | TSM/006277 | 8128361 | Retrofitting | MVS | GO2021002539PH | 18/11/2020 | 86.07 | 0 | 86.07 | Malda Division |  | 57.73 | 0 | 0 | 0 | 57.73 | 57.73 | 0 | 0 | 0 | 57.73 | 67.07 | 72
115 | MALDAH | SM/06857 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme | TSM/005686 | 8128316 | Retrofitting | MVS | GO2021001802PH | 07/10/2020 | 91.69 | 0 | 91.69 | Malda Division |  | 47.4 | 0 | 0 | 0 | 47.4 | 47.4 | 0 | 0 | 0 | 47.4 | 51.7 | 70
116 | MALDAH | SM/06858 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme | TSM/005687 | 8128318 | Retrofitting | MVS | GO2021001804PH | 07/10/2020 | 59.54 | 0 | 59.54 | Malda Division |  | 57.78 | 0 | 0 | 0 | 57.78 | 46.32 | 0 | 0 | 0 | 46.32 | 77.8 | 98
117 | MALDAH | SM/06859 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme | TSM/005688 | 5344418 | Retrofitting | MVS | GO2021001806PH | 07/10/2020 | 71.47 | 0 | 71.47 | Malda Division |  | 60 | 0 | 1.08 | 0 | 61.08 | 60 | 0 | 1.08 | 0 | 61.08 | 85.45 | 100
118 | MALDAH | SM/07973 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte | TSM/006282 | 8202062 | Retrofitting | MVS | GO2021005524PH | 26/01/2021 | 5777.65 | 0 | 5777.65 | Malda Division |  | 1638.58 | 0 | 49.89 | 0 | 1688.47 | 1635.2 | 0 | 49.89 | 0 | 1685.09 | 29.17 | 61
119 | MALDAH | SM/06860 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme | TSM/005689 | 6260105 | Retrofitting | MVS | GO2021001807PH | 07/10/2020 | 93.04 | 0 | 93.04 | Malda Division |  | 54.36 | 0 | 0 | 0 | 54.36 | 54.36 | 0 | 0 | 0 | 54.36 | 58.43 | 100
120 | MALDAH | SM/06861 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme | TSM/005690 | 8128320 | Retrofitting | MVS | GO2021001808PH | 07/10/2020 | 89.31 | 0 | 89.31 | Malda Division |  | 22.71 | 0 | 8.62 | 0 | 31.33 | 22.71 | 0 | 8.62 | 0 | 31.33 | 35.08 | 55
121 | MALDAH | SM/06862 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme | TSM/005691 | 8128323 | Retrofitting | SVS | GO2021001809PH | 07/10/2020 | 49.15 | 0 | 49.15 | Malda Division |  | 20.07 | 0 | 0 | 0 | 20.07 | 20.07 | 0 | 0 | 0 | 20.07 | 40.84 | 53
122 | MALDAH | SM/06863 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme | TSM/005692 | 8128325 | Retrofitting | MVS | GO2021001818PH | 07/10/2020 | 54.86 | 0 | 54.86 | Malda Division |  | 41 | 0 | 0 | 12 | 53 | 40.35 | 0 | 0 | 12 | 52.35 | 95.43 | 98
123 | MALDAH | SM/08283 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block | TSM/005678 | 8195707 | Retrofitting | MVS | GO2021005947PH | 01/02/2021 | 406.26 | 0 | 406.26 | Malda Arsenic Area W/S Division |  | 404.85 | 0 | 0 | 0 | 404.85 | 404.85 | 0 | 0 | 0 | 404.85 | 99.65 | 80
124 | MALDAH | SM/06864 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme | TSM/005693 | 8128333 | Retrofitting | MVS | GO2021001819PH | 07/10/2020 | 64.66 | 0 | 64.66 | Malda Division |  | 54.51 | 0 | 0 | 0 | 54.51 | 54.51 | 0 | 0 | 0 | 54.51 | 84.29 | 89
125 | MALDAH | SM/06865 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme | TSM/005694 | 8128336 | Retrofitting | MVS | GO2021001820PH | 07/10/2020 | 43.73 | 0 | 43.73 | Malda Division |  | 41.39 | 0 | 0 | 0 | 41.39 | 41.39 | 0 | 0 | 0 | 41.39 | 94.65 | 92
126 | MALDAH | SM/06866 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme | TSM/005695 | 8128339 | Retrofitting | MVS | GO2021001821PH | 07/10/2020 | 79.87 | 0 | 79.87 | Malda Division |  | 57.03 | 0 | 1.58 | 0 | 58.6 | 57.03 | 0 | 1.58 | 0 | 58.6 | 73.37 | 82
127 | MALDAH | SM/06867 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme | TSM/005696 | 8128342 | Retrofitting | MVS | GO2021001822PH | 07/10/2020 | 92.99 | 0 | 92.99 | Malda Division |  | 71.55 | 0 | 0 | 0 | 71.55 | 71.55 | 0 | 0 | 0 | 71.55 | 76.94 | 78
128 | MALDAH | SM/06868 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme | TSM/005697 | 8128345 | Retrofitting | SVS | GO2021001829PH | 08/10/2020 | 61.47 | 0 | 61.47 | Malda Division |  | 44.5 | 0 | 3.76 | 0 | 48.26 | 44.5 | 0 | 3.76 | 0 | 48.26 | 78.51 | 84
129 | MALDAH | SM/06849 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme | TSM/005676 | 8123357 | Retrofitting | SVS | GO2021001835PH | 08/10/2020 | 73.35 | 0 | 73.35 | Malda Arsenic Area W/S Division |  | 60 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 81.8 | 90
130 | MALDAH | SM/06869 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme | TSM/005698 | 8128348 | Retrofitting | MVS | GO2021001830PH | 08/10/2020 | 87.63 | 0 | 87.63 | Malda Division |  | 66.83 | 0 | 0 | 0 | 66.83 | 66.83 | 0 | 0 | 0 | 66.83 | 76.26 | 81
131 | MALDAH | SM/06870 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme | TSM/005699 | 8128349 | Retrofitting | MVS | GO2021001831PH | 08/10/2020 | 92.34 | 0 | 92.34 | Malda Division |  | 50 | 0 | 0 | 0 | 50 | 45.91 | 0 | 0 | 0 | 45.91 | 49.72 | 62
132 | MALDAH | SM/06848 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block | TSM/005677 | 8136196 | Retrofitting | MVS | GO2021001836PH | 08/10/2020 | 85.66 | 0 | 85.66 | Malda Arsenic Area W/S Division |  | 85.66 | 0 | 0 | 0 | 85.66 | 85.66 | 0 | 0 | 0 | 85.66 | 100 | 100
133 | MALDAH | SM/06986 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme | TSM/006275 | 8123760 | Retrofitting | SVS | GO2021002507PH | 11/11/2020 | 35.94 | 0 | 35.94 | Malda Arsenic Area W/S Division |  | 34.96 | 0 | 0 | 0 | 34.96 | 34.96 | 0 | 0 | 0 | 34.96 | 97.27 | 90
134 | MALDAH | SM/06871 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme | TSM/005700 | 8128350 | Retrofitting | MVS | GO2021001832PH | 08/10/2020 | 54.06 | 0 | 54.06 | Malda Division |  | 50.94 | 0 | 0 | 0 | 50.94 | 50.94 | 0 | 0 | 0 | 50.94 | 94.22 | 94
135 | MALDAH | SM/06872 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme | TSM/005701 | 8128353 | Retrofitting | SVS | GO2021001833PH | 08/10/2020 | 87.48 | 0 | 87.48 | Malda Division |  | 69.69 | 0 | 0 | 0 | 69.69 | 69.69 | 0 | 0 | 0 | 69.69 | 79.67 | 84
136 | MALDAH | SM/09659 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc | TSM/008231 | 8391035 | Retrofitting | MVS | GO2122005760PH | 23/11/2021 | 246.4 | 0 | 246.4 | Malda Arsenic Area W/S Division |  | 143.88 | 0 | 28.4 | 0 | 172.28 | 143.88 | 0 | 28.4 | 0 | 172.28 | 69.92 | 75
137 | MALDAH | SM/09593 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl | TSM/008233 | 8390877 | Retrofitting | MVS | GO2122005744PH | 23/11/2021 | 577.48 | 0 | 577.48 | Malda Arsenic Area W/S Division |  | 208.86 | 0 | 69.63 | 0 | 278.49 | 208.86 | 0 | 69.63 | 0 | 278.49 | 48.23 | 71
138 | MALDAH | SM/09647 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo | TSM/008236 | 40000286 | Retrofitting | MVS | GO2122005756PH | 23/11/2021 | 363.53 | 0 | 363.53 | Malda Arsenic Area W/S Division |  | 202.35 | 0 | 0.12 | 0 | 202.48 | 202.35 | 0 | 0.12 | 0 | 202.48 | 55.7 | 65
139 | MALDAH | SM/09646 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | TSM/008229 | 40000289 | Retrofitting | MVS | GO2122005756PH | 23/11/2021 | 394.52 | 0 | 394.52 | Malda Arsenic Area W/S Division |  | 258.2 | 0 | 13.97 | 0 | 272.17 | 258.2 | 0 | 13.97 | 0 | 272.17 | 68.99 | 79
140 | MALDAH | SM/09663 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik | TSM/008225 | 40000326 | Retrofitting | MVS | GO2122005758PH | 23/11/2021 | 506.2 | 0 | 506.2 | Malda Arsenic Area W/S Division |  | 179.94 | 0 | 0 | 0 | 179.94 | 179.94 | 0 | 0 | 0 | 179.94 | 35.55 | 45
141 | MALDAH | SM/09592 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- | TSM/008227 | 8390870 | Retrofitting | MVS | GO2122005744PH | 23/11/2021 | 464.42 | 0 | 464.42 | Malda Arsenic Area W/S Division |  | 215.86 | 0 | 34.55 | 0 | 250.41 | 215.86 | 0 | 34.55 | 0 | 250.41 | 53.92 | 59
142 | MALDAH | SM/09652 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl | TSM/008226 | 40000478 | Retrofitting | MVS | GO2122005753PH | 23/11/2021 | 450.25 | 0 | 450.25 | Malda Arsenic Area W/S Division |  | 272.23 | 0 | 0 | 0 | 272.23 | 272.23 | 0 | 0 | 0 | 272.23 | 60.46 | 66
143 | MALDAH | SM/09587 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | TSM/008223 | 8390842 | Retrofitting | MVS | GO2122005747PH | 23/11/2021 | 154.36 | 0 | 154.36 | Malda Arsenic Area W/S Division |  | 105.26 | 0 | 20.13 | 0 | 125.39 | 105.21 | 0 | 20.13 | 0 | 125.34 | 81.2 | 86
144 | MALDAH | SM/09662 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B | TSM/008377 | 40000396 | Retrofitting | MVS | GO2122005758PH | 23/11/2021 | 470.57 | 0 | 470.57 | Malda Arsenic Area W/S Division |  | 211.05 | 0 | 35.75 | 0 | 246.8 | 211.05 | 0 | 35.75 | 0 | 246.8 | 52.45 | 56
145 | MALDAH | SM/09591 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block | TSM/008224 | 8390833 | Retrofitting | MVS | GO2122005747PH | 23/11/2021 | 145.97 | 0 | 145.97 | Malda Arsenic Area W/S Division |  | 84.4 | 0 | 0 | 0 | 84.4 | 84.4 | 0 | 0 | 0 | 84.4 | 57.82 | 63
146 | MALDAH | SM/09590 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha | TSM/008219 | 8390847 | Retrofitting | MVS | GO2122005747PH | 23/11/2021 | 235.98 | 0 | 235.98 | Malda Arsenic Area W/S Division |  | 95.01 | 0 | 0 | 0 | 95.01 | 95.01 | 0 | 0 | 0 | 95.01 | 40.26 | 47
147 | MALDAH | SM/09650 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | TSM/008222 | 40000482 | Retrofitting | MVS | GO2122005755PH | 23/11/2021 | 589.71 | 0 | 589.71 | Malda Arsenic Area W/S Division |  | 219.54 | 0 | 0 | 0 | 219.54 | 219.54 | 0 | 0 | 0 | 219.54 | 37.23 | 50
148 | MALDAH | SM/09648 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo | TSM/008228 | 40000485 | Retrofitting | MVS | GO2122005756PH | 23/11/2021 | 242.47 | 0 | 242.47 | Malda Arsenic Area W/S Division |  | 242.26 | 0 | 0 | 0 | 242.26 | 242.26 | 0 | 0 | 0 | 242.26 | 99.91 | 99
149 | MALDAH | SM/09649 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar | TSM/008214 | 40000480 | Retrofitting | MVS | GO2122005755PH | 23/11/2021 | 213.41 | 0 | 213.41 | Malda Arsenic Area W/S Division |  | 164.83 | 0 | 0 | 0 | 164.83 | 164.83 | 0 | 0 | 0 | 164.83 | 77.24 | 85
150 | MALDAH | SM/09588 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc | TSM/008217 | 8390861 | Retrofitting | SVS | GO2122005747PH | 23/11/2021 | 354.85 | 0 | 354.85 | Malda Arsenic Area W/S Division |  | 245.83 | 0 | 47.26 | 0 | 293.09 | 245.83 | 0 | 47.26 | 0 | 293.09 | 82.59 | 88
151 | MALDAH | SM/09660 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block | TSM/008221 | 8391039 | Retrofitting | MVS | GO2122005760PH | 23/11/2021 | 161.36 | 0 | 161.36 | Malda Arsenic Area W/S Division |  | 95.63 | 0 | 1.23 | 0 | 96.86 | 95.63 | 0 | 1.23 | 0 | 96.86 | 60.03 | 87
152 | MALDAH | SM/09651 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl | TSM/008238 | 40000327 | Retrofitting | MVS | GO2122005755PH | 23/11/2021 | 189.35 | 0 | 189.35 | Malda Arsenic Area W/S Division |  | 107.65 | 0 | 0 | 0 | 107.65 | 107.65 | 0 | 0 | 0 | 107.65 | 56.85 | 65
153 | MALDAH | SM/09656 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl | TSM/008234 | 40000483 | Retrofitting | MVS | GO2122005752PH | 23/11/2021 | 598.68 | 0 | 598.68 | Malda Arsenic Area W/S Division |  | 63.15 | 0 | 0 | 0 | 63.15 | 63.15 | 0 | 0 | 0 | 63.15 | 10.55 | 18
154 | MALDAH | SM/09589 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar | TSM/008376 | 8390856 | Retrofitting | MVS | GO2122005747PH | 23/11/2021 | 67.89 | 0 | 67.89 | Malda Arsenic Area W/S Division |  | 33.89 | 0 | 0 | 0 | 33.89 | 33.89 | 0 | 0 | 0 | 33.89 | 49.91 | 58
155 | MALDAH | SM/09657 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc | TSM/008220 | 40000484 | Retrofitting | MVS | GO2122005752PH | 23/11/2021 | 356.57 | 0 | 356.57 | Malda Arsenic Area W/S Division |  | 102.56 | 0 | 0 | 0 | 102.56 | 102.56 | 0 | 0 | 0 | 102.56 | 28.76 | 34
156 | MALDAH | SM/09654 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo | TSM/008401 | 40000479 | Retrofitting | MVS | GO2122005753PH | 23/11/2021 | 63.53 | 0 | 63.53 | Malda Arsenic Area W/S Division |  | 49 | 0 | 0 | 0 | 49 | 49 | 0 | 0 | 0 | 49 | 77.12 | 85
157 | MALDAH | SM/09661 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | TSM/008232 | 40000409 | Retrofitting | MVS | GO2122005759PH | 23/11/2021 | 883.23 | 0 | 883.23 | Malda Arsenic Area W/S Division |  | 151.53 | 0 | 4.92 | 0 | 156.45 | 151.53 | 0 | 4.92 | 0 | 156.45 | 17.71 | 25
158 | MALDAH | SM/09655 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block | TSM/008235 | 40000408 | Retrofitting | MVS | GO2122005753PH | 23/11/2021 | 986.55 | 0 | 986.55 | Malda Arsenic Area W/S Division |  | 136.77 | 0 | 0 | 0 | 136.77 | 136.77 | 0 | 0 | 0 | 136.77 | 13.86 | 20
159 | MALDAH | SM/09653 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III | TSM/008230 | 40000284 | Retrofitting | MVS | GO2122005753PH | 23/11/2021 | 445.56 | 0 | 445.56 | Malda Arsenic Area W/S Division |  | 317.81 | 0 | 50.53 | 0 | 368.34 | 317.81 | 0 | 50.53 | 0 | 368.34 | 82.67 | 91
160 | MALDAH | SM/09658 | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha | TSM/008237 | 8391024 | Retrofitting | MVS | GO2122005760PH | 23/11/2021 | 505.89 | 0 | 505.89 | Malda Arsenic Area W/S Division |  | 90.82 | 0 | 0 | 0 | 90.82 | 90.82 | 0 | 0 | 0 | 90.82 | 17.95 | 25
161 | MALDAH | SM/08760 | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo | TSM/007490 | 8364808 | Retrofitting | MVS | GO2122003130PH | 08/09/2021 | 183.54 | 0 | 183.54 | Malda Arsenic Area W/S Division |  | 113.78 | 0 | 14.54 | 0 | 128.33 | 113.78 | 0 | 14.54 | 0 | 128.33 | 69.92 | 50
162 | MALDAH | SM/11916 | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE | TSM/011047 | 40037483 | Retrofitting | MVS | GO2223006622PH | 22/08/2022 | 496.83 | 0 | 496.83 | Malda Arsenic Area W/S Division |  | 91.96 | 0 | 0 | 0 | 91.96 | 91.96 | 0 | 0 | 0 | 91.96 | 18.51 | 23
163 | MALDAH | SM/11912 | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011051 | 40037463 | Retrofitting | MVS | GO2223006614PH | 22/08/2022 | 322.33 | 0 | 322.33 | Malda Arsenic Area W/S Division |  | 48.47 | 0 | 0 | 0 | 48.47 | 48.47 | 0 | 0 | 0 | 48.47 | 15.04 | 20
164 | MALDAH | SM/11914 | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011053 | 40037440 | Retrofitting | MVS | GO2223006624PH | 22/08/2022 | 211.54 | 0 | 211.54 | Malda Arsenic Area W/S Division |  | 4.63 | 0 | 0 | 0 | 4.63 | 4.63 | 0 | 0 | 0 | 4.63 | 2.19 | 12
165 | MALDAH | SM/11911 | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011054 | 40037246 | Retrofitting | MVS | GO2223006616PH | 22/08/2022 | 937.95 | 0 | 937.95 | Malda Arsenic Area W/S Division |  | 3.94 | 0 | 0 | 0 | 3.94 | 3.94 | 0 | 0 | 0 | 3.94 | 0.42 | 22
166 | MALDAH | SM/11913 | Providing Functional Household Tap Connection (FHTC) under command area of Panchanadapur and Hamidpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011050 | 40037468 | Retrofitting | MVS | GO2223006612PH | 22/08/2022 | 343.66 | 0 | 343.66 | Malda Arsenic Area W/S Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
167 | MALDAH | SM/11917 | Providing Functional Household Tap Connection (FHTC) under command area of Paramanandapur, Biswambhar Binodpur, Bishnupur Shrirampara, Kamalpur, Paschim Narayanpur, Enayetpur and Gouripurr Zone Water Supply Scheme at Manikchak Block under Malda Arsenic Ar | TSM/011052 | 40037458 | Retrofitting | MVS | GO2223006623PH | 22/08/2022 | 521.52 | 0 | 521.52 | Malda Arsenic Area W/S Division |  | 1.35 | 0 | 0 | 0 | 1.35 | 1.35 | 0 | 0 | 0 | 1.35 | 0.26 | 17
168 | MALDAH | SM/11915 | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011049 | 40037477 | Retrofitting | MVS | GO2223006617PH | 22/08/2022 | 685.6 | 0 | 685.6 | Malda Arsenic Area W/S Division |  | 22.09 | 0 | 0 | 0 | 22.09 | 22.09 | 0 | 0 | 0 | 22.09 | 3.22 | 12
169 | MALDAH | SM/10430 | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | TSM/011061 | 40037983 | Retrofitting | MVS | GO2223000193PH | 12/04/2022 | 546.45 | 0 | 546.45 | Malda Arsenic Area W/S Division |  | 3.9 | 0 | 0 | 0 | 3.9 | 3.9 | 0 | 0 | 0 | 3.9 | 0.71 | 6
170 | MALDAH | SM/07972 | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem | TSM/006280 | 8203403 | Retrofitting | MVS | GO2021005525PH | 26/01/2021 | 2518.77 | 0 | 2518.77 | Malda Division |  | 1184.74 | 0 | 16.94 | 0 | 1201.68 | 1184.74 | 0 | 16.94 | 0 | 1201.68 | 47.71 | 79
171 | MALDAH | SM/14100 | Pukuria Piped Water Supply Scheme | TSM/011879 | 40035034 | New | SVS | GO2223011014PH | 15/12/2022 | 1797.44 | 86.75 | 1884.19 | Malda Division | Malda Mechanical Division | 470.79 | 46.77 | 108.44 | 0 | 626 | 470.79 | 46.77 | 108.44 | 0 | 626 | 33.22 | 58
172 | MALDAH | SM/15140 | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED | TSM/018015 | 40047237 | New | MVS | GO2223013337PH | 06/02/2023 | 686.26 | 82.34 | 768.6 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 184.11 | 40.63 | 23.12 | 0 | 247.86 | 184.11 | 40.63 | 23.12 | 0 | 247.86 | 32.25 | 80
173 | MALDAH | SM/12194 | PUTIA PWSS | TSM/013011 | 40027595 | New | SVS | GO2223007222PH | 07/09/2022 | 61.6 | 20.55 | 82.16 | Malda Division | Malda Mechanical Division | 40.98 | 13.28 | 1.03 | 0 | 55.3 | 40.98 | 13.28 | 1.03 | 0 | 55.3 | 67.31 | 84
174 | MALDAH | SM/14174 | RAHIMPUR Piped Water Supply Scheme | TSM/015255 | 40034867 | New | MVS | GO2223011642PH | 09/01/2023 | 1032.36 | 45.05 | 1077.41 | Malda Division | Malda Mechanical Division | 717.55 | 41.24 | 25.08 | 0 | 783.86 | 717.55 | 41.24 | 25.08 | 0 | 783.86 | 72.75 | 99
175 | MALDAH | SM/14461 | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | TSM/013552 | 40034892 | New | SVS | GO2223012358PH | 20/01/2023 | 402.54 | 45.43 | 447.97 | Malda Division | Malda Mechanical Division | 95.18 | 30.24 | 34.33 | 0 | 159.75 | 95.18 | 30.24 | 34.33 | 0 | 159.75 | 35.66 | 69
176 | MALDAH | SM/14097 | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/011274 | 40035016 | New | MVS | GO2223011019PH | 15/12/2022 | 1080.31 | 63.59 | 1143.9 | Malda Division | Malda Mechanical Division | 110.08 | 36.72 | 50.98 | 0 | 197.78 | 110.08 | 35.96 | 50.98 | 0 | 197.03 | 17.22 | 59
177 | MALDAH | SM/15275 | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED | TSM/017775 | 40047228 | New | MVS | GO2223013266PH | 04/02/2023 | 904.33 | 90.06 | 994.39 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 101.13 | 17.28 | 146.57 | 0 | 264.98 | 101.13 | 17.28 | 146.57 | 0 | 264.98 | 26.65 | 60
178 | MALDAH | SM/17201 | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED | TSM/017477 | 40056023 | New | SVS | GO2223016064PH | 15/03/2023 | 631.1 | 83.62 | 714.72 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 109.9 | 47.87 | 0 | 0 | 157.77 | 109.9 | 43.51 | 0 | 0 | 153.41 | 21.46 | 55
179 | MALDAH | SM/12187 | SAHAPUR Piped Water Supply Scheme | TSM/013245 | 40022366 | New | SVS | GO2223007120PH | 06/09/2022 | 91.64 | 20.63 | 112.27 | Malda Division | Malda Mechanical Division | 38.44 | 17.04 | 6.03 | 0 | 61.51 | 38.44 | 17.04 | 6.03 | 0 | 61.51 | 54.79 | 90
180 | MALDAH | SM/11968 | Sahapur Piped Water Supply Scheme | TSM/010990 | 40016201 | New | MVS | GO2223006721PH | 26/08/2022 | 1075.79 | 59.25 | 1135.04 | Malda Division | Malda Mechanical Division | 314.14 | 26.45 | 89.29 | 0 | 429.88 | 314.14 | 26.45 | 89.29 | 0 | 429.88 | 37.87 | 52
181 | MALDAH | SM/12766 | SAIDPUR Piped Water Supply Scheme | TSM/014263 | 40027626 | New | MVS | GO2223007988PH | 20/09/2022 | 800.09 | 46.69 | 846.78 | Malda Division | Malda Mechanical Division | 382.68 | 32.46 | 30.22 | 0 | 445.35 | 382.68 | 32.46 | 30.22 | 0 | 445.35 | 52.59 | 76
182 | MALDAH | SM/12337 | Sanjail PWSS in Old Malda Block in District Malda | TSM/011706 | 40014620 | New | MVS | GO2223007479PH | 12/09/2022 | 336.8 | 43.95 | 380.75 | Malda Division | Malda Mechanical Division | 238.27 | 28.75 | 17.01 | 0 | 284.03 | 238.27 | 28.75 | 17.01 | 0 | 284.03 | 74.6 | 76
183 | MALDAH | SM/12184 | SERBABAR BALARAMPUR Piped Water Supply Scheme | TSM/013253 | 40027587 | New | MVS | GO2223007177PH | 07/09/2022 | 789.75 | 44.9 | 834.65 | Malda Division | Malda Mechanical Division | 189.24 | 38.2 | 44.06 | 0 | 271.51 | 189.24 | 38.2 | 44.06 | 0 | 271.51 | 32.53 | 92
184 | MALDAH | SM/12631 | Sharanpur Piped Water Supply Scheme | TSM/013210 | 40027622 | New | MVS | GO2223007806PH | 19/09/2022 | 340.14 | 43.06 | 383.2 | Malda Division | Malda Mechanical Division | 109.1 | 32.9 | 29.42 | 0 | 171.42 | 109.1 | 32.9 | 29.42 | 0 | 171.42 | 44.73 | 87
185 | MALDAH | SM/15063 | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016220 | 40044100 | Augmentation | SVS | GO2223013186PH | 04/02/2023 | 105.36 | 19.24 | 124.6 | Malda Division | Malda Mechanical Division | 49.63 | 13.93 | 0 | 0 | 63.56 | 49.63 | 13.93 | 0 | 0 | 63.56 | 51.01 | 78
186 | MALDAH | SM/12314 | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012797 | 40026270 | Augmentation | SVS | GO2223007370PH | 09/09/2022 | 101.44 | 34.07 | 135.51 | Malda Division | Malda Mechanical Division | 48.77 | 16.38 | 0 | 0 | 65.15 | 48.77 | 16.38 | 0 | 0 | 65.15 | 48.08 | 70
187 | MALDAH | SM/12312 | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012799 | 40026008 | Augmentation | MVS | GO2223007382PH | 09/09/2022 | 99.47 | 32.34 | 131.81 | Malda Division | Malda Mechanical Division | 50.4 | 14.1 | 0 | 0 | 64.5 | 50.4 | 14.1 | 0 | 0 | 64.5 | 48.93 | 67
188 | MALDAH | SM/15141 | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED | TSM/017481 | 40047781 | Augmentation | SVS | GO2223013336PH | 06/02/2023 | 111.61 | 20.05 | 131.66 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 76.5 | 15.68 | 0 | 0 | 92.18 | 76.5 | 15.68 | 0 | 0 | 92.18 | 70.01 | 82
189 | MALDAH | SM/15074 | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016722 | 40044420 | Augmentation | MVS | GO2223013183PH | 04/02/2023 | 64.66 | 19.16 | 83.83 | Malda Division | Malda Mechanical Division | 24.18 | 12.52 | 0 | 0 | 36.7 | 24.18 | 12.52 | 0 | 0 | 36.7 | 43.78 | 78
190 | MALDAH | SM/15113 | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015614 | 40046394 | Augmentation | MVS | GO2223013180PH | 04/02/2023 | 221.51 | 39.57 | 261.08 | Malda Division | Malda Mechanical Division | 134.1 | 13.67 | 0 | 0 | 147.78 | 134.1 | 13.67 | 0 | 0 | 147.78 | 56.6 | 76
191 | MALDAH | SM/12760 | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015035 | 40026215 | Augmentation | MVS | GO2223007981PH | 20/09/2022 | 199.85 | 20.26 | 220.11 | Malda Division | Malda Mechanical Division | 2.48 | 3.92 | 0 | 0.27 | 6.67 | 2.48 | 3.92 | 0 | 0.27 | 6.67 | 3.03 | 56
192 | MALDAH | SM/15083 | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016679 | 40044393 | Augmentation | MVS | GO2223013141PH | 04/02/2023 | 56.8 | 19.16 | 75.97 | Malda Division | Malda Mechanical Division | 5.35 | 6.13 | 0 | 0 | 11.48 | 5.35 | 6.13 | 0 | 0 | 11.48 | 15.11 | 72
193 | MALDAH | SM/15105 | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016549 | 40046091 | Augmentation | MVS | GO2223013153PH | 04/02/2023 | 191.06 | 21.31 | 212.37 | Malda Division | Malda Mechanical Division | 147.22 | 19.6 | 0 | 0 | 166.82 | 147.22 | 19.6 | 0 | 0 | 166.82 | 78.55 | 84
194 | MALDAH | SM/15201 | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015613 | 40046545 | Augmentation | MVS | GO2223013236PH | 06/02/2023 | 177.12 | 19.15 | 196.28 | Malda Division | Malda Mechanical Division | 94.87 | 16.23 | 0 | 0 | 111.09 | 94.87 | 16.23 | 0 | 0 | 111.09 | 56.6 | 87
195 | MALDAH | SM/15073 | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016694 | 40044299 | Augmentation | MVS | GO2223013144PH | 04/02/2023 | 76.64 | 19.67 | 96.31 | Malda Division | Malda Mechanical Division | 13.44 | 14.59 | 0 | 0 | 28.03 | 13.44 | 14.59 | 0 | 0 | 28.03 | 29.1 | 78
196 | MALDAH | SM/15090 | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017129 | 40044929 | Augmentation | MVS | GO2223013165PH | 04/02/2023 | 82.84 | 19.67 | 102.52 | Malda Division | Malda Mechanical Division | 44.26 | 16.3 | 0 | 0 | 60.56 | 44.26 | 16.3 | 0 | 0 | 60.56 | 59.08 | 73
197 | MALDAH | SM/15079 | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016720 | 40044189 | Augmentation | MVS | GO2223013168PH | 04/02/2023 | 126.74 | 39.35 | 166.09 | Malda Division | Malda Mechanical Division | 78.25 | 31.04 | 7.39 | 0 | 116.68 | 78.25 | 31.04 | 7.39 | 0 | 116.68 | 70.25 | 84
198 | MALDAH | SM/12761 | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014744 | 40026213 | Augmentation | MVS | GO2223007983PH | 20/09/2022 | 243.31 | 52.36 | 295.68 | Malda Division | Malda Mechanical Division | 188.55 | 37.19 | 0 | 0 | 225.74 | 188.55 | 37.19 | 0 | 0 | 225.74 | 76.35 | 79
199 | MALDAH | SM/15111 | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016285 | 40046240 | Augmentation | MVS | GO2223013181PH | 04/02/2023 | 234.38 | 38.35 | 272.73 | Malda Division | Malda Mechanical Division | 90.96 | 30.85 | 0 | 0 | 121.81 | 90.96 | 30.85 | 0 | 0 | 121.81 | 44.66 | 83
200 | MALDAH | SM/15057 | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017203 | 40046495 | Augmentation | SVS | GO2223013145PH | 04/02/2023 | 44.42 | 19.84 | 64.27 | Malda Division | Malda Mechanical Division | 4.63 | 9.93 | 0 | 0 | 14.56 | 4.63 | 9.93 | 0 | 0 | 14.56 | 22.65 | 54
201 | MALDAH | SM/15106 | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016529 | 40046749 | Augmentation | MVS | GO2223013189PH | 04/02/2023 | 129.63 | 19.84 | 149.47 | Malda Division | Malda Mechanical Division | 37.72 | 16.17 | 0 | 0 | 53.89 | 37.72 | 16.17 | 0 | 0 | 53.89 | 36.05 | 58
202 | MALDAH | SM/14420 | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/015034 | 40062474 | Augmentation | SVS | GO2223012353PH | 20/01/2023 | 153.29 | 19.69 | 172.98 | Malda Division | Malda Mechanical Division | 7.48 | 4.69 | 0 | 0 | 12.17 | 7.48 | 4.69 | 0 | 0 | 12.17 | 7.04 | 45
203 | MALDAH | SM/12317 | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014339 | 40026137 | Augmentation | MVS | GO2223007377PH | 09/09/2022 | 206.52 | 74.66 | 281.18 | Malda Division | Malda Mechanical Division | 76.19 | 31.52 | 0 | 0 | 107.71 | 76.19 | 31.52 | 0 | 0 | 107.71 | 38.31 | 49
204 | MALDAH | SM/15080 | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016719 | 40044271 | Augmentation | MVS | GO2223013171PH | 04/02/2023 | 175.37 | 38.35 | 213.72 | Malda Division | Malda Mechanical Division | 103.5 | 21.54 | 0 | 0 | 125.04 | 103.5 | 21.54 | 0 | 0 | 125.04 | 58.51 | 62
205 | MALDAH | SM/15190 | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016606 | 40044131 | Augmentation | SVS | GO2223013328PH | 06/02/2023 | 83.6 | 20.31 | 103.91 | Malda Division | Malda Mechanical Division | 46.19 | 19.66 | 0 | 0 | 65.85 | 46.19 | 19.66 | 0 | 0 | 65.85 | 63.37 | 99
206 | MALDAH | SM/12763 | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014459 | 40026214 | Augmentation | MVS | GO2223007980PH | 20/09/2022 | 294.83 | 74.66 | 369.49 | Malda Division | Malda Mechanical Division | 147.96 | 28.14 | 0 | 0 | 176.1 | 147.88 | 28.14 | 0 | 0 | 176.02 | 47.64 | 54
207 | MALDAH | SM/12316 | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014342 | 40026037 | Augmentation | MVS | GO2223007381PH | 09/09/2022 | 136.42 | 31.39 | 167.81 | Malda Division | Malda Mechanical Division | 70.38 | 18.26 | 0 | 0 | 88.63 | 70.38 | 18.26 | 0 | 0 | 88.63 | 52.82 | 63
208 | MALDAH | SM/15093 | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016347 | 40046531 | Augmentation | MVS | GO2223013175PH | 04/02/2023 | 157.34 | 39.57 | 196.91 | Malda Division | Malda Mechanical Division | 32.52 | 22.17 | 3.08 | 0 | 57.77 | 32.52 | 22.17 | 3.08 | 0 | 57.77 | 29.34 | 58
209 | MALDAH | SM/15102 | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016470 | 40045479 | Augmentation | MVS | GO2223013157PH | 04/02/2023 | 84.13 | 20.18 | 104.31 | Malda Division | Malda Mechanical Division | 53.26 | 17.86 | 6.16 | 0 | 77.28 | 53.26 | 17.86 | 6.16 | 0 | 77.28 | 74.09 | 58
210 | MALDAH | SM/12315 | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012801 | 40026210 | Augmentation | MVS | GO2223007376PH | 09/09/2022 | 141.77 | 32.96 | 174.73 | Malda Division | Malda Mechanical Division | 67.15 | 17.4 | 0 | 0.27 | 84.82 | 67.15 | 17.4 | 0 | 0.27 | 84.82 | 48.54 | 56
211 | MALDAH | SM/15110 | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016354 | 40044964 | Augmentation | MVS | GO2223013159PH | 04/02/2023 | 98.27 | 21.13 | 119.4 | Malda Division | Malda Mechanical Division | 48.65 | 18.01 | 0 | 0 | 66.66 | 48.65 | 18.01 | 0 | 0 | 66.66 | 55.83 | 85
212 | MALDAH | SM/12313 | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012798 | 40027816 | Augmentation | MVS | GO2223007375PH | 09/09/2022 | 112.26 | 33.07 | 145.33 | Malda Division | Malda Mechanical Division | 55.76 | 13.99 | 0 | 0 | 69.75 | 55.76 | 13.99 | 0 | 0 | 69.75 | 48 | 55
213 | MALDAH | SM/12305 | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012802 | 40026030 | Augmentation | MVS | GO2223007371PH | 09/09/2022 | 117.33 | 35.06 | 152.39 | Malda Division | Malda Mechanical Division | 57.89 | 12.61 | 0 | 0 | 70.51 | 57.89 | 12.61 | 0 | 0 | 70.51 | 46.27 | 62
214 | MALDAH | SM/15062 | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016552 | 40044072 | Augmentation | SVS | GO2223013185PH | 04/02/2023 | 72.93 | 20.17 | 93.1 | Malda Division | Malda Mechanical Division | 34.2 | 10.03 | 0 | 0 | 44.23 | 34.2 | 10.03 | 0 | 0 | 44.23 | 47.5 | 52
215 | MALDAH | SM/15112 | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016501 | 40046308 | Augmentation | MVS | GO2223013182PH | 04/02/2023 | 64.46 | 20.31 | 84.77 | Malda Division | Malda Mechanical Division | 6.87 | 9.22 | 0 | 0 | 16.09 | 6.87 | 9.22 | 0 | 0 | 16.09 | 18.98 | 49
216 | MALDAH | SM/15108 | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016471 | 40046081 | Augmentation | MVS | GO2223013190PH | 04/02/2023 | 81.26 | 19.17 | 100.43 | Malda Division | Malda Mechanical Division | 28.96 | 18.15 | 1.85 | 0 | 48.96 | 28.96 | 18.15 | 1.85 | 0 | 48.96 | 48.75 | 97
217 | MALDAH | SM/12311 | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/012800 | 40026104 | Augmentation | MVS | GO2223007383PH | 09/09/2022 | 281.91 | 53.37 | 335.27 | Malda Division | Malda Mechanical Division | 144.44 | 28.21 | 3.08 | 0 | 175.72 | 144.44 | 28.21 | 3.08 | 0 | 175.72 | 52.41 | 60
218 | MALDAH | SM/12323 | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/014344 | 40026113 | Augmentation | MVS | GO2223007380PH | 09/09/2022 | 146.38 | 34.07 | 180.45 | Malda Division | Malda Mechanical Division | 76.21 | 0 | 0 | 0.27 | 76.49 | 76.21 | 0 | 0 | 0.27 | 76.49 | 42.38 | 43
219 | MALDAH | SM/15065 | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/016724 | 40044079 | Augmentation | SVS | GO2223013149PH | 04/02/2023 | 195.78 | 20.31 | 216.09 | Malda Division | Malda Mechanical Division | 159.71 | 15.28 | 0 | 0 | 174.99 | 159.71 | 15.28 | 0 | 0 | 174.99 | 80.98 | 85
220 | MALDAH | SM/15091 | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | TSM/017125 | 40044160 | Augmentation | MVS | GO2223013139PH | 04/02/2023 | 63.96 | 20.31 | 84.27 | Malda Division | Malda Mechanical Division | 25.76 | 13.78 | 0 | 0 | 39.54 | 25.76 | 13.78 | 0 | 0 | 39.54 | 46.92 | 79
221 | MALDAH | SM/15144 | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED | TSM/017480 | 40047035 | Augmentation | MVS | GO2223013334PH | 06/02/2023 | 125.98 | 18.99 | 144.97 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 45.53 | 15.35 | 0 | 0 | 60.89 | 45.53 | 15.35 | 0 | 0 | 60.89 | 42 | 85
222 | MALDAH | SM/18911 | SOURCE AUGMENTATION TROUGH INTRODUCING ROLLING TYPE BARGE FOR RAW WATER LIFTING FROM RIVER FULHAR AT INTAKE STATION OF BALUPUR WATER SUPPLY SCHEME UNDER RATUA-I BLOCK IN THE DISTRICT OF MALDA UNDER MALDA MECHANICAL DIVISION, PHE DTE. | TSM/021467 | 40067387 | Augmentation | MVS | PHE/IV/3072/W-670/23 | 09/10/2023 | 0 | 109.49 | 109.49 |  | Malda Mechanical Division | 0 | 42.04 | 0 | 0 | 42.04 | 0 | 42.04 | 0 | 0 | 42.04 | 38.4 | 39
223 | MALDAH | SM/12764 | SRI CHANDRAPUR Piped Water Supply Scheme | TSM/014411 | 40027624 | New | MVS | GO2223007989PH | 20/09/2022 | 660 | 43.14 | 703.14 | Malda Division | Malda Mechanical Division | 196.91 | 36.62 | 50.4 | 0 | 283.93 | 196.91 | 36.62 | 50.4 | 0 | 283.93 | 40.38 | 76
224 | MALDAH | SM/18685 | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | TSM/017908 | 40057312 | New | MVS | 2246/PHE-28011/113/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 14877.48 | 485.84 | 15363.32 | Malda Division | Malda Mechanical Division | 2134.19 | 79.7 | 1887.86 | 0 | 4101.75 | 2046.28 | 79.7 | 1887.86 | 0 | 4013.83 | 26.13 | 35
225 | MALDAH | SM/15962 | SUJAPUR PIPED WATER SUPPLY SCHEME | TSM/018437 | 40057341 | New | MVS | GO2223014615PH | 22/02/2023 | 543.77 | 42.31 | 586.08 | Malda Division | Malda Mechanical Division | 109.67 | 3.94 | 2.22 | 0 | 115.83 | 109.67 | 2.94 | 2.22 | 0 | 114.83 | 19.59 | 62
226 | MALDAH | SM/15950 | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED | TSM/018013 | 40055913 | New | SVS | GO2223014629PH | 22/02/2023 | 427.98 | 63.42 | 491.4 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 114.72 | 36.56 | 0 | 0 | 151.28 | 114.72 | 35.79 | 0 | 0 | 150.51 | 30.63 | 80
227 | MALDAH | SM/12196 | SULTANNAGAR PWSS | TSM/012936 | 40027597 | New | MVS | GO2223007216PH | 07/09/2022 | 467.89 | 44.85 | 512.75 | Malda Division | Malda Mechanical Division | 178.93 | 32.24 | 36.44 | 0 | 247.62 | 178.93 | 32.24 | 36.44 | 0 | 247.62 | 48.29 | 69
228 | MALDAH | SM/18686 | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | TSM/018373 | 40065428 | New | MVS | 2246/PHE-28011/113/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 63755.77 | 4313.35 | 68069.12 | Malda Division | Malda Mechanical Division | 2554.5 | 3.41 | 10499.45 | 0 | 13057.36 | 1279.8 | 3.41 | 10499.45 | 0 | 11782.66 | 17.31 | 31
229 | MALDAH | SM/12185 | SWARUPGANJ Piped Water Supply Scheme | TSM/013249 | 40027588 | New | MVS | GO2223007127PH | 07/09/2022 | 714.61 | 46.77 | 761.39 | Malda Division | Malda Mechanical Division | 290.15 | 35.37 | 36.07 | 0 | 361.58 | 290.15 | 35.37 | 36.07 | 0 | 361.58 | 47.49 | 85
230 | MALDAH | SM/12189 | TALPUKUR Piped Water Supply Scheme | TSM/013199 | 40027590 | New | MVS | GO2223007228PH | 07/09/2022 | 685.37 | 44.69 | 730.06 | Malda Division | Malda Mechanical Division | 390.83 | 33.32 | 28.22 | 0 | 452.37 | 390.83 | 33.32 | 28.22 | 0 | 452.37 | 61.96 | 83
231 | MALDAH | SM/12881 | UTTAR BHAKURIA Piped Water Supply Scheme. | TSM/013230 | 40027631 | New | SVS | GO2223008163PH | 23/09/2022 | 65.66 | 20.58 | 86.24 | Malda Division | Malda Mechanical Division | 28.08 | 14.18 | 1.32 | 0 | 43.59 | 28.08 | 14.18 | 1.32 | 0 | 43.59 | 50.55 | 83
232 | MALDAH | SM/18418 | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED | TSM/017806 | 40047241 | New | MVS | 1873/PHE-28011/202/2023-SCHM CELL-Dept. of PHE | 13/07/2023 | 1192.82 | 117.07 | 1309.89 | Malda Arsenic Area W/S Division | Malda Mechanical Division | 102.14 | 13.76 | 142.82 | 0 | 258.72 | 102.14 | 13.76 | 142.82 | 0 | 258.72 | 19.75 | 28
233 | MALDAH | SM/12765 | Uttar Mahinagar Piped Water Supply Scheme | TSM/014266 | 40027625 | New | MVS | GO2223007990PH | 20/09/2022 | 360.71 | 43.05 | 403.76 | Malda Division | Malda Mechanical Division | 132.61 | 8.05 | 25.78 | 0 | 166.45 | 132.61 | 8.05 | 25.78 | 0 | 166.45 | 41.22 | 39
234 | MALDAH | SM/12077 | WARI Piped Water Supply Scheme | TSM/011955 | 40022273 | New | MVS | GO2223007011PH | 02/09/2022 | 1009.62 | 67.79 | 1077.41 | Malda Division | Malda Mechanical Division | 483.97 | 45.42 | 55.34 | 0 | 584.73 | 483.97 | 45.42 | 55.34 | 0 | 584.73 | 54.27 | 79
Total | [9 empty] | 285638.38 | 23275.91 | 308914.29 |  |  | 60427.83 | 4628.11 | 35725.84 | 19.68 | 100801.47 | 59003.06 | 4564.44 | 35725.84 | 19.68 | 99313.03 | 32.15