## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PURBA BARDHAMAN) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PURBA BARDHAMAN | SM/15725 | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME | TSM/017966 | 40046449 | Augmentation | MVS | GO2223014223PH | 20/02/2023 | 96.14 | 0 | 96.14 | Burdwan Division |  | 1.32 | 0 | 0 | 0 | 1.32 | 1.32 | 0 | 0 | 0 | 1.32 | 1.37
2 | PURBA BARDHAMAN | SM/10032 | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) | TSM/008767 | 40011243 | Augmentation | MVS | GO2122008407PH | 19/01/2022 | 1021.34 | 48.59 | 1069.93 | Burdwan Division | Central Mechanical Division | 770.3 | 23.5 | 0 | 0 | 793.8 | 770.3 | 23.5 | 0 | 0 | 793.8 | 74.19
3 | PURBA BARDHAMAN | SM/10061 | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009467 | 40002282 | Augmentation | MVS | GO2122008725PH | 25/01/2022 | 693.56 | 0 | 693.56 | Burdwan Division | Central Mechanical Division | 455.55 | 0 | 0 | 0 | 455.55 | 455.55 | 0 | 0 | 0 | 455.55 | 65.68
4 | PURBA BARDHAMAN | SM/10060 | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009468 | 40002432 | Augmentation | MVS | GO2122008726PH | 25/01/2022 | 489.63 | 0 | 489.63 | Burdwan Division | Central Mechanical Division | 435.31 | 0 | 0 | 0 | 435.31 | 435.31 | 0 | 0 | 0 | 435.31 | 88.91
5 | PURBA BARDHAMAN | SM/09488 | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008830 | 40009808 | Augmentation | MVS | GO2122005588PH | 19/11/2021 | 344.93 | 0 | 344.93 | Burdwan Division | Central Mechanical Division | 248.72 | 0 | 0 | 0 | 248.72 | 248.72 | 0 | 0 | 0 | 248.72 | 72.11
6 | PURBA BARDHAMAN | SM/15560 | AUGMENTATION BHALKI Z-I & Z-II PWSS | TSM/019284 | 40046282 | Augmentation | MVS | GO2223013925PH | 16/02/2023 | 396.89 | 69.65 | 466.54 | Durgapur W/S Division | Central Mechanical Division | 11.5 | 15.6 | 0 | 0 | 27.1 | 11.5 | 15.6 | 0 | 0 | 27.1 | 5.81 | 60
7 | PURBA BARDHAMAN | SM/09403 | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008580 | 40008252 | Augmentation | MVS | GO2122005518PH | 17/11/2021 | 651.77 | 0 | 651.77 | Burdwan Division |  | 440.82 | 0 | 26.86 | 0 | 467.68 | 440.82 | 0 | 26.86 | 0 | 467.68 | 71.75
8 | PURBA BARDHAMAN | SM/15152 | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | TSM/017554 | 40063615 | Augmentation | SVS | GO2223013468PH | 07/02/2023 | 455.63 | 27.64 | 483.27 | Burdwan Division | Central Mechanical Division | 337.38 | 6.92 | 0 | 0 | 344.3 | 337.38 | 6.92 | 0 | 0 | 344.3 | 71.24
9 | PURBA BARDHAMAN | SM/16304 | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME | TSM/019608 | 40053122 | Augmentation | MVS | GO2223014766PH | 23/02/2023 | 245.95 | 40.5 | 286.45 | Burdwan Division | Central Mechanical Division | 43.51 | 0 | 0 | 0 | 43.51 | 43.51 | 0 | 0 | 0 | 43.51 | 15.19 | 90
10 | PURBA BARDHAMAN | SM/15568 | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME | TSM/017601 | 40047820 | Augmentation | MVS | GO2223013929PH | 16/02/2023 | 529.68 | 54.17 | 583.85 | Burdwan Division | Central Mechanical Division | 144.49 | 7.25 | 0 | 0 | 151.74 | 144.49 | 7.25 | 0 | 0 | 151.74 | 25.99
11 | PURBA BARDHAMAN | SM/16196 | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME | TSM/019606 | 40062652 | Augmentation | SVS | GO2223014779PH | 23/02/2023 | 222.22 | 40.5 | 262.71 | Burdwan Division | Central Mechanical Division | 39.59 | 1.02 | 0 | 0 | 40.62 | 39.59 | 1.02 | 0 | 0 | 40.62 | 15.46
12 | PURBA BARDHAMAN | SM/09416 | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District | TSM/008530 | 40008294 | Augmentation | SVS | GO2122005519PH | 17/11/2021 | 563.41 | 0 | 563.41 | Burdwan Division |  | 421.04 | 0 | 22.94 | 0 | 443.98 | 421.04 | 0 | 22.94 | 0 | 443.98 | 78.8 | 80
13 | PURBA BARDHAMAN | SM/16017 | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME | TSM/017528 | 40053156 | Augmentation | MVS | GO2223014481PH | 21/02/2023 | 131.33 | 12.98 | 144.31 | Burdwan Division | Central Mechanical Division | 85.39 | 7.65 | 0 | 0 | 93.04 | 85.39 | 7.65 | 0 | 0 | 93.04 | 64.47
14 | PURBA BARDHAMAN | SM/15159 | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | TSM/018160 | 40046402 | Augmentation | SVS | GO2223013461PH | 07/02/2023 | 232.29 | 55.28 | 287.57 | Burdwan Division | Central Mechanical Division | 95.97 | 4.88 | 0 | 0 | 100.84 | 95.97 | 4.88 | 0 | 0 | 100.84 | 35.07
15 | PURBA BARDHAMAN | SM/09411 | Augmentation of Ganganandapur PWSS for providing FHTC. | TSM/008073 | 40007935 | Augmentation | MVS | GO2122005479PH | 17/11/2021 | 808.85 | 0 | 808.85 | Burdwan Division |  | 603.09 | 0 | 18.45 | 0 | 621.54 | 603.09 | 0 | 18.45 | 0 | 621.54 | 76.84
16 | PURBA BARDHAMAN | SM/09406 | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008534 | 40007947 | Augmentation | MVS | GO2122005481PH | 17/11/2021 | 316.97 | 0 | 316.97 | Burdwan Division |  | 296.49 | 0 | 11.25 | 0 | 307.73 | 296.49 | 0 | 11.25 | 0 | 307.73 | 97.09 | 98
17 | PURBA BARDHAMAN | SM/09494 | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008742 | 40008343 | Augmentation | SVS | GO2122005607PH | 19/11/2021 | 354.12 | 0 | 354.12 | Burdwan Division | Central Mechanical Division | 302.41 | 0 | 11.04 | 0 | 313.45 | 302.41 | 0 | 11.04 | 0 | 313.45 | 88.51 | 90
18 | PURBA BARDHAMAN | SM/10337 | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009140 | 40002592 | Augmentation | MVS | GO2122010688PH | 14/03/2022 | 1288.91 | 71.09 | 1360.01 | Burdwan Division | Central Mechanical Division | 1067.96 | 8.28 | 0 | 0 | 1076.24 | 1067.96 | 8.28 | 0 | 0 | 1076.24 | 79.13 | 85
19 | PURBA BARDHAMAN | SM/09568 | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008750 | 40008371 | Augmentation | MVS | GO2122005683PH | 22/11/2021 | 455.89 | 0 | 455.89 | Burdwan Division | Central Mechanical Division | 424.13 | 0 | 12.95 | 0 | 437.08 | 424.13 | 0 | 12.95 | 0 | 437.08 | 95.87 | 95
20 | PURBA BARDHAMAN | SM/10130 | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008749 | 40008526 | Augmentation | MVS | GO2122009276PH | 08/02/2022 | 1002.31 | 21.41 | 1023.72 | Burdwan Division | Central Mechanical Division | 901.49 | 15.25 | 0 | 0 | 916.73 | 901.49 | 15.25 | 0 | 0 | 916.73 | 89.55 | 90
21 | PURBA BARDHAMAN | SM/10085 | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008802 | 40006963 | Augmentation | MVS | GO2021008862PH | 31/01/2022 | 3231.45 | 0 | 3231.45 | Burdwan Division | Central Mechanical Division | 1951.68 | 0 | 82.17 | 0 | 2033.86 | 1950.91 | 0 | 82.17 | 0 | 2033.08 | 62.92 | 90
22 | PURBA BARDHAMAN | SM/09404 | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008529 | 40008063 | Augmentation | MVS | GO2122005482PH | 17/11/2021 | 851.6 | 0 | 851.6 | Burdwan Division |  | 786.48 | 0 | 4.66 | 0 | 791.14 | 786.48 | 0 | 4.66 | 0 | 791.14 | 92.9 | 99
23 | PURBA BARDHAMAN | SM/09569 | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008747 | 40008369 | Augmentation | MVS | GO2122005683PH | 22/11/2021 | 527.28 | 0 | 527.28 | Burdwan Division | Central Mechanical Division | 393.03 | 0 | 16.58 | 0 | 409.61 | 393.03 | 0 | 16.58 | 0 | 409.61 | 77.68
24 | PURBA BARDHAMAN | SM/10123 | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008752 | 40008528 | Augmentation | MVS | GO2122009422PH | 08/02/2022 | 1083.3 | 0 | 1083.3 | Burdwan Division | Central Mechanical Division | 558.19 | 0 | 0 | 0 | 558.19 | 558.19 | 0 | 0 | 0 | 558.19 | 51.53
25 | PURBA BARDHAMAN | SM/15166 | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | TSM/019278 | 40046054 | Augmentation | MVS | GO2223013507PH | 08/02/2023 | 171.34 | 55.12 | 226.46 | Burdwan Division | Central Mechanical Division | 68.41 | 13.75 | 0 | 0 | 82.16 | 68.41 | 13.75 | 0 | 0 | 82.16 | 36.28
26 | PURBA BARDHAMAN | SM/09489 | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008828 | 40008322 | Augmentation | MVS | GO2122005588PH | 19/11/2021 | 599.17 | 0 | 599.17 | Burdwan Division | Central Mechanical Division | 556.28 | 0 | 0 | 0 | 556.28 | 556.28 | 0 | 0 | 0 | 556.28 | 92.84 | 65
27 | PURBA BARDHAMAN | SM/09413 | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008533 | 40008082 | Augmentation | MVS | GO2122005484PH | 17/11/2021 | 564.13 | 0 | 564.13 | Burdwan Division |  | 521.19 | 0 | 15.49 | 0 | 536.68 | 521.19 | 0 | 15.49 | 0 | 536.68 | 95.14 | 100
28 | PURBA BARDHAMAN | SM/08998 | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT | TSM/008574 | 40007900 | Augmentation | MVS | GO2122004676PH | 29/10/2021 | 497.47 | 0 | 497.47 | Burdwan Division |  | 477.05 | 0 | 0 | 0 | 477.05 | 477.05 | 0 | 0 | 0 | 477.05 | 95.9 | 99
29 | PURBA BARDHAMAN | SM/15194 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | TSM/017978 | 40046441 | Augmentation | MVS | GO2223013522PH | 08/02/2023 | 268.6 | 72.73 | 341.33 | Burdwan Division | Central Mechanical Division | 70.15 | 17.1 | 0 | 0 | 87.26 | 70.15 | 17.1 | 0 | 0 | 87.26 | 25.56
30 | PURBA BARDHAMAN | SM/15722 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | TSM/017997 | 40046260 | Augmentation | MVS | GO2223014229PH | 20/02/2023 | 42.15 | 50.71 | 92.86 | Burdwan Division | Central Mechanical Division | 24.33 | 0 | 0 | 0 | 24.33 | 24.33 | 0 | 0 | 0 | 24.33 | 26.2
31 | PURBA BARDHAMAN | SM/15565 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI | TSM/018105 | 40046201 | Augmentation | MVS | GO2223013930PH | 16/02/2023 | 52.89 | 55.38 | 108.27 | Burdwan Division | Central Mechanical Division | 6.09 | 0 | 0 | 0 | 6.09 | 6.09 | 0 | 0 | 0 | 6.09 | 5.62
32 | PURBA BARDHAMAN | SM/15203 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | TSM/018026 | 40046245 | Augmentation | MVS | GO2223013470PH | 07/02/2023 | 98.48 | 55.19 | 153.66 | Burdwan Division | Central Mechanical Division | 42.73 | 20.51 | 0 | 0 | 63.24 | 42.73 | 20.51 | 0 | 0 | 63.24 | 41.15
33 | PURBA BARDHAMAN | SM/15753 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | TSM/018004 | 40046255 | Augmentation | MVS | GO2223014227PH | 20/02/2023 | 126.2 | 0 | 126.2 | Burdwan Division |  | 38.53 | 0 | 0 | 0 | 38.53 | 38.53 | 0 | 0 | 0 | 38.53 | 30.53
34 | PURBA BARDHAMAN | SM/15723 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN | TSM/017996 | 40062507 | Augmentation | MVS | GO2223014224PH | 20/02/2023 | 80.03 | 50.71 | 130.73 | Burdwan Division | Central Mechanical Division | 60.49 | 18.6 | 0 | 0 | 79.09 | 60.49 | 18.6 | 0 | 0 | 79.09 | 60.5 | 95
35 | PURBA BARDHAMAN | SM/16192 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA | TSM/019358 | 40062609 | Augmentation | SVS | GO2223014782PH | 23/02/2023 | 350.05 | 36.05 | 386.1 | Burdwan Division | Central Mechanical Division | 85.93 | 23.39 | 0 | 0 | 109.32 | 85.93 | 23.39 | 0 | 0 | 109.32 | 28.31
36 | PURBA BARDHAMAN | SM/15185 | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | TSM/019254 | 40046295 | Augmentation | MVS | GO2223013459PH | 07/02/2023 | 346.46 | 50.71 | 397.16 | Burdwan Division | Central Mechanical Division | 66.76 | 8.97 | 0 | 0 | 75.74 | 66.76 | 8.97 | 0 | 0 | 75.74 | 19.07
37 | PURBA BARDHAMAN | SM/15184 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | TSM/019252 | 40046354 | Augmentation | MVS | GO2223013467PH | 07/02/2023 | 169.72 | 50.71 | 220.43 | Burdwan Division | Central Mechanical Division | 51.37 | 18.29 | 0 | 0 | 69.67 | 51.37 | 15.04 | 0 | 0 | 66.41 | 30.13 | 70
38 | PURBA BARDHAMAN | SM/09700 | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. | TSM/008425 | 40008412 | Augmentation | SVS | GO2122005974PH | 26/11/2021 | 625.09 | 0 | 625.09 | Burdwan Division | Central Mechanical Division | 509.3 | 0 | 29.32 | 0 | 538.61 | 509.3 | 0 | 29.32 | 0 | 538.61 | 86.17 | 100
39 | PURBA BARDHAMAN | SM/09715 | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008426 | 40008472 | Augmentation | MVS | GO2122005981PH | 26/11/2021 | 523.43 | 0 | 523.43 | Burdwan Division | Central Mechanical Division | 357.36 | 0 | 21.26 | 0 | 378.62 | 357.36 | 0 | 21.26 | 0 | 378.62 | 72.33 | 90
40 | PURBA BARDHAMAN | SM/09714 | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008335 | 40008436 | Augmentation | MVS | GO2122005977PH | 26/11/2021 | 754.02 | 0 | 754.02 | Durgapur W/S Division |  | 430.46 | 0 | 21.79 | 0 | 452.25 | 430.46 | 0 | 21.79 | 0 | 452.25 | 59.98 | 80
41 | PURBA BARDHAMAN | SM/10391 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | TSM/010056 | 40065688 | Augmentation | MVS | GO2122011265PH | 24/03/2022 | 906.76 | 35.55 | 942.3 | Burdwan Division | Central Mechanical Division | 746.99 | 19.47 | 0 | 0 | 766.46 | 746.99 | 19.47 | 0 | 0 | 766.46 | 81.34 | 11
42 | PURBA BARDHAMAN | SM/09713 | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008334 | 40008400 | Augmentation | MVS | GO2122005972PH | 26/11/2021 | 594.6 | 0 | 594.6 | Durgapur W/S Division |  | 462.39 | 0 | 42.77 | 0 | 505.16 | 462.39 | 0 | 42.77 | 0 | 505.16 | 84.96 | 100
43 | PURBA BARDHAMAN | SM/09712 | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008333 | 40008405 | Augmentation | MVS | GO2122005973PH | 26/11/2021 | 732.87 | 0 | 732.87 | Durgapur W/S Division | Central Mechanical Division | 248.27 | 0 | 35.56 | 0 | 283.84 | 248.27 | 0 | 35.56 | 0 | 283.84 | 38.73 | 20
44 | PURBA BARDHAMAN | SM/09699 | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008332 | 40008413 | Augmentation | SVS | GO2122005974PH | 26/11/2021 | 323.86 | 0 | 323.86 | Durgapur W/S Division |  | 302.1 | 0 | 1.88 | 0 | 303.98 | 302.1 | 0 | 1.88 | 0 | 303.98 | 93.86 | 100
45 | PURBA BARDHAMAN | SM/09873 | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009224 | 40008522 | Augmentation | MVS | GO2122006490PH | 06/12/2021 | 623.75 | 28.05 | 651.8 | Burdwan Division | Central Mechanical Division | 239.69 | 0 | 17.54 | 0 | 257.23 | 239.69 | 0 | 17.54 | 0 | 257.23 | 39.46 | 25
46 | PURBA BARDHAMAN | SM/19113 | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. | TSM/019253 | 40067438 | Augmentation | MVS | PHE/IV/3824/W-772/23 | 22/12/2023 | 123.42 | 0 | 123.42 | Burdwan Division |  | 1.85 | 0 | 0 | 0 | 1.85 | 1.85 | 0 | 0 | 0 | 1.85 | 1.5
47 | PURBA BARDHAMAN | SM/09493 | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008751 | 40008359 | Augmentation | MVS | GO2122005608PH | 19/11/2021 | 371.84 | 0 | 371.84 | Burdwan Division | Central Mechanical Division | 353.99 | 0 | 0 | 0 | 353.99 | 353.99 | 0 | 0 | 0 | 353.99 | 95.2 | 80
48 | PURBA BARDHAMAN | SM/16774 | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | TSM/019268 | 40062808 | Augmentation | MVS | GO2223015706PH | 13/03/2023 | 220 | 55.12 | 275.12 | Burdwan Division | Central Mechanical Division | 79 | 17.97 | 0 | 0 | 96.97 | 79 | 17.97 | 0 | 0 | 96.97 | 35.25
49 | PURBA BARDHAMAN | SM/09492 | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008753 | 40008364 | Augmentation | MVS | GO2122005608PH | 19/11/2021 | 586.55 | 0 | 586.55 | Burdwan Division |  | 559.2 | 0 | 16.61 | 0 | 575.81 | 559.2 | 0 | 16.61 | 0 | 575.81 | 98.17 | 95
50 | PURBA BARDHAMAN | SM/09405 | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008579 | 40008234 | Augmentation | SVS | GO2122005481PH | 17/11/2021 | 262.41 | 0 | 262.41 | Burdwan Division |  | 259.18 | 0 | 3.23 | 0 | 262.41 | 259.18 | 0 | 3.23 | 0 | 262.41 | 100 | 100
51 | PURBA BARDHAMAN | SM/10057 | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009461 | 40002893 | Augmentation | MVS | GO2122008729PH | 25/01/2022 | 947.41 | 24.63 | 972.04 | Burdwan Division | Central Mechanical Division | 591.71 | 19.41 | 0 | 0 | 611.12 | 591.71 | 19.41 | 0 | 0 | 611.12 | 62.87
52 | PURBA BARDHAMAN | SM/10056 | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009463 | 40002911 | Augmentation | MVS | GO2122008722PH | 25/01/2022 | 726.35 | 0 | 726.35 | Burdwan Division | Central Mechanical Division | 648.97 | 0 | 41.12 | 0 | 690.09 | 648.97 | 0 | 41.12 | 0 | 690.09 | 95.01 | 30
53 | PURBA BARDHAMAN | SM/10059 | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009464 | 40002910 | Augmentation | SVS | GO2122008727PH | 25/01/2022 | 79.18 | 0 | 79.18 | Burdwan Division | Central Mechanical Division | 59.75 | 0 | 1.32 | 0 | 61.07 | 59.75 | 0 | 1.32 | 0 | 61.07 | 77.13 | 100
54 | PURBA BARDHAMAN | SM/09408 | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman | TSM/008525 | 40008264 | Augmentation | MVS | GO2122005520PH | 17/11/2021 | 495.29 | 0 | 495.29 | Burdwan Division |  | 478.97 | 0 | 15.56 | 0 | 494.53 | 478.97 | 0 | 15.56 | 0 | 494.53 | 99.85 | 60
55 | PURBA BARDHAMAN | SM/15183 | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | TSM/019275 | 40046025 | Augmentation | MVS | GO2223013445PH | 07/02/2023 | 256.63 | 110.23 | 366.86 | Burdwan Division | Central Mechanical Division | 158.81 | 35.2 | 0 | 0 | 194.01 | 158.81 | 35.2 | 0 | 0 | 194.01 | 52.88
56 | PURBA BARDHAMAN | SM/09495 | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008577 | 40008349 | Augmentation | MVS | GO2122005607PH | 19/11/2021 | 531.47 | 0 | 531.47 | Burdwan Division | Central Mechanical Division | 523.64 | 0 | 0.13 | 0 | 523.78 | 523.64 | 0 | 0.13 | 0 | 523.78 | 98.55 | 100
57 | PURBA BARDHAMAN | SM/09412 | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District | TSM/008535 | 40007915 | Augmentation | MVS | GO2122005475PH | 17/11/2021 | 537.66 | 0 | 537.66 | Burdwan Division |  | 397.22 | 0 | 7.95 | 0 | 405.18 | 397.22 | 0 | 7.95 | 0 | 405.18 | 75.36 | 90
58 | PURBA BARDHAMAN | SM/09566 | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/008526 | 40008374 | Augmentation | MVS | GO2122005692PH | 22/11/2021 | 623.11 | 0 | 623.11 | Burdwan Division | Central Mechanical Division | 522.01 | 0 | 20.19 | 0 | 542.19 | 522.01 | 0 | 20.19 | 0 | 542.19 | 87.01 | 78
59 | PURBA BARDHAMAN | SM/15602 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM | TSM/019256 | 40046000 | Augmentation | MVS | GO2223013928PH | 16/02/2023 | 700.54 | 0 | 700.54 | Burdwan Division |  | 235.78 | 0 | 0 | 0 | 235.78 | 235.78 | 0 | 0 | 0 | 235.78 | 33.66 | 50
60 | PURBA BARDHAMAN | SM/14014 | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | TSM/011595 | 40047953 | Augmentation | MVS | GO2223010483PH | 05/12/2022 | 813.11 | 35.55 | 848.66 | Burdwan Division | Central Mechanical Division | 431.17 | 30.11 | 0 | 0 | 461.29 | 431.17 | 30.11 | 0 | 0 | 461.29 | 54.35 | 40
61 | PURBA BARDHAMAN | SM/16293 | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | TSM/020229 | 40062759 | Augmentation | SVS | GO2223014761PH | 23/02/2023 | 211.57 | 40.5 | 252.07 | Burdwan Division | Central Mechanical Division | 98.63 | 0 | 0 | 0 | 98.63 | 98.63 | 0 | 0 | 0 | 98.63 | 39.13
62 | PURBA BARDHAMAN | SM/09717 | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) | TSM/008336 | 40008443 | Augmentation | MVS | GO2122005978PH | 26/11/2021 | 530.67 | 0 | 530.67 | Burdwan Division |  | 347.62 | 0 | 2.12 | 0 | 349.74 | 347.62 | 0 | 2.12 | 0 | 349.74 | 65.91
63 | PURBA BARDHAMAN | SM/16299 | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME | TSM/019615 | 40062673 | Augmentation | SVS | GO2223014780PH | 23/02/2023 | 165.1 | 40.5 | 205.59 | Burdwan Division | Central Mechanical Division | 109.26 | 15.47 | 0 | 0 | 124.73 | 109.26 | 15.47 | 0 | 0 | 124.73 | 60.67
64 | PURBA BARDHAMAN | SM/15562 | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME | TSM/018170 | 40046489 | Augmentation | MVS | GO2223013933PH | 16/02/2023 | 382.95 | 27.64 | 410.59 | Burdwan Division | Central Mechanical Division | 106.59 | 3.75 | 0 | 0 | 110.34 | 106.59 | 3.75 | 0 | 0 | 110.34 | 26.87 | 10
65 | PURBA BARDHAMAN | SM/16297 | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | TSM/019618 | 40062687 | Augmentation | SVS | GO2223014781PH | 23/02/2023 | 214.43 | 40.5 | 254.93 | Burdwan Division | Central Mechanical Division | 123.84 | 3.77 | 0 | 0 | 127.61 | 123.84 | 3.77 | 0 | 0 | 127.61 | 50.06
66 | PURBA BARDHAMAN | SM/16016 | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME | TSM/017536 | 40053382 | Augmentation | SVS | GO2223014470PH | 21/02/2023 | 118.32 | 27.11 | 145.44 | Burdwan Division | Central Mechanical Division | 46.04 | 14.29 | 0 | 0 | 60.34 | 46.04 | 14.29 | 0 | 0 | 60.34 | 41.48 | 95
67 | PURBA BARDHAMAN | SM/16301 | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | TSM/019614 | 40053177 | Augmentation | MVS | GO2223014773PH | 23/02/2023 | 225.61 | 76.09 | 301.7 | Burdwan Division | Central Mechanical Division | 83.72 | 6.49 | 0 | 0 | 90.21 | 83.72 | 6.49 | 0 | 0 | 90.21 | 29.9
68 | PURBA BARDHAMAN | SM/16487 | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | TSM/018139 | 40046128 | Augmentation | MVS | GO2223015176PH | 02/03/2023 | 802.57 | 55.28 | 857.85 | Burdwan Division | Central Mechanical Division | 16.53 | 0 | 0 | 0 | 16.53 | 16.53 | 0 | 0 | 0 | 16.53 | 1.93 | 5
69 | PURBA BARDHAMAN | SM/09414 | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District | TSM/008532 | 40008282 | Augmentation | SVS | GO2122005517PH | 17/11/2021 | 487.81 | 0 | 487.81 | Burdwan Division |  | 381.76 | 0 | 5.67 | 0 | 387.42 | 381.76 | 0 | 5.67 | 0 | 387.42 | 79.42 | 85
70 | PURBA BARDHAMAN | SM/16298 | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | TSM/019621 | 40062704 | Augmentation | MVS | GO2223014775PH | 23/02/2023 | 323.26 | 55.84 | 379.1 | Burdwan Division | Central Mechanical Division | 22.69 | 0.89 | 0 | 0 | 23.58 | 22.69 | 0.89 | 0 | 0 | 23.58 | 6.22
71 | PURBA BARDHAMAN | SM/09407 | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008445 | 40008036 | Augmentation | MVS | GO2122005481PH | 17/11/2021 | 159.5 | 0 | 159.5 | Burdwan Division |  | 142.12 | 0 | 9.97 | 0 | 152.09 | 142.12 | 0 | 9.97 | 0 | 152.09 | 95.35
72 | PURBA BARDHAMAN | SM/15555 | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME | TSM/017550 | 40062999 | Augmentation | SVS | GO2223013926PH | 16/02/2023 | 352.42 | 27.64 | 380.06 | Burdwan Division | Central Mechanical Division | 127.18 | 9.5 | 0 | 0 | 136.68 | 127.18 | 9.5 | 0 | 0 | 136.68 | 35.96
73 | PURBA BARDHAMAN | SM/09719 | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) | TSM/008337 | 40008457 | Augmentation | SVS | GO2122005979PH | 26/11/2021 | 677.83 | 0 | 677.83 | Burdwan Division |  | 460.26 | 0 | 26.85 | 0 | 487.11 | 460.26 | 0 | 26.85 | 0 | 487.11 | 71.86 | 90
74 | PURBA BARDHAMAN | SM/09718 | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. | TSM/008172 | 40008529 | Augmentation | MVS | GO2122005971PH | 26/11/2021 | 802.22 | 0 | 802.22 | Burdwan Division | Central Mechanical Division | 546.69 | 0 | 105.45 | 0 | 652.13 | 546.69 | 0 | 105.45 | 0 | 652.13 | 81.29 | 80
75 | PURBA BARDHAMAN | SM/16193 | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME | TSM/019603 | 40062638 | Augmentation | SVS | GO2223014764PH | 23/02/2023 | 174.08 | 40.5 | 214.58 | Burdwan Division | Central Mechanical Division | 15.27 | 0 | 0 | 0 | 15.27 | 15.27 | 0 | 0 | 0 | 15.27 | 7.12
76 | PURBA BARDHAMAN | SM/15571 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | TSM/018386 | 40053385 | Augmentation | MVS | GO2223013919PH | 16/02/2023 | 657.74 | 246.94 | 904.68 | Burdwan Division | Central Mechanical Division | 264.77 | 0.05 | 6.16 | 0 | 270.98 | 264.77 | 0.05 | 6.16 | 0 | 270.98 | 29.95
77 | PURBA BARDHAMAN | SM/16014 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II | TSM/018387 | 40053368 | Augmentation | MVS | GO2223014465PH | 21/02/2023 | 979.43 | 0 | 979.43 | Burdwan Division |  | 22 | 0 | 6.16 | 0 | 28.16 | 22 | 0 | 6.16 | 0 | 28.16 | 2.87
78 | PURBA BARDHAMAN | SM/15588 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III | TSM/018388 | 40053350 | Augmentation | MVS | GO2223013920PH | 16/02/2023 | 793.59 | 0 | 793.59 | Burdwan Division |  | 0 | 0 | 33.64 | 0 | 33.64 | 0 | 0 | 33.64 | 0 | 33.64 | 4.24
79 | PURBA BARDHAMAN | SM/16307 | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | TSM/018389 | 40053354 | Augmentation | MVS | GO2223014777PH | 23/02/2023 | 965.63 | 0 | 965.63 | Burdwan Division |  | 122.14 | 0 | 6.16 | 0 | 128.3 | 122.14 | 0 | 6.16 | 0 | 128.3 | 13.29
80 | PURBA BARDHAMAN | SM/16306 | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME | TSM/019607 | 40062779 | Augmentation | SVS | GO2223014786PH | 23/02/2023 | 190.16 | 55.84 | 246 | Burdwan Division | Central Mechanical Division | 17.56 | 0 | 0 | 0 | 17.56 | 17.56 | 0 | 0 | 0 | 17.56 | 7.14
81 | PURBA BARDHAMAN | SM/16486 | AUGMENTATION OF RAYAN (PART-II) PWSS | TSM/018136 | 40046232 | Augmentation | MVS | GO2223015178PH | 02/03/2023 | 741.62 | 30.75 | 772.37 | Burdwan Division | Central Mechanical Division | 0 | 5.11 | 0 | 0 | 5.11 | 0 | 5.11 | 0 | 0 | 5.11 | 0.66
82 | PURBA BARDHAMAN | SM/16548 | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME | TSM/018151 | 40046408 | Augmentation | SVS | GO2223015485PH | 10/03/2023 | 282.19 | 30.75 | 312.94 | Burdwan Division | Central Mechanical Division | 79.31 | 6.45 | 0 | 0 | 85.77 | 79.31 | 6.45 | 0 | 0 | 85.77 | 27.41 | 30
83 | PURBA BARDHAMAN | SM/16022 | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME | TSM/017520 | 40062321 | Augmentation | SVS | GO2223014482PH | 21/02/2023 | 132.21 | 13.01 | 145.22 | Burdwan Division | Central Mechanical Division | 128.04 | 3.16 | 0 | 0 | 131.2 | 128.04 | 3.16 | 0 | 0 | 131.2 | 90.34
84 | PURBA BARDHAMAN | SM/09716 | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. | TSM/008170 | 40008465 | Augmentation | MVS | GO2122005980PH | 26/11/2021 | 652.1 | 0 | 652.1 | Burdwan Division |  | 147.81 | 0 | 15.25 | 0 | 163.06 | 147.81 | 0 | 15.25 | 0 | 163.06 | 25
85 | PURBA BARDHAMAN | SM/09921 | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal | TSM/008453 | 40008524 | Augmentation | MVS | GO2122006617PH | 10/12/2021 | 1106.28 | 38.32 | 1144.6 | Burdwan Division | Central Mechanical Division | 707.53 | 34.52 | 118.66 | 0 | 860.71 | 707.53 | 34.52 | 118.66 | 0 | 860.71 | 75.2
86 | PURBA BARDHAMAN | SM/15178 | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | TSM/019265 | 40046211 | Augmentation | MVS | GO2223013457PH | 07/02/2023 | 218.01 | 55.12 | 273.13 | Burdwan Division | Central Mechanical Division | 12.67 | 5.58 | 0 | 0 | 18.25 | 12.67 | 5.58 | 0 | 0 | 18.25 | 6.68
87 | PURBA BARDHAMAN | SM/15182 | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | TSM/019270 | 40046259 | Augmentation | MVS | GO2223013454PH | 07/02/2023 | 224.46 | 55.12 | 279.58 | Burdwan Division | Central Mechanical Division | 6.03 | 0 | 0 | 0 | 6.03 | 6.03 | 0 | 0 | 0 | 6.03 | 2.16
88 | PURBA BARDHAMAN | SM/15173 | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | TSM/019279 | 40046075 | Augmentation | MVS | GO2223013453PH | 07/02/2023 | 232.66 | 55.11 | 287.77 | Burdwan Division | Central Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | PURBA BARDHAMAN | SM/18439 | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL | TSM/019289 | 40046070 | Augmentation | MVS | 1933/PHE-28011/150/2023-ESTT CELL-Dept. of PHE | 18/07/2023 | 2227.97 | 53.22 | 2281.19 | Burdwan Division | Central Mechanical Division | 1201.67 | 3.61 | 0 | 0 | 1205.28 | 1201.67 | 3.61 | 0 | 0 | 1205.28 | 52.84 | 50
90 | PURBA BARDHAMAN | SM/09410 | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District | TSM/008451 | 40008303 | Augmentation | MVS | GO2122005521PH | 17/11/2021 | 697.69 | 0 | 697.69 | Burdwan Division |  | 379.57 | 0 | 16.89 | 0 | 396.47 | 379.57 | 0 | 16.89 | 0 | 396.47 | 56.83 | 80
91 | PURBA BARDHAMAN | SM/15557 | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME | TSM/017541 | 40062680 | Augmentation | SVS | GO2223013932PH | 16/02/2023 | 694.42 | 27.64 | 722.06 | Burdwan Division | Central Mechanical Division | 252.17 | 19.23 | 0 | 0 | 271.4 | 252.17 | 19.23 | 0 | 0 | 271.4 | 37.59
92 | PURBA BARDHAMAN | SM/15573 | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME | TSM/017545 | 40062854 | Augmentation | MVS | GO2223013927PH | 16/02/2023 | 523.9 | 0 | 523.9 | Burdwan Division |  | 74.02 | 0 | 0 | 0 | 74.02 | 74.02 | 0 | 0 | 0 | 74.02 | 14.13
93 | PURBA BARDHAMAN | SM/18112 | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | TSM/019276 | 40046043 | Augmentation | MVS | GO2223017755PH | 27/03/2023 | 186.31 | 110.23 | 296.54 | Burdwan Division | Central Mechanical Division | 2.59 | 11.9 | 0 | 0 | 14.49 | 2.59 | 11.9 | 0 | 0 | 14.49 | 4.89
94 | PURBA BARDHAMAN | SM/15556 | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME | TSM/018152 | 40046411 | Augmentation | SVS | GO2223013931PH | 16/02/2023 | 186.07 | 30.75 | 216.81 | Burdwan Division | Central Mechanical Division | 34.69 | 14.92 | 0 | 0 | 49.61 | 34.69 | 14.92 | 0 | 0 | 49.61 | 22.88 | 99
95 | PURBA BARDHAMAN | SM/15176 | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | TSM/019285 | 40046317 | Augmentation | MVS | GO2223013506PH | 08/02/2023 | 148.17 | 69.65 | 217.82 | Durgapur W/S Division | Central Mechanical Division | 34.32 | 19.2 | 0 | 0 | 53.52 | 34.32 | 19.2 | 0 | 0 | 53.52 | 24.57 | 72
96 | PURBA BARDHAMAN | SM/15191 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | TSM/018125 | 40046212 | Augmentation | MVS | GO2223013521PH | 08/02/2023 | 153.47 | 72.73 | 226.2 | Burdwan Division | Central Mechanical Division | 55.5 | 26.83 | 0 | 0 | 82.33 | 55.5 | 26.83 | 0 | 0 | 82.33 | 36.4
97 | PURBA BARDHAMAN | SM/15192 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | TSM/018132 | 40046222 | Augmentation | MVS | GO2223013520PH | 08/02/2023 | 252.12 | 50.71 | 302.82 | Burdwan Division | Central Mechanical Division | 213.85 | 35.52 | 0 | 0 | 249.37 | 213.85 | 35.52 | 0 | 0 | 249.37 | 82.35
98 | PURBA BARDHAMAN | SM/15181 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | TSM/018216 | 40046346 | Augmentation | MVS | GO2223013512PH | 08/02/2023 | 79.48 | 72.73 | 152.21 | Burdwan Division | Central Mechanical Division | 22.65 | 51.07 | 0 | 0 | 73.71 | 22.65 | 51.07 | 0 | 0 | 73.71 | 48.43
99 | PURBA BARDHAMAN | SM/15205 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA | TSM/018141 | 40046233 | Augmentation | MVS | GO2223013518PH | 07/02/2023 | 80.39 | 0 | 80.39 | Burdwan Division |  | 0.77 | 0 | 0 | 0 | 0.77 | 0.77 | 0 | 0 | 0 | 0.77 | 0.96
100 | PURBA BARDHAMAN | SM/15179 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | TSM/018206 | 40046335 | Augmentation | MVS | GO2223013508PH | 08/02/2023 | 94.84 | 50.71 | 145.55 | Burdwan Division | Central Mechanical Division | 0 | 3.25 | 0 | 0 | 3.25 | 0 | 3.25 | 0 | 0 | 3.25 | 2.23
101 | PURBA BARDHAMAN | SM/15175 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | TSM/018188 | 40046322 | Augmentation | MVS | GO2223013512PH | 08/02/2023 | 174.65 | 0 | 174.65 | Burdwan Division | Central Mechanical Division | 103.62 | 0 | 0 | 0 | 103.62 | 103.62 | 0 | 0 | 0 | 103.62 | 59.33
102 | PURBA BARDHAMAN | SM/15718 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA | TSM/018150 | 40046242 | Augmentation | MVS | GO2223014230PH | 20/02/2023 | 56.48 | 0 | 56.48 | Burdwan Division |  | 10.1 | 0 | 0 | 0 | 10.1 | 10.1 | 0 | 0 | 0 | 10.1 | 17.88
103 | PURBA BARDHAMAN | SM/15187 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | TSM/018185 | 40046275 | Augmentation | MVS | GO2223013515PH | 08/02/2023 | 108.07 | 36.05 | 144.12 | Burdwan Division | Central Mechanical Division | 40.27 | 13.36 | 0 | 0 | 53.63 | 40.27 | 13.36 | 0 | 0 | 53.63 | 37.21
104 | PURBA BARDHAMAN | SM/15701 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR | TSM/018161 | 40046271 | Augmentation | MVS | GO2223014231PH | 20/02/2023 | 57.66 | 86.82 | 144.48 | Burdwan Division | Central Mechanical Division | 20.55 | 22.14 | 0 | 0 | 42.69 | 20.55 | 22.14 | 0 | 0 | 42.69 | 29.55
105 | PURBA BARDHAMAN | SM/16479 | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | TSM/018352 | 40067463 | Augmentation | SVS | GO2223015177PH | 02/03/2023 | 379.59 | 54.17 | 433.76 | Burdwan Division | Central Mechanical Division | 91.43 | 16.57 | 0 | 0 | 108 | 91.43 | 16.57 | 0 | 0 | 108 | 24.9 | 30
106 | PURBA BARDHAMAN | SM/10270 | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009133 | 40002639 | Augmentation | MVS | GO2122010085PH | 25/02/2022 | 1007.19 | 88.87 | 1096.06 | Burdwan Division | Central Mechanical Division | 741.68 | 39.75 | 0 | 0 | 781.43 | 741.68 | 39.75 | 0 | 0 | 781.43 | 71.29
107 | PURBA BARDHAMAN | SM/10058 | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT | TSM/009137 | 40002720 | Augmentation | MVS | GO2122008724PH | 25/01/2022 | 969.93 | 17.77 | 987.71 | Burdwan Division | Central Mechanical Division | 890.76 | 1.97 | 0 | 0 | 892.73 | 890.76 | 1.97 | 0 | 0 | 892.73 | 90.38 | 95
108 | PURBA BARDHAMAN | SM/10481 | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN | TSM/009953 | 40018519 | Augmentation | MVS | GO2223000266PH | 13/04/2022 | 708.24 | 41.75 | 749.99 | Burdwan Division | Central Mechanical Division | 341.23 | 40.42 | 12.32 | 0 | 393.97 | 341.23 | 40.42 | 12.32 | 0 | 393.97 | 52.53
109 | PURBA BARDHAMAN | SM/15309 | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | TSM/009941 | 40048283 | Augmentation | MVS | GO2223013472PH | 09/02/2023 | 668.48 | 41.75 | 710.23 | Burdwan Division | Central Mechanical Division | 272.73 | 20.06 | 0 | 0 | 292.8 | 272.73 | 20.06 | 0 | 0 | 292.8 | 41.23 | 50
110 | PURBA BARDHAMAN | SM/09415 | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL | TSM/008531 | 40008076 | Augmentation | SVS | GO2122005483PH | 17/11/2021 | 443 | 0 | 443 | Burdwan Division |  | 304.97 | 0 | 9.17 | 0 | 314.14 | 304.97 | 0 | 9.17 | 0 | 314.14 | 70.91 | 80
111 | PURBA BARDHAMAN | SM/09409 | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL | TSM/008524 | 40008193 | Augmentation | SVS | GO2122005485PH | 17/11/2021 | 532.8 | 0 | 532.8 | Burdwan Division |  | 442.95 | 0 | 8.18 | 0 | 451.13 | 442.95 | 0 | 8.18 | 0 | 451.13 | 84.67 | 82
112 | PURBA BARDHAMAN | SM/12116 | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio | TSM/010125 | 40062678 | Augmentation | SVS | GO2223007231PH | 07/09/2022 | 73.22 | 0 | 73.22 | Burdwan Division |  | 53.15 | 0 | 0 | 0 | 53.15 | 53.15 | 0 | 0 | 0 | 53.15 | 72.59 | 97
113 | PURBA BARDHAMAN | SM/09103 | Rejuvenation of Bhalki Water Supply Scheme. | TSM/007380 | 40005619 | Augmentation | MVS | GO2122004566PH | 29/10/2021 | 293.35 | 0 | 293.35 | Burdwan Division |  | 280.08 | 0 | 0 | 0 | 280.08 | 280.08 | 0 | 0 | 0 | 280.08 | 95.48 | 100
Total | [9 empty] | 55323.41 | 3126.3 | 58449.7 |  |  | 31484.36 | 781.95 | 881.27 | 0 | 33147.59 | 31483.59 | 778.7 | 881.27 | 0 | 33143.56 | 56.7