## JJM Schemes Financial Status (P
JJM Schemes Financial Status (PURBA BARDHAMAN) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | PURBA BARDHAMAN | SM/08704 | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | TSM/007676 | 8368902 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 267.25 | 0 | 267.25 | Burdwan Division |  | 116.92 | 0 | 0 | 0 | 116.92 | 115.88 | 0 | 0 | 0 | 115.88 | 43.36 | 6
2 | PURBA BARDHAMAN | SM/08706 | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. | TSM/007677 | 6919663 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 99.81 | 0 | 99.81 | Burdwan Division |  | 43.14 | 0 | 0 | 0 | 43.14 | 43.14 | 0 | 0 | 0 | 43.14 | 43.22 | 87
3 | PURBA BARDHAMAN | SM/08699 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B | TSM/007673 | 40018510 | Retrofitting | MVS | GO2122002847PH | 01/09/2021 | 198.59 | 0 | 198.59 | Burdwan Division |  | 96.6 | 0 | 5.5 | 0 | 102.1 | 96.6 | 0 | 5.5 | 0 | 102.1 | 51.41 | 50
4 | PURBA BARDHAMAN | SM/08705 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007675 | 6323350 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 119.29 | 0 | 119.29 | Durgapur W/S Division |  | 61.98 | 0 | 0 | 0 | 61.98 | 57.73 | 0 | 0 | 0 | 57.73 | 48.4 | 93
5 | PURBA BARDHAMAN | SM/08702 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007670 | 5348549 | Retrofitting | SVS | GO2122002917PH | 03/09/2021 | 60.29 | 0 | 60.29 | Burdwan Division |  | 60 | 0 | 0 | 0 | 60 | 50.24 | 0 | 0 | 0 | 50.24 | 83.32 | 92
6 | PURBA BARDHAMAN | SM/08700 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007669 | 6559103 | Retrofitting | MVS | GO2122002847PH | 01/09/2021 | 63.32 | 0 | 63.32 | Burdwan Division |  | 45.32 | 0 | 0 | 0 | 45.32 | 45.32 | 0 | 0 | 0 | 45.32 | 71.57 | 100
7 | PURBA BARDHAMAN | SM/08712 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio | TSM/007672 | 6151164 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 147.7 | 0 | 147.7 | Burdwan Division |  | 114.82 | 0 | 10.07 | 0 | 124.89 | 110.1 | 0 | 10.07 | 0 | 120.17 | 81.36 | 98
8 | PURBA BARDHAMAN | SM/08707 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007671 | 40001073 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 181.66 | 0 | 181.66 | Burdwan Division |  | 67.19 | 0 | 0 | 0 | 67.19 | 67.19 | 0 | 0 | 0 | 67.19 | 36.98 | 95
9 | PURBA BARDHAMAN | SM/08717 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007667 | 40001081 | Retrofitting | SVS | GO2122002917PH | 03/09/2021 | 46.27 | 0 | 46.27 | Burdwan Division |  | 46 | 0 | 0 | 0 | 46 | 40.97 | 0 | 0 | 0 | 40.97 | 88.54 | 100
10 | PURBA BARDHAMAN | SM/08715 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007674 | 6132611 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 143.24 | 0 | 143.24 | Burdwan Division |  | 76.7 | 0 | 0 | 0 | 76.7 | 76.7 | 0 | 0 | 0 | 76.7 | 53.54 | 96
11 | PURBA BARDHAMAN | SM/08716 | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007668 | 40001080 | Retrofitting | SVS | GO2122002917PH | 03/09/2021 | 80.58 | 0 | 80.58 | Burdwan Division |  | 80.5 | 0 | 0 | 0 | 80.5 | 68.88 | 0 | 0 | 0 | 68.88 | 85.48 | 95
12 | PURBA BARDHAMAN | SM/07203 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme | TSM/006210 | 8136245 | Retrofitting | MVS | GO2021003126PH | 08/12/2020 | 47.76 | 0 | 47.76 | Burdwan Division |  | 23.99 | 0 | 0 | 0 | 23.99 | 22.44 | 0 | 0 | 0 | 22.44 | 46.99 | 36
13 | PURBA BARDHAMAN | SM/07202 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme | TSM/006217 | 8136267 | Retrofitting | SVS | GO2021003124PH | 08/12/2020 | 46.9 | 0 | 46.9 | Burdwan Division |  | 23.34 | 0 | 0 | 0 | 23.34 | 23.34 | 0 | 0 | 0 | 23.34 | 49.75 | 76
14 | PURBA BARDHAMAN | SM/07205 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme | TSM/006223 | 8136393 | Retrofitting | MVS | GO2021003131PH | 08/12/2020 | 39.16 | 0 | 39.16 | Burdwan Division |  | 23.45 | 0 | 0 | 0 | 23.45 | 23.45 | 0 | 0 | 0 | 23.45 | 59.88 | 43
15 | PURBA BARDHAMAN | SM/07201 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme | TSM/006207 | 8136281 | Retrofitting | SVS | GO2021003122PH | 08/12/2020 | 47.47 | 0 | 47.47 | Burdwan Division |  | 27.03 | 0 | 0 | 0 | 27.03 | 25.85 | 0 | 0 | 0 | 25.85 | 54.45 | 80
16 | PURBA BARDHAMAN | SM/07204 | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme | TSM/006222 | 8136379 | Retrofitting | SVS | GO2021003129PH | 08/12/2020 | 99.8 | 0 | 99.8 | Burdwan Division |  | 62.87 | 0 | 0 | 0 | 62.87 | 62.87 | 0 | 0 | 0 | 62.87 | 63 | 43
17 | PURBA BARDHAMAN | SM/12081 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR | TSM/014286 | 40022080 | Retrofitting | MVS | GO2223007003PH | 02/09/2022 | 58.96 | 0 | 58.96 | Burdwan Division |  | 38.9 | 0 | 0 | 0 | 38.9 | 38.9 | 0 | 0 | 0 | 38.9 | 65.97 | 95
18 | PURBA BARDHAMAN | SM/08030 | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | TSM/006592 | 8204595 | Retrofitting | MVS | GO2021005343PH | 25/01/2021 | 1902.4 | 0 | 1902.4 | Burdwan Division |  | 1718.9 | 0 | 0 | 0 | 1718.9 | 1718.9 | 0 | 0 | 0 | 1718.9 | 90.35 | 95
19 | PURBA BARDHAMAN | SM/06752 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS | TSM/005625 | 8136287 | Retrofitting | MVS | GO2021001230PH | 18/09/2020 | 81.95 | 0 | 81.95 | Burdwan Division |  | 74.05 | 0 | 7.9 | 0 | 81.95 | 74.05 | 0 | 7.9 | 0 | 81.95 | 100 | 43
20 | PURBA BARDHAMAN | SM/06753 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS | TSM/005626 | 8136044 | Retrofitting | MVS | GO2021001229PH | 18/09/2020 | 53.37 | 0 | 53.37 | Burdwan Division |  | 15 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 28.1 | 45
21 | PURBA BARDHAMAN | SM/06749 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS | TSM/005621 | 40065393 | Retrofitting | MVS | GO2021001226PH | 18/09/2020 | 93.49 | 0 | 93.49 | Burdwan Division |  | 49.68 | 0 | 0 | 0 | 49.68 | 49.68 | 0 | 0 | 0 | 49.68 | 53.14 | 95
22 | PURBA BARDHAMAN | SM/06745 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS | TSM/005619 | 8136030 | Retrofitting | MVS | GO2021001233PH | 18/09/2020 | 78.36 | 0 | 78.36 | Burdwan Division |  | 78.36 | 0 | 0 | 0 | 78.36 | 78.18 | 0 | 0 | 0 | 78.18 | 99.77 | 43
23 | PURBA BARDHAMAN | SM/06750 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS | TSM/005618 | 8136261 | Retrofitting | SVS | GO2021001225PH | 18/09/2020 | 58.89 | 0 | 58.89 | Burdwan Division |  | 58.89 | 0 | 0 | 0 | 58.89 | 49.8 | 0 | 0 | 0 | 49.8 | 84.57 | 82
24 | PURBA BARDHAMAN | SM/06770 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS | TSM/005616 | 8136278 | Retrofitting | MVS | GO2021001366PH | 22/09/2020 | 46.11 | 0 | 46.11 | Burdwan Division |  | 38.3 | 0 | 0 | 0 | 38.3 | 38.3 | 0 | 0 | 0 | 38.3 | 83.06 | 36
25 | PURBA BARDHAMAN | SM/06751 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS | TSM/005623 | 6151164 | Retrofitting | MVS | GO2021001228PH | 18/09/2020 | 99.03 | 0 | 99.03 | Burdwan Division |  | 98.04 | 0 | 0 | 0 | 98.04 | 98.04 | 0 | 0 | 0 | 98.04 | 99.01 | 98
26 | PURBA BARDHAMAN | SM/06747 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS | TSM/005628 | 8136105 | Retrofitting | MVS | GO2021001231PH | 18/09/2020 | 39.12 | 0 | 39.12 | Burdwan Division |  | 10.58 | 0 | 0 | 0 | 10.58 | 10.58 | 0 | 0 | 0 | 10.58 | 27.04 | 43
27 | PURBA BARDHAMAN | SM/06772 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS | TSM/005624 | 8136124 | Retrofitting | MVS | GO2021001369PH | 22/09/2020 | 74.63 | 0 | 74.63 | Burdwan Division |  | 55.92 | 0 | 0 | 0 | 55.92 | 55.92 | 0 | 0 | 0 | 55.92 | 74.94 | 43
28 | PURBA BARDHAMAN | SM/06768 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS | TSM/005614 | 8136006 | Retrofitting | SVS | GO2021001365PH | 22/09/2020 | 37.98 | 0 | 37.98 | Burdwan Division |  | 27.17 | 0 | 0 | 0 | 27.17 | 27.17 | 0 | 0 | 0 | 27.17 | 71.53 | 85
29 | PURBA BARDHAMAN | SM/06771 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS | TSM/005617 | 8136238 | Retrofitting | MVS | GO2021001364PH | 22/09/2020 | 91.38 | 0 | 91.38 | Burdwan Division |  | 90.84 | 0 | 0 | 0 | 90.84 | 90.84 | 0 | 0 | 0 | 90.84 | 99.42 | 68
30 | PURBA BARDHAMAN | SM/06773 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS | TSM/005620 | 8136252 | Retrofitting | SVS | GO2021001368PH | 22/09/2020 | 60.25 | 0 | 60.25 | Burdwan Division |  | 60.25 | 0 | 0 | 0 | 60.25 | 60.22 | 0 | 0 | 0 | 60.22 | 99.95 | 43
31 | PURBA BARDHAMAN | SM/06769 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS | TSM/005615 | 8136228 | Retrofitting | SVS | GO2021001367PH | 22/09/2020 | 89.62 | 0 | 89.62 | Burdwan Division |  | 89.62 | 0 | 0 | 0 | 89.62 | 89.62 | 0 | 0 | 0 | 89.62 | 100 | 43
32 | PURBA BARDHAMAN | SM/06748 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS | TSM/005622 | 6559103 | Retrofitting | MVS | GO2021001227PH | 18/09/2020 | 99.68 | 0 | 99.68 | Burdwan Division |  | 99.68 | 0 | 0 | 0 | 99.68 | 99.68 | 0 | 0 | 0 | 99.68 | 100 | 100
33 | PURBA BARDHAMAN | SM/06746 | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS | TSM/005627 | 7326945 | Retrofitting | MVS | GO2021001232PH | 18/09/2020 | 72.6 | 0 | 72.6 | Burdwan Division |  | 70.34 | 0 | 0 | 0 | 70.34 | 70.29 | 0 | 0 | 0 | 70.29 | 96.81 | 86
34 | PURBA BARDHAMAN | SM/07861 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block | TSM/006629 | 5348510 | Retrofitting | MVS | GO2021004575PH | 14/01/2021 | 253.82 | 0 | 253.82 | Burdwan Division |  | 167.28 | 0 | 0 | 0 | 167.28 | 167.28 | 0 | 0 | 0 | 167.28 | 65.91 | 94
35 | PURBA BARDHAMAN | SM/07829 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | TSM/006680 | 6132538 | Retrofitting | MVS | GO2021004374PH | 08/01/2021 | 239.55 | 0 | 239.55 | Durgapur W/S Division | Central Mechanical Division | 107.6 | 0 | 0 | 0 | 107.6 | 107.6 | 0 | 0 | 0 | 107.6 | 44.92 | 96
36 | PURBA BARDHAMAN | SM/07782 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block | TSM/006692 | 8193475 | Retrofitting | MVS | GO2021004383PH | 08/01/2021 | 117.85 | 0 | 117.85 | Burdwan Division |  | 117.85 | 0 | 0 | 0 | 117.85 | 117.85 | 0 | 0 | 0 | 117.85 | 100 | 25
37 | PURBA BARDHAMAN | SM/08701 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007681 | 7368574 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 505.33 | 0 | 505.33 | Burdwan Division |  | 99.71 | 0 | 0.55 | 0 | 100.26 | 99.71 | 0 | 0.55 | 0 | 100.26 | 19.84 | 86
38 | PURBA BARDHAMAN | SM/07819 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme | TSM/006647 | 6348404 | Retrofitting | MVS | GO2021004348PH | 08/01/2021 | 257.15 | 0 | 257.15 | Burdwan Division |  | 36.59 | 0 | 0 | 0 | 36.59 | 36.59 | 0 | 0 | 0 | 36.59 | 14.23 | 94
39 | PURBA BARDHAMAN | SM/06969 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme | TSM/006218 | 5348549 | Retrofitting | SVS | GO2021002451PH | 09/11/2020 | 83.79 | 0 | 83.79 | Burdwan Division |  | 83.79 | 0 | 0 | 0 | 83.79 | 83.72 | 0 | 0 | 0 | 83.72 | 99.91 | 92
40 | PURBA BARDHAMAN | SM/07817 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | TSM/006588 | 7770017 | Retrofitting | MVS | GO2021004367PH | 08/01/2021 | 132.65 | 0 | 132.65 | Durgapur W/S Division |  | 76.66 | 0 | 0 | 0 | 76.66 | 75.52 | 0 | 0 | 0 | 75.52 | 56.94 | 70
41 | PURBA BARDHAMAN | SM/08703 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007680 | 7333148 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 196.29 | 0 | 196.29 | Burdwan Division |  | 82.35 | 0 | 0 | 0 | 82.35 | 80.8 | 0 | 0 | 0 | 80.8 | 41.16 | 86
42 | PURBA BARDHAMAN | SM/07866 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block | TSM/006659 | 8196236 | Retrofitting | MVS | GO2021004574PH | 14/01/2021 | 283.41 | 0 | 283.41 | Burdwan Division |  | 255.92 | 0 | 22.25 | 0 | 278.17 | 255.92 | 0 | 22.25 | 0 | 278.17 | 98.15 | 6
43 | PURBA BARDHAMAN | SM/07870 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block | TSM/006682 | 6858823 | Retrofitting | MVS | GO2021004576PH | 14/01/2021 | 157.93 | 0 | 157.93 | Durgapur W/S Division | Central Mechanical Division | 44.01 | 0 | 0 | 0 | 44.01 | 43.43 | 0 | 0 | 0 | 43.43 | 27.5 | 86
44 | PURBA BARDHAMAN | SM/07776 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | TSM/006602 | 7755627 | Retrofitting | MVS | GO2021004378PH | 08/01/2021 | 123.62 | 0 | 123.62 | Burdwan Division |  | 47.59 | 0 | 5.5 | 0 | 53.09 | 47.59 | 0 | 5.5 | 0 | 53.09 | 42.95 | 51
45 | PURBA BARDHAMAN | SM/07871 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block | TSM/006700 | 8193883 | Retrofitting | MVS | GO2021004568PH | 14/01/2021 | 255.84 | 0 | 255.84 | Burdwan Division |  | 52.67 | 0 | 0 | 7.52 | 60.19 | 52.67 | 0 | 0 | 7.52 | 60.19 | 23.53 | 95
46 | PURBA BARDHAMAN | SM/06962 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme | TSM/006219 | 6151193 | Retrofitting | MVS | GO2021002450PH | 09/11/2020 | 99.94 | 0 | 99.94 | Burdwan Division |  | 86.73 | 0 | 0 | 0 | 86.73 | 86.73 | 0 | 0 | 0 | 86.73 | 86.78 | 100
47 | PURBA BARDHAMAN | SM/06965 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme | TSM/006200 | 8136412 | Retrofitting | MVS | GO2021002444PH | 09/11/2020 | 91.43 | 0 | 91.43 | Burdwan Division |  | 47.35 | 0 | 0 | 0 | 47.35 | 45.75 | 0 | 0 | 0 | 45.75 | 50.03 | 43
48 | PURBA BARDHAMAN | SM/07857 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block | TSM/006600 | 7940868 | Retrofitting | MVS | GO2021004577PH | 14/01/2021 | 110.71 | 0 | 110.71 | Burdwan Division |  | 101.63 | 0 | 9.09 | 0 | 110.71 | 101.63 | 0 | 9.09 | 0 | 110.71 | 100 | 22
49 | PURBA BARDHAMAN | SM/06964 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | TSM/006204 | 6323350 | Retrofitting | MVS | GO2021002446PH | 09/11/2020 | 99.26 | 0 | 99.26 | Durgapur W/S Division |  | 99.26 | 0 | 0 | 0 | 99.26 | 94.16 | 0 | 0 | 0 | 94.16 | 94.87 | 93
50 | PURBA BARDHAMAN | SM/06968 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme | TSM/006212 | 8136355 | Retrofitting | MVS | GO2021002449PH | 09/11/2020 | 99.96 | 0 | 99.96 | Burdwan Division |  | 99.96 | 0 | 0 | 0 | 99.96 | 99.96 | 0 | 0 | 0 | 99.96 | 100 | 43
51 | PURBA BARDHAMAN | SM/07824 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | TSM/006672 | 7326951 | Retrofitting | MVS | GO2021004373PH | 08/01/2021 | 117.09 | 0 | 117.09 | Durgapur W/S Division |  | 93.17 | 0 | 0 | 0 | 93.17 | 93.17 | 0 | 0 | 0 | 93.17 | 79.57 | 55
52 | PURBA BARDHAMAN | SM/07804 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block | TSM/006667 | 8190564 | Retrofitting | MVS | GO2021004174PH | 07/01/2021 | 79.59 | 0 | 79.59 | Burdwan Division | Central Mechanical Division | 51.33 | 0 | 0 | 0 | 51.33 | 51.33 | 0 | 0 | 0 | 51.33 | 64.49 | 6
53 | PURBA BARDHAMAN | SM/07780 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block | TSM/006671 | 5348595 | Retrofitting | MVS | GO2021004381PH | 08/01/2021 | 297.21 | 0 | 297.21 | Burdwan Division |  | 132.09 | 0 | 0 | 0 | 132.09 | 132.09 | 0 | 0 | 0 | 132.09 | 44.44 | 98
54 | PURBA BARDHAMAN | SM/07797 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block | TSM/006593 | 7940720 | Retrofitting | MVS | GO2021004195PH | 07/01/2021 | 39.14 | 0 | 39.14 | Burdwan Division |  | 11.22 | 0 | 0 | 0 | 11.22 | 11.22 | 0 | 0 | 0 | 11.22 | 28.66 | 5
55 | PURBA BARDHAMAN | SM/07821 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme | TSM/006625 | 6858825 | Retrofitting | MVS | GO2021004347PH | 08/01/2021 | 105.81 | 0 | 105.81 | Burdwan Division |  | 57.85 | 0 | 0 | 0 | 57.85 | 57.85 | 0 | 0 | 0 | 57.85 | 54.67 | 86
56 | PURBA BARDHAMAN | SM/07869 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | TSM/006683 | 6858819 | Retrofitting | SVS | GO2021004564PH | 14/01/2021 | 109.48 | 0 | 109.48 | Durgapur W/S Division |  | 58.35 | 0 | 0 | 0 | 58.35 | 31.2 | 0 | 0 | 0 | 31.2 | 28.5 | 70
57 | PURBA BARDHAMAN | SM/07800 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme | TSM/006622 | 40065373 | Retrofitting | MVS | GO2021004180PH | 07/01/2021 | 90.29 | 0 | 90.29 | Burdwan Division |  | 20.41 | 0 | 0 | 0 | 20.41 | 20.41 | 0 | 0 | 0 | 20.41 | 22.61 | 80
58 | PURBA BARDHAMAN | SM/07777 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block | TSM/006591 | 7940709 | Retrofitting | MVS | GO2021004382PH | 08/01/2021 | 100.12 | 0 | 100.12 | Burdwan Division |  | 75.72 | 0 | 0 | 0 | 75.72 | 75.72 | 0 | 0 | 0 | 75.72 | 75.63 | 31
59 | PURBA BARDHAMAN | SM/06971 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme | TSM/006221 | 8136189 | Retrofitting | MVS | GO2021002453PH | 09/11/2020 | 99.89 | 0 | 99.89 | Burdwan Division |  | 80.46 | 0 | 0 | 0 | 80.46 | 79.28 | 0 | 0 | 0 | 79.28 | 79.36 | 43
60 | PURBA BARDHAMAN | SM/07818 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block | TSM/006598 | 7941627 | Retrofitting | MVS | GO2021004355PH | 08/01/2021 | 122.01 | 0 | 122.01 | Burdwan Division |  | 120.25 | 0 | 0 | 0 | 120.25 | 120.25 | 0 | 0 | 0 | 120.25 | 98.55 | 37
61 | PURBA BARDHAMAN | SM/07860 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme | TSM/006641 | 8195484 | Retrofitting | MVS | GO2021004573PH | 14/01/2021 | 115.29 | 0 | 115.29 | Burdwan Division |  | 14.63 | 0 | 0 | 0 | 14.63 | 14.63 | 0 | 0 | 0 | 14.63 | 12.69 | 6
62 | PURBA BARDHAMAN | SM/06966 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme | TSM/006202 | 8136213 | Retrofitting | MVS | GO2021002445PH | 09/11/2020 | 98.36 | 0 | 98.36 | Burdwan Division |  | 98.36 | 0 | 0 | 0 | 98.36 | 98.36 | 0 | 0 | 0 | 98.36 | 100 | 43
63 | PURBA BARDHAMAN | SM/07803 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block | TSM/006663 | 8191813 | Retrofitting | SVS | GO2021004175PH | 07/01/2021 | 71.15 | 0 | 71.15 | Burdwan Division |  | 38 | 0 | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 38 | 53.41 | 95
64 | PURBA BARDHAMAN | SM/09104 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. | TSM/008315 | 8390825 | Retrofitting | MVS | GO2122004566PH | 28/10/2021 | 245.18 | 0 | 245.18 | Burdwan Division |  | 72.49 | 0 | 0 | 0 | 72.49 | 72.49 | 0 | 0 | 0 | 72.49 | 29.57 | 2
65 | PURBA BARDHAMAN | SM/07781 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | TSM/006685 | 6822210 | Retrofitting | MVS | GO2021004380PH | 08/01/2021 | 103.35 | 0 | 103.35 | Durgapur W/S Division |  | 60.13 | 0 | 0 | 0 | 60.13 | 58.47 | 0 | 0 | 0 | 58.47 | 56.57 | 75
66 | PURBA BARDHAMAN | SM/07805 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block | TSM/006666 | 8190592 | Retrofitting | SVS | GO2021004182PH | 07/01/2021 | 46.03 | 0 | 46.03 | Burdwan Division |  | 25.5 | 0 | 0 | 0 | 25.5 | 25.5 | 0 | 0 | 0 | 25.5 | 55.4 | 2
67 | PURBA BARDHAMAN | SM/08708 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007678 | 40020214 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 112.85 | 0 | 112.85 | Durgapur W/S Division |  | 86.21 | 0 | 0 | 0 | 86.21 | 86.21 | 0 | 0 | 0 | 86.21 | 76.4 | 100
68 | PURBA BARDHAMAN | SM/07806 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block | TSM/006665 | 8191783 | Retrofitting | SVS | GO2021004177PH | 07/01/2021 | 26.44 | 0 | 26.44 | Burdwan Division |  | 20.41 | 0 | 0 | 0 | 20.41 | 20.41 | 0 | 0 | 0 | 20.41 | 77.17 | 6
69 | PURBA BARDHAMAN | SM/08709 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. | TSM/007684 | 7942241 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 327.79 | 0 | 327.79 | Burdwan Division |  | 327.61 | 0 | 0 | 0 | 327.61 | 327.61 | 0 | 0 | 0 | 327.61 | 99.95 | 5
70 | PURBA BARDHAMAN | SM/07816 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block | TSM/006596 | 7734410 | Retrofitting | MVS | GO2021004353PH | 08/01/2021 | 109.06 | 0 | 109.06 | Burdwan Division |  | 90.65 | 0 | 0 | 0 | 90.65 | 86.04 | 0 | 0 | 0 | 86.04 | 78.9 | 47
71 | PURBA BARDHAMAN | SM/07868 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block | TSM/006689 | 6151105 | Retrofitting | MVS | GO2021004569PH | 14/01/2021 | 249.54 | 0 | 249.54 | Burdwan Division |  | 50.34 | 0 | 0 | 0 | 50.34 | 50.34 | 0 | 0 | 0 | 50.34 | 20.17 | 98
72 | PURBA BARDHAMAN | SM/07802 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block | TSM/006661 | 8190534 | Retrofitting | SVS | GO2021004192PH | 07/01/2021 | 28.42 | 0 | 28.42 | Burdwan Division |  | 25.53 | 0 | 0 | 0 | 25.53 | 25.53 | 0 | 0 | 0 | 25.53 | 89.82 | 2
73 | PURBA BARDHAMAN | SM/07811 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kasiara Piped Water Supply Scheme atMangolkote Block | TSM/006694 | 8198681 | Retrofitting | MVS | GO2021004146PH | 07/01/2021 | 65.25 | 0 | 65.25 | Burdwan Division |  | 65.25 | 0 | 0 | 0 | 65.25 | 65.25 | 0 | 0 | 0 | 65.25 | 100 | 73
74 | PURBA BARDHAMAN | SM/08710 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | TSM/007685 | 7942234 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 268.29 | 0 | 268.29 | Durgapur W/S Division |  | 159.13 | 0 | 17.62 | 0 | 176.75 | 158.64 | 0 | 17.62 | 0 | 176.26 | 65.7 | 10
75 | PURBA BARDHAMAN | SM/07820 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme | TSM/006627 | 8176653 | Retrofitting | MVS | GO2021004369PH | 08/01/2021 | 141.29 | 0 | 141.29 | Burdwan Division |  | 128.19 | 0 | 0 | 0 | 128.19 | 128.16 | 0 | 0 | 0 | 128.16 | 90.71 | 6
76 | PURBA BARDHAMAN | SM/07863 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme | TSM/006643 | 8195304 | Retrofitting | MVS | GO2021004572PH | 14/01/2021 | 125.64 | 0 | 125.64 | Burdwan Division |  | 78.16 | 0 | 0 | 0 | 78.16 | 78.16 | 0 | 0 | 0 | 78.16 | 62.21 | 6
77 | PURBA BARDHAMAN | SM/07827 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block | TSM/006664 | 8190439 | Retrofitting | MVS | GO2021004371PH | 08/01/2021 | 126.36 | 0 | 126.36 | Burdwan Division |  | 112.79 | 0 | 0 | 0 | 112.79 | 111.35 | 0 | 0 | 0 | 111.35 | 88.12 | 90
78 | PURBA BARDHAMAN | SM/08711 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. | TSM/007683 | 7942229 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 211.86 | 0 | 211.86 | Burdwan Division |  | 195.76 | 0 | 0 | 0 | 195.76 | 195.76 | 0 | 0 | 0 | 195.76 | 92.4 | 25
79 | PURBA BARDHAMAN | SM/07826 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block | TSM/006662 | 8199578 | Retrofitting | MVS | GO2021004356PH | 08/01/2021 | 104.89 | 0 | 104.89 | Burdwan Division |  | 41.08 | 0 | 0 | 0 | 41.08 | 41.08 | 0 | 0 | 0 | 41.08 | 39.16 | 58
80 | PURBA BARDHAMAN | SM/07779 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block | TSM/006590 | 7481719 | Retrofitting | MVS | GO2021004379PH | 08/01/2021 | 142.32 | 0 | 142.32 | Burdwan Division |  | 78.95 | 0 | 0 | 0 | 78.95 | 78.95 | 0 | 0 | 0 | 78.95 | 55.48 | 92
81 | PURBA BARDHAMAN | SM/07862 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme | TSM/006623 | 6165471 | Retrofitting | MVS | GO2021004578PH | 14/01/2021 | 136.5 | 0 | 136.5 | Burdwan Division |  | 100.12 | 0 | 0 | 0 | 100.12 | 100.12 | 0 | 0 | 0 | 100.12 | 73.35 | 90
82 | PURBA BARDHAMAN | SM/07867 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block | TSM/006668 | 6165473 | Retrofitting | MVS | GO2021004565PH | 14/01/2021 | 168.95 | 0 | 168.95 | Burdwan Division |  | 115.89 | 0 | 0 | 0 | 115.89 | 115.89 | 0 | 0 | 0 | 115.89 | 68.59 | 100
83 | PURBA BARDHAMAN | SM/07855 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block | TSM/006616 | 7326865 | Retrofitting | MVS | GO2021004389PH | 14/01/2021 | 184.84 | 0 | 184.84 | Burdwan Division |  | 184.75 | 0 | 0 | 0 | 184.75 | 184.75 | 0 | 0 | 0 | 184.75 | 99.95 | 65
84 | PURBA BARDHAMAN | SM/07799 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block | TSM/006601 | 7940851 | Retrofitting | MVS | GO2021004164PH | 07/01/2021 | 67.65 | 0 | 67.65 | Burdwan Division |  | 16.66 | 0 | 0 | 0 | 16.66 | 16.66 | 0 | 0 | 0 | 16.66 | 24.63 | 31
85 | PURBA BARDHAMAN | SM/07825 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme | TSM/006658 | 8190069 | Retrofitting | MVS | GO2021004358PH | 08/01/2021 | 121.31 | 0 | 121.31 | Burdwan Division |  | 101.18 | 0 | 13.71 | 0 | 114.89 | 100.92 | 0 | 13.71 | 0 | 114.63 | 94.49 | 2
86 | PURBA BARDHAMAN | SM/07859 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block | TSM/006606 | 8192616 | Retrofitting | SVS | GO2021004566PH | 14/01/2021 | 134.62 | 0 | 134.62 | Burdwan Division |  | 128.92 | 0 | 0 | 0 | 128.92 | 128.92 | 0 | 0 | 0 | 128.92 | 95.76 | 100
87 | PURBA BARDHAMAN | SM/07815 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block | TSM/006603 | 7940700 | Retrofitting | MVS | GO2021004360PH | 08/01/2021 | 162.76 | 0 | 162.76 | Burdwan Division |  | 140.72 | 0 | 0 | 0 | 140.72 | 140.72 | 0 | 0 | 0 | 140.72 | 86.46 | 25
88 | PURBA BARDHAMAN | SM/07822 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme | TSM/006624 | 8179178 | Retrofitting | MVS | GO2021004350PH | 08/01/2021 | 205.82 | 0 | 205.82 | Burdwan Division |  | 171.93 | 0 | 0 | 0 | 171.93 | 171.93 | 0 | 0 | 0 | 171.93 | 83.53 | 6
89 | PURBA BARDHAMAN | SM/07798 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block | TSM/006615 | 7940818 | Retrofitting | MVS | GO2021004198PH | 07/01/2021 | 88.92 | 0 | 88.92 | Burdwan Division |  | 88.84 | 0 | 0 | 0 | 88.84 | 88.84 | 0 | 0 | 0 | 88.84 | 99.91 | 31
90 | PURBA BARDHAMAN | SM/07864 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme | TSM/006652 | 8195522 | Retrofitting | MVS | GO2021004580PH | 14/01/2021 | 148.07 | 0 | 148.07 | Burdwan Division |  | 130.37 | 0 | 0 | 0 | 130.37 | 130.37 | 0 | 0 | 0 | 130.37 | 88.05 | 2
91 | PURBA BARDHAMAN | SM/07801 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme | TSM/006654 | 8199551 | Retrofitting | MVS | GO2021004172PH | 07/01/2021 | 96.93 | 0 | 96.93 | Burdwan Division |  | 64.78 | 0 | 0 | 0 | 64.78 | 64.75 | 0 | 0 | 0 | 64.75 | 66.8 | 2
92 | PURBA BARDHAMAN | SM/06972 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme | TSM/006224 | 8136290 | Retrofitting | MVS | GO2021002454PH | 09/11/2020 | 99.97 | 0 | 99.97 | Burdwan Division |  | 84.84 | 0 | 0 | 0 | 84.84 | 84.84 | 0 | 0 | 0 | 84.84 | 84.87 | 36
93 | PURBA BARDHAMAN | SM/06970 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme | TSM/006220 | 8136362 | Retrofitting | MVS | GO2021002452PH | 09/11/2020 | 70.91 | 0 | 70.91 | Burdwan Division |  | 63.23 | 0 | 0 | 0 | 63.23 | 63.23 | 0 | 0 | 0 | 63.23 | 89.18 | 43
94 | PURBA BARDHAMAN | SM/08713 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. | TSM/007679 | 40001470 | Retrofitting | SVS | GO2122002917PH | 03/09/2021 | 52.2 | 0 | 52.2 | Burdwan Division |  | 27.42 | 0 | 0 | 0 | 27.42 | 19.81 | 0 | 0 | 0 | 19.81 | 37.96 | 97
95 | PURBA BARDHAMAN | SM/07814 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block | TSM/006594 | 7401846 | Retrofitting | MVS | GO2021004361PH | 08/01/2021 | 191.46 | 0 | 191.46 | Burdwan Division |  | 85 | 0 | 0 | 0 | 85 | 85 | 0 | 0 | 0 | 85 | 44.4 | 53
96 | PURBA BARDHAMAN | SM/06967 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme | TSM/006205 | 8136331 | Retrofitting | SVS | GO2021002447PH | 09/11/2020 | 81.42 | 0 | 81.42 | Burdwan Division |  | 42.26 | 0 | 0 | 0 | 42.26 | 42.26 | 0 | 0 | 0 | 42.26 | 51.9 | 43
97 | PURBA BARDHAMAN | SM/08714 | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. | TSM/007682 | 6904391 | Retrofitting | MVS | GO2122002917PH | 03/09/2021 | 177.72 | 0 | 177.72 | Burdwan Division |  | 103.09 | 0 | 0 | 0 | 103.09 | 103.09 | 0 | 0 | 0 | 103.09 | 58.01 | 100
98 | PURBA BARDHAMAN | SM/07808 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | TSM/006677 | 7751710 | Retrofitting | MVS | GO2021004170PH | 07/01/2021 | 89.76 | 0 | 89.76 | Durgapur W/S Division |  | 68.7 | 0 | 0 | 0 | 68.7 | 68.7 | 0 | 0 | 0 | 68.7 | 76.54 | 10
99 | PURBA BARDHAMAN | SM/07807 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | TSM/006679 | 8186758 | Retrofitting | SVS | GO2021004162PH | 07/01/2021 | 62.17 | 0 | 62.17 | Durgapur W/S Division |  | 42.7 | 0 | 0 | 0 | 42.7 | 42.7 | 0 | 0 | 0 | 42.7 | 68.69 | 80
100 | PURBA BARDHAMAN | SM/06963 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme | TSM/006209 | 6132611 | Retrofitting | MVS | GO2021002448PH | 09/11/2020 | 99.85 | 0 | 99.85 | Burdwan Division |  | 99.85 | 0 | 0 | 0 | 99.85 | 99.21 | 0 | 0 | 0 | 99.21 | 99.36 | 96
101 | PURBA BARDHAMAN | SM/07865 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme | TSM/006651 | 7326847 | Retrofitting | MVS | GO2021004570PH | 14/01/2021 | 106.28 | 0 | 106.28 | Burdwan Division |  | 48.72 | 0 | 0 | 0 | 48.72 | 48.72 | 0 | 0 | 0 | 48.72 | 45.84 | 92
102 | PURBA BARDHAMAN | SM/07873 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAMKRISHNAPUR Piped Water Supply Scheme at Raina-I Block | TSM/006614 | 7940596 | Retrofitting | MVS | GO2021004743PH | 19/01/2021 | 47.08 | 0 | 47.08 | Burdwan Division |  | 35.45 | 0 | 0 | 0 | 35.45 | 35.45 | 0 | 0 | 0 | 35.45 | 75.3 | 25
103 | PURBA BARDHAMAN | SM/07778 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block | TSM/006609 | 7942278 | Retrofitting | MVS | GO2021004375PH | 08/01/2021 | 113.22 | 0 | 113.22 | Burdwan Division |  | 89.64 | 0 | 0 | 0 | 89.64 | 89.64 | 0 | 0 | 0 | 89.64 | 79.17 | 25
104 | PURBA BARDHAMAN | SM/07813 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block | TSM/006607 | 7755659 | Retrofitting | MVS | GO2021004364PH | 08/01/2021 | 139.08 | 0 | 139.08 | Burdwan Division |  | 76.55 | 0 | 0 | 0 | 76.55 | 76.11 | 0 | 0 | 0 | 76.11 | 54.73 | 67
105 | PURBA BARDHAMAN | SM/07828 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block | TSM/006687 | 8185968 | Retrofitting | MVS | GO2021004345PH | 08/01/2021 | 261 | 0 | 261 | Burdwan Division |  | 133.26 | 0 | 0 | 0 | 133.26 | 133.26 | 0 | 0 | 0 | 133.26 | 51.06 | 12
106 | PURBA BARDHAMAN | SM/07858 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block | TSM/006610 | 7942268 | Retrofitting | MVS | GO2021004579PH | 14/01/2021 | 205.59 | 0 | 205.59 | Burdwan Division |  | 191.4 | 0 | 0 | 0 | 191.4 | 191.39 | 0 | 0 | 0 | 191.39 | 93.09 | 36
107 | PURBA BARDHAMAN | SM/07856 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block | TSM/006608 | 7751696 | Retrofitting | MVS | GO2021004567PH | 14/01/2021 | 129.06 | 0 | 129.06 | Burdwan Division |  | 98.24 | 0 | 0 | 0 | 98.24 | 96.7 | 0 | 0 | 0 | 96.7 | 74.93 | 37
108 | PURBA BARDHAMAN | SM/07823 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme | TSM/006626 | 7326972 | Retrofitting | MVS | GO2021004351PH | 08/01/2021 | 151.83 | 0 | 151.83 | Burdwan Division |  | 64.35 | 0 | 0 | 0 | 64.35 | 64.35 | 0 | 0 | 0 | 64.35 | 42.38 | 71
109 | PURBA BARDHAMAN | SM/07809 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | TSM/006675 | 8186775 | Retrofitting | MVS | GO2021004168PH | 07/01/2021 | 69.73 | 0 | 69.73 | Durgapur W/S Division |  | 69.21 | 0 | 0 | 0 | 69.21 | 68.16 | 0 | 0 | 0 | 68.16 | 97.75 | 80
110 | PURBA BARDHAMAN | SM/07812 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block | TSM/006613 | 7734412 | Retrofitting | MVS | GO2021004370PH | 08/01/2021 | 116.95 | 0 | 116.95 | Burdwan Division |  | 58.56 | 0 | 0 | 0 | 58.56 | 58.29 | 0 | 0 | 0 | 58.29 | 49.84 | 59
111 | PURBA BARDHAMAN | SM/07810 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | TSM/006674 | 8189682 | Retrofitting | MVS | GO2021004167PH | 07/01/2021 | 83.84 | 0 | 83.84 | Durgapur W/S Division |  | 58.05 | 0 | 0 | 0 | 58.05 | 58.05 | 0 | 0 | 0 | 58.05 | 69.23 | 80
112 | PURBA BARDHAMAN | SM/07830 | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block | TSM/006673 | 6165462 | Retrofitting | MVS | GO2021004372PH | 08/01/2021 | 121.39 | 0 | 121.39 | Burdwan Division |  | 31.31 | 0 | 0 | 0 | 31.31 | 31.31 | 0 | 0 | 0 | 31.31 | 25.79 | 100
113 | PURBA BARDHAMAN | SM/07775 | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block | TSM/006599 | 7573238 | Retrofitting | MVS | GO2021004377PH | 08/01/2021 | 120.55 | 0 | 120.55 | Burdwan Division |  | 68.5 | 0 | 0 | 0 | 68.5 | 68.48 | 0 | 0 | 0 | 68.48 | 56.81 | 84
114 | PURBA BARDHAMAN | SM/12080 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. | TSM/013345 | 40028652 | Retrofitting | MVS | GO2223007002PH | 02/09/2022 | 26.74 | 0 | 26.74 | Burdwan Division |  | 17.18 | 0 | 0 | 0 | 17.18 | 17.18 | 0 | 0 | 0 | 17.18 | 64.25 | 95
115 | PURBA BARDHAMAN | SM/08101 | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block | TSM/006604 | 7368611 | Retrofitting | MVS | GO2021007291PH | 19/02/2021 | 402.29 | 0 | 402.29 | Burdwan Division |  | 166.98 | 0 | 0 | 0 | 166.98 | 166.98 | 0 | 0 | 0 | 166.98 | 41.51 | 16
116 | PURBA BARDHAMAN | SM/08102 | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme | TSM/006645 | 5429673 | Retrofitting | MVS | GO2021007288PH | 19/02/2021 | 489.24 | 0 | 489.24 | Burdwan Division |  | 187.96 | 0 | 0 | 0 | 187.96 | 187.96 | 0 | 0 | 0 | 187.96 | 38.42 | 96
117 | PURBA BARDHAMAN | SM/07556 | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme | TSM/006660 | 8178554 | Retrofitting | MVS | GO2021003971PH | 31/12/2020 | 52.23 | 0 | 52.23 | Burdwan Division |  | 32.18 | 0 | 0 | 0 | 32.18 | 32.08 | 0 | 0 | 0 | 32.08 | 61.42 | 6
118 | PURBA BARDHAMAN | SM/07547 | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme | TSM/006587 | 8189745 | Retrofitting | MVS | GO2021003955PH | 31/12/2020 | 41.6 | 0 | 41.6 | Durgapur W/S Division |  | 41.6 | 0 | 0 | 0 | 41.6 | 41.6 | 0 | 0 | 0 | 41.6 | 100 | 37
119 | PURBA BARDHAMAN | SM/07554 | Providing Functional Household Tap Connection (FHTC) under the command area of Chandutia Piped Water Supply Scheme | TSM/006650 | 8176606 | Retrofitting | MVS | GO2021003973PH | 31/12/2020 | 26.82 | 0 | 26.82 | Burdwan Division |  | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 18.64 | 25
120 | PURBA BARDHAMAN | SM/07545 | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme | TSM/006611 | 7755544 | Retrofitting | MVS | GO2021003959PH | 31/12/2020 | 73.51 | 0 | 73.51 | Burdwan Division |  | 53.04 | 0 | 0 | 0 | 53.04 | 52.98 | 0 | 0 | 0 | 52.98 | 72.08 | 56
121 | PURBA BARDHAMAN | SM/07548 | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | TSM/006589 | 7940716 | Retrofitting | MVS | GO2021003969PH | 31/12/2020 | 89.96 | 0 | 89.96 | Durgapur W/S Division |  | 70.03 | 0 | 0 | 0 | 70.03 | 70.03 | 0 | 0 | 0 | 70.03 | 77.85 | 75
122 | PURBA BARDHAMAN | SM/07549 | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme | TSM/006597 | 7751699 | Retrofitting | MVS | GO2021003967PH | 31/12/2020 | 82.44 | 0 | 82.44 | Burdwan Division |  | 34.32 | 0 | 0 | 0 | 34.32 | 29.05 | 0 | 0 | 0 | 29.05 | 35.23 | 59
123 | PURBA BARDHAMAN | SM/07544 | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme | TSM/006620 | 7392433 | Retrofitting | MVS | GO2021003970PH | 31/12/2020 | 73.32 | 0 | 73.32 | Burdwan Division |  | 73.17 | 0 | 0 | 0 | 73.17 | 73.12 | 0 | 0 | 0 | 73.12 | 99.72 | 38
124 | PURBA BARDHAMAN | SM/07550 | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme | TSM/006595 | 7940703 | Retrofitting | MVS | GO2021003956PH | 31/12/2020 | 94.55 | 0 | 94.55 | Burdwan Division |  | 93.34 | 0 | 0.62 | 0 | 93.95 | 93.34 | 0 | 0.62 | 0 | 93.95 | 99.37 | 5
125 | PURBA BARDHAMAN | SM/07552 | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme | TSM/006605 | 8228981 | Retrofitting | SVS | GO2021003958PH | 31/12/2020 | 92.04 | 0 | 92.04 | Burdwan Division |  | 70.62 | 0 | 0 | 0 | 70.62 | 70.62 | 0 | 0 | 0 | 70.62 | 76.72 | 25
126 | PURBA BARDHAMAN | SM/07555 | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme | TSM/006653 | 8193904 | Retrofitting | SVS | GO2021003966PH | 31/12/2020 | 16.96 | 0 | 16.96 | Burdwan Division |  | 13.75 | 0 | 0 | 0 | 13.75 | 13.75 | 0 | 0 | 0 | 13.75 | 81.09 | 95
127 | PURBA BARDHAMAN | SM/07557 | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme | TSM/006657 | 6904398 | Retrofitting | MVS | GO2021003963PH | 31/12/2020 | 74.73 | 0 | 74.73 | Burdwan Division |  | 40.03 | 0 | 0 | 0 | 40.03 | 40.03 | 0 | 0 | 0 | 40.03 | 53.57 | 81
128 | PURBA BARDHAMAN | SM/07551 | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme | TSM/006612 | 7942250 | Retrofitting | MVS | GO2021003962PH | 31/12/2020 | 57.39 | 0 | 57.39 | Burdwan Division |  | 48.31 | 0 | 0 | 0 | 48.31 | 48.31 | 0 | 0 | 0 | 48.31 | 84.19 | 31
129 | PURBA BARDHAMAN | SM/07553 | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme | TSM/006649 | 8176881 | Retrofitting | MVS | GO2021003972PH | 31/12/2020 | 99.79 | 0 | 99.79 | Burdwan Division |  | 97.35 | 0 | 0 | 0 | 97.35 | 97.35 | 0 | 0 | 0 | 97.35 | 97.56 | 25
130 | PURBA BARDHAMAN | SM/07546 | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme | TSM/006621 | 7573232 | Retrofitting | MVS | GO2021003965PH | 31/12/2020 | 95.87 | 0 | 95.87 | Burdwan Division |  | 67.22 | 0 | 0 | 0 | 67.22 | 67.22 | 0 | 0 | 0 | 67.22 | 70.12 | 39
131 | PURBA BARDHAMAN | SM/13043 | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B | TSM/010059 | 40027343 | Retrofitting | SVS | GO2223008464PH | 29/09/2022 | 109.18 | 0 | 109.18 | Burdwan Division |  | 40.76 | 0 | 0 | 0 | 40.76 | 40.76 | 0 | 0 | 0 | 40.76 | 37.33 | 95
132 | PURBA BARDHAMAN | SM/15195 | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | TSM/018214 | 40046340 | Retrofitting | MVS | GO2223013509PH | 08/02/2023 | 107.27 | 0 | 107.27 | Burdwan Division |  | 64.64 | 0 | 0 | 0 | 64.64 | 64.64 | 0 | 0 | 0 | 64.64 | 60.26
133 | PURBA BARDHAMAN | SM/16488 | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MUGURA | TSM/017721 | 40063043 | Retrofitting | MVS | GO2223015180PH | 02/03/2023 | 39.97 | 0 | 39.97 | Burdwan Division |  | 19.33 | 0 | 0 | 0 | 19.33 | 19.33 | 0 | 0 | 0 | 19.33 | 48.38
134 | PURBA BARDHAMAN | SM/16489 | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL | TSM/017973 | 40046454 | Retrofitting | MVS | GO2223015179PH | 02/03/2023 | 57.12 | 0 | 57.12 | Burdwan Division |  | 27.95 | 0 | 0 | 0 | 27.95 | 27.95 | 0 | 0 | 0 | 27.95 | 48.94 | 95
135 | PURBA BARDHAMAN | SM/16290 | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | TSM/019604 | 40053330 | Retrofitting | MVS | GO2223014770PH | 23/02/2023 | 167.64 | 0 | 167.64 | Burdwan Division |  | 57.89 | 0 | 0 | 0 | 57.89 | 57.89 | 0 | 0 | 0 | 57.89 | 34.54 | 75
136 | PURBA BARDHAMAN | SM/16289 | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C | TSM/019605 | 40053391 | Retrofitting | MVS | GO2223014774PH | 23/02/2023 | 94.64 | 0 | 94.64 | Burdwan Division |  | 35.74 | 0 | 0 | 0 | 35.74 | 35.74 | 0 | 0 | 0 | 35.74 | 37.76 | 95
137 | PURBA BARDHAMAN | SM/16349 | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | TSM/019630 | 40062735 | Retrofitting | MVS | GO2223014767PH | 23/02/2023 | 126.77 | 0 | 126.77 | Burdwan Division |  | 84.19 | 0 | 0 | 0 | 84.19 | 84.19 | 0 | 0 | 0 | 84.19 | 66.41
138 | PURBA BARDHAMAN | SM/10055 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | TSM/009277 | 40002923 | Retrofitting | MVS | GO2122008723PH | 25/01/2022 | 114.87 | 0 | 114.87 | Durgapur W/S Division | Central Mechanical Division | 49.18 | 0 | 0 | 0 | 49.18 | 49.18 | 0 | 0 | 0 | 49.18 | 42.82 | 95
139 | PURBA BARDHAMAN | SM/08105 | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman | TSM/006669 | 6348430 | Retrofitting | MVS | GO2021007284PH | 19/02/2021 | 311.16 | 0 | 311.16 | Burdwan Division |  | 193.93 | 0 | 0 | 0 | 193.93 | 193.93 | 0 | 0 | 0 | 193.93 | 62.33 | 90
140 | PURBA BARDHAMAN | SM/08104 | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman | TSM/006656 | 8207391 | Retrofitting | MVS | GO2021007285PH | 19/02/2021 | 365.23 | 0 | 365.23 | Burdwan Division |  | 238.57 | 0 | 0 | 0 | 238.57 | 238.56 | 0 | 0 | 0 | 238.56 | 65.32 | 95
141 | PURBA BARDHAMAN | SM/08103 | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman | TSM/006655 | 8207373 | Retrofitting | SVS | GO2021007287PH | 19/02/2021 | 331.6 | 0 | 331.6 | Burdwan Division |  | 305.33 | 0 | 0 | 0 | 305.33 | 305.33 | 0 | 0 | 0 | 305.33 | 92.08 | 95
142 | PURBA BARDHAMAN | SM/08033 | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar | TSM/006696 | 8200846 | Retrofitting | MVS | GO2021005350PH | 25/01/2021 | 1100.67 | 0 | 1100.67 | Burdwan Division |  | 403.96 | 0 | 0 | 8.31 | 412.26 | 403.59 | 0 | 0 | 8.31 | 411.9 | 37.42 | 6
143 | PURBA BARDHAMAN | SM/08034 | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | TSM/006698 | 8201043 | Retrofitting | MVS | GO2021005352PH | 25/01/2021 | 1050.88 | 75.2 | 1126.08 | Durgapur W/S Division | Central Mechanical Division | 462.64 | 10.64 | 0 | 0 | 473.28 | 461.88 | 0 | 0 | 0 | 461.88 | 41.02 | 80
144 | PURBA BARDHAMAN | SM/08031 | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme | TSM/006628 | 6260076 | Retrofitting | MVS | GO2021005347PH | 25/01/2021 | 301.39 | 0 | 301.39 | Burdwan Division |  | 236.43 | 0 | 5.5 | 0 | 241.93 | 236.43 | 0 | 5.5 | 0 | 241.93 | 80.27 | 93
Total | [9 empty] | 21990.81 | 75.2 | 22066.01 |  |  | 13938.47 | 10.64 | 98.29 | 15.83 | 14063.23 | 13824.9 | 0 | 98.29 | 15.83 | 13939.02 | 63.17