## JJM Schemes Financial Status (H
JJM Schemes Financial Status (HOOGHLY) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | HOOGHLY | SM/09207 | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008681 | 40015553 | Augmentation | MVS | GO2122004728PH | 30/10/2021 | 35.42 | 0 | 35.42 | Hooghly Division |  | 31 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 31 | 87.53 | 90
2 | HOOGHLY | SM/09208 | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008680 | 40015552 | Augmentation | MVS | GO2122004728PH | 30/10/2021 | 35.42 | 0 | 35.42 | Hooghly Division |  | 6.15 | 0 | 0 | 0 | 6.15 | 6.15 | 0 | 0 | 0 | 6.15 | 17.37 | 20
3 | HOOGHLY | SM/18644 | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK | TSM/019199 | 40039086 | Augmentation | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1987.77 | 111.82 | 2099.59 | Hooghly Division | Electrical Division | 24.5 | 29.68 | 69.13 | 0 | 123.31 | 24.5 | 29.68 | 69.13 | 0 | 123.31 | 5.87
4 | HOOGHLY | SM/18770 | Augmentation of Balipur Water Supply Scheme | TSM/014800 | 40033269 | Augmentation | MVS | 2562/PHE-28011/76/2023-ESTT CELL-Dept. of PHE | 25/08/2023 | 1097.18 | 55.62 | 1152.8 | Hooghly Division | Electrical Division | 383.53 | 31.88 | 3.08 | 0 | 418.48 | 383.53 | 31.88 | 3.08 | 0 | 418.48 | 36.3 | 65
5 | HOOGHLY | SM/10005 | Augmentation of Champadanga Water Supply Scheme | TSM/009191 | 40012787 | Augmentation | MVS | GO2122006985PH | 20/12/2021 | 1476.93 | 55.62 | 1532.55 | Hooghly Division | Electrical Division | 938.36 | 28.91 | 155.78 | 23.79 | 1146.84 | 936.49 | 28.91 | 155.78 | 23.79 | 1144.97 | 74.71 | 78
6 | HOOGHLY | SM/10467 | Augmentation of Chanparai Water Supply Scheme | TSM/009960 | 40013062 | Augmentation | MVS | GO2223000208PH | 13/04/2022 | 386.65 | 27.81 | 414.46 | Hooghly Division | Electrical Division | 256.52 | 13.57 | 20.44 | 0 | 290.53 | 256.52 | 13.57 | 20.44 | 0 | 290.53 | 70.1 | 75
7 | HOOGHLY | SM/15788 | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | TSM/020227 | 40039165 | Augmentation | MVS | GO2223014269PH | 20/02/2023 | 280.99 | 27.81 | 308.8 | Hooghly Division | Electrical Division | 0 | 0 | 0.31 | 0 | 0.31 | 0 | 0 | 0.31 | 0 | 0.31 | 0.1 | 35
8 | HOOGHLY | SM/18670 | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | TSM/014859 | 40032795 | Augmentation | MVS | 2239/PHE-28011/76/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1048.73 | 83.43 | 1132.16 | Hooghly Division | Electrical Division | 113.96 | 6.98 | 3.29 | 0 | 124.23 | 113.96 | 6.98 | 3.29 | 0 | 124.23 | 10.97
9 | HOOGHLY | SM/15787 | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | TSM/020224 | 40042580 | Augmentation | MVS | GO2223014276PH | 20/02/2023 | 413.65 | 27.81 | 441.46 | Hooghly Division | Electrical Division | 244.46 | 3.58 | 61 | 0 | 309.05 | 244.46 | 3.58 | 61 | 0 | 309.05 | 70.01 | 70
10 | HOOGHLY | SM/16351 | Augmentation of Gobindapur Water Supply Scheme | TSM/014860 | 40033260 | Augmentation | MVS | GO2223014970PH | 28/02/2023 | 303.38 | 27.81 | 331.19 | Hooghly Division | Electrical Division | 200.87 | 14.83 | 1.39 | 0 | 217.08 | 200.87 | 14.83 | 1.39 | 0 | 217.08 | 65.55 | 80
11 | HOOGHLY | SM/12228 | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | TSM/014829 | 40033118 | Augmentation | MVS | GO2223007106PH | 07/09/2022 | 686.37 | 55.62 | 741.99 | Hooghly Division | Electrical Division | 252.15 | 26.91 | 19.81 | 0 | 298.86 | 252.15 | 26.91 | 19.81 | 0 | 298.86 | 40.28 | 45
12 | HOOGHLY | SM/11464 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011268 | 40016297 | Augmentation | MVS | GO2223004994PH | 12/07/2022 | 314.16 | 55.62 | 369.78 | Hooghly Division | Electrical Division | 75.38 | 22.37 | 55.42 | 0 | 153.18 | 75.38 | 22.37 | 55.42 | 0 | 153.18 | 41.42 | 60
13 | HOOGHLY | SM/11463 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011273 | 40017046 | Augmentation | MVS | GO2223004989PH | 12/07/2022 | 919.3 | 55.62 | 974.92 | Hooghly Division | Electrical Division | 360.98 | 33.09 | 211.95 | 18.99 | 625.01 | 360.98 | 33.09 | 211.95 | 18.99 | 625.01 | 64.11 | 60
14 | HOOGHLY | SM/11461 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011261 | 40016288 | Augmentation | MVS | GO2223004987PH | 12/07/2022 | 273.89 | 55.62 | 329.51 | Hooghly Division | Electrical Division | 160.05 | 27.67 | 37.94 | 14.12 | 239.78 | 160.05 | 27.67 | 37.94 | 14.12 | 239.78 | 72.77 | 86
15 | HOOGHLY | SM/11468 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011249 | 40016348 | Augmentation | MVS | GO2223004993PH | 12/07/2022 | 625.73 | 83.43 | 709.16 | Hooghly Division | Electrical Division | 367.89 | 34.45 | 44.74 | 20.24 | 467.31 | 367.89 | 34.45 | 44.74 | 20.24 | 467.31 | 65.9 | 80
16 | HOOGHLY | SM/11467 | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | TSM/011255 | 40016352 | Augmentation | SVS | GO2223004992PH | 12/07/2022 | 524.93 | 27.81 | 552.74 | Hooghly Division | Electrical Division | 327.44 | 24.42 | 17.86 | 9.62 | 379.33 | 327.44 | 24.42 | 17.86 | 9.62 | 379.33 | 68.63 | 90
17 | HOOGHLY | SM/11462 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE | TSM/011280 | 40016292 | Augmentation | MVS | GO2223004988PH | 12/07/2022 | 709.7 | 55.62 | 765.32 | Hooghly Division | Electrical Division | 371.98 | 11.4 | 34.93 | 18.83 | 437.14 | 371.98 | 11.4 | 34.93 | 18.83 | 437.14 | 57.12 | 60
18 | HOOGHLY | SM/14040 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI | TSM/011881 | 40030427 | Augmentation | MVS | GO2223010771PH | 12/12/2022 | 1154.24 | 111.24 | 1265.48 | Hooghly Division | Electrical Division | 582.08 | 59.4 | 83.27 | 0 | 724.74 | 580.09 | 57.36 | 83.27 | 0 | 720.72 | 56.95 | 15
19 | HOOGHLY | SM/11868 | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR | TSM/011915 | 40019626 | Augmentation | MVS | GO2223006409PH | 17/08/2022 | 781.8 | 55.62 | 837.42 | Hooghly Division | Electrical Division | 445.36 | 30.85 | 38.65 | 0 | 514.86 | 445.36 | 30.85 | 38.65 | 0 | 514.86 | 61.48 | 60
20 | HOOGHLY | SM/09692 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | TSM/008348 | 40008802 | Augmentation | MVS | GO2122005911PH | 25/11/2021 | 444.24 | 0 | 444.24 | Hooghly Division |  | 296.95 | 0 | 5.48 | 10.83 | 313.26 | 296.95 | 0 | 5.48 | 10.83 | 313.26 | 70.52 | 65
21 | HOOGHLY | SM/09691 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | TSM/008347 | 40008434 | Augmentation | MVS | GO2122005911PH | 25/11/2021 | 541.55 | 0 | 541.55 | Hooghly Division |  | 320.64 | 0 | 37.65 | 0 | 358.29 | 320.64 | 0 | 37.65 | 0 | 358.29 | 66.16 | 75
22 | HOOGHLY | SM/10341 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. | TSM/008350 | 40012098 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1037.36 | 0 | 1037.36 | Hooghly Division | Electrical Division | 576.94 | 0 | 82.16 | 40.98 | 700.09 | 576.94 | 0 | 82.16 | 40.98 | 700.09 | 67.49 | 90
23 | HOOGHLY | SM/10340 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. | TSM/008349 | 40012138 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1822.88 | 0 | 1822.88 | Hooghly Division |  | 1056.24 | 38.52 | 112.63 | 13.75 | 1221.14 | 1056.24 | 38.52 | 112.63 | 13.75 | 1221.14 | 66.99 | 75
24 | HOOGHLY | SM/09690 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | TSM/008331 | 40008660 | Augmentation | MVS | GO2122005912PH | 25/11/2021 | 350.38 | 0 | 350.38 | Hooghly Division |  | 233.89 | 0 | 47.73 | 0 | 281.62 | 233.89 | 0 | 47.73 | 0 | 281.62 | 80.37 | 90
25 | HOOGHLY | SM/09698 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | TSM/008329 | 40008639 | Augmentation | MVS | GO2122005910PH | 25/11/2021 | 592.7 | 27.81 | 620.51 | Hooghly Division | Electrical Division | 220.08 | 20.76 | 23.57 | 0 | 264.41 | 220.08 | 20.76 | 23.57 | 0 | 264.41 | 42.61 | 85
26 | HOOGHLY | SM/11867 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN | TSM/011916 | 40019539 | Augmentation | MVS | GO2223006445PH | 17/08/2022 | 391.23 | 55.62 | 446.85 | Hooghly Division | Electrical Division | 333.73 | 38.92 | 6.04 | 0 | 378.69 | 333.73 | 38.92 | 6.04 | 0 | 378.69 | 84.75 | 80
27 | HOOGHLY | SM/12369 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR | TSM/009964 | 40032501 | Augmentation | MVS | GO2223007582PH | 13/09/2022 | 3422.29 | 333.72 | 3756.01 | Hooghly Division | Electrical Division | 838.98 | 151.76 | 251.86 | 0 | 1242.6 | 838.98 | 151.76 | 251.86 | 0 | 1242.6 | 33.08 | 45
28 | HOOGHLY | SM/11466 | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | TSM/011236 | 40021824 | Augmentation | SVS | GO2223004991PH | 12/07/2022 | 534.88 | 55.62 | 590.5 | Hooghly Division | Electrical Division | 273.18 | 37.18 | 11.93 | 0 | 322.29 | 273.18 | 37.18 | 11.93 | 0 | 322.29 | 54.58 | 80
29 | HOOGHLY | SM/10338 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. | TSM/008325 | 40011612 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1195.42 | 111.24 | 1306.66 | Hooghly Division | Electrical Division | 572.87 | 101.8 | 43.07 | 33.69 | 751.43 | 572.87 | 101.8 | 43.07 | 33.69 | 751.43 | 57.51 | 85
30 | HOOGHLY | SM/11924 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME | TSM/011627 | 40019519 | Augmentation | MVS | GO2223006611PH | 22/08/2022 | 721.01 | 27.81 | 748.82 | Hooghly Division | Electrical Division | 415.11 | 23.71 | 48.4 | 0 | 487.22 | 415.11 | 23.71 | 48.4 | 0 | 487.22 | 65.07 | 65
31 | HOOGHLY | SM/11166 | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali | TSM/010115 | 40014617 | Augmentation | MVS | GO2223003785PH | 02/06/2022 | 868.02 | 27.81 | 895.83 | Hooghly Division | Electrical Division | 394.49 | 27.79 | 189.22 | 0 | 611.5 | 394.49 | 27.79 | 189.22 | 0 | 611.5 | 68.26 | 70
32 | HOOGHLY | SM/15891 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | TSM/011632 | 40037190 | Augmentation | MVS | GO2223014281PH | 20/02/2023 | 95.22 | 56.53 | 151.75 | Hooghly Division | Electrical Division | 58.18 | 40.91 | 32.88 | 0 | 131.97 | 58.18 | 40.91 | 32.88 | 0 | 131.97 | 86.97 | 90
33 | HOOGHLY | SM/09695 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | TSM/008327 | 40007373 | Augmentation | MVS | GO2122005907PH | 25/11/2021 | 826.24 | 27.81 | 854.05 | Hooghly Division | Electrical Division | 532.7 | 24.13 | 88.16 | 0 | 644.99 | 532.14 | 24.13 | 88.16 | 0 | 644.43 | 75.46 | 85
34 | HOOGHLY | SM/10339 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. | TSM/008330 | 40011288 | Augmentation | MVS | GO2122010687PH | 14/03/2022 | 1297.28 | 55.62 | 1352.9 | Hooghly Division | Electrical Division | 465.71 | 39.01 | 79.09 | 23.93 | 607.74 | 461.51 | 39.01 | 79.09 | 23.93 | 603.54 | 44.61 | 50
35 | HOOGHLY | SM/09688 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | TSM/008326 | 40008251 | Augmentation | SVS | GO2122005912PH | 25/11/2021 | 278.45 | 0 | 278.45 | Hooghly Division |  | 242.94 | 0 | 11.24 | 0 | 254.18 | 242.94 | 0 | 11.24 | 0 | 254.18 | 91.28 | 95
36 | HOOGHLY | SM/18397 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | TSM/009649 | 40032742 | Augmentation | MVS | 1846/PHE-28011/96/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 3602.14 | 444.96 | 4047.1 | Hooghly Division | Electrical Division | 1106.61 | 130.8 | 0 | 0 | 1237.42 | 1093.12 | 130.8 | 0 | 0 | 1223.93 | 30.24 | 45
37 | HOOGHLY | SM/09790 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. | TSM/008323 | 40010372 | Augmentation | MVS | GO2122006244PH | 30/11/2021 | 508.53 | 0 | 508.53 | Hooghly Division |  | 218.12 | 0 | 40.32 | 0 | 258.44 | 218.12 | 0 | 40.32 | 0 | 258.44 | 50.82 | 70
38 | HOOGHLY | SM/09689 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | TSM/008328 | 40007487 | Augmentation | SVS | GO2122005912PH | 25/11/2021 | 333.93 | 0 | 333.93 | Hooghly Division |  | 212.85 | 0 | 28.96 | 0 | 241.82 | 212.83 | 0 | 28.96 | 0 | 241.79 | 72.41 | 85
39 | HOOGHLY | SM/11167 | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur | TSM/010116 | 40014614 | Augmentation | SVS | GO2223003786PH | 02/06/2022 | 466.76 | 27.81 | 494.57 | Hooghly Division | Electrical Division | 171.57 | 15.15 | 51.92 | 0 | 238.65 | 171.57 | 15.15 | 51.92 | 0 | 238.65 | 48.25 | 30
40 | HOOGHLY | SM/11465 | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. | TSM/011257 | 40016266 | Augmentation | SVS | GO2223004990PH | 12/07/2022 | 279.54 | 27.81 | 307.35 | Hooghly Division | Electrical Division | 180.08 | 17.86 | 17.06 | 0 | 215 | 180.08 | 17.86 | 17.06 | 0 | 215 | 69.95 | 85
41 | HOOGHLY | SM/09694 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | TSM/008324 | 40007155 | Augmentation | SVS | GO2122005908PH | 25/11/2021 | 716.39 | 55.62 | 772.01 | Hooghly Division | Electrical Division | 516.66 | 45.48 | 20.29 | 10.33 | 592.77 | 506.05 | 45.48 | 20.29 | 10.33 | 582.16 | 75.41 | 80
42 | HOOGHLY | SM/09693 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | TSM/008322 | 40006898 | Augmentation | MVS | GO2122005909PH | 25/11/2021 | 587.82 | 27.81 | 615.63 | Hooghly Division | Electrical Division | 416.54 | 26.1 | 56.28 | 22.59 | 521.51 | 415.87 | 26.1 | 56.28 | 22.59 | 520.85 | 84.6 | 85
43 | HOOGHLY | SM/11866 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | TSM/011917 | 40019521 | Augmentation | MVS | GO2223006401PH | 17/08/2022 | 634.18 | 55.62 | 689.8 | Hooghly Division | Electrical Division | 398.8 | 51.67 | 78.28 | 0 | 528.76 | 398.8 | 51.67 | 78.28 | 0 | 528.76 | 76.65 | 70
44 | HOOGHLY | SM/13349 | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR | TSM/009963 | 40027496 | Augmentation | MVS | GO2223008971PH | 19/10/2022 | 1196.03 | 139.05 | 1335.08 | Hooghly Division | Electrical Division | 529.97 | 70.57 | 20.42 | 0 | 620.96 | 529.97 | 70.57 | 20.42 | 0 | 620.96 | 46.51 | 50
45 | HOOGHLY | SM/09984 | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | TSM/009193 | 40012896 | Augmentation | MVS | GO2122006876PH | 16/12/2021 | 1251.54 | 83.43 | 1334.97 | Hooghly Division | Electrical Division | 708.31 | 53.29 | 433.57 | 30.45 | 1225.62 | 708.27 | 53.29 | 433.57 | 30.45 | 1225.58 | 91.81 | 92
46 | HOOGHLY | SM/09983 | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA | TSM/009209 | 40012800 | Augmentation | MVS | GO2122006876PH | 16/12/2021 | 1207.55 | 55.62 | 1263.17 | Hooghly Division | Electrical Division | 726.98 | 25.16 | 133 | 0 | 885.14 | 726.98 | 25.16 | 133 | 0 | 885.14 | 70.07 | 80
47 | HOOGHLY | SM/10004 | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR | TSM/009196 | 40017964 | Augmentation | MVS | GO2122006985PH | 20/12/2021 | 1498.34 | 55.62 | 1553.96 | Hooghly Division | Electrical Division | 827.49 | 0 | 119.79 | 0 | 947.29 | 824.49 | 0 | 119.79 | 0 | 944.29 | 60.77 | 80
48 | HOOGHLY | SM/12370 | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR | TSM/009198 | 40031733 | Augmentation | MVS | GO2223007587PH | 13/09/2022 | 1185.08 | 83.43 | 1268.51 | Hooghly Division | Electrical Division | 547.08 | 38.72 | 246.81 | 0 | 832.6 | 547.08 | 38.72 | 246.81 | 0 | 832.6 | 65.64 | 65
49 | HOOGHLY | SM/09982 | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | TSM/009212 | 40012791 | Augmentation | MVS | GO2122006876PH | 16/12/2021 | 1398.41 | 83.43 | 1481.84 | Hooghly Division | Electrical Division | 1033.87 | 35.42 | 47.85 | 0 | 1117.14 | 1033.87 | 35.42 | 47.85 | 0 | 1117.14 | 75.39 | 80
50 | HOOGHLY | SM/10022 | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR | TSM/009210 | 40010480 | Augmentation | MVS | GO2122007890PH | 05/01/2022 | 2139.27 | 111.24 | 2250.51 | Hooghly Division | Electrical Division | 1471.6 | 67.71 | 256.74 | 0 | 1796.05 | 1471.6 | 67.71 | 256.74 | 0 | 1796.05 | 79.81 | 75
51 | HOOGHLY | SM/09791 | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR | TSM/009205 | 40014416 | Augmentation | MVS | GO2122006243PH | 30/11/2021 | 829.8 | 55.62 | 885.42 | Hooghly Division | Electrical Division | 474.74 | 26.03 | 104.61 | 20.63 | 626.01 | 474.74 | 26.03 | 104.61 | 20.63 | 626.01 | 70.7 | 70
52 | HOOGHLY | SM/16119 | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/020424 | 40053142 | Augmentation | MVS | GO2223014675PH | 22/02/2023 | 526.83 | 31.21 | 558.04 | Hooghly Division | Electrical Division | 131.11 | 20.2 | 1.23 | 0 | 152.54 | 131.11 | 20.2 | 1.23 | 0 | 152.54 | 27.33 | 30
53 | HOOGHLY | SM/15243 | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016236 | 40032891 | Augmentation | MVS | GO2223013437PH | 07/02/2023 | 426.46 | 55.91 | 482.37 | Hooghly Division | Electrical Division | 227.06 | 10.41 | 37.48 | 0 | 274.95 | 227.06 | 10.41 | 37.48 | 0 | 274.95 | 57 | 60
54 | HOOGHLY | SM/18339 | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | TSM/014834 | 40033264 | Augmentation | MVS | 1736/PHE-28011/28/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 996.6 | 55.62 | 1052.22 | Hooghly Division | Electrical Division | 488.05 | 30.94 | 24.04 | 0 | 543.04 | 488.05 | 30.94 | 24.04 | 0 | 543.04 | 51.61 | 70
55 | HOOGHLY | SM/16564 | Augmentation of Kulteghori Piped Water Supply Scheme | TSM/015885 | 40032551 | Augmentation | MVS | GO2223015499PH | 10/03/2023 | 32.83 | 26.27 | 59.1 | Hooghly Division | Electrical Division | 1.95 | 24.36 | 0 | 0 | 26.31 | 1.95 | 24.36 | 0 | 0 | 26.31 | 44.52 | 40
56 | HOOGHLY | SM/10451 | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME | TSM/009987 | 40013122 | Augmentation | MVS | GO2223000189PH | 12/04/2022 | 933.74 | 55.62 | 989.36 | Hooghly Division | Electrical Division | 430.17 | 31.81 | 92.41 | 0 | 554.4 | 430.17 | 31.81 | 92.41 | 0 | 554.4 | 56.04 | 55
57 | HOOGHLY | SM/09604 | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008678 | 40029551 | Augmentation | SVS | GO2122005740PH | 23/11/2021 | 16.13 | 27.81 | 43.94 | Hooghly Division | Electrical Division | 0 | 3.06 | 0 | 11.36 | 14.42 | 0 | 3.06 | 0 | 11.36 | 14.42 | 32.82 | 35
58 | HOOGHLY | SM/16120 | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | TSM/020412 | 40059492 | Augmentation | MVS | GO2223014673PH | 22/02/2023 | 390.1 | 27.81 | 417.91 | Hooghly Division | Electrical Division | 176.31 | 13.87 | 17.17 | 0 | 207.34 | 176.31 | 13.87 | 17.17 | 0 | 207.34 | 49.61 | 80
59 | HOOGHLY | SM/18645 | Augmentation Of Piped Water Supply Scheme For KHANAKUL | TSM/017854 | 40037751 | Augmentation | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1144.5 | 55.62 | 1200.12 | Hooghly Division | Electrical Division | 84.61 | 7.74 | 31.5 | 0 | 123.85 | 83.01 | 7.74 | 31.5 | 0 | 122.25 | 10.19 | 35
60 | HOOGHLY | SM/18643 | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | TSM/017860 | 40042889 | Augmentation | MVS | 2169/PHE-28011/82/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1092.79 | 55.62 | 1148.41 | Hooghly Division | Electrical Division | 180.61 | 9.2 | 39.87 | 0 | 229.69 | 180.61 | 9.2 | 39.87 | 0 | 229.69 | 20 | 35
61 | HOOGHLY | SM/10468 | Augmentation of Polba Water Supply Scheme | TSM/009961 | 40019604 | Augmentation | MVS | GO2223000209PH | 13/04/2022 | 908.02 | 55.62 | 963.64 | Hooghly Division | Electrical Division | 709.3 | 53.98 | 40.33 | 0 | 803.61 | 704.14 | 53.98 | 40.33 | 0 | 798.45 | 82.86 | 85
62 | HOOGHLY | SM/13348 | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME | TSM/009962 | 40027555 | Augmentation | MVS | GO2223008972PH | 19/10/2022 | 1035.99 | 55.62 | 1091.61 | Hooghly Division | Electrical Division | 718.53 | 30.56 | 69.6 | 0 | 818.7 | 718.53 | 30.56 | 69.6 | 0 | 818.7 | 75 | 75
63 | HOOGHLY | SM/11969 | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | TSM/009988 | 40024123 | Augmentation | MVS | GO2223006753PH | 29/08/2022 | 984.79 | 111.24 | 1096.03 | Hooghly Division | Electrical Division | 425.43 | 66.97 | 90.4 | 10.04 | 592.84 | 424.85 | 66.97 | 90.4 | 10.04 | 592.25 | 54.04 | 55
64 | HOOGHLY | SM/09516 | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008674 | 40014417 | Augmentation | MVS | GO2122005586PH | 19/11/2021 | 16.13 | 27.81 | 43.94 | Hooghly Division | Electrical Division | 4.04 | 19.92 | 0 | 0 | 23.95 | 4.04 | 19.92 | 0 | 0 | 23.95 | 54.52 | 60
65 | HOOGHLY | SM/09517 | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | TSM/008677 | 40014432 | Augmentation | MVS | GO2122005586PH | 19/11/2021 | 16.13 | 27.81 | 43.94 | Hooghly Division | Electrical Division | 7.73 | 25.32 | 0 | 0 | 33.05 | 7.73 | 25.32 | 0 | 0 | 33.05 | 75.22 | 80
66 | HOOGHLY | SM/10023 | Augmentation of Salepur-Duttapur Water Supply Scheme | TSM/009194 | 40009723 | Augmentation | MVS | GO2122007890PH | 05/01/2022 | 1404.39 | 55.62 | 1460.01 | Hooghly Division | Electrical Division | 963.06 | 27.61 | 86.18 | 0 | 1076.86 | 963.06 | 27.61 | 86.18 | 0 | 1076.86 | 73.76 | 80
67 | HOOGHLY | SM/18347 | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | TSM/015380 | 40032993 | Augmentation | MVS | 1738/PHE-28011/73/2023-ESTT CELL-Dept. of PHE | 04/07/2023 | 936.08 | 111.24 | 1047.32 | Hooghly Division | Electrical Division | 247.41 | 33.75 | 32.99 | 0 | 314.16 | 247.41 | 33.75 | 32.99 | 0 | 314.16 | 30 | 40
68 | HOOGHLY | SM/19036 | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | TSM/018539 | 7401871 | Augmentation | MVS | 3432/PHE-28011/249/2023-ESTT CELL-Dept. of PHE | 08/11/2023 | 25379 | 421.8 | 25800.8 | Hooghly Division | Electrical Division | 5194.01 | 0 | 276.75 | 0 | 5470.76 | 3883.53 | 0 | 276.75 | 0 | 4160.28 | 16.12 | 60
69 | HOOGHLY | SM/15898 | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | TSM/018701 | 40039081 | Augmentation | MVS | GO2223014280PH | 20/02/2023 | 37.4 | 33.73 | 71.13 | Hooghly Division | Electrical Division | 14.91 | 14.31 | 2.46 | 11.1 | 42.78 | 14.91 | 14.31 | 2.46 | 11.1 | 42.78 | 60.14 | 90
70 | HOOGHLY | SM/16449 | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se | TSM/013031 | 40043440 | Augmentation | MVS | GO2223014987PH | 28/02/2023 | 64.68 | 64.02 | 128.7 | Hooghly Division | Electrical Division | 18.95 | 27.41 | 0 | 21.16 | 67.53 | 18.95 | 27.41 | 0 | 21.16 | 67.53 | 52.47 | 85
71 | HOOGHLY | SM/16450 | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S | TSM/013033 | 40043440 | Augmentation | MVS | GO2223014986PH | 28/02/2023 | 72.15 | 64.02 | 136.17 | Hooghly Division | Electrical Division | 12.85 | 33.97 | 0.62 | 44.75 | 92.18 | 12.85 | 33.97 | 0.62 | 44.75 | 92.18 | 67.69 | 85
72 | HOOGHLY | SM/16448 | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under | TSM/013029 | 40037303 | Augmentation | SVS | GO2223014989PH | 28/02/2023 | 37.31 | 26.27 | 63.58 | Hooghly Division | Electrical Division | 24.27 | 16.88 | 2.77 | 0 | 43.92 | 24.27 | 16.88 | 2.77 | 0 | 43.92 | 69.08 | 80
73 | HOOGHLY | SM/16447 | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und | TSM/013254 | 40037316 | Augmentation | SVS | GO2223014988PH | 28/02/2023 | 77.88 | 31.15 | 109.03 | Hooghly Division | Electrical Division | 51.97 | 19.28 | 8.93 | 11 | 91.18 | 51.97 | 19.28 | 8.93 | 11 | 91.18 | 83.63 | 85
74 | HOOGHLY | SM/18927 | Improvement of BHANDARHATI Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block-Arambagh | TSM/020497 | 40067454 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 64.44 | 27.81 | 92.25 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
75 | HOOGHLY | SM/18929 | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | TSM/020405 | 40067447 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 138.69 | 55.62 | 194.31 | Hooghly Division | Electrical Division | 67.07 | 15.32 | 0 | 0 | 82.39 | 67.07 | 15.32 | 0 | 0 | 82.39 | 42.4 | 50
76 | HOOGHLY | SM/15901 | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK | TSM/020255 | 40039091 | Augmentation | MVS | GO2223014270PH | 25/02/2023 | 219.96 | 0 | 219.96 | Hooghly Division | Electrical Division | 81.58 | 0 | 0 | 0 | 81.58 | 81.58 | 0 | 0 | 0 | 81.58 | 37.09 | 60
77 | HOOGHLY | SM/18928 | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | TSM/020494 | 40067444 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 106.86 | 55.62 | 162.48 | Hooghly Division | Electrical Division | 20.43 | 0 | 0 | 0 | 20.43 | 20.43 | 0 | 0 | 0 | 20.43 | 12.57 | 20
78 | HOOGHLY | SM/18926 | Improvement of ¿MEGHSAR¿ Piped Water Supply Scheme by laying of HDPE Pipeline by HDD Process & Open cut method including restoration work at Mahanad Bandel Road within Meghsar PWSS under Chinsurah Sub Division. | TSM/020548 | 40067476 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 164.41 | 0 | 164.41 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 0.58 | 1
79 | HOOGHLY | SM/18931 | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme | TSM/020469 | 40067480 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 0 | 83.25 | 83.25 |  | Electrical Division | 0 | 27.26 | 0 | 0 | 27.26 | 0 | 27.26 | 0 | 0 | 27.26 | 32.74 | 60
80 | HOOGHLY | SM/18930 | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. | TSM/020453 | 40067481 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 0 | 55.3 | 55.3 |  | Electrical Division | 0 | 36.53 | 0 | 0 | 36.53 | 0 | 36.53 | 0 | 0 | 36.53 | 66.06
81 | HOOGHLY | SM/18980 | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK | TSM/020554 | 40067350 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 1.81 | 0 | 0 | 0 | 1.81 | 1.81 | 0 | 0 | 0 | 1.81 | 1.76 | 2
82 | HOOGHLY | SM/18943 | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/020550 | 40067437 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 52.61 | 32.82 | 85.43 | Hooghly Division | Electrical Division | 21.79 | 11.53 | 0 | 0 | 33.32 | 21.79 | 11.53 | 0 | 0 | 33.32 | 39 | 35
83 | HOOGHLY | SM/13346 | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/014980 | 40028614 | Augmentation | MVS | GO2223008467PH | 29/09/2022 | 152.36 | 62.29 | 214.65 | Hooghly Division | Electrical Division | 122.6 | 27.63 | 0 | 0 | 150.23 | 105.76 | 27.63 | 0 | 0 | 133.38 | 62.14 | 99
84 | HOOGHLY | SM/18950 | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | TSM/020465 | 40067407 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 6.57 | 9.1 | 0 | 0 | 15.66 | 6.57 | 9.1 | 0 | 0 | 15.66 | 10.22 | 12
85 | HOOGHLY | SM/09423 | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | TSM/008682 | 40033635 | Augmentation | MVS | GO2122005524PH | 17/11/2021 | 43.82 | 0 | 43.82 | Hooghly Division | Electrical Division | 6.73 | 15.28 | 0 | 12 | 34.01 | 6.73 | 15.28 | 0 | 12 | 34.01 | 77.61 | 80
86 | HOOGHLY | SM/16124 | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block | TSM/020386 | 40053398 | Augmentation | MVS | GO2223014672PH | 22/02/2023 | 135.14 | 55.62 | 190.76 | Hooghly Division | Electrical Division | 0 | 2.8 | 0 | 0 | 2.8 | 0 | 2.8 | 0 | 0 | 2.8 | 1.47 | 50
87 | HOOGHLY | SM/18941 | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020552 | 40067440 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 17.08 | 4.01 | 0 | 0 | 21.09 | 17.08 | 4.01 | 0 | 0 | 21.09 | 11.19
88 | HOOGHLY | SM/18958 | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | TSM/020455 | 40067422 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 100.17 | 55.62 | 155.79 | Hooghly Division | Electrical Division | 0 | 9.55 | 0 | 0 | 9.55 | 0 | 9.55 | 0 | 0 | 9.55 | 6.13 | 50
89 | HOOGHLY | SM/15799 | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/016328 | 40037221 | Augmentation | MVS | GO2223014258PH | 20/02/2023 | 139.28 | 62.29 | 201.57 | Hooghly Division | Electrical Division | 81.2 | 32.07 | 0 | 0 | 113.28 | 81.2 | 32.07 | 0 | 0 | 113.28 | 56.2 | 55
90 | HOOGHLY | SM/18944 | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020549 | 40067436 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 19.22 | 21.63 | 0 | 0 | 40.85 | 19.22 | 21.63 | 0 | 0 | 40.85 | 21.67 | 15
91 | HOOGHLY | SM/13344 | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/014984 | 40032981 | Augmentation | MVS | GO2223008474PH | 29/09/2022 | 173.39 | 62.29 | 235.69 | Hooghly Division | Electrical Division | 72.5 | 61.36 | 37.77 | 0 | 171.63 | 72.5 | 61.36 | 37.77 | 0 | 171.63 | 72.82 | 70
92 | HOOGHLY | SM/18961 | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | TSM/020451 | 40067468 | Augmentation | SVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 118.86 | 55.62 | 174.48 | Hooghly Division | Electrical Division | 26.32 | 13.62 | 0 | 0 | 39.95 | 26.32 | 13.62 | 0 | 0 | 39.95 | 22.89 | 50
93 | HOOGHLY | SM/19161 | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | TSM/011658 | 40067475 | Augmentation | SVS | PHE/IV/193/W-03/24 | 18/01/2024 | 24.95 | 26.27 | 51.21 | Hooghly Division | Electrical Division | 9.45 | 10.87 | 0 | 0 | 20.32 | 9.45 | 10.87 | 0 | 0 | 20.32 | 39.68 | 85
94 | HOOGHLY | SM/15803 | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | TSM/020252 | 40067472 | Augmentation | MVS | GO2223014181PH | 17/02/2023 | 35.39 | 27.81 | 63.2 | Hooghly Division | Electrical Division | 9.91 | 0 | 0 | 0 | 9.91 | 9.91 | 0 | 0 | 0 | 9.91 | 15.68 | 90
95 | HOOGHLY | SM/15794 | Source Augmentation of Bamonjol PWSS | TSM/018694 | 40039078 | Augmentation | MVS | GO2223014175PH | 17/02/2023 | 28.89 | 26.27 | 55.16 | Hooghly Division | Electrical Division | 11.12 | 11.84 | 0 | 0 | 22.96 | 11.12 | 11.84 | 0 | 0 | 22.96 | 41.62 | 60
96 | HOOGHLY | SM/18936 | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020666 | 40067458 | Augmentation | SVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 8.27 | 0 | 0 | 8.27 | 0 | 8.27 | 0 | 0 | 8.27 | 4.39
97 | HOOGHLY | SM/18973 | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020634 | 40067370 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 2.51 | 0 | 0 | 0 | 2.51 | 2.51 | 0 | 0 | 0 | 2.51 | 1.33 | 2
98 | HOOGHLY | SM/15813 | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | TSM/020241 | 40067473 | Augmentation | MVS | GO2223014295PH | 20/02/2023 | 44.42 | 27.81 | 72.23 | Hooghly Division | Electrical Division | 12.33 | 7.9 | 0 | 0 | 20.23 | 12.33 | 7.9 | 0 | 0 | 20.23 | 28.01 | 30
99 | HOOGHLY | SM/15800 | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/016351 | 40039172 | Augmentation | MVS | GO2223014190PH | 17/02/2023 | 116.4 | 62.29 | 178.69 | Hooghly Division | Electrical Division | 21.16 | 21.13 | 35.98 | 0 | 78.26 | 21.16 | 21.13 | 35.98 | 0 | 78.26 | 43.8 | 45
100 | HOOGHLY | SM/18968 | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | TSM/020439 | 40067346 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 27 | 18.23 | 45.23 | Hooghly Division | Electrical Division | 24.07 | 0 | 0 | 0 | 24.07 | 24.07 | 0 | 0 | 0 | 24.07 | 53.23 | 20
101 | HOOGHLY | SM/18940 | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020639 | 40067441 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 30.51 | 12.67 | 0 | 0 | 43.18 | 30.51 | 12.67 | 0 | 0 | 43.18 | 22.91 | 10
102 | HOOGHLY | SM/18966 | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | TSM/020442 | 40067397 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 352.41 | 55.62 | 408.03 | Hooghly Division | Electrical Division | 75.59 | 15.66 | 0 | 0 | 91.25 | 75.59 | 15.66 | 0 | 0 | 91.25 | 22.36 | 50
103 | HOOGHLY | SM/18967 | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | TSM/020441 | 40067395 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 96.57 | 27.81 | 124.38 | Hooghly Division | Electrical Division | 38.92 | 21.18 | 0 | 0 | 60.09 | 38.92 | 21.18 | 0 | 0 | 60.09 | 48.31
104 | HOOGHLY | SM/18937 | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020642 | 40067443 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 19.63 | 0 | 0 | 0 | 19.63 | 19.63 | 0 | 0 | 0 | 19.63 | 10.42
105 | HOOGHLY | SM/15812 | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | TSM/020237 | 6904467 | Augmentation | MVS | GO2223014182PH | 17/02/2023 | 48.06 | 27.81 | 75.87 | Hooghly Division | Electrical Division | 0 | 0 | 9.76 | 0 | 9.76 | 0 | 0 | 9.76 | 0 | 9.76 | 12.86 | 35
106 | HOOGHLY | SM/18975 | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/020632 | 40067369 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 45.23 | 34.82 | 0 | 0 | 80.05 | 45.23 | 34.82 | 0 | 0 | 80.05 | 42.47 | 15
107 | HOOGHLY | SM/18981 | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020553 | 40067348 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | HOOGHLY | SM/18978 | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020629 | 40067355 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 34.59 | 22.66 | 0 | 0 | 57.25 | 34.59 | 22.66 | 0 | 0 | 57.25 | 30.38 | 30
109 | HOOGHLY | SM/13410 | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/015551 | 40030197 | Augmentation | MVS | GO2223009170PH | 02/11/2022 | 186.59 | 62.29 | 248.89 | Hooghly Division | Electrical Division | 67.16 | 35.22 | 37.77 | 0 | 140.15 | 67.16 | 35.22 | 37.77 | 0 | 140.15 | 56.31 | 55
110 | HOOGHLY | SM/16130 | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block | TSM/020404 | 40053400 | Augmentation | MVS | GO2223014676PH | 22/02/2023 | 122.86 | 55.62 | 178.48 | Hooghly Division | Electrical Division | 23.17 | 11.02 | 0 | 0 | 34.19 | 23.17 | 11.02 | 0 | 0 | 34.19 | 19.16 | 50
111 | HOOGHLY | SM/18959 | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | TSM/020454 | 40067416 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 48.12 | 27.81 | 75.93 | Hooghly Division | Electrical Division | 0 | 8.76 | 0 | 0 | 8.76 | 0 | 8.76 | 0 | 0 | 8.76 | 11.54 | 95
112 | HOOGHLY | SM/13343 | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/014990 | 40032912 | Augmentation | MVS | GO2223008470PH | 29/09/2022 | 160.4 | 62.29 | 222.7 | Hooghly Division | Electrical Division | 47.98 | 40.5 | 0 | 0 | 88.48 | 47.98 | 40.5 | 0 | 0 | 88.48 | 39.73 | 55
113 | HOOGHLY | SM/18942 | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020551 | 40067439 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 31.61 | 8.83 | 0 | 0 | 40.44 | 31.61 | 8.83 | 0 | 0 | 40.44 | 39.25 | 10
114 | HOOGHLY | SM/18939 | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020640 | 40067442 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 9.61 | 0 | 0 | 9.61 | 0 | 9.61 | 0 | 0 | 9.61 | 5.1
115 | HOOGHLY | SM/18935 | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020671 | 40067451 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 11.82 | 11.08 | 0 | 0 | 22.9 | 11.82 | 11.08 | 0 | 0 | 22.9 | 12.15 | 10
116 | HOOGHLY | SM/15809 | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | TSM/020245 | 6904470 | Augmentation | MVS | GO2223014263PH | 20/02/2023 | 97.41 | 55.62 | 153.03 | Hooghly Division | Electrical Division | 13.26 | 3.31 | 12.16 | 0 | 28.73 | 13.26 | 3.31 | 12.16 | 0 | 28.73 | 18.77 | 95
117 | HOOGHLY | SM/18953 | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | TSM/020461 | 40067423 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 35.02 | 32.82 | 67.84 | Hooghly Division | Electrical Division | 28.8 | 12.57 | 0 | 0 | 41.36 | 28.8 | 12.57 | 0 | 0 | 41.36 | 60.97 | 65
118 | HOOGHLY | SM/18965 | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | TSM/020447 | 40067469 | Augmentation | SVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 119.06 | 55.62 | 174.68 | Hooghly Division | Electrical Division | 12.28 | 0 | 0 | 0 | 12.28 | 12.28 | 0 | 0 | 0 | 12.28 | 7.03 | 20
119 | HOOGHLY | SM/15801 | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK | TSM/016521 | 40037226 | Augmentation | MVS | GO2223014189PH | 17/02/2023 | 116.4 | 62.29 | 178.69 | Hooghly Division | Electrical Division | 53.97 | 23.16 | 35.71 | 0 | 112.84 | 53.97 | 23.16 | 35.71 | 0 | 112.84 | 63.15 | 40
120 | HOOGHLY | SM/18979 | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK | TSM/020555 | 40067353 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 70.22 | 32.82 | 103.03 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | HOOGHLY | SM/15798 | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/018380 | 40039044 | Augmentation | MVS | GO2223014188PH | 17/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 29.04 | 21.4 | 37.77 | 0 | 88.21 | 29.04 | 21.4 | 37.77 | 0 | 88.21 | 77.17 | 80
122 | HOOGHLY | SM/18948 | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | TSM/020478 | 40067408 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 32.6 | 4.17 | 0 | 0 | 36.77 | 32.6 | 4.17 | 0 | 0 | 36.77 | 23.99 | 25
123 | HOOGHLY | SM/18964 | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | TSM/020448 | 40067410 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 138.89 | 55.62 | 194.51 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | HOOGHLY | SM/18938 | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020641 | 40067356 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 26.29 | 26.95 | 0 | 0 | 53.25 | 26.29 | 26.95 | 0 | 0 | 53.25 | 28.25 | 15
125 | HOOGHLY | SM/18957 | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block | TSM/020456 | 40067470 | Augmentation | SVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 90.45 | 55.62 | 146.07 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | HOOGHLY | SM/18956 | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | TSM/020457 | 40067420 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 35.02 | 32.82 | 67.84 | Hooghly Division | Electrical Division | 13.72 | 4.02 | 0 | 0 | 17.74 | 13.72 | 4.02 | 0 | 0 | 17.74 | 26.15 | 22
127 | HOOGHLY | SM/18960 | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | TSM/020452 | 40067471 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 117.26 | 55.62 | 172.88 | Hooghly Division | Electrical Division | 0 | 20.9 | 0 | 0 | 20.9 | 0 | 20.9 | 0 | 0 | 20.9 | 12.09 | 90
128 | HOOGHLY | SM/15815 | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | TSM/020228 | 0 | Augmentation | MVS | GO2223014279PH | 20/02/2023 | 40.05 | 27.81 | 67.86 | Hooghly Division | Electrical Division | 5.06 | 0 | 0 | 0 | 5.06 | 5.06 | 0 | 0 | 0 | 5.06 | 7.46 | 56
129 | HOOGHLY | SM/18934 | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020672 | 40067343 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 28.58 | 13.56 | 0 | 0 | 42.14 | 28.58 | 13.56 | 0 | 0 | 42.14 | 22.36
130 | HOOGHLY | SM/16122 | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | TSM/020384 | 40053403 | Augmentation | MVS | GO2223014674PH | 22/02/2023 | 143.25 | 55.62 | 198.87 | Hooghly Division | Electrical Division | 31.18 | 50.72 | 0 | 0 | 81.9 | 31.18 | 50.72 | 0 | 0 | 81.9 | 41.18 | 95
131 | HOOGHLY | SM/18945 | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020546 | 40067435 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 2.7 | 8.23 | 0 | 0 | 10.93 | 2.7 | 8.23 | 0 | 0 | 10.93 | 5.8
132 | HOOGHLY | SM/15808 | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | TSM/020246 | 40042900 | Augmentation | MVS | GO2223014183PH | 17/02/2023 | 49.98 | 27.81 | 77.79 | Hooghly Division | Electrical Division | 10.72 | 3.95 | 0 | 0 | 14.67 | 10.72 | 3.95 | 0 | 0 | 14.67 | 18.86 | 30
133 | HOOGHLY | SM/18974 | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | TSM/020633 | 40067409 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 32.03 | 12.07 | 0 | 0 | 44.1 | 32.03 | 12.07 | 0 | 0 | 44.1 | 23.4 | 15
134 | HOOGHLY | SM/18972 | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020635 | 40067462 | Augmentation | SVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 4.12 | 0 | 0 | 4.12 | 0 | 4.12 | 0 | 0 | 4.12 | 2.18 | 5
135 | HOOGHLY | SM/15811 | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | TSM/020243 | 0 | Augmentation | MVS | GO2223014186PH | 17/02/2023 | 37.77 | 27.81 | 65.58 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
136 | HOOGHLY | SM/15814 | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | TSM/020242 | 40042968 | Augmentation | MVS | GO2223014282PH | 20/02/2023 | 73.89 | 55.62 | 129.51 | Hooghly Division | Electrical Division | 11.07 | 23.35 | 0 | 0 | 34.43 | 11.07 | 23.35 | 0 | 0 | 34.43 | 26.58 | 50
137 | HOOGHLY | SM/18955 | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | TSM/020458 | 40067391 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 35.02 | 32.82 | 67.84 | Hooghly Division | Electrical Division | 5.81 | 0 | 0 | 0 | 5.81 | 5.81 | 0 | 0 | 0 | 5.81 | 8.56 | 10
138 | HOOGHLY | SM/15802 | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | TSM/020250 | 40043401 | Augmentation | MVS | GO2223014257PH | 20/02/2023 | 38.61 | 27.81 | 66.42 | Hooghly Division | Electrical Division | 16.12 | 15.75 | 6.01 | 0 | 37.89 | 16.12 | 15.75 | 6.01 | 0 | 37.89 | 57.04 | 70
139 | HOOGHLY | SM/15899 | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/018192 | 40038980 | Augmentation | MVS | GO2223014278PH | 20/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 48.65 | 14.26 | 20.39 | 0 | 83.3 | 48.65 | 14.26 | 20.39 | 0 | 83.3 | 72.87 | 75
140 | HOOGHLY | SM/13345 | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/014975 | 40028612 | Augmentation | MVS | GO2223008486PH | 29/09/2022 | 163.29 | 62.29 | 225.59 | Hooghly Division | Electrical Division | 158.53 | 56.77 | 0 | 0 | 215.31 | 140.02 | 56.77 | 0 | 0 | 196.8 | 87.24 | 95
141 | HOOGHLY | SM/15796 | Source Augmentation of Malia PWSS | TSM/018687 | 40039057 | Augmentation | MVS | GO2223014286PH | 20/02/2023 | 28.89 | 26.27 | 55.16 | Hooghly Division | Electrical Division | 22.65 | 20.9 | 0 | 0 | 43.55 | 22.65 | 20.9 | 0 | 0 | 43.55 | 78.95 | 80
142 | HOOGHLY | SM/18977 | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020630 | 40067365 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 4.09 | 0 | 0 | 0 | 4.09 | 4.09 | 0 | 0 | 0 | 4.09 | 2.17 | 5
143 | HOOGHLY | SM/18954 | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | TSM/020460 | 40067400 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 18.76 | 39.43 | 0 | 0 | 58.18 | 18.76 | 39.43 | 0 | 0 | 58.18 | 37.96 | 20
144 | HOOGHLY | SM/18970 | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020637 | 40067345 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 13.22 | 24.14 | 0 | 0 | 37.37 | 13.22 | 24.14 | 0 | 0 | 37.37 | 19.83
145 | HOOGHLY | SM/18976 | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020631 | 40067456 | Augmentation | SVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 0.51 | 2
146 | HOOGHLY | SM/18933 | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020675 | 40067449 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 0.51 | 1
147 | HOOGHLY | SM/18963 | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block | TSM/020449 | 40067411 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 35.52 | 27.81 | 63.33 | Hooghly Division | Electrical Division | 17.73 | 10.8 | 0 | 0 | 28.53 | 17.73 | 10.8 | 0 | 0 | 28.53 | 45.05 | 50
148 | HOOGHLY | SM/18791 | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | TSM/011639 | 40037195 | Augmentation | MVS | PHE/IV/2693/W-387/23 | 07/09/2023 | 44.65 | 27.81 | 72.46 | Hooghly Division | Electrical Division | 0.38 | 21.09 | 0 | 0 | 21.47 | 0.38 | 21.09 | 0 | 0 | 21.47 | 29.63 | 80
149 | HOOGHLY | SM/18946 | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020544 | 40067460 | Augmentation | SVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | HOOGHLY | SM/15795 | Source Augmentation of Paschim Joykrishnapur PWSS | TSM/018693 | 40039062 | Augmentation | MVS | GO2223014283PH | 20/02/2023 | 57.79 | 52.53 | 110.32 | Hooghly Division | Electrical Division | 26.48 | 34.57 | 26.06 | 0 | 87.11 | 26.48 | 34.57 | 26.06 | 0 | 87.11 | 78.96 | 85
151 | HOOGHLY | SM/15900 | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/018379 | 40039042 | Augmentation | MVS | GO2223014277PH | 20/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 25.61 | 17.08 | 1.85 | 0 | 44.54 | 25.61 | 17.08 | 1.85 | 0 | 44.54 | 38.96 | 40
152 | HOOGHLY | SM/15804 | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | TSM/020251 | 40043149 | Augmentation | MVS | GO2223014184PH | 17/02/2023 | 87.4 | 27.81 | 115.21 | Hooghly Division | Electrical Division | 9.95 | 3.55 | 6.01 | 0 | 19.52 | 9.95 | 3.55 | 6.01 | 0 | 19.52 | 16.94 | 80
153 | HOOGHLY | SM/18951 | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | TSM/020464 | 40067403 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 14.46 | 7.18 | 0 | 0 | 21.64 | 14.46 | 7.18 | 0 | 0 | 21.64 | 14.12 | 5
154 | HOOGHLY | SM/15807 | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | TSM/020247 | 40039157 | Augmentation | MVS | GO2223014187PH | 17/02/2023 | 73.34 | 55.62 | 128.96 | Hooghly Division | Electrical Division | 11.04 | 23.07 | 12.16 | 0 | 46.27 | 11.04 | 23.07 | 12.16 | 0 | 46.27 | 35.88 | 45
155 | HOOGHLY | SM/18952 | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | TSM/020462 | 40067402 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 87.63 | 65.63 | 153.27 | Hooghly Division | Electrical Division | 46.79 | 15.74 | 0 | 0 | 62.53 | 46.79 | 15.74 | 0 | 0 | 62.53 | 40.8 | 15
156 | HOOGHLY | SM/15806 | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block | TSM/020248 | 6904457 | Augmentation | MVS | GO2223014292PH | 20/02/2023 | 38 | 27.81 | 65.81 | Hooghly Division | Electrical Division | 0 | 0 | 6.32 | 0 | 6.32 | 0 | 0 | 6.32 | 0 | 6.32 | 9.6 | 100
157 | HOOGHLY | SM/15805 | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | TSM/020249 | 40043096 | Augmentation | MVS | GO2223014179PH | 17/02/2023 | 36.28 | 27.81 | 64.09 | Hooghly Division | Electrical Division | 18.4 | 13.48 | 0 | 0 | 31.89 | 18.4 | 13.48 | 0 | 0 | 31.89 | 49.75 | 90
158 | HOOGHLY | SM/13677 | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | TSM/014958 | 40032931 | Augmentation | MVS | GO2223008476PH | 29/09/2022 | 233.29 | 62.29 | 295.58 | Hooghly Division | Electrical Division | 97.45 | 38.34 | 0 | 0 | 135.79 | 97.45 | 38.34 | 0 | 0 | 135.79 | 45.94 | 45
159 | HOOGHLY | SM/18947 | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block | TSM/020492 | 40067434 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 85.29 | 55.62 | 140.91 | Hooghly Division | Electrical Division | 0 | 41.85 | 0 | 0 | 41.85 | 0 | 41.85 | 0 | 0 | 41.85 | 29.7 | 80
160 | HOOGHLY | SM/18971 | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/020636 | 40067374 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 14.22 | 8.69 | 0 | 0 | 22.9 | 14.22 | 8.69 | 0 | 0 | 22.9 | 12.15 | 10
161 | HOOGHLY | SM/16121 | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | TSM/020378 | 40053407 | Augmentation | SVS | GO2223014679PH | 22/02/2023 | 108.04 | 55.62 | 163.66 | Hooghly Division | Electrical Division | 38.57 | 44 | 0 | 0 | 82.57 | 38.57 | 44 | 0 | 0 | 82.57 | 50.45 | 80
162 | HOOGHLY | SM/15797 | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/018201 | 40039009 | Augmentation | MVS | GO2223014260PH | 20/02/2023 | 83.16 | 31.15 | 114.3 | Hooghly Division | Electrical Division | 35.18 | 30.98 | 37.77 | 0 | 103.93 | 35.18 | 30.98 | 37.77 | 0 | 103.93 | 90.92 | 95
163 | HOOGHLY | SM/15793 | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | TSM/018794 | 40039084 | Augmentation | MVS | GO2223014176PH | 17/02/2023 | 26.02 | 26.27 | 52.29 | Hooghly Division | Electrical Division | 3.57 | 6.12 | 0 | 0 | 9.68 | 3.57 | 6.12 | 0 | 0 | 9.68 | 18.52
164 | HOOGHLY | SM/18962 | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | TSM/020450 | 40067413 | Augmentation | MVS | PHE/IV/3110/W-657/23 | 10/10/2023 | 137.06 | 55.62 | 192.68 | Hooghly Division | Electrical Division | 14.3 | 3.42 | 0 | 0 | 17.72 | 14.3 | 3.42 | 0 | 0 | 17.72 | 9.2 | 25
165 | HOOGHLY | SM/13409 | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | TSM/015548 | 40029480 | Augmentation | MVS | GO2223009172PH | 02/11/2022 | 139.28 | 62.29 | 201.57 | Hooghly Division | Electrical Division | 41.68 | 24.68 | 36.39 | 0 | 102.75 | 41.68 | 24.68 | 36.39 | 0 | 102.75 | 50.98 | 50
166 | HOOGHLY | SM/15810 | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | TSM/020244 | 7764511 | Augmentation | MVS | GO2223014185PH | 17/02/2023 | 36.55 | 27.81 | 64.36 | Hooghly Division | Electrical Division | 29.28 | 15.03 | 0 | 0 | 44.3 | 29.28 | 15.03 | 0 | 0 | 44.3 | 68.83 | 100
167 | HOOGHLY | SM/18969 | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020638 | 40067352 | Augmentation | MVS | PHE/IV/3111/W-659/23 | 10/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 39.87 | 17.09 | 0 | 0 | 56.96 | 39.87 | 17.09 | 0 | 0 | 56.96 | 30.22 | 20
168 | HOOGHLY | SM/13411 | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK | TSM/015549 | 40030029 | Augmentation | MVS | GO2223009171PH | 02/11/2022 | 134.88 | 62.29 | 197.18 | Hooghly Division | Electrical Division | 76.38 | 24.46 | 37.77 | 0 | 138.61 | 76.38 | 24.46 | 37.77 | 0 | 138.61 | 70.3 | 50
169 | HOOGHLY | SM/18932 | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | TSM/020676 | 40067448 | Augmentation | MVS | PHE/IV/3074/W-659/23 | 09/10/2023 | 122.84 | 65.63 | 188.47 | Hooghly Division | Electrical Division | 15.84 | 0 | 0 | 0 | 15.84 | 15.84 | 0 | 0 | 0 | 15.84 | 8.4 | 10
170 | HOOGHLY | SM/18949 | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | TSM/020467 | 40067427 | Augmentation | MVS | PHE/IV/3109/W-657/23 | 10/10/2023 | 79.13 | 65.63 | 144.76 | Hooghly Division | Electrical Division | 28.26 | 6.27 | 0 | 0 | 34.53 | 28.26 | 6.27 | 0 | 0 | 34.53 | 23.85 | 5
Total | [9 empty] | 91332.46 | 9274.18 | 100606.64 |  |  | 33918.02 | 3460.89 | 4838.4 | 434.18 | 42651.49 | 32528.39 | 3458.85 | 4838.4 | 434.18 | 41259.82 | 41.01