## JJM Schemes Financial Status (H
JJM Schemes Financial Status (HOOGHLY) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | HOOGHLY | SM/06754 | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS | TSM/005640 | 8136198 | Retrofitting | MVS | GO2021001277PH | 18/09/2020 | 73.81 | 0 | 73.81 | Hooghly Division |  | 68.4 | 0 | 0 | 0 | 68.4 | 68.4 | 0 | 0 | 0 | 68.4 | 92.68 | 65
2 | HOOGHLY | SM/16648 | RETROFITTING FOR BANDIPUR WS SCHEME | TSM/020287 | 40053395 | Retrofitting | MVS | GO2223015929PH | 14/03/2023 | 99.14 | 0 | 99.14 | Hooghly Division |  | 39.43 | 0 | 0 | 0 | 39.43 | 39.43 | 0 | 0 | 0 | 39.43 | 39.77 | 50
3 | HOOGHLY | SM/06987 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme | TSM/006249 | 40015217 | Retrofitting | MVS | GO2021002508PH | 11/11/2020 | 92.65 | 0 | 92.65 | Hooghly Division |  | 58.57 | 0 | 0 | 0 | 58.57 | 58.57 | 0 | 0 | 0 | 58.57 | 63.22 | 45
4 | HOOGHLY | SM/07463 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme | TSM/006269 | 8190797 | Retrofitting | MVS | GO2021003869PH | 30/12/2020 | 130.74 | 0 | 130.74 | Hooghly Division |  | 126.93 | 0 | 0 | 0 | 126.93 | 126.93 | 0 | 0 | 0 | 126.93 | 97.08 | 85
5 | HOOGHLY | SM/06989 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme | TSM/006261 | 6132548 | Retrofitting | SVS | GO2021002510PH | 11/11/2020 | 57.3 | 0 | 57.3 | Hooghly Division |  | 20.6 | 0 | 0 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 20.6 | 35.95 | 80
6 | HOOGHLY | SM/06990 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme | TSM/006262 | 40033155 | Retrofitting | SVS | GO2021002511PH | 11/11/2020 | 80.57 | 0 | 80.57 | Hooghly Division |  | 80.02 | 0 | 0 | 0 | 80.02 | 80.02 | 0 | 0 | 0 | 80.02 | 99.32 | 80
7 | HOOGHLY | SM/06992 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme | TSM/006263 | 8136239 | Retrofitting | SVS | GO2021002513PH | 11/11/2020 | 98.98 | 0 | 98.98 | Hooghly Division |  | 54.1 | 0 | 12.32 | 8.98 | 75.4 | 54.1 | 0 | 12.32 | 8.98 | 75.4 | 76.18 | 90
8 | HOOGHLY | SM/07149 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme | TSM/006264 | 8136249 | Retrofitting | MVS | GO2021002887PH | 01/12/2020 | 77.24 | 0 | 77.24 | Hooghly Division |  | 60 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 77.68 | 90
9 | HOOGHLY | SM/07150 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under | TSM/006265 | 8136249 | Retrofitting | MVS | GO2021002885PH | 01/12/2020 | 56.16 | 0 | 56.16 | Hooghly Division |  | 10.01 | 0 | 0 | 0 | 10.01 | 10.01 | 0 | 0 | 0 | 10.01 | 17.83 | 90
10 | HOOGHLY | SM/06993 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme | TSM/006266 | 8136260 | Retrofitting | MVS | GO2021002515PH | 11/11/2020 | 79.51 | 0 | 79.51 | Hooghly Division |  | 27.88 | 0 | 0 | 0 | 27.88 | 27.88 | 0 | 0 | 0 | 27.88 | 35.06 | 40
11 | HOOGHLY | SM/07462 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme | TSM/006270 | 8190834 | Retrofitting | MVS | GO2021003871PH | 30/12/2020 | 184.15 | 0 | 184.15 | Hooghly Division |  | 106.68 | 0 | 0 | 0 | 106.68 | 106.59 | 0 | 0 | 0 | 106.59 | 57.88 | 90
12 | HOOGHLY | SM/07461 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | TSM/006271 | 8190841 | Retrofitting | MVS | GO2021003873PH | 30/12/2020 | 111.14 | 0 | 111.14 | Hooghly Division |  | 95.18 | 0 | 0 | 0 | 95.18 | 90.79 | 0 | 0 | 0 | 90.79 | 81.69 | 95
13 | HOOGHLY | SM/06994 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio | TSM/006267 | 8136263 | Retrofitting | SVS | GO2021002516PH | 11/11/2020 | 68.52 | 0 | 68.52 | Hooghly Division |  | 68 | 0 | 0 | 0 | 68 | 68 | 0 | 0 | 0 | 68 | 99.24 | 80
14 | HOOGHLY | SM/07151 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik | TSM/006268 | 8136263 | Retrofitting | SVS | GO2021002886PH | 01/12/2020 | 69.81 | 0 | 69.81 | Hooghly Division |  | 56.87 | 0 | 0 | 0 | 56.87 | 53.95 | 0 | 0 | 0 | 53.95 | 77.28 | 80
15 | HOOGHLY | SM/07460 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | TSM/006272 | 8190866 | Retrofitting | SVS | GO2021003874PH | 30/12/2020 | 145.28 | 0 | 145.28 | Hooghly Division |  | 121.48 | 0 | 0.08 | 0 | 121.56 | 113.67 | 0 | 0.08 | 0 | 113.76 | 78.3 | 80
16 | HOOGHLY | SM/06991 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme | TSM/006273 | 8136271 | Retrofitting | MVS | GO2021002518PH | 11/11/2020 | 83.37 | 0 | 83.37 | Hooghly Division |  | 80.94 | 0 | 0 | 0 | 80.94 | 80.94 | 0 | 0 | 0 | 80.94 | 97.09 | 97
17 | HOOGHLY | SM/06988 | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar Mouza of Borhol Zone-II Water Supply Scheme | TSM/006259 | 0 | Retrofitting | MVS | GO2021002509PH | 11/11/2020 | 75.19 | 0 | 75.19 | Hooghly Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
18 | HOOGHLY | SM/18108 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Chopa Water Supply Scheme under Dhaniakhali Block | TSM/020536 | 40066220 | Retrofitting | MVS | GO2223017785PH | 27/03/2023 | 20.53 | 0 | 20.53 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | HOOGHLY | SM/18107 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block | TSM/020540 | 40066218 | Retrofitting | MVS | GO2223017782PH | 27/03/2023 | 21.7 | 0 | 21.7 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | HOOGHLY | SM/18106 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block | TSM/020539 | 40066214 | Retrofitting | MVS | GO2223017772PH | 27/03/2023 | 21.11 | 0 | 21.11 | Hooghly Division | Electrical Division | 0.95 | 0 | 0 | 0 | 0.95 | 0.95 | 0 | 0 | 0 | 0.95 | 4.52 | 10
21 | HOOGHLY | SM/18109 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block | TSM/020535 | 40066215 | Retrofitting | MVS | GO2223017776PH | 27/03/2023 | 41.33 | 0 | 41.33 | Hooghly Division | Electrical Division | 6.03 | 0 | 0 | 0 | 6.03 | 6.03 | 0 | 0 | 0 | 6.03 | 14.59 | 5
22 | HOOGHLY | SM/18111 | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Hasampur Water Supply Scheme Under Dhaniakhali Block | TSM/020538 | 40066224 | Retrofitting | MVS | GO2223017779PH | 27/03/2023 | 20.53 | 0 | 20.53 | Hooghly Division | Electrical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | HOOGHLY | SM/06763 | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) | TSM/005631 | 7355421 | Retrofitting | MVS | GO2021001268PH | 18/09/2020 | 99.47 | 0 | 99.47 | Hooghly Division |  | 60.55 | 0 | 0 | 0 | 60.55 | 60.55 | 0 | 0 | 0 | 60.55 | 60.87 | 70
24 | HOOGHLY | SM/06766 | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) | TSM/005639 | 8136198 | Retrofitting | MVS | GO2021001275PH | 18/09/2020 | 93.4 | 0 | 93.4 | Hooghly Division |  | 90.43 | 0 | 0 | 0.24 | 90.67 | 90.43 | 0 | 0 | 0.24 | 90.67 | 97.08 | 65
25 | HOOGHLY | SM/06757 | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 1374 nos Functional Household Tap Connection(FHTC) | TSM/005632 | 8136095 | Retrofitting | MVS | GO2021001278PH | 18/09/2020 | 99.73 | 0 | 99.73 | Hooghly Division |  | 7.58 | 0 | 0 | 0 | 7.58 | 7.58 | 0 | 0 | 0 | 7.58 | 7.6 | 45
26 | HOOGHLY | SM/06760 | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) | TSM/005633 | 8136095 | Retrofitting | MVS | GO2021001279PH | 18/09/2020 | 43.92 | 0 | 43.92 | Hooghly Division |  | 0 | 0 | 0 | 13.77 | 13.77 | 0 | 0 | 0 | 13.77 | 13.77 | 31.35 | 45
27 | HOOGHLY | SM/06761 | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) | TSM/005634 | 8136095 | Retrofitting | MVS | GO2021001271PH | 18/09/2020 | 83.39 | 0 | 83.39 | Hooghly Division |  | 74.75 | 0 | 0 | 7.25 | 82 | 74.75 | 0 | 0 | 7.25 | 82 | 98.34 | 45
28 | HOOGHLY | SM/06765 | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | TSM/005642 | 8136209 | Retrofitting | MVS | GO2021001274PH | 18/09/2020 | 89.54 | 0 | 89.54 | Hooghly Division |  | 61.03 | 0 | 12.32 | 0 | 73.35 | 49.06 | 0 | 12.32 | 0 | 61.38 | 68.55 | 80
29 | HOOGHLY | SM/11004 | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | TSM/010297 | 7589585 | Retrofitting | MVS | GO2223003715PH | 01/06/2022 | 244.08 | 0 | 244.08 | Hooghly Division |  | 190.88 | 0 | 0 | 0 | 190.88 | 190.88 | 0 | 0 | 0 | 190.88 | 78.2 | 90
30 | HOOGHLY | SM/11003 | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010356 | 7355467 | Retrofitting | MVS | GO2223003717PH | 01/06/2022 | 51.92 | 0 | 51.92 | Hooghly Division |  | 2.43 | 0 | 12.32 | 0 | 14.75 | 2.43 | 0 | 12.32 | 0 | 14.75 | 28.42 | 100
31 | HOOGHLY | SM/11005 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | TSM/009992 | 40014757 | Retrofitting | MVS | GO2223003714PH | 01/06/2022 | 270.62 | 0 | 270.62 | Hooghly Division | Electrical Division | 219.67 | 0 | 11.4 | 0 | 231.07 | 219.67 | 0 | 11.4 | 0 | 231.07 | 85.39 | 75
32 | HOOGHLY | SM/11165 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME | TSM/009991 | 40014663 | Retrofitting | MVS | GO2223003788PH | 02/06/2022 | 264.04 | 0 | 264.04 | Hooghly Division |  | 118.69 | 0 | 11.4 | 10.83 | 140.92 | 118.69 | 0 | 11.4 | 10.83 | 140.92 | 53.37 | 90
33 | HOOGHLY | SM/12001 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME | TSM/010987 | 7940575 | Retrofitting | MVS | GO2223006903PH | 01/09/2022 | 88.46 | 0 | 88.46 | Hooghly Division |  | 59.67 | 0 | 0 | 0 | 59.67 | 59.67 | 0 | 0 | 0 | 59.67 | 67.46 | 95
34 | HOOGHLY | SM/12000 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME | TSM/011111 | 40026587 | Retrofitting | MVS | GO2223006904PH | 01/09/2022 | 148.75 | 0 | 148.75 | Hooghly Division |  | 40.78 | 0 | 0 | 0 | 40.78 | 40.78 | 0 | 0 | 0 | 40.78 | 27.42 | 90
35 | HOOGHLY | SM/11990 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME | TSM/011098 | 40026375 | Retrofitting | MVS | GO2223006906PH | 01/09/2022 | 376.63 | 0 | 376.63 | Hooghly Division |  | 172.77 | 0 | 15.88 | 0 | 188.65 | 172.77 | 0 | 15.88 | 0 | 188.65 | 50.09 | 75
36 | HOOGHLY | SM/11002 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME | TSM/009990 | 40014821 | Retrofitting | MVS | GO2223003718PH | 01/06/2022 | 371.11 | 0 | 371.11 | Hooghly Division |  | 139.89 | 0 | 5.7 | 0 | 145.59 | 139.89 | 0 | 5.7 | 0 | 145.59 | 39.23 | 40
37 | HOOGHLY | SM/11999 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BATANAL WATER SUPPLY SCHEME | TSM/011094 | 7940623 | Retrofitting | MVS | GO2223006907PH | 01/09/2022 | 218.68 | 0 | 218.68 | Hooghly Division |  | 73.68 | 0 | 0 | 0 | 73.68 | 73.68 | 0 | 0 | 0 | 73.68 | 33.69 | 90
38 | HOOGHLY | SM/12012 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) | TSM/010979 | 40021236 | Retrofitting | SVS | GO2223006908PH | 01/09/2022 | 47.77 | 0 | 47.77 | Hooghly Division |  | 45.38 | 0 | 0 | 0 | 45.38 | 45.38 | 0 | 0 | 0 | 45.38 | 95 | 98
39 | HOOGHLY | SM/12014 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME | TSM/011091 | 7940552 | Retrofitting | MVS | GO2223006909PH | 01/09/2022 | 197.98 | 0 | 197.98 | Hooghly Division |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
40 | HOOGHLY | SM/11997 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME | TSM/011090 | 40019990 | Retrofitting | MVS | GO2223006899PH | 01/09/2022 | 213.94 | 0 | 213.94 | Hooghly Division |  | 73.26 | 0 | 0 | 0 | 73.26 | 73.26 | 0 | 0 | 0 | 73.26 | 34.24 | 35
41 | HOOGHLY | SM/12015 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME | TSM/010985 | 7940820 | Retrofitting | MVS | GO2223006911PH | 01/09/2022 | 163.75 | 0 | 163.75 | Hooghly Division |  | 117.86 | 0 | 0 | 0 | 117.86 | 117.86 | 0 | 0 | 0 | 117.86 | 71.97 | 95
42 | HOOGHLY | SM/11998 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME | TSM/010984 | 7573630 | Retrofitting | MVS | GO2223006914PH | 01/09/2022 | 140.93 | 0 | 140.93 | Hooghly Division |  | 25.49 | 0 | 0 | 0 | 25.49 | 25.49 | 0 | 0 | 0 | 25.49 | 18.09 | 100
43 | HOOGHLY | SM/12002 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) | TSM/010980 | 7940671 | Retrofitting | MVS | GO2223006915PH | 01/09/2022 | 217.2 | 0 | 217.2 | Hooghly Division |  | 97.18 | 0 | 0 | 0 | 97.18 | 97.18 | 0 | 0 | 0 | 97.18 | 44.74 | 95
44 | HOOGHLY | SM/12013 | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SRIPUR-BALAGARH WATER SUPPLY SCHEME | TSM/011088 | 40019969 | Retrofitting | MVS | GO2223006917PH | 01/09/2022 | 199.03 | 0 | 199.03 | Hooghly Division |  | 30.15 | 0 | 0 | 0 | 30.15 | 30.15 | 0 | 0 | 0 | 30.15 | 15.15 | 20
45 | HOOGHLY | SM/10135 | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | TSM/009771 | 40004908 | Retrofitting | MVS | GO2122009346PH | 08/02/2022 | 137.19 | 0 | 137.19 | Hooghly Division |  | 84.42 | 0 | 0 | 0 | 84.42 | 84.42 | 0 | 0 | 0 | 84.42 | 61.53 | 65
46 | HOOGHLY | SM/10134 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte | TSM/009772 | 40004892 | Retrofitting | MVS | GO2122009358PH | 08/02/2022 | 88.95 | 0 | 88.95 | Hooghly Division |  | 57.55 | 0 | 0 | 0 | 57.55 | 57.55 | 0 | 0 | 0 | 57.55 | 64.7 | 70
47 | HOOGHLY | SM/10133 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. | TSM/009778 | 40004896 | Retrofitting | MVS | GO2122009342PH | 08/02/2022 | 99.96 | 0 | 99.96 | Hooghly Division |  | 86.06 | 0 | 10.98 | 0 | 97.04 | 86.06 | 0 | 10.98 | 0 | 97.04 | 97.08 | 96
48 | HOOGHLY | SM/10132 | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte | TSM/009779 | 40004906 | Retrofitting | MVS | GO2122009348PH | 08/02/2022 | 126.17 | 0 | 126.17 | Hooghly Division |  | 80.4 | 0 | 0 | 0 | 80.4 | 80.4 | 0 | 0 | 0 | 80.4 | 63.72 | 65
49 | HOOGHLY | SM/06764 | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme | TSM/005636 | 8136191 | Retrofitting | MVS | GO2021001273PH | 18/09/2020 | 70.7 | 0 | 70.7 | Hooghly Division |  | 62.91 | 0 | 0 | 0 | 62.91 | 62.91 | 0 | 0 | 0 | 62.91 | 88.99 | 90
50 | HOOGHLY | SM/10136 | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme | TSM/009766 | 40004909 | Retrofitting | MVS | GO2122009343PH | 08/02/2022 | 104.32 | 0 | 104.32 | Hooghly Division |  | 48.85 | 0 | 0 | 0 | 48.85 | 48.85 | 0 | 0 | 0 | 48.85 | 46.82 | 45
51 | HOOGHLY | SM/07540 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | TSM/006701 | 8199368 | Retrofitting | MVS | GO2021003919PH | 31/12/2020 | 66.84 | 0 | 66.84 | Hooghly Division |  | 50.2 | 0 | 0 | 10.28 | 60.48 | 45.15 | 0 | 0 | 10.28 | 55.44 | 82.94 | 95
52 | HOOGHLY | SM/09069 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. | TSM/008206 | 6865610 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 95.2 | 0 | 95.2 | Hooghly Division |  | 22.5 | 0 | 0 | 4.21 | 26.71 | 22.5 | 0 | 0 | 4.21 | 26.71 | 28.06 | 50
53 | HOOGHLY | SM/07442 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. | TSM/006691 | 8191612 | Retrofitting | MVS | GO2021003865PH | 30/12/2020 | 123.87 | 0 | 123.87 | Hooghly Division |  | 90.58 | 0 | 0 | 23.55 | 114.13 | 90.58 | 0 | 0 | 23.55 | 114.13 | 92.13 | 95
54 | HOOGHLY | SM/07534 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | TSM/006676 | 8199398 | Retrofitting | MVS | GO2021003920PH | 31/12/2020 | 72.23 | 0 | 72.23 | Hooghly Division |  | 67.59 | 0 | 0 | 0 | 67.59 | 67.59 | 0 | 0 | 0 | 67.59 | 93.58 | 70
55 | HOOGHLY | SM/07946 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. | TSM/007127 | 7350475 | Retrofitting | MVS | GO2021004958PH | 21/01/2021 | 97.35 | 0 | 97.35 | Hooghly Division |  | 94.29 | 0 | 0 | 0 | 94.29 | 94.06 | 0 | 0 | 0 | 94.06 | 96.62 | 70
56 | HOOGHLY | SM/07957 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. | TSM/007137 | 8197306 | Retrofitting | MVS | GO2021004978PH | 21/01/2021 | 163.57 | 0 | 163.57 | Hooghly Division |  | 95.91 | 0 | 0 | 0 | 95.91 | 84.06 | 0 | 0 | 0 | 84.06 | 51.39 | 70
57 | HOOGHLY | SM/07958 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | TSM/007138 | 8197334 | Retrofitting | MVS | GO2021004969PH | 21/01/2021 | 119.68 | 0 | 119.68 | Hooghly Division |  | 109.14 | 0 | 0 | 0 | 109.14 | 109.14 | 0 | 0 | 0 | 109.14 | 91.19 | 96
58 | HOOGHLY | SM/08743 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | TSM/007483 | 7940653 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 147.07 | 0 | 147.07 | Hooghly Division |  | 72.1 | 0 | 0 | 0 | 72.1 | 58.28 | 0 | 0 | 0 | 58.28 | 39.63 | 100
59 | HOOGHLY | SM/08738 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | TSM/007386 | 7940555 | Retrofitting | SVS | GO2122003172PH | 09/09/2021 | 134.58 | 0 | 134.58 | Hooghly Division |  | 125.65 | 0 | 0 | 0 | 125.65 | 120.65 | 0 | 0 | 0 | 120.65 | 89.65 | 95
60 | HOOGHLY | SM/07948 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | TSM/007129 | 8196760 | Retrofitting | MVS | GO2021004957PH | 21/01/2021 | 98.47 | 0 | 98.47 | Hooghly Division |  | 95.26 | 0 | 0 | 0 | 95.26 | 95.07 | 0 | 0 | 0 | 95.07 | 96.56 | 75
61 | HOOGHLY | SM/09777 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008321 | 7747635 | Retrofitting | MVS | GO2122006245PH | 30/11/2021 | 131.1 | 0 | 131.1 | Hooghly Division |  | 89.15 | 0 | 0 | 0 | 89.15 | 89.15 | 0 | 0 | 0 | 89.15 | 68 | 75
62 | HOOGHLY | SM/08744 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BHANGAMORA WATER SUPPLY SCHEME. | TSM/007484 | 7733799 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 80.9 | 0 | 80.9 | Hooghly Division |  | 60.95 | 0 | 0 | 0 | 60.95 | 48.27 | 0 | 0 | 0 | 48.27 | 59.67 | 100
63 | HOOGHLY | SM/07537 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | TSM/006707 | 8199346 | Retrofitting | MVS | GO2021003916PH | 31/12/2020 | 95.57 | 0 | 95.57 | Hooghly Division |  | 70.99 | 0 | 0 | 14.56 | 85.55 | 70.99 | 0 | 0 | 14.56 | 85.55 | 89.52 | 95
64 | HOOGHLY | SM/07443 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. | TSM/006693 | 6687858 | Retrofitting | MVS | GO2021003862PH | 30/12/2020 | 115.31 | 0 | 115.31 | Hooghly Division |  | 88.89 | 0 | 11 | 0 | 99.89 | 88.89 | 0 | 11 | 0 | 99.89 | 86.63 | 100
65 | HOOGHLY | SM/09072 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. | TSM/008211 | 8384696 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 42.14 | 0 | 42.14 | Hooghly Division | Electrical Division | 31.91 | 0 | 0 | 0 | 31.91 | 31.91 | 0 | 0 | 0 | 31.91 | 75.71 | 80
66 | HOOGHLY | SM/07542 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | TSM/006695 | 8197903 | Retrofitting | MVS | GO2021003913PH | 31/12/2020 | 95.57 | 0 | 95.57 | Hooghly Division |  | 72.98 | 0 | 0 | 0 | 72.98 | 69.44 | 0 | 0 | 0 | 69.44 | 72.66 | 80
67 | HOOGHLY | SM/09774 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008318 | 40003519 | Retrofitting | MVS | GO2122006246PH | 30/11/2021 | 166.04 | 0 | 166.04 | Hooghly Division |  | 9.65 | 0 | 0 | 0 | 9.65 | 9.65 | 0 | 0 | 0 | 9.65 | 5.81 | 5
68 | HOOGHLY | SM/07945 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | TSM/007126 | 7401878 | Retrofitting | MVS | GO2021004952PH | 21/01/2021 | 74.37 | 0 | 74.37 | Hooghly Division |  | 60.07 | 0 | 10.98 | 0 | 71.05 | 60.07 | 0 | 10.98 | 0 | 71.05 | 95.54 | 98
69 | HOOGHLY | SM/07955 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | TSM/007135 | 8197031 | Retrofitting | MVS | GO2021004962PH | 21/01/2021 | 166.55 | 0 | 166.55 | Hooghly Division |  | 141.44 | 0 | 0 | 0 | 141.44 | 141.43 | 0 | 0 | 0 | 141.43 | 84.92 | 90
70 | HOOGHLY | SM/07438 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. | TSM/006702 | 8192740 | Retrofitting | MVS | GO2021003877PH | 30/12/2020 | 272.67 | 0 | 272.67 | Hooghly Division |  | 0 | 0 | 0.08 | 0 | 0.08 | 0 | 0 | 0.08 | 0 | 0.08 | 0.03 | 5
71 | HOOGHLY | SM/07536 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | TSM/006708 | 8192815 | Retrofitting | MVS | GO2021003921PH | 31/12/2020 | 81.79 | 0 | 81.79 | Hooghly Division |  | 75.25 | 0 | 0 | 0 | 75.25 | 74.43 | 0 | 0 | 0 | 74.43 | 91.01 | 98
72 | HOOGHLY | SM/08741 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | TSM/007389 | 7747627 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 214.13 | 0 | 214.13 | Hooghly Division |  | 149.19 | 0 | 0 | 0 | 149.19 | 128.74 | 0 | 0 | 0 | 128.74 | 60.13 | 100
73 | HOOGHLY | SM/08742 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | TSM/007390 | 7940587 | Retrofitting | SVS | GO2122003172PH | 09/09/2021 | 176.84 | 0 | 176.84 | Hooghly Division |  | 154.03 | 0 | 10.43 | 0 | 164.46 | 154.03 | 0 | 10.43 | 0 | 164.46 | 93 | 95
74 | HOOGHLY | SM/07949 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | TSM/007130 | 8196833 | Retrofitting | MVS | GO2021004959PH | 21/01/2021 | 99.58 | 0 | 99.58 | Hooghly Division |  | 91.39 | 0 | 0 | 0 | 91.39 | 91.38 | 0 | 0 | 0 | 91.38 | 91.77 | 99
75 | HOOGHLY | SM/07952 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | TSM/007139 | 8197445 | Retrofitting | MVS | GO2021004979PH | 21/01/2021 | 212.07 | 0 | 212.07 | Hooghly Division |  | 191.4 | 0 | 0 | 14.43 | 205.83 | 191.4 | 0 | 0 | 14.43 | 205.83 | 97.06 | 98
76 | HOOGHLY | SM/08740 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | TSM/007388 | 7813939 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 230.84 | 0 | 230.84 | Hooghly Division |  | 218.11 | 0 | 0 | 0 | 218.11 | 200.4 | 0 | 0 | 0 | 200.4 | 86.81 | 95
77 | HOOGHLY | SM/07539 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. | TSM/006705 | 8199334 | Retrofitting | SVS | GO2021003915PH | 31/12/2020 | 35.08 | 0 | 35.08 | Hooghly Division |  | 32.42 | 0 | 2.66 | 0 | 35.08 | 32.42 | 0 | 2.66 | 0 | 35.08 | 100 | 96
78 | HOOGHLY | SM/09068 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | TSM/008204 | 7940560 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 80.21 | 0 | 80.21 | Hooghly Division |  | 14.88 | 0 | 0 | 0 | 14.88 | 14.88 | 0 | 0 | 0 | 14.88 | 18.55 | 100
79 | HOOGHLY | SM/09067 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | TSM/008203 | 7763276 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 131.23 | 0 | 131.23 | Hooghly Division |  | 52.39 | 0 | 0 | 0 | 52.39 | 52.39 | 0 | 0 | 0 | 52.39 | 39.92 | 100
80 | HOOGHLY | SM/07439 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | TSM/006697 | 8191751 | Retrofitting | MVS | GO2021003868PH | 30/12/2020 | 157.36 | 0 | 157.36 | Hooghly Division |  | 146.44 | 0 | 0 | 0 | 146.44 | 146.44 | 0 | 0 | 0 | 146.44 | 93.06 | 95
81 | HOOGHLY | SM/09775 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008319 | 7747555 | Retrofitting | MVS | GO2122006245PH | 30/11/2021 | 234.97 | 0 | 234.97 | Hooghly Division |  | 150.43 | 0 | 0 | 0 | 150.43 | 150.43 | 0 | 0 | 0 | 150.43 | 64.02 | 75
82 | HOOGHLY | SM/07436 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. | TSM/006678 | 8190882 | Retrofitting | MVS | GO2021003878PH | 30/12/2020 | 288.46 | 0 | 288.46 | Hooghly Division |  | 268.81 | 0 | 0 | 11.25 | 280.06 | 268.77 | 0 | 0 | 11.25 | 280.02 | 97.07 | 98
83 | HOOGHLY | SM/07956 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | TSM/007136 | 8197040 | Retrofitting | MVS | GO2021004980PH | 21/01/2021 | 203.01 | 0 | 203.01 | Hooghly Division |  | 167.86 | 0 | 0.08 | 0 | 167.94 | 165.83 | 0 | 0.08 | 0 | 165.92 | 81.73 | 85
84 | HOOGHLY | SM/07535 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | TSM/006681 | 8197892 | Retrofitting | MVS | GO2021003912PH | 31/12/2020 | 57.39 | 0 | 57.39 | Hooghly Division |  | 55.68 | 0 | 0 | 0 | 55.68 | 55.68 | 0 | 0 | 0 | 55.68 | 97.02 | 75
85 | HOOGHLY | SM/07953 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. | TSM/007133 | 7395830 | Retrofitting | MVS | GO2021004977PH | 21/01/2021 | 78.24 | 0 | 78.24 | Hooghly Division |  | 63.24 | 0 | 12.32 | 0 | 75.56 | 63.1 | 0 | 12.32 | 0 | 75.42 | 96.4 | 100
86 | HOOGHLY | SM/07441 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | TSM/006688 | 8191600 | Retrofitting | MVS | GO2021003855PH | 30/12/2020 | 128.62 | 0 | 128.62 | Hooghly Division |  | 115.23 | 0 | 10.98 | 0 | 126.21 | 95.47 | 0 | 10.98 | 0 | 106.45 | 82.77 | 96
87 | HOOGHLY | SM/09776 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008320 | 7362766 | Retrofitting | MVS | GO2122006245PH | 30/11/2021 | 130.24 | 0 | 130.24 | Hooghly Division |  | 70.61 | 0 | 0 | 0 | 70.61 | 70.61 | 0 | 0 | 0 | 70.61 | 54.22 | 60
88 | HOOGHLY | SM/09773 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008317 | 7401863 | Retrofitting | MVS | GO2122006246PH | 30/11/2021 | 95.96 | 0 | 95.96 | Hooghly Division |  | 58.52 | 0 | 0 | 0 | 58.52 | 56.59 | 0 | 0 | 0 | 56.59 | 58.97 | 65
89 | HOOGHLY | SM/07437 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. | TSM/006703 | 8192790 | Retrofitting | MVS | GO2021003872PH | 30/12/2020 | 278.22 | 0 | 278.22 | Hooghly Division |  | 157.54 | 0 | 10.98 | 0 | 168.52 | 156.14 | 0 | 10.98 | 0 | 167.12 | 60.07 | 65
90 | HOOGHLY | SM/07440 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. | TSM/006686 | 8191532 | Retrofitting | MVS | GO2021003858PH | 30/12/2020 | 230.1 | 0 | 230.1 | Hooghly Division |  | 190.94 | 0 | 0 | 0 | 190.94 | 190.94 | 0 | 0 | 0 | 190.94 | 82.98 | 85
91 | HOOGHLY | SM/07538 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | TSM/006706 | 8199354 | Retrofitting | SVS | GO2021003917PH | 31/12/2020 | 32.62 | 0 | 32.62 | Hooghly Division |  | 21.83 | 0 | 0 | 0 | 21.83 | 21.83 | 0 | 0 | 0 | 21.83 | 66.91 | 70
92 | HOOGHLY | SM/08739 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | TSM/007387 | 7573681 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 197.26 | 0 | 197.26 | Hooghly Division |  | 101.84 | 0 | 0 | 0 | 101.84 | 101.84 | 0 | 0 | 0 | 101.84 | 51.62 | 75
93 | HOOGHLY | SM/07954 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | TSM/007134 | 8197021 | Retrofitting | MVS | GO2021004974PH | 21/01/2021 | 247.47 | 0 | 247.47 | Hooghly Division |  | 179.28 | 0 | 0 | 0 | 179.28 | 178.68 | 0 | 0 | 0 | 178.68 | 72.2 | 70
94 | HOOGHLY | SM/07950 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | TSM/007131 | 8196987 | Retrofitting | MVS | GO2021004961PH | 21/01/2021 | 99.37 | 0 | 99.37 | Hooghly Division |  | 99.34 | 0 | 0 | 0 | 99.34 | 99.34 | 0 | 0 | 0 | 99.34 | 99.96 | 99
95 | HOOGHLY | SM/07543 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | TSM/006684 | 8197868 | Retrofitting | MVS | GO2021003909PH | 31/12/2020 | 86.15 | 0 | 86.15 | Hooghly Division |  | 46.56 | 0 | 0 | 0 | 46.56 | 46.56 | 0 | 0 | 0 | 46.56 | 54.05 | 70
96 | HOOGHLY | SM/07951 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | TSM/007132 | 8196994 | Retrofitting | MVS | GO2021004975PH | 21/01/2021 | 99.86 | 0 | 99.86 | Hooghly Division |  | 96.94 | 0 | 0 | 0 | 96.94 | 96.94 | 0 | 0 | 0 | 96.94 | 97.08 | 98
97 | HOOGHLY | SM/07947 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. | TSM/007128 | 8196823 | Retrofitting | MVS | GO2021004971PH | 21/01/2021 | 83.61 | 0 | 83.61 | Hooghly Division |  | 51.7 | 0 | 5.7 | 0 | 57.4 | 51.7 | 0 | 5.7 | 0 | 57.4 | 68.65 | 40
98 | HOOGHLY | SM/07541 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME | TSM/006699 | 8197916 | Retrofitting | MVS | GO2021003914PH | 31/12/2020 | 56.68 | 0 | 56.68 | Hooghly Division |  | 52.12 | 0 | 0 | 0 | 52.12 | 52.12 | 0 | 0 | 0 | 52.12 | 91.96 | 90
99 | HOOGHLY | SM/09772 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | TSM/008316 | 40002442 | Retrofitting | MVS | GO2122006246PH | 30/11/2021 | 337.05 | 0 | 337.05 | Hooghly Division |  | 229.22 | 0 | 0 | 56.76 | 285.98 | 228.29 | 0 | 0 | 56.76 | 285.06 | 84.57 | 80
100 | HOOGHLY | SM/08737 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. | TSM/007385 | 7940569 | Retrofitting | MVS | GO2122003172PH | 09/09/2021 | 163.87 | 0 | 163.87 | Hooghly Division |  | 66.97 | 0 | 0 | 0 | 66.97 | 66.97 | 0 | 0 | 0 | 66.97 | 40.87 | 100
101 | HOOGHLY | SM/09070 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | TSM/008207 | 8390218 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 136.85 | 0 | 136.85 | Hooghly Division |  | 121.86 | 0 | 0 | 11 | 132.86 | 121.86 | 0 | 0 | 11 | 132.86 | 97.09 | 70
102 | HOOGHLY | SM/09071 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. | TSM/008209 | 8390229 | Retrofitting | SVS | GO2122004569PH | 28/10/2021 | 50.04 | 0 | 50.04 | Hooghly Division |  | 25.3 | 0 | 0 | 0 | 25.3 | 23.45 | 0 | 0 | 0 | 23.45 | 46.86 | 55
103 | HOOGHLY | SM/07944 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | TSM/007125 | 7597918 | Retrofitting | MVS | GO2021004973PH | 21/01/2021 | 48.29 | 0 | 48.29 | Hooghly Division |  | 33.53 | 0 | 0 | 0 | 33.53 | 33.53 | 0 | 0 | 0 | 33.53 | 69.43 | 90
104 | HOOGHLY | SM/06762 | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme | TSM/005637 | 8136191 | Retrofitting | MVS | GO2021001272PH | 18/09/2020 | 87.72 | 0 | 87.72 | Hooghly Division |  | 58.51 | 0 | 0 | 0 | 58.51 | 58.51 | 0 | 0 | 0 | 58.51 | 66.7 | 90
105 | HOOGHLY | SM/09066 | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | TSM/008215 | 7401875 | Retrofitting | MVS | GO2122004569PH | 28/10/2021 | 97.91 | 0 | 97.91 | Hooghly Division |  | 61.71 | 0 | 0 | 11.5 | 73.21 | 52.89 | 0 | 0 | 11.5 | 64.39 | 65.76 | 100
106 | HOOGHLY | SM/18110 | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme | TSM/020534 | 40066205 | Retrofitting | MVS | GO2223017771PH | 27/03/2023 | 142.51 | 0 | 142.51 | Hooghly Division |  | 101.92 | 0 | 0 | 0 | 101.92 | 101.92 | 0 | 0 | 0 | 101.92 | 71.51 | 75
107 | HOOGHLY | SM/06767 | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | TSM/005641 | 8136209 | Retrofitting | MVS | GO2021001276PH | 18/09/2020 | 99.51 | 0 | 99.51 | Hooghly Division |  | 95.2 | 0 | 0 | 0 | 95.2 | 64.62 | 0 | 0 | 0 | 64.62 | 64.94 | 80
108 | HOOGHLY | SM/06759 | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme | TSM/005638 | 8136191 | Retrofitting | SVS | GO2021001270PH | 18/09/2020 | 40.46 | 0 | 40.46 | Hooghly Division |  | 39 | 0 | 0 | 0 | 39 | 39 | 0 | 0 | 0 | 39 | 96.38 | 90
109 | HOOGHLY | SM/06758 | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Rajarambati, Talandu, Taragun Mouza of Digsui-Heora (Zone-II) PWSS | TSM/005635 | 8136095 | Retrofitting | MVS | GO2021001269PH | 18/09/2020 | 74.68 | 0 | 74.68 | Hooghly Division |  | 29.43 | 0 | 0 | 0 | 29.43 | 29.43 | 0 | 0 | 0 | 29.43 | 39.41 | 45
110 | HOOGHLY | SM/10131 | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME | TSM/009864 | 40004900 | Retrofitting | MVS | GO2122009347PH | 08/02/2022 | 83.52 | 0 | 83.52 | Hooghly Division |  | 52.06 | 0 | 0 | 0 | 52.06 | 52.06 | 0 | 0 | 0 | 52.06 | 62.33 | 65
111 | HOOGHLY | SM/13357 | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | TSM/010438 | 40027926 | Retrofitting | MVS | GO2223008944PH | 19/10/2022 | 38.98 | 0 | 38.98 | Hooghly Division |  | 31.74 | 0 | 0 | 0 | 31.74 | 31.74 | 0 | 0 | 0 | 31.74 | 81.45 | 85
112 | HOOGHLY | SM/06755 | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) | TSM/005629 | 8136162 | Retrofitting | SVS | GO2021001280PH | 18/09/2020 | 99.95 | 0 | 99.95 | Hooghly Division |  | 97.04 | 0 | 2.92 | 0 | 99.95 | 97.04 | 0 | 2.92 | 0 | 99.95 | 100 | 85
113 | HOOGHLY | SM/06756 | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) | TSM/005630 | 7355467 | Retrofitting | MVS | GO2021001281PH | 18/09/2020 | 99.92 | 0 | 99.92 | Hooghly Division |  | 97 | 0 | 0 | 0 | 97 | 97 | 0 | 0 | 0 | 97 | 97.08 | 100
114 | HOOGHLY | SM/11001 | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010361 | 40014814 | Retrofitting | MVS | GO2223003716PH | 01/06/2022 | 128.04 | 0 | 128.04 | Hooghly Division | Electrical Division | 48.47 | 0 | 11.4 | 0 | 59.87 | 48.47 | 0 | 11.4 | 0 | 59.87 | 46.76 | 50
115 | HOOGHLY | SM/13356 | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | TSM/010441 | 40027945 | Retrofitting | MVS | GO2223008931PH | 19/10/2022 | 103.91 | 0 | 103.91 | Hooghly Division |  | 54.39 | 0 | 0 | 0 | 54.39 | 54.39 | 0 | 0 | 0 | 54.39 | 52.35 | 50
116 | HOOGHLY | SM/13355 | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010499 | 40027938 | Retrofitting | MVS | GO2223008941PH | 19/10/2022 | 139.24 | 0 | 139.24 | Hooghly Division |  | 0.7 | 0 | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0.7 | 0.5 | 5
117 | HOOGHLY | SM/13354 | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010506 | 40027946 | Retrofitting | MVS | GO2223008937PH | 19/10/2022 | 295.6 | 0 | 295.6 | Hooghly Division |  | 80.33 | 0 | 0 | 0 | 80.33 | 80.33 | 0 | 0 | 0 | 80.33 | 27.17 | 40
118 | HOOGHLY | SM/12882 | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010507 | 40026588 | Retrofitting | MVS | GO2223008138PH | 23/09/2022 | 409.9 | 0 | 409.9 | Hooghly Division |  | 80 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 80 | 19.52 | 25
119 | HOOGHLY | SM/11225 | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010362 | 6865612 | Retrofitting | MVS | GO2223004151PH | 16/06/2022 | 271.91 | 0 | 271.91 | Hooghly Division |  | 44.6 | 0 | 0 | 0 | 44.6 | 44.6 | 0 | 0 | 0 | 44.6 | 16.4 | 98
120 | HOOGHLY | SM/13353 | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE | TSM/010508 | 40027922 | Retrofitting | MVS | GO2223008949PH | 19/10/2022 | 186.31 | 0 | 186.31 | Hooghly Division |  | 117.26 | 0 | 0 | 0 | 117.26 | 117.26 | 0 | 0 | 0 | 117.26 | 62.94 | 85
121 | HOOGHLY | SM/11006 | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. | TSM/010364 | 7544501 | Retrofitting | SVS | GO2223003712PH | 01/06/2022 | 77.49 | 0 | 77.49 | Hooghly Division |  | 4.69 | 0 | 0 | 0 | 4.69 | 4.69 | 0 | 0 | 0 | 4.69 | 6.05 | 20
Total | [9 empty] | 15680.46 | 0 | 15680.46 |  |  | 9298.54 | 0 | 181.94 | 198.61 | 9679.09 | 9111.94 | 0 | 181.94 | 198.61 | 9492.49 | 60.54