## JJM Schemes Financial Status (H
JJM Schemes Financial Status (HOWRAH) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | HOWRAH | SM/18565 | Augmentation of Ground Water Based Harop (Zone-I & II) Piped Water Supply Scheme | TSM/017876 | 40034293 | Augmentation | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1051.92 | 124.01 | 1175.93 | Howrah Division | Electrical Division | 88.33 | 26.97 | 11.4 | 0 | 126.69 | 88.33 | 26.97 | 11.4 | 0 | 126.69 | 10.77 | 30
2 | HOWRAH | SM/19186 | Augmentation of Surface Water Based Water Supply Scheme for Shyampur-I & II and part of Bagnan-I, Bagnan-II and Uluberia-I Blocks | TSM/019280 | 40042934 | Augmentation | MVS | 631/PHE-28011/220/2023-ESTT CELL-Dept. of PHE | 06/03/2024 | 45532.55 | 9787 | 55319.55 | Howrah Division | Electrical Division | 215.53 | 116.65 | 2725.8 | 0 | 3057.98 | 215.53 | 116.65 | 2725.8 | 0 | 3057.98 | 5.53 | 20
3 | HOWRAH | SM/11159 | Makardaha PWSS with provision of FHTC in connection of Domjur Block | TSM/010688 | 40026097 | Augmentation | MVS | GO2223003772PH | 02/06/2022 | 1034.65 | 49.5 | 1084.15 | Howrah Division | Electrical Division | 476.25 | 44.07 | 74.08 | 0 | 594.39 | 476.25 | 44.07 | 74.08 | 0 | 594.39 | 54.83 | 75
4 | HOWRAH | SM/18848 | Source Augmentation of Chitnan Water Supply Scheme | TSM/021553 | 40067378 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 12.73 | 4.85 | 0 | 0 | 17.58 | 12.73 | 4.85 | 0 | 0 | 17.58 | 15.25 | 75
5 | HOWRAH | SM/12874 | Augmentation of Bamunhati Water Supply Scheme | TSM/012517 | 40046847 | Augmentation | MVS | GO2223008169PH | 23/09/2022 | 1185.08 | 118.82 | 1303.9 | Howrah Division | Electrical Division | 43.42 | 0 | 113.87 | 0 | 157.29 | 43.42 | 0 | 113.87 | 0 | 157.29 | 12.06 | 45
6 | HOWRAH | SM/10145 | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | TSM/008353 | 40009853 | Augmentation | MVS | GO2122009619PH | 10/02/2022 | 1074.46 | 18.15 | 1092.62 | Howrah Division | Electrical Division | 728.74 | 17.46 | 16.61 | 0 | 762.8 | 728.74 | 17.46 | 16.61 | 0 | 762.8 | 69.81 | 78
7 | HOWRAH | SM/10020 | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | TSM/008354 | 40009800 | Augmentation | MVS | GO2122007937PH | 05/01/2022 | 1486.8 | 37.42 | 1524.22 | Howrah Division | Electrical Division | 1125.46 | 35.88 | 118.74 | 0 | 1280.08 | 1125.46 | 35.88 | 118.74 | 0 | 1280.08 | 83.98 | 57
8 | HOWRAH | SM/09930 | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | TSM/008801 | 40009743 | Augmentation | MVS | GO2122006610PH | 09/12/2021 | 653.16 | 25.88 | 679.04 | Howrah Division | Electrical Division | 357.08 | 24.3 | 0 | 0 | 381.39 | 357.08 | 24.3 | 0 | 0 | 381.39 | 56.17 | 85
9 | HOWRAH | SM/15186 | Augmentation of Ground Water Based Piped Water Supply Scheme with Functional Household Tap Connection for Joargarh | TSM/011062 | 40041479 | Augmentation | MVS | GO2223013414PH | 07/02/2023 | 753.96 | 73 | 826.95 | Howrah Division | Electrical Division | 192.51 | 5.13 | 76.66 | 0 | 274.31 | 192.51 | 5.13 | 76.66 | 0 | 274.31 | 33.17 | 41
10 | HOWRAH | SM/09351 | Augmentation of Ground water based PWSS Bhurshit Bamunpara | TSM/008620 | 40011752 | Augmentation | MVS | GO2122005397PH | 12/11/2021 | 618.61 | 0 | 618.61 | Howrah Division | Electrical Division | 490.7 | 0 | 97.38 | 0 | 588.08 | 490.64 | 0 | 97.38 | 0 | 588.01 | 95.05 | 96
11 | HOWRAH | SM/09586 | Augmentation of Ground Water Based PWSS for Shekrahati | TSM/008595 | 40009699 | Augmentation | MVS | GO2122005672PH | 22/11/2021 | 576.22 | 23.98 | 600.2 | Howrah Division | Electrical Division | 347.15 | 13.45 | 43.11 | 0 | 403.71 | 347.15 | 13.45 | 43.11 | 0 | 403.71 | 67.26 | 97
12 | HOWRAH | SM/10146 | Augmentation of Ground water based PWSS Jujarsah | TSM/008639 | 40009676 | Augmentation | MVS | GO2122009618PH | 10/02/2022 | 1488.67 | 111.95 | 1600.62 | Howrah Division | Electrical Division | 628.93 | 6.57 | 276.33 | 0 | 911.83 | 628.93 | 6.57 | 276.33 | 0 | 911.83 | 56.97 | 66
13 | HOWRAH | SM/09350 | Augmentation of Ground water based PWSS Kanupat. | TSM/008622 | 40012002 | Augmentation | MVS | GO2122005391PH | 12/11/2021 | 390.73 | 23.98 | 414.71 | Howrah Division | Electrical Division | 231.46 | 8.07 | 11.87 | 9.37 | 260.76 | 231.46 | 8.07 | 11.87 | 9.37 | 260.76 | 62.88 | 98
14 | HOWRAH | SM/09349 | Augmentation of Ground water based PWSS Mankur Deulgram | TSM/008627 | 40009877 | Augmentation | MVS | GO2122005394PH | 12/11/2021 | 951.27 | 42.13 | 993.4 | Howrah Division | Electrical Division | 540.57 | 28.21 | 63.68 | 0 | 632.45 | 540.57 | 28.21 | 63.68 | 0 | 632.45 | 63.67 | 72
15 | HOWRAH | SM/09347 | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | TSM/008640 | 40009678 | Augmentation | MVS | GO2122005392PH | 12/11/2021 | 529.86 | 16.59 | 546.45 | Howrah Division | Electrical Division | 309.04 | 16.54 | 58.4 | 33.93 | 417.91 | 309.04 | 16.54 | 58.4 | 33.93 | 417.91 | 76.48 | 69
16 | HOWRAH | SM/09348 | Augmentation of Ground water based PWSS Pancharul | TSM/008635 | 40009873 | Augmentation | MVS | GO2122005395PH | 12/11/2021 | 738.12 | 23.98 | 762.1 | Howrah Division | Electrical Division | 490.99 | 9.99 | 33.66 | 0 | 534.65 | 490.99 | 9.99 | 33.66 | 0 | 534.65 | 70.15 | 95
17 | HOWRAH | SM/10143 | Augmentation of Ground water based PWSS Pulgustia | TSM/008637 | 40005287 | Augmentation | MVS | GO2122009587PH | 09/02/2022 | 652.4 | 56.32 | 708.72 | Howrah Division | Electrical Division | 570.45 | 54.68 | 62.95 | 0 | 688.08 | 570.45 | 54.68 | 62.95 | 0 | 688.08 | 97.09 | 98
18 | HOWRAH | SM/18567 | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | TSM/017891 | 40046852 | Augmentation | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1262.25 | 154.01 | 1416.25 | Howrah Division | Electrical Division | 381.63 | 30.7 | 0 | 0 | 412.33 | 381.63 | 30.7 | 0 | 0 | 412.33 | 29.11 | 60
19 | HOWRAH | SM/09428 | Augmentation of Ground water PWSS for Islampur | TSM/008589 | 40009796 | Augmentation | MVS | GO2122005477PH | 17/11/2021 | 730.26 | 23.99 | 754.25 | Howrah Division | Electrical Division | 387.16 | 20.38 | 27.6 | 0 | 435.14 | 387.16 | 20.38 | 27.6 | 0 | 435.14 | 57.69 | 81
20 | HOWRAH | SM/10021 | Augmentation of Kanpur Piped water supply scheme (Zone-II) | TSM/008513 | 40009622 | Augmentation | MVS | GO2122007939PH | 05/01/2022 | 1489.28 | 63.87 | 1553.14 | Howrah Division | Electrical Division | 565.14 | 40.86 | 48.78 | 39.93 | 694.72 | 565.14 | 40.86 | 48.78 | 39.93 | 694.72 | 44.73 | 90
21 | HOWRAH | SM/16947 | Augmentation of Keshabpur Water supply scheme | TSM/010465 | 40065699 | Augmentation | SVS | GO2223016574PH | 16/03/2023 | 857.9 | 0 | 857.9 | Howrah Division | Electrical Division | 160.37 | 8.98 | 60.32 | 0 | 229.68 | 160.37 | 8.98 | 60.32 | 0 | 229.68 | 26.77 | 85
22 | HOWRAH | SM/11271 | Augmentation of Khalatpur PWSS | TSM/008963 | 40021524 | Augmentation | MVS | GO2223004442PH | 24/06/2022 | 957.54 | 27.83 | 985.37 | Howrah Division | Electrical Division | 339.2 | 0 | 19.61 | 0 | 358.82 | 339.2 | 0 | 19.61 | 0 | 358.82 | 36.41 | 92
23 | HOWRAH | SM/10035 | Augmentation of Maju piped water supply scheme. | TSM/008091 | 40046828 | Augmentation | MVS | GO2122008405PH | 19/01/2022 | 1628.89 | 63.87 | 1692.75 | Howrah Division | Electrical Division | 1012.94 | 48.68 | 97.34 | 0 | 1158.96 | 1012.94 | 44.43 | 97.34 | 0 | 1154.71 | 68.21 | 5
24 | HOWRAH | SM/09720 | Augmentation of Nischintapur piped water supply scheme. | TSM/008092 | 40005599 | Augmentation | MVS | GO2122005968PH | 26/11/2021 | 589.85 | 0 | 589.85 | Howrah Division |  | 397.41 | 0 | 19.07 | 0 | 416.47 | 397.41 | 0 | 19.07 | 0 | 416.47 | 70.61 | 95
25 | HOWRAH | SM/19187 | Augmentation of surface water based Sankrail Piped water supply scheme | TSM/019257 | 40041744 | Augmentation | MVS | 631/PHE-28011/220/2023-ESTT CELL-Dept. of PHE | 06/03/2024 | 33316.69 | 663.61 | 33980.3 | Howrah Division | Electrical Division | 714.06 | 0 | 1931.2 | 0 | 2645.25 | 714.06 | 0 | 1931.2 | 0 | 2645.25 | 7.78 | 25
26 | HOWRAH | SM/18398 | Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme | TSM/010806 | 40048641 | Augmentation | MVS | 1847/PHE-28011/86/2023-ESTT CELL-Dept. of PHE | 12/07/2023 | 1809.87 | 77.28 | 1887.15 | Howrah Division |  | 787.64 | 17.22 | 229 | 0 | 1033.86 | 787.64 | 17.22 | 229 | 0 | 1033.86 | 54.78 | 65
27 | HOWRAH | SM/09429 | Aumentation of PWSS for Surikhali | TSM/008596 | 40009613 | Augmentation | SVS | GO2122005480PH | 17/11/2021 | 278.74 | 55.01 | 333.75 | Howrah Division | Electrical Division | 184.28 | 19.44 | 0 | 0 | 203.72 | 184.24 | 19.44 | 0 | 0 | 203.67 | 61.03 | 98
28 | HOWRAH | SM/11723 | Banharishpur PWSS with FHTC Block Panchla, District-Howrah | TSM/011532 | 40046834 | Augmentation | MVS | GO2223005913PH | 02/08/2022 | 777.32 | 75.85 | 853.17 | Howrah Division | Electrical Division | 368.49 | 42.98 | 42.89 | 0 | 454.36 | 368.49 | 42.98 | 42.89 | 0 | 454.36 | 53.26 | 91
29 | HOWRAH | SM/18560 | DEULPUR & GANGADHARPUR ZONE-I PIPED WATER SUPPLY SCHEME. | TSM/014806 | 40046851 | Augmentation | MVS | 2142/PHE-28011/120/2023-ESTT CELL-Dept. of PHE | 31/07/2023 | 1356.34 | 67.87 | 1424.21 | Howrah Division | Electrical Division | 481.42 | 6.52 | 94.66 | 0 | 582.61 | 481.42 | 6.52 | 94.66 | 0 | 582.61 | 40.91 | 64
30 | HOWRAH | SM/14154 | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | TSM/015277 | 40046826 | Augmentation | MVS | GO2223011612PH | 05/01/2023 | 1379.66 | 80.6 | 1460.26 | Howrah Division | Electrical Division | 386.74 | 0.32 | 316.82 | 0 | 703.89 | 386.74 | 0.32 | 316.82 | 0 | 703.89 | 48.2 | 90
31 | HOWRAH | SM/14095 | DPR for the augmentation scheme of Bargachia PWSS under Howrah Division | TSM/010279 | 40046837 | Augmentation | MVS | GO2223010908PH | 14/12/2022 | 7698.57 | 513.14 | 8211.71 | Howrah Division | Electrical Division | 3003.83 | 346.01 | 483.01 | 0 | 3832.86 | 3003.83 | 300.82 | 483.01 | 0 | 3787.67 | 46.13 | 55
32 | HOWRAH | SM/11168 | Rampur PWSS | TSM/008769 | 40021516 | Augmentation | MVS | GO2223003775PH | 02/06/2022 | 586.44 | 27.83 | 614.27 | Howrah Division | Electrical Division | 343.3 | 0 | 0 | 0 | 343.3 | 343.3 | 0 | 0 | 0 | 343.3 | 55.89 | 92
33 | HOWRAH | SM/08966 | Rejuvenation of Amta Piped water supply scheme. | TSM/005366 | 40011765 | Augmentation | MVS | GO2122003932PH | 28/10/2021 | 2432.63 | 79.11 | 2511.74 | Howrah Division | Electrical Division | 2007.07 | 74.68 | 58.95 | 0 | 2140.7 | 2007.07 | 74.68 | 58.95 | 0 | 2140.7 | 85.23 | 98
34 | HOWRAH | SM/18882 | Source Augmentaion of kulgacchi Water Supply Scheme | TSM/021380 | 40067372 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 162.52 | 89.03 | 251.54 | Howrah Division | Electrical Division | 79.8 | 54.65 | 0 | 0 | 134.45 | 79.8 | 54.65 | 0 | 0 | 134.45 | 53.45 | 95
35 | HOWRAH | SM/18883 | Source Augmentation of Amragari Water Supply Scheme | TSM/021379 | 40067401 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 430.61 | 61.38 | 491.99 | Howrah Division | Electrical Division | 29.12 | 48.83 | 0 | 0 | 77.95 | 29.12 | 48.83 | 0 | 0 | 77.95 | 15.84 | 45
36 | HOWRAH | SM/18885 | Source Augmentation of Balichak Water Supply Scheme | TSM/021377 | 40067396 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 115.78 | 61.38 | 177.16 | Howrah Division | Electrical Division | 28.06 | 31.24 | 0 | 0 | 59.29 | 28.06 | 31.24 | 0 | 0 | 59.29 | 33.47 | 45
37 | HOWRAH | SM/18850 | Source Augmentation of Bauria Water Supply Scheme | TSM/021551 | 40067375 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 79.14 | 10.4 | 0 | 0 | 89.54 | 79.14 | 10.4 | 0 | 0 | 89.54 | 77.7 | 92
38 | HOWRAH | SM/18845 | Source Augmentation of Beldubi Water Supply Scheme | TSM/021363 | 40067384 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 121.41 | 33.73 | 155.14 | Howrah Division | Electrical Division | 29.53 | 4.8 | 0 | 0 | 34.34 | 29.53 | 4.8 | 0 | 0 | 34.34 | 22.13 | 91
39 | HOWRAH | SM/18846 | Source Augmentation of Bikihakola Water Supply Scheme | TSM/021345 | 40067382 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 425.05 | 33.72 | 458.77 | Howrah Division | Electrical Division | 63.64 | 0 | 0 | 0 | 63.64 | 63.64 | 0 | 0 | 0 | 63.64 | 13.87 | 36
40 | HOWRAH | SM/18849 | Source Augmentation of Garbhabanipur Water Supply Scheme | TSM/021552 | 40067377 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 14.62 | 12.18 | 0 | 0 | 26.8 | 14.62 | 12.18 | 0 | 0 | 26.8 | 23.25 | 60
41 | HOWRAH | SM/18843 | Source Augmentation of Gobindapur Piped Water Supply Scheme | TSM/021367 | 40067388 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 111.55 | 33.73 | 145.28 | Howrah Division | Electrical Division | 56.45 | 19.93 | 0 | 0 | 76.38 | 56.45 | 19.93 | 0 | 0 | 76.38 | 52.58 | 80
42 | HOWRAH | SM/18842 | Source Augmentation of Laskarpur Piped Water Supply Scheme | TSM/021371 | 40067389 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 154.56 | 67.45 | 222.01 | Howrah Division | Electrical Division | 32.32 | 58.48 | 0 | 0 | 90.79 | 32.32 | 58.48 | 0 | 0 | 90.79 | 40.9 | 95
43 | HOWRAH | SM/18841 | Source Augmentation of Majhu Khetra Water Supply Scheme | TSM/021407 | 40067478 | Augmentation | SVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 81.52 | 33.73 | 115.24 | Howrah Division | Electrical Division | 16.09 | 0 | 0 | 0 | 16.09 | 16.09 | 0 | 0 | 0 | 16.09 | 13.96 | 98
44 | HOWRAH | SM/18847 | Source Augmentation of Nakubar Water Supply Scheme | TSM/021308 | 40067379 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 127.82 | 61.38 | 189.2 | Howrah Division | Electrical Division | 11.44 | 9.56 | 0 | 0 | 21 | 11.44 | 9.56 | 0 | 0 | 21 | 11.1 | 90
45 | HOWRAH | SM/18844 | Source Augmentation of Sahapur Piped Water Supply Scheme | TSM/021366 | 40067385 | Augmentation | MVS | 2975/PHE/IV/W-660/23 | 29/09/2023 | 119.08 | 33.73 | 152.8 | Howrah Division | Electrical Division | 1.31 | 6.26 | 0 | 0 | 7.57 | 1.31 | 6.26 | 0 | 0 | 7.57 | 4.95 | 63
46 | HOWRAH | SM/18884 | Source Augmentation of Sarda Water Supply Scheme | TSM/021378 | 40067398 | Augmentation | MVS | PHE/IV/3035/W-658/23 | 05/10/2023 | 77.61 | 61.38 | 138.99 | Howrah Division | Electrical Division | 0.78 | 4.13 | 0 | 0 | 4.9 | 0.78 | 4.13 | 0 | 0 | 4.9 | 3.53 | 22
Total | [9 empty] | 118042.73 | 13178.36 | 131221.09 |  |  | 18812.34 | 1330 | 7213.79 | 83.23 | 27439.36 | 18812.24 | 1280.56 | 7213.79 | 83.23 | 27389.82 | 20.87