## JJM Schemes Financial Status (S
JJM Schemes Financial Status (SOUTH 24 PARGANAS) (Rs. in Lakh)
Sl No. | District | Scheme Code | Scheme Name | TSM Code | IMIS Code | Scheme Catgory | Scheme coverage type | Administrative Approval |  | Sanctioned Cost |  |  | Civil Division | Mech./Elec. Division | Allotment |  |  |  |  | Expenditure |  |  |  |  | % Expenditure | % Physical Progress
[8 empty] | Number | Date | Civil | Mech./Elec. | Total |  |  | Civil | Mech./Elec. | Resource | Central Drilling | Total | Civil | Mech./Elec. | Resource | Central Drilling | Total
1 | SOUTH 24 PARGANAS | SM/11988 | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | TSM/011226 | 40025993 | New | SVS | GO2223006885PH | 01/09/2022 | 280.13 | 71.66 | 351.79 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 182.56 | 19.93 | 3.34 | 0 | 205.82 | 182.56 | 19.93 | 3.34 | 0 | 205.82 | 58.51 | 68
2 | SOUTH 24 PARGANAS | SM/13801 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011610 | 40034037 | New | SVS | GO2223009957PH | 22/11/2022 | 778.37 | 75.49 | 853.87 | Alipore Division | South 24 Pgs Mechanical Division | 201.49 | 7.83 | 9.54 | 0 | 218.85 | 201.49 | 7.83 | 9.54 | 0 | 218.85 | 25.63 | 0
3 | SOUTH 24 PARGANAS | SM/18392 | BALIARA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011013 | 40035973 | New | SVS | 1815/PHE-28011/211/2023-ESTT CELL-Dept. of PHE | 11/07/2023 | 961.3 | 53.47 | 1014.76 | Alipore Division | South 24 Pgs Mechanical Division | 273.85 | 0 | 16.9 | 0 | 290.75 | 269.25 | 0 | 16.9 | 0 | 286.14 | 28.2 | 30
4 | SOUTH 24 PARGANAS | SM/12044 | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | TSM/010740 | 40026140 | New | MVS | GO2223006889PH | 01/09/2022 | 841.38 | 78.5 | 919.88 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 223.57 | 18.25 | 16.88 | 0 | 258.71 | 223.57 | 18.25 | 16.88 | 0 | 258.71 | 28.12 | 50
5 | SOUTH 24 PARGANAS | SM/14419 | CHANDPUR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | TSM/010665 | 40033918 | New | MVS | GO2223012151PH | 20/01/2023 | 1003.89 | 76.05 | 1079.94 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 288.41 | 0 | 56.73 | 0 | 345.14 | 288.41 | 0 | 56.73 | 0 | 345.14 | 31.96 | 32
6 | SOUTH 24 PARGANAS | SM/18394 | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | TSM/017111 | 40035213 | New | MVS | 1817/PHE-28011/182/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1198.45 | 47.27 | 1245.72 | Alipore Division | South 24 Pgs Mechanical Division | 438.55 | 20.01 | 59.01 | 0 | 517.57 | 431.24 | 20.01 | 59.01 | 0 | 510.26 | 40.96 | 45
7 | SOUTH 24 PARGANAS | SM/18684 | DAKSHIN DURGAPUR & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION PHE DTE. | TSM/011020 | 40066198 | New | MVS | 2245/PHE-28011/229/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1251.64 | 49.24 | 1300.88 | Alipore Division | South 24 Pgs Mechanical Division | 681.82 | 8.67 | 48.39 | 0 | 738.88 | 681.82 | 8.67 | 48.39 | 0 | 738.88 | 56.8 | 55
8 | SOUTH 24 PARGANAS | SM/16758 | Dakshin Durgapur Piped Water Supply Scheme. | TSM/003912 | 40060099 | New | SVS | GO2223015683PH | 13/03/2023 | 763.9 | 36.37 | 800.27 | Alipore Division | South 24 Pgs Mechanical Division | 389.91 | 0 | 41.98 | 0 | 431.9 | 389.91 | 0 | 41.98 | 0 | 431.9 | 53.97 | 60
9 | SOUTH 24 PARGANAS | SM/15633 | DETAILED PROJECT REPORT FORPROPOSED GROUND WATER BASED DONGAJORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KULTALI BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT | TSM/020398 | 40053038 | New | SVS | GO2223013879PH | 15/02/2023 | 98.69 | 21.23 | 119.91 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.39 | 0 | 0 | 0 | 2.39 | 2.39 | 0 | 0 | 0 | 2.39 | 2 | 0
10 | SOUTH 24 PARGANAS | SM/18127 | DURGANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011063 | 40066195 | New | SVS | GO2223017946PH | 29/03/2023 | 195.22 | 22.34 | 217.56 | Alipore Division | South 24 Pgs Mechanical Division | 57.72 | 0 | 2.72 | 0 | 60.44 | 57.72 | 0 | 2.72 | 0 | 60.44 | 27.78 | 62
11 | SOUTH 24 PARGANAS | SM/12043 | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | TSM/010678 | 40026128 | New | MVS | GO2223006888PH | 01/09/2022 | 904.48 | 76.7 | 981.18 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 156.61 | 0 | 24.44 | 0 | 181.04 | 156.61 | 0 | 24.44 | 0 | 181.04 | 18.45 | 40
12 | SOUTH 24 PARGANAS | SM/14988 | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | TSM/017110 | 40035211 | New | SVS | GO2223013173PH | 04/02/2023 | 453.74 | 69.8 | 523.55 | Alipore Division | South 24 Pgs Mechanical Division | 271.57 | 23.56 | 11.5 | 0 | 306.64 | 271.57 | 23.56 | 11.5 | 0 | 306.64 | 58.57 | 95
13 | SOUTH 24 PARGANAS | SM/15524 | GOPALNAGAR UTTAR ZONE-I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011055 | 40032818 | New | MVS | GO2223013999PH | 16/02/2023 | 1124.68 | 43.99 | 1168.66 | Alipore Division | South 24 Pgs Mechanical Division | 241.1 | 9.61 | 36.95 | 0 | 287.65 | 241.1 | 9.61 | 36.95 | 0 | 287.65 | 24.61 | 0
14 | SOUTH 24 PARGANAS | SM/13974 | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | TSM/016105 | 40035320 | New | SVS | GO2223010327PH | 01/12/2022 | 722.86 | 75.49 | 798.36 | Alipore Division | South 24 Pgs Mechanical Division | 420.23 | 6.73 | 9.46 | 0 | 436.41 | 404.38 | 6.73 | 9.46 | 0 | 420.56 | 52.68 | 93
15 | SOUTH 24 PARGANAS | SM/14156 | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | TSM/015403 | 40034582 | New | MVS | GO2223011626PH | 05/01/2023 | 1170.12 | 107.48 | 1277.6 | Alipore Division | South 24 Pgs Mechanical Division | 435.89 | 0 | 77.43 | 0 | 513.32 | 435.89 | 0 | 77.43 | 0 | 513.32 | 40.18 | 90
16 | SOUTH 24 PARGANAS | SM/12733 | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011946 | 40028498 | New | SVS | GO2223007931PH | 20/09/2022 | 642.04 | 71.66 | 713.69 | Alipore Division | South 24 Pgs Mechanical Division | 386.82 | 22.67 | 43.75 | 0 | 453.23 | 386.82 | 12.61 | 43.75 | 0 | 443.17 | 62.1 | 80
17 | SOUTH 24 PARGANAS | SM/11848 | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | TSM/011952 | 40019085 | New | MVS | GO2223006310PH | 16/08/2022 | 814.61 | 71.66 | 886.26 | Alipore Division | South 24 Pgs Mechanical Division | 397.26 | 0 | 12.17 | 0 | 409.42 | 387.61 | 0 | 12.17 | 0 | 399.78 | 45.11 | 82
18 | SOUTH 24 PARGANAS | SM/13840 | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | TSM/015936 | 40034597 | New | SVS | GO2223010124PH | 25/11/2022 | 520.55 | 71.66 | 592.21 | Alipore Division | South 24 Pgs Mechanical Division | 131.42 | 6.72 | 46.68 | 0 | 184.82 | 131.42 | 6.72 | 46.68 | 0 | 184.82 | 31.21 | 52
19 | SOUTH 24 PARGANAS | SM/16294 | GROUND WATER BASED BHUBANNAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015386 | 40049227 | New | SVS | GO2223014839PH | 24/02/2023 | 768.73 | 71.66 | 840.39 | Alipore Division | South 24 Pgs Mechanical Division | 56.84 | 0 | 51.19 | 0 | 108.03 | 56.84 | 0 | 51.19 | 0 | 108.03 | 12.85 | 30
20 | SOUTH 24 PARGANAS | SM/13975 | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | TSM/016104 | 40035288 | New | MVS | GO2223010329PH | 01/12/2022 | 679.11 | 107.48 | 786.59 | Alipore Division | South 24 Pgs Mechanical Division | 281.74 | 46.3 | 100.82 | 0 | 428.86 | 281.74 | 46.3 | 100.82 | 0 | 428.86 | 54.52 | 62
21 | SOUTH 24 PARGANAS | SM/13839 | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | TSM/015937 | 40034592 | New | SVS | GO2223010115PH | 25/11/2022 | 606.18 | 71.66 | 677.84 | Alipore Division | South 24 Pgs Mechanical Division | 155.72 | 7.92 | 53.94 | 0 | 217.58 | 155.72 | 7.92 | 53.94 | 0 | 217.58 | 32.1 | 38
22 | SOUTH 24 PARGANAS | SM/18718 | GROUND WATER BASED BROJABALLAVPUR (ZONE-I & II) PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-PATHARPRATIMA,DISTRICT - SOUTH 24 PARGANAS | TSM/015410 | 40049223 | New | SVS | 2342/PHE-28011/233/2023-ESTT CELL-Dept. of PHE | 10/08/2023 | 1137.08 | 143.31 | 1280.39 | Alipore Division | South 24 Pgs Mechanical Division | 492.92 | 0 | 41.95 | 0 | 534.87 | 492.92 | 0 | 41.95 | 0 | 534.87 | 41.77 | 52
23 | SOUTH 24 PARGANAS | SM/13011 | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011097 | 40033934 | New | MVS | GO2223008394PH | 29/09/2022 | 870.04 | 71.66 | 941.69 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 172.33 | 29.39 | 9.43 | 0 | 211.15 | 172.33 | 29.39 | 9.43 | 0 | 211.15 | 22.42 | 56
24 | SOUTH 24 PARGANAS | SM/13835 | GROUND WATER BASED CHHOTO BANASHYAM NAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/016114 | 40037413 | New | SVS | GO2223010121PH | 25/11/2022 | 792.86 | 71.66 | 864.51 | Alipore Division | South 24 Pgs Mechanical Division | 249.51 | 10.48 | 11.07 | 0 | 271.07 | 249.51 | 10.48 | 11.07 | 0 | 271.07 | 31.35 | 73
25 | SOUTH 24 PARGANAS | SM/15527 | GROUND WATER BASED CHIMTA (ZONE-I&II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION,PHE DTE, BLOCK-GOSABA, DISTRICT-SOUTH 24 PARGANAS | TSM/016112 | 40035303 | New | SVS | GO2223014000PH | 16/02/2023 | 872.36 | 143.31 | 1015.67 | Alipore Division | South 24 Pgs Mechanical Division | 351.49 | 17.09 | 45.84 | 0 | 414.41 | 346.31 | 17.09 | 45.84 | 0 | 409.24 | 40.29 | 0
26 | SOUTH 24 PARGANAS | SM/13797 | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011941 | 40034030 | New | SVS | GO2223009951PH | 22/11/2022 | 464.99 | 71.66 | 536.65 | Alipore Division | South 24 Pgs Mechanical Division | 238.85 | 0 | 9.3 | 0 | 248.15 | 210.78 | 0 | 9.3 | 0 | 220.08 | 41.01 | 50
27 | SOUTH 24 PARGANAS | SM/16027 | GROUND WATER BASED DEBNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-NAMKHANA, DISTRICT-SOUTH 24 PARAGANAS | TSM/016701 | 40036936 | New | SVS | GO2223014532PH | 22/02/2023 | 730.52 | 71.66 | 802.18 | Alipore Division | South 24 Pgs Mechanical Division | 451.19 | 8.37 | 26.82 | 0 | 486.38 | 451.19 | 8.37 | 26.82 | 0 | 486.38 | 60.63 | 92
28 | SOUTH 24 PARGANAS | SM/11499 | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011007 | 40034079 | New | MVS | GO2223005184PH | 19/07/2022 | 566.81 | 71.66 | 638.47 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 284.46 | 38.04 | 44.43 | 0 | 366.93 | 284.46 | 38.04 | 44.43 | 0 | 366.93 | 57.47 | 80
29 | SOUTH 24 PARGANAS | SM/13842 | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | TSM/015904 | 40034588 | New | SVS | GO2223010111PH | 25/11/2022 | 357.29 | 71.66 | 428.95 | Alipore Division | South 24 Pgs Mechanical Division | 112.13 | 0 | 19.22 | 0 | 131.35 | 112.13 | 0 | 19.22 | 0 | 131.35 | 30.62 | 54
30 | SOUTH 24 PARGANAS | SM/13973 | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | TSM/016109 | 40035297 | New | SVS | GO2223010325PH | 01/12/2022 | 451.82 | 71.66 | 523.48 | Alipore Division | South 24 Pgs Mechanical Division | 193.4 | 28.44 | 28.99 | 0 | 250.84 | 193.4 | 28.44 | 28.99 | 0 | 250.84 | 47.92 | 72
31 | SOUTH 24 PARGANAS | SM/13843 | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | TSM/015899 | 40034589 | New | SVS | GO2223010120PH | 25/11/2022 | 632.19 | 75.49 | 707.69 | Alipore Division | South 24 Pgs Mechanical Division | 171.74 | 9.23 | 8.2 | 0 | 189.17 | 171.74 | 4.53 | 8.2 | 0 | 184.47 | 26.07 | 61
32 | SOUTH 24 PARGANAS | SM/13834 | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | TSM/015945 | 40034595 | New | SVS | GO2223010117PH | 25/11/2022 | 377.97 | 71.66 | 449.63 | Alipore Division | South 24 Pgs Mechanical Division | 105.63 | 5.22 | 10.96 | 0 | 121.81 | 105.63 | 0 | 10.96 | 0 | 116.59 | 25.93 | 47
33 | SOUTH 24 PARGANAS | SM/14157 | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015400 | 40034027 | New | SVS | GO2223011624PH | 05/01/2023 | 1089.39 | 107.48 | 1196.88 | Alipore Division | South 24 Pgs Mechanical Division | 184.64 | 0 | 24.21 | 0 | 208.86 | 184.64 | 0 | 24.21 | 0 | 208.86 | 17.45 | 25
34 | SOUTH 24 PARGANAS | SM/11849 | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011951 | 40019081 | New | SVS | GO2223006314PH | 16/08/2022 | 582.13 | 71.66 | 653.78 | Alipore Division | South 24 Pgs Mechanical Division | 121.8 | 0 | 26.19 | 0 | 147.99 | 121.8 | 0 | 26.19 | 0 | 147.99 | 22.64 | 30
35 | SOUTH 24 PARGANAS | SM/12635 | Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR Blockunder South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011095 | 40025976 | New | MVS | GO2223007811PH | 19/09/2022 | 694.4 | 71.66 | 766.05 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 171.99 | 10.33 | 8.83 | 0 | 191.14 | 171.99 | 10.33 | 8.83 | 0 | 191.14 | 24.95 | 37
36 | SOUTH 24 PARGANAS | SM/11501 | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011012 | 40025987 | New | MVS | GO2223005181PH | 19/07/2022 | 696.42 | 71.66 | 768.07 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 90.82 | 29.14 | 8.73 | 0 | 128.69 | 90.82 | 28.26 | 8.73 | 0 | 127.81 | 16.64 | 51
37 | SOUTH 24 PARGANAS | SM/13836 | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | TSM/015943 | 40034594 | New | SVS | GO2223010127PH | 25/11/2022 | 383.82 | 71.66 | 455.48 | Alipore Division | South 24 Pgs Mechanical Division | 94.97 | 11.99 | 44.87 | 0 | 151.83 | 86.59 | 11.99 | 44.87 | 0 | 143.45 | 31.49 | 46
38 | SOUTH 24 PARGANAS | SM/12636 | Ground water based JELERHAT piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011011 | 40026144 | New | MVS | GO2223007813PH | 19/09/2022 | 682.04 | 71.66 | 753.69 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 266.53 | 5.08 | 10.3 | 0 | 281.91 | 266.53 | 5.08 | 10.3 | 0 | 281.91 | 37.4 | 29
39 | SOUTH 24 PARGANAS | SM/18682 | GROUND WATER BASED KAKDWIP PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION, DISTRICT SOUTH 24 PARGANAS. | TSM/015387 | 40066197 | New | SVS | 2245/PHE-28011/229/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1569.64 | 107.48 | 1677.13 | Alipore Division | South 24 Pgs Mechanical Division | 130.82 | 28.82 | 51.64 | 0 | 211.28 | 130.82 | 28.82 | 51.64 | 0 | 211.28 | 12.6 | 66
40 | SOUTH 24 PARGANAS | SM/13837 | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | TSM/015942 | 40034596 | New | SVS | GO2223010123PH | 25/11/2022 | 667.43 | 71.66 | 739.08 | Alipore Division | South 24 Pgs Mechanical Division | 206.72 | 11.64 | 30.47 | 0 | 248.83 | 182.46 | 7.57 | 30.47 | 0 | 220.5 | 29.83 | 58
41 | SOUTH 24 PARGANAS | SM/13838 | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | TSM/015940 | 40034593 | New | SVS | GO2223010118PH | 25/11/2022 | 544.09 | 71.66 | 615.74 | Alipore Division | South 24 Pgs Mechanical Division | 236.55 | 10.55 | 59.64 | 0 | 306.74 | 236.55 | 0 | 59.64 | 0 | 296.19 | 48.1 | 78
42 | SOUTH 24 PARGANAS | SM/18673 | GROUND WATER BASED KSHETRA MOHANPUR (ZONE I & II), PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS | TSM/016106 | 40049221 | New | SVS | 2241/PHE-28011/200/2023-SCHM CELL-Dept. of PHE | 04/08/2023 | 1049.32 | 143.31 | 1192.64 | Alipore Division | South 24 Pgs Mechanical Division | 265.01 | 17.52 | 4.05 | 0 | 286.59 | 252.74 | 17.52 | 4.05 | 0 | 274.32 | 23 | 53
43 | SOUTH 24 PARGANAS | SM/11500 | Ground water based KURULI piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011008 | 40026258 | New | MVS | GO2223005179PH | 19/07/2022 | 669.61 | 71.66 | 741.27 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 327.71 | 45.41 | 9.32 | 0 | 382.44 | 327.71 | 45.41 | 9.32 | 0 | 382.44 | 51.59 | 51
44 | SOUTH 24 PARGANAS | SM/11877 | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011619 | 40019090 | New | MVS | GO2223006372PH | 17/08/2022 | 731.98 | 71.66 | 803.64 | Alipore Division | South 24 Pgs Mechanical Division | 203.37 | 5.32 | 48.55 | 0 | 257.24 | 199.23 | 5.32 | 48.55 | 0 | 253.1 | 31.49 | 30
45 | SOUTH 24 PARGANAS | SM/18126 | GROUND WATER BASED MADHUSUDANPUR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | TSM/011944 | 40066196 | New | SVS | GO2223017940PH | 29/03/2023 | 541.5 | 35.83 | 577.33 | Alipore Division | South 24 Pgs Mechanical Division | 256.6 | 9.14 | 11.45 | 0 | 277.18 | 240.92 | 9.14 | 11.45 | 0 | 261.5 | 45.3 | 72
46 | SOUTH 24 PARGANAS | SM/16291 | GROUND WATER BASED MANMATHANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015397 | 40049220 | New | SVS | GO2223014836PH | 24/02/2023 | 888 | 71.66 | 959.66 | Alipore Division | South 24 Pgs Mechanical Division | 206.3 | 0 | 46.59 | 0 | 252.89 | 206.3 | 0 | 46.59 | 0 | 252.89 | 26.35 | 40
47 | SOUTH 24 PARGANAS | SM/13964 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Anduldaha Gopalpur village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sys | TSM/014812 | 40035203 | New | SVS | GO2223010351PH | 01/12/2022 | 35.77 | 8.75 | 44.52 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | SOUTH 24 PARGANAS | SM/12575 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of BAINTALA village of Tambuldaha-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution syste | TSM/013450 | 40034031 | New | SVS | GO2223007748PH | 15/09/2022 | 35.65 | 8.75 | 44.39 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 4.7 | 0 | 0 | 4.7 | 0 | 4.7 | 0 | 0 | 4.7 | 10.59 | 12
49 | SOUTH 24 PARGANAS | SM/12759 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Bhairabitala village of Keoratala Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, | TSM/014816 | 40028665 | New | SVS | GO2223007941PH | 20/09/2022 | 35.82 | 8.75 | 44.57 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0.66 | 0 | 0.66 | 0 | 0 | 0.66 | 0 | 0.66 | 1.48 | 0
50 | SOUTH 24 PARGANAS | SM/12756 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Bijoyrampur village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, B | TSM/014808 | 40028647 | New | SVS | GO2223007940PH | 20/09/2022 | 35.39 | 8.75 | 44.14 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0.6 | 1.35 | 0
51 | SOUTH 24 PARGANAS | SM/13961 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Chak Ruplaskar village of Ramkishore Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system | TSM/014819 | 40035201 | New | SVS | GO2223010354PH | 01/12/2022 | 34.62 | 8.75 | 43.37 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | SOUTH 24 PARGANAS | SM/12573 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of HAZRABAND village of Netra Gram Panchayet in Diamond Harbour-I Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution syst | TSM/013461 | 0 | New | SVS | GO2223007734PH | 15/09/2022 | 36.5 | 8.75 | 45.25 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | SOUTH 24 PARGANAS | SM/12757 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kabasenre village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou | TSM/014809 | 40028651 | New | SVS | GO2223007944PH | 20/09/2022 | 34.53 | 8.75 | 43.28 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | SOUTH 24 PARGANAS | SM/12758 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Kamarchak village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bou | TSM/014810 | 40028662 | New | SVS | GO2223007942PH | 22/09/2022 | 35.13 | 8.75 | 43.88 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0.56 | 0 | 0.56 | 0 | 0 | 0.56 | 0 | 0.56 | 1.28 | 0
55 | SOUTH 24 PARGANAS | SM/12576 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of KULER KHOJ village of Tambuldaha-II Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | TSM/013459 | 40067390 | New | SVS | GO2223007735PH | 15/09/2022 | 36.46 | 8.75 | 45.21 | Alipore Division | South 24 Pgs Mechanical Division | 26.16 | 0 | 0 | 0 | 26.16 | 26.16 | 0 | 0 | 0 | 26.16 | 57.86 | 80
56 | SOUTH 24 PARGANAS | SM/13073 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Mithakundu village of Kamarchak Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, Bo | TSM/014811 | 40028663 | New | SVS | GO2223008451PH | 29/09/2022 | 35.05 | 8.75 | 43.8 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0.55 | 0 | 0.55 | 0 | 0 | 0.55 | 0 | 0.55 | 1.25 | 0
57 | SOUTH 24 PARGANAS | SM/13963 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Padmapukhuria village of Karanjali Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution system, | TSM/014814 | 40035198 | New | SVS | GO2223010352PH | 01/12/2022 | 35.35 | 8.75 | 44.1 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | SOUTH 24 PARGANAS | SM/12574 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of PAR KALUGACHHI village of Deuli-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.5 km distribution syst | TSM/013449 | 40034032 | New | SVS | GO2223007754PH | 15/09/2022 | 36.42 | 8.75 | 45.17 | Alipore Division | South 24 Pgs Mechanical Division | 25.66 | 11.27 | 0 | 0 | 36.93 | 25.66 | 11.27 | 0 | 0 | 36.93 | 81.76 | 98
59 | SOUTH 24 PARGANAS | SM/12984 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of RADHABALLABHPUR village of Dearak Gram Panchayet in Diamond Harbour-I Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distributi | TSM/013460 | 40028584 | New | SVS | GO2223008381PH | 28/09/2022 | 34.92 | 8.75 | 43.67 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0.53 | 0 | 0.53 | 0 | 0 | 0.53 | 0 | 0.53 | 1.21 | 0
60 | SOUTH 24 PARGANAS | SM/13962 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Ramanandapur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | TSM/014818 | 40035200 | New | SVS | GO2223010353PH | 01/12/2022 | 35.77 | 8.75 | 44.52 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | SOUTH 24 PARGANAS | SM/12755 | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Uttar Damodarpur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distributio | TSM/014820 | 40028670 | New | SVS | GO2223007943PH | 20/09/2022 | 36.12 | 8.75 | 44.87 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 0 | 0.7 | 0 | 0.7 | 0 | 0 | 0.7 | 0 | 0.7 | 1.57 | 0
62 | SOUTH 24 PARGANAS | SM/12577 | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | TSM/013463 | 40060027 | New | SVS | GO2223007738PH | 15/09/2022 | 29.92 | 8.75 | 38.67 | Alipore Division | South 24 Pgs Mechanical Division | 0 | 2.71 | 0 | 0 | 2.71 | 0 | 2.71 | 0 | 0 | 2.71 | 7.01 | 0
63 | SOUTH 24 PARGANAS | SM/13978 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015392 | 40034029 | New | SVS | GO2223010320PH | 01/12/2022 | 80.57 | 7.71 | 88.28 | Alipore Division | South 24 Pgs Mechanical Division | 27.11 | 0 | 1.57 | 0 | 28.68 | 17.68 | 0 | 1.57 | 0 | 19.25 | 21.8 | 44
64 | SOUTH 24 PARGANAS | SM/15577 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR KHAGRA UNDER ALIPORE DIVISION, BLOCK-CANNING-II, DISTRICT-SOUTH 24 PARGANAS | TSM/017752 | 40036949 | New | SVS | GO2223013886PH | 15/02/2023 | 210.94 | 7.94 | 218.88 | Alipore Division | South 24 Pgs Mechanical Division | 177.1 | 0 | 0 | 0 | 177.1 | 177.1 | 0 | 0 | 0 | 177.1 | 80.91 | 82
65 | SOUTH 24 PARGANAS | SM/15046 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR NARAYANGANJ, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS. | TSM/018314 | 40036984 | New | SVS | GO2223012961PH | 03/02/2023 | 86.75 | 7.71 | 94.46 | Alipore Division | South 24 Pgs Mechanical Division | 56.08 | 0 | 2.48 | 0 | 58.57 | 56.08 | 0 | 2.48 | 0 | 58.57 | 62 | 86
66 | SOUTH 24 PARGANAS | SM/15050 | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | TSM/018293 | 40036967 | New | SVS | GO2223012960PH | 03/02/2023 | 102.26 | 7.71 | 109.97 | Alipore Division | South 24 Pgs Mechanical Division | 4.91 | 0 | 2.38 | 0 | 7.3 | 0 | 0 | 2.38 | 0 | 2.38 | 2.17 | 33
67 | SOUTH 24 PARGANAS | SM/16292 | GROUND WATER BASED MRINALNAGAR PIPE WATER SUPPLY SCHEME, BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | TSM/015396 | 40049219 | New | SVS | GO2223014837PH | 24/02/2023 | 893.93 | 71.66 | 965.59 | Alipore Division | South 24 Pgs Mechanical Division | 328.96 | 0 | 17.06 | 0 | 346.03 | 328.96 | 0 | 17.06 | 0 | 346.03 | 35.84 | 40
68 | SOUTH 24 PARGANAS | SM/14158 | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | TSM/015408 | 40035217 | New | MVS | GO2223011625PH | 05/01/2023 | 958.35 | 71.66 | 1030 | Alipore Division | South 24 Pgs Mechanical Division | 111.88 | 35.61 | 23.39 | 0 | 170.87 | 111.88 | 35.61 | 23.39 | 0 | 170.87 | 16.59 | 72
69 | SOUTH 24 PARGANAS | SM/13827 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRANARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011628 | 40034041 | New | SVS | GO2223010073PH | 25/11/2022 | 458.11 | 75.49 | 533.61 | Alipore Division | South 24 Pgs Mechanical Division | 153.88 | 0 | 29.84 | 0 | 183.72 | 153.88 | 0 | 29.84 | 0 | 183.72 | 34.43 | 50
70 | SOUTH 24 PARGANAS | SM/12732 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BHAJNA UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011581 | 40028492 | New | SVS | GO2223007932PH | 20/09/2022 | 587.08 | 75.49 | 662.57 | Alipore Division | South 24 Pgs Mechanical Division | 254.78 | 17.71 | 10.03 | 0 | 282.52 | 254.78 | 17.71 | 10.03 | 0 | 282.52 | 42.64 | 50
71 | SOUTH 24 PARGANAS | SM/13763 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN KASHINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011582 | 40034033 | New | SVS | GO2223009891PH | 18/11/2022 | 535.48 | 75.49 | 610.98 | Alipore Division | South 24 Pgs Mechanical Division | 122.47 | 0 | 30.59 | 0 | 153.05 | 122.47 | 0 | 30.59 | 0 | 153.05 | 25.05 | 20
72 | SOUTH 24 PARGANAS | SM/13869 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011585 | 40035271 | New | SVS | GO2223010128PH | 25/11/2022 | 536.31 | 75.49 | 611.8 | Alipore Division | South 24 Pgs Mechanical Division | 145.65 | 15.06 | 45.22 | 0 | 205.93 | 145.65 | 15.06 | 45.22 | 0 | 205.93 | 33.66 | 66
73 | SOUTH 24 PARGANAS | SM/13764 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DIGAMBERPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011256 | 40035430 | New | SVS | GO2223009892PH | 18/11/2022 | 616.16 | 75.49 | 691.66 | Alipore Division | South 24 Pgs Mechanical Division | 209.59 | 0 | 37.7 | 0 | 247.29 | 209.53 | 0 | 37.7 | 0 | 247.23 | 35.74 | 40
74 | SOUTH 24 PARGANAS | SM/13803 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DURGA GOBINDOPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011606 | 40034035 | New | SVS | GO2223009952PH | 22/11/2022 | 538.77 | 75.49 | 614.26 | Alipore Division | South 24 Pgs Mechanical Division | 136.05 | 0 | 40.99 | 0 | 177.04 | 136.05 | 0 | 40.99 | 0 | 177.04 | 28.82 | 62
75 | SOUTH 24 PARGANAS | SM/11744 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GAYADHAM, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011259 | 40018954 | New | MVS | GO2223006014PH | 03/08/2022 | 510.22 | 75.49 | 585.72 | Alipore Division | South 24 Pgs Mechanical Division | 274.13 | 6.06 | 65.29 | 0 | 345.48 | 274.13 | 6.06 | 65.29 | 0 | 345.48 | 58.98 | 84
76 | SOUTH 24 PARGANAS | SM/13870 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOPALNAGAR UTTAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 | TSM/011611 | 40034039 | New | SVS | GO2223010122PH | 25/11/2022 | 559.57 | 75.49 | 635.06 | Alipore Division | South 24 Pgs Mechanical Division | 324.57 | 9.39 | 9.81 | 0 | 343.77 | 324.57 | 9.39 | 9.81 | 0 | 343.77 | 54.13 | 51
77 | SOUTH 24 PARGANAS | SM/13804 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPRASTHA PWSS , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011587 | 40034034 | New | MVS | GO2223009953PH | 22/11/2022 | 357.99 | 75.49 | 433.48 | Alipore Division | South 24 Pgs Mechanical Division | 48.58 | 0 | 27.02 | 0 | 75.59 | 48.58 | 0 | 27.02 | 0 | 75.59 | 17.44 | 19
78 | SOUTH 24 PARGANAS | SM/13871 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KRISHNADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011605 | 40035262 | New | SVS | GO2223010113PH | 25/11/2022 | 573.95 | 75.49 | 649.44 | Alipore Division | South 24 Pgs Mechanical Division | 119.8 | 3.37 | 5.77 | 0 | 128.93 | 119.8 | 3.37 | 5.77 | 0 | 128.93 | 19.85 | 16
79 | SOUTH 24 PARGANAS | SM/11746 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUMARPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011263 | 40019072 | New | MVS | GO2223006006PH | 03/08/2022 | 747.18 | 75.49 | 822.67 | Alipore Division | South 24 Pgs Mechanical Division | 270.46 | 0 | 34.08 | 0 | 304.54 | 270.46 | 0 | 34.08 | 0 | 304.54 | 37.02 | 60
80 | SOUTH 24 PARGANAS | SM/11745 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011262 | 40018958 | New | SVS | GO2223006003PH | 03/08/2022 | 444.17 | 71.66 | 515.83 | Alipore Division | South 24 Pgs Mechanical Division | 221.58 | 8.71 | 8.15 | 0 | 238.43 | 221.58 | 5.72 | 8.15 | 0 | 235.45 | 45.64 | 50
81 | SOUTH 24 PARGANAS | SM/13760 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PASCHIM SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011631 | 40034042 | New | SVS | GO2223009890PH | 18/11/2022 | 609.32 | 71.66 | 680.98 | Alipore Division | South 24 Pgs Mechanical Division | 444.56 | 36.7 | 30.19 | 0 | 511.45 | 444.56 | 36.7 | 30.19 | 0 | 511.45 | 75.11 | 0
82 | SOUTH 24 PARGANAS | SM/11846 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PIPRAKHALI UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011580 | 40019096 | New | SVS | GO2223006284PH | 16/08/2022 | 387.8 | 75.49 | 463.3 | Alipore Division | South 24 Pgs Mechanical Division | 149.56 | 16.85 | 4.3 | 0 | 170.71 | 140.77 | 16.85 | 4.3 | 0 | 161.92 | 34.95 | 70
83 | SOUTH 24 PARGANAS | SM/13800 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011626 | 40034040 | New | SVS | GO2223009956PH | 22/11/2022 | 535.08 | 71.66 | 606.73 | Alipore Division | South 24 Pgs Mechanical Division | 448.65 | 17.74 | 33.45 | 0 | 499.83 | 448.65 | 6.99 | 33.45 | 0 | 489.09 | 80.61 | 0
84 | SOUTH 24 PARGANAS | SM/13799 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SURENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011633 | 40032982 | New | SVS | GO2223009955PH | 22/11/2022 | 594.52 | 75.49 | 670.02 | Alipore Division | South 24 Pgs Mechanical Division | 163.18 | 0 | 52.35 | 0 | 215.53 | 163.18 | 0 | 52.35 | 0 | 215.53 | 32.17 | 34
85 | SOUTH 24 PARGANAS | SM/13802 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAKHASKHALI , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011607 | 40034036 | New | SVS | GO2223009954PH | 22/11/2022 | 905.59 | 75.49 | 981.09 | Alipore Division | South 24 Pgs Mechanical Division | 461.03 | 28.53 | 30.6 | 0 | 520.16 | 461.03 | 26.77 | 30.6 | 0 | 518.4 | 52.84 | 75
86 | SOUTH 24 PARGANAS | SM/13965 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011629 | 40051497 | New | MVS | GO2223010350PH | 01/12/2022 | 649.88 | 75.49 | 725.37 | Alipore Division | South 24 Pgs Mechanical Division | 483.31 | 35.16 | 32.92 | 0 | 551.38 | 483.31 | 35.16 | 32.92 | 0 | 551.38 | 76.01 | 88
87 | SOUTH 24 PARGANAS | SM/13828 | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011267 | 40032850 | New | SVS | GO2223010045PH | 25/11/2022 | 830.11 | 75.49 | 905.61 | Alipore Division | South 24 Pgs Mechanical Division | 379.76 | 10.04 | 27.92 | 0 | 417.73 | 379.76 | 10.04 | 27.92 | 0 | 417.73 | 46.13 | 0
88 | SOUTH 24 PARGANAS | SM/11296 | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | TSM/009670 | 40033599 | New | SVS | GO2223004567PH | 28/06/2022 | 272.39 | 29.87 | 302.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 133.9 | 3.79 | 6.78 | 0 | 144.46 | 133.9 | 3.79 | 6.78 | 0 | 144.46 | 47.79 | 48
89 | SOUTH 24 PARGANAS | SM/11295 | Ground water based piped water supply scheme at Chitrasali (Chitrasali,J.L-112), Baruipur Block under South 24 Parganas dist | TSM/009669 | 40033904 | New | SVS | GO2223004566PH | 28/06/2022 | 119.25 | 29.87 | 149.12 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 52.1 | 9.43 | 6.4 | 0 | 67.93 | 52.1 | 9.43 | 6.4 | 0 | 67.93 | 45.56 | 81
90 | SOUTH 24 PARGANAS | SM/11299 | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | TSM/009671 | 40033608 | New | SVS | GO2223004571PH | 28/06/2022 | 185.05 | 29.87 | 214.92 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 85.52 | 13.08 | 7.06 | 0 | 105.66 | 85.52 | 13.08 | 7.06 | 0 | 105.66 | 49.16 | 51
91 | SOUTH 24 PARGANAS | SM/11294 | Ground water based piped water supply scheme at Kalyanpur, Khodarbazar (Khodarbazar CT, J.L-40), Baruipur Block under South 24 Parganas dist.(PART-I) | TSM/009672 | 40033937 | New | SVS | GO2223004568PH | 28/06/2022 | 139.15 | 29.87 | 169.02 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 80.25 | 3.58 | 5.01 | 0 | 88.84 | 80.25 | 3.58 | 5.01 | 0 | 88.84 | 52.56 | 77
92 | SOUTH 24 PARGANAS | SM/11297 | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | TSM/009674 | 40035427 | New | SVS | GO2223004569PH | 28/06/2022 | 162.9 | 29.87 | 192.77 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 2.51 | 0 | 6.01 | 0 | 8.53 | 2.51 | 0 | 6.01 | 0 | 8.53 | 4.42 | 5
93 | SOUTH 24 PARGANAS | SM/11298 | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | TSM/009673 | 40033604 | New | SVS | GO2223004570PH | 28/06/2022 | 206.22 | 29.87 | 236.09 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 184.93 | 5.31 | 8.48 | 0 | 198.71 | 184.93 | 5.31 | 8.48 | 0 | 198.71 | 84.17 | 48
94 | SOUTH 24 PARGANAS | SM/11279 | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | TSM/010734 | 40049580 | New | SVS | GO2223004441PH | 24/06/2022 | 816.73 | 71.66 | 888.39 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 197.77 | 33.13 | 24.43 | 0 | 255.33 | 197.77 | 31.7 | 24.43 | 0 | 253.91 | 28.58 | 72
95 | SOUTH 24 PARGANAS | SM/12873 | Ground water based piped water supply scheme for Champahati (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Baruipur District South 24-Pgns. | TSM/010745 | 40034309 | New | SVS | GO2223008158PH | 23/09/2022 | 720.64 | 71.66 | 792.29 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 184.85 | 18.04 | 36.85 | 0 | 239.75 | 184.85 | 18.04 | 36.85 | 0 | 239.75 | 30.26 | 75
96 | SOUTH 24 PARGANAS | SM/11278 | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | TSM/010744 | 40034274 | New | SVS | GO2223004451PH | 24/06/2022 | 392.5 | 71.66 | 464.16 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 67.46 | 11.57 | 18.41 | 0 | 97.44 | 67.46 | 11.57 | 18.41 | 0 | 97.44 | 20.99 | 29
97 | SOUTH 24 PARGANAS | SM/11280 | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | TSM/010741 | 40034619 | New | SVS | GO2223004453PH | 24/06/2022 | 649.61 | 71.66 | 721.27 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 302.23 | 15.69 | 45.14 | 0 | 363.06 | 302.23 | 15.69 | 45.14 | 0 | 363.06 | 50.34 | 50
98 | SOUTH 24 PARGANAS | SM/11277 | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | TSM/010747 | 40034491 | New | MVS | GO2223004449PH | 24/06/2022 | 742.08 | 71.66 | 813.74 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 325.19 | 8.55 | 253.29 | 0 | 587.03 | 325.19 | 8.55 | 253.29 | 0 | 587.03 | 72.14 | 49
99 | SOUTH 24 PARGANAS | SM/11276 | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | TSM/010754 | 40034475 | New | SVS | GO2223004448PH | 24/06/2022 | 732.31 | 71.66 | 803.97 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 313.37 | 10.24 | 53.77 | 0 | 377.38 | 313.37 | 10.24 | 53.77 | 0 | 377.38 | 46.94 | 0
100 | SOUTH 24 PARGANAS | SM/13844 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBNAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/015898 | 40034590 | New | SVS | GO2223010112PH | 25/11/2022 | 954.77 | 75.49 | 1030.27 | Alipore Division | South 24 Pgs Mechanical Division | 122.31 | 0 | 27.15 | 0 | 149.46 | 122.31 | 0 | 27.15 | 0 | 149.46 | 14.51 | 68
101 | SOUTH 24 PARGANAS | SM/13841 | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR UTTAR SURENDRAGANJ, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/015908 | 40034587 | New | SVS | GO2223010114PH | 25/11/2022 | 562.03 | 75.49 | 637.52 | Alipore Division | South 24 Pgs Mechanical Division | 561.84 | 12 | 7.38 | 0 | 581.22 | 561.84 | 10.11 | 7.38 | 0 | 579.33 | 90.87 | 0
102 | SOUTH 24 PARGANAS | SM/13976 | GROUND WATER BASED RAMGOPALPUR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | TSM/015405 | 40034583 | New | SVS | GO2223010321PH | 01/12/2022 | 557.16 | 75.49 | 632.65 | Alipore Division | South 24 Pgs Mechanical Division | 220.97 | 4.97 | 34.86 | 0 | 260.8 | 140 | 4.97 | 34.86 | 0 | 179.83 | 28.42 | 60
103 | SOUTH 24 PARGANAS | SM/11850 | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | TSM/011945 | 40019074 | New | SVS | GO2223006285PH | 16/08/2022 | 475.41 | 71.66 | 547.06 | Alipore Division | South 24 Pgs Mechanical Division | 230.37 | 28.12 | 11.64 | 0 | 270.13 | 230.37 | 28.12 | 11.64 | 0 | 270.13 | 49.38 | 44
104 | SOUTH 24 PARGANAS | SM/13846 | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | TSM/015401 | 40034585 | New | MVS | GO2223010126PH | 25/11/2022 | 632.41 | 75.49 | 707.91 | Alipore Division | South 24 Pgs Mechanical Division | 237.13 | 12.59 | 46.03 | 0 | 295.76 | 163.63 | 12.59 | 46.03 | 0 | 222.26 | 31.4 | 60
105 | SOUTH 24 PARGANAS | SM/13977 | GROUND WATER BASED WATER SUPPLY SCHEME FOR DAKSHIN MADHUSUDANPUR UNDER ALIPORE DIVISION, BLOCK-PATAHRPRATIMA,DISTRICT - SOUTH 24 PARGANAS | TSM/015395 | 40034028 | New | MVS | GO2223010322PH | 01/12/2022 | 487.52 | 75.49 | 563.02 | Alipore Division | South 24 Pgs Mechanical Division | 138 | 30.84 | 26.32 | 0 | 195.16 | 138 | 30.84 | 26.32 | 0 | 195.16 | 34.66 | 60
106 | SOUTH 24 PARGANAS | SM/13867 | GROUND WATER BASED WATER SUPPLY SCHEME FOR PURBA DWAROKAPUR UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA,DISTRICT-SOUTH 24 PARGANAS | TSM/015897 | 40034591 | New | SVS | GO2223010116PH | 25/11/2022 | 511.87 | 75.49 | 587.37 | Alipore Division | South 24 Pgs Mechanical Division | 171.57 | 28.96 | 26.19 | 0 | 226.72 | 171.57 | 28.96 | 26.19 | 0 | 226.72 | 38.6 | 66
107 | SOUTH 24 PARGANAS | SM/13868 | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | TSM/015407 | 40034584 | New | MVS | GO2223010048PH | 25/11/2022 | 585.77 | 75.49 | 661.26 | Alipore Division | South 24 Pgs Mechanical Division | 154.94 | 0 | 19.34 | 0 | 174.28 | 154.94 | 0 | 19.34 | 0 | 174.28 | 26.36 | 28
108 | SOUTH 24 PARGANAS | SM/14984 | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | TSM/016092 | 40035278 | New | MVS | GO2223013148PH | 04/02/2023 | 288.06 | 71.66 | 359.72 | Alipore Division | South 24 Pgs Mechanical Division | 44.41 | 10.32 | 24.06 | 0 | 78.79 | 44.41 | 10.32 | 24.06 | 0 | 78.79 | 21.9 | 50
109 | SOUTH 24 PARGANAS | SM/13845 | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | TSM/015874 | 40034586 | New | SVS | GO2223010119PH | 25/11/2022 | 443.32 | 75.49 | 518.82 | Alipore Division | South 24 Pgs Mechanical Division | 134.58 | 16.95 | 37.57 | 0 | 189.1 | 134.58 | 16.95 | 37.57 | 0 | 189.1 | 36.45 | 68
110 | SOUTH 24 PARGANAS | SM/18128 | ISWARIPUR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION,PHE DTE. | TSM/011042 | 40066194 | New | SVS | GO2223017941PH | 29/03/2023 | 129.52 | 20.71 | 150.23 | Alipore Division | South 24 Pgs Mechanical Division | 57.59 | 3.87 | 2.19 | 0 | 63.65 | 57.59 | 3.87 | 2.19 | 0 | 63.65 | 42.37 | 49
111 | SOUTH 24 PARGANAS | SM/11273 | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | TSM/010767 | 40026132 | New | MVS | GO2223004440PH | 24/06/2022 | 918.73 | 75.02 | 993.75 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 634.03 | 42.59 | 16.4 | 0 | 693.03 | 634.03 | 41.71 | 16.4 | 0 | 692.14 | 69.65 | 80
112 | SOUTH 24 PARGANAS | SM/12016 | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | TSM/010748 | 40026117 | New | MVS | GO2223006890PH | 01/09/2022 | 846.12 | 79.02 | 925.13 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 141.11 | 14.69 | 58.72 | 0 | 214.52 | 141.11 | 14.69 | 58.72 | 0 | 214.52 | 23.19 | 45
113 | SOUTH 24 PARGANAS | SM/15525 | MADHABNAGAR ZONE - I PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/010690 | 40035410 | New | MVS | GO2223013997PH | 16/02/2023 | 1394.62 | 46.32 | 1440.94 | Alipore Division | South 24 Pgs Mechanical Division | 79.53 | 18.33 | 16.67 | 0 | 114.53 | 68.58 | 18.33 | 16.67 | 0 | 103.58 | 7.19 | 7
114 | SOUTH 24 PARGANAS | SM/14462 | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011018 | 40032540 | New | MVS | GO2223012264PH | 20/01/2023 | 1360.76 | 46.32 | 1407.08 | Alipore Division | South 24 Pgs Mechanical Division | 341.19 | 16.27 | 16.59 | 0 | 374.04 | 341.19 | 16.27 | 16.59 | 0 | 374.04 | 26.58 | 38
115 | SOUTH 24 PARGANAS | SM/12017 | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | TSM/010689 | 40026121 | New | MVS | GO2223006891PH | 01/09/2022 | 919.91 | 76.72 | 996.63 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 279.55 | 22.81 | 57.41 | 0 | 359.77 | 279.55 | 22.81 | 57.41 | 0 | 359.77 | 36.1 | 47
116 | SOUTH 24 PARGANAS | SM/18395 | PATIBANIA PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER ALIPORE DIVISION, PHE DTE. | TSM/017112 | 40035206 | New | MVS | 1817/PHE-28011/182/2023-SCHM CELL-Dept. of PHE | 11/07/2023 | 1243.24 | 46.72 | 1289.96 | Alipore Division | South 24 Pgs Mechanical Division | 367.66 | 14.15 | 63.56 | 0 | 445.36 | 367.66 | 14.15 | 63.56 | 0 | 445.36 | 34.53 | 60
117 | SOUTH 24 PARGANAS | SM/11160 | Piped water supply scheme for Asuti-I and Asuti-II GP under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. | TSM/010373 | 40027056 | New | MVS | GO2223003746PH | 02/06/2022 | 2050.89 | 119.48 | 2170.37 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 1147.92 | 19.64 | 408.98 | 0 | 1576.54 | 1147.92 | 19.64 | 408.98 | 0 | 1576.54 | 72.64 | 72
118 | SOUTH 24 PARGANAS | SM/11488 | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | TSM/010374 | 40018966 | New | MVS | GO2223005082PH | 15/07/2022 | 999.64 | 0 | 999.64 | South 24 Pgs. W/S Division - I |  | 471.71 | 0 | 0 | 0 | 471.71 | 471.71 | 0 | 0 | 0 | 471.71 | 47.19 | 89
119 | SOUTH 24 PARGANAS | SM/11493 | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011230 | 40025878 | New | SVS | GO2223005189PH | 19/07/2022 | 409.23 | 71.66 | 480.88 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 147.74 | 0 | 27.39 | 0 | 175.13 | 147.74 | 0 | 27.39 | 0 | 175.13 | 36.42 | 67
120 | SOUTH 24 PARGANAS | SM/11497 | Proposed ground water based BHARU RAMKRISHNAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011211 | 40025998 | New | SVS | GO2223005176PH | 19/07/2022 | 493.02 | 71.66 | 564.67 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 133.52 | 10.2 | 52.62 | 0 | 196.33 | 133.52 | 10.2 | 52.62 | 0 | 196.33 | 34.77 | 35
121 | SOUTH 24 PARGANAS | SM/11496 | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011224 | 40025988 | New | MVS | GO2223005182PH | 19/07/2022 | 408.24 | 71.66 | 479.9 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 131.64 | 19.71 | 21.67 | 0 | 173.02 | 131.64 | 19.71 | 21.67 | 0 | 173.02 | 36.05 | 66
122 | SOUTH 24 PARGANAS | SM/11498 | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011201 | 40025986 | New | MVS | GO2223005178PH | 19/07/2022 | 433.17 | 71.66 | 504.82 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 134.37 | 29.55 | 29.31 | 0 | 193.22 | 134.37 | 29.55 | 29.31 | 0 | 193.22 | 38.27 | 62
123 | SOUTH 24 PARGANAS | SM/11503 | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011196 | 40025982 | New | SVS | GO2223005188PH | 19/07/2022 | 395.6 | 71.66 | 467.26 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 133.63 | 35.71 | 20.58 | 0 | 189.92 | 133.63 | 19.16 | 20.58 | 0 | 173.37 | 37.1 | 61
124 | SOUTH 24 PARGANAS | SM/11502 | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011195 | 40025945 | New | MVS | GO2223005186PH | 19/07/2022 | 378.4 | 71.66 | 450.06 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 139.62 | 19.5 | 19.81 | 0 | 178.93 | 139.62 | 19.5 | 19.81 | 0 | 178.93 | 39.76 | 66
125 | SOUTH 24 PARGANAS | SM/12045 | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011202 | 40025996 | New | MVS | GO2223006887PH | 01/09/2022 | 394.67 | 71.66 | 466.33 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 111.06 | 0 | 25.82 | 0 | 136.89 | 111.06 | 0 | 25.82 | 0 | 136.89 | 29.35 | 41
126 | SOUTH 24 PARGANAS | SM/11495 | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011225 | 40033600 | New | MVS | GO2223005191PH | 19/07/2022 | 668.53 | 71.66 | 740.19 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 410.28 | 21.35 | 18.8 | 0 | 450.43 | 410.28 | 21.35 | 18.8 | 0 | 450.43 | 60.85 | 68
127 | SOUTH 24 PARGANAS | SM/11494 | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | TSM/011229 | 40025887 | New | SVS | GO2223005190PH | 19/07/2022 | 419.58 | 71.66 | 491.24 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 129.48 | 23.11 | 22.6 | 0 | 175.19 | 129.48 | 17.76 | 22.6 | 0 | 169.83 | 34.57 | 83
128 | SOUTH 24 PARGANAS | SM/13798 | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | TSM/011641 | 40032962 | New | SVS | GO2223009958PH | 22/11/2022 | 811.81 | 113.24 | 925.05 | Alipore Division | South 24 Pgs Mechanical Division | 511.66 | 34.51 | 33.99 | 0 | 580.15 | 511.66 | 34.51 | 33.99 | 0 | 580.15 | 62.72 | 57
129 | SOUTH 24 PARGANAS | SM/11267 | Providing 100% FHTC in Zone-V at Barijpur mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010758 | 40034909 | New | MVS | GO2223004397PH | 23/06/2022 | 753.66 | 0 | 753.66 | South 24 Pgs. W/S Division - I |  | 61.13 | 0 | 57.32 | 0 | 118.45 | 61.13 | 0 | 57.32 | 0 | 118.45 | 15.72 | 20
130 | SOUTH 24 PARGANAS | SM/11253 | PROVIDING 100% FHTC IN ZONE-VI A & ZONE-VI B AT MADHYA GURGURIA MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010552 | 40035931 | New | MVS | GO2223004338PH | 22/06/2022 | 585.88 | 0 | 585.88 | South 24 Pgs. W/S Division - I |  | 130.5 | 0 | 41.82 | 0 | 172.32 | 130.5 | 0 | 41.82 | 0 | 172.32 | 29.41 | 50
131 | SOUTH 24 PARGANAS | SM/11264 | Providing 100% FHTC in Zone-VI at Sadhukhan Ardari Ektara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010761 | 40034923 | New | MVS | GO2223004394PH | 23/06/2022 | 747.46 | 0 | 747.46 | South 24 Pgs. W/S Division - I |  | 10.26 | 0 | 56.86 | 0 | 67.11 | 10.26 | 0 | 56.86 | 0 | 67.11 | 8.98 | 5
132 | SOUTH 24 PARGANAS | SM/11254 | PROVIDING 100% FHTC IN ZONE-VII A & ZONE-VII B AT MAIPIT MOUZA OF KULTALI BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE | TSM/010553 | 40035903 | New | MVS | GO2223004339PH | 22/06/2022 | 803.21 | 0 | 803.21 | South 24 Pgs. W/S Division - I |  | 202.14 | 0 | 58.56 | 0 | 260.7 | 202.14 | 0 | 58.56 | 0 | 260.7 | 32.46 | 30
133 | SOUTH 24 PARGANAS | SM/11261 | Providing 100% FHTC in Zone-VII at Ajodhyanagar mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010774 | 40034997 | New | MVS | GO2223004390PH | 23/06/2022 | 277.69 | 0 | 277.69 | South 24 Pgs. W/S Division - I |  | 0 | 0 | 42.22 | 0 | 42.22 | 0 | 0 | 42.22 | 0 | 42.22 | 15.2 | 50
134 | SOUTH 24 PARGANAS | SM/11260 | Providing 100% FHTC in Zone-VIII at Khela Rampur Sirakol mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010780 | 40035019 | New | MVS | GO2223004388PH | 23/06/2022 | 913 | 0 | 913 | South 24 Pgs. W/S Division - I |  | 44.96 | 0 | 69.45 | 0 | 114.4 | 44.96 | 0 | 69.45 | 0 | 114.4 | 12.53 | 50
135 | SOUTH 24 PARGANAS | SM/11263 | Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte | TSM/010766 | 40035488 | New | MVS | GO2223004393PH | 23/06/2022 | 749.74 | 0 | 749.74 | South 24 Pgs. W/S Division - I |  | 128.96 | 0 | 57.02 | 0 | 185.98 | 128.96 | 0 | 57.02 | 0 | 185.98 | 24.81 | 30
136 | SOUTH 24 PARGANAS | SM/11262 | Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010770 | 40035512 | New | MVS | GO2223004391PH | 23/06/2022 | 387.24 | 0 | 387.24 | South 24 Pgs. W/S Division - I |  | 48.35 | 0 | 234.99 | 0 | 283.34 | 48.35 | 0 | 234.99 | 0 | 283.34 | 73.17 | 50
137 | SOUTH 24 PARGANAS | SM/11487 | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | TSM/010530 | 40026589 | New | MVS | GO2223005124PH | 15/07/2022 | 673.5 | 119.48 | 792.98 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 575.06 | 55.18 | 16.17 | 0 | 646.41 | 575.06 | 55.18 | 16.17 | 0 | 646.41 | 81.52 | 89
138 | SOUTH 24 PARGANAS | SM/11245 | Providing Functional Household Tap Connection (FHTC) in Zone-I at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010772 | 40034692 | New | MVS | GO2223004319PH | 22/06/2022 | 744.81 | 0 | 744.81 | South 24 Pgs. W/S Division - I |  | 11.53 | 0 | 57.77 | 0 | 69.31 | 11.53 | 0 | 57.77 | 0 | 69.31 | 9.31 | 40
139 | SOUTH 24 PARGANAS | SM/11243 | Providing Functional Household Tap Connection (FHTC) in Zone-II at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010783 | 40034900 | New | MVS | GO2223004328PH | 22/06/2022 | 765.3 | 0 | 765.3 | South 24 Pgs. W/S Division - I |  | 80.54 | 0 | 59.25 | 0 | 139.79 | 80.54 | 0 | 59.25 | 0 | 139.79 | 18.27 | 40
140 | SOUTH 24 PARGANAS | SM/11244 | Providing Functional Household Tap Connection (FHTC) in Zone-III at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte | TSM/010826 | 40034946 | New | MVS | GO2223004318PH | 22/06/2022 | 619.31 | 0 | 619.31 | South 24 Pgs. W/S Division - I |  | 69.44 | 0 | 47.52 | 0 | 116.96 | 69.44 | 0 | 47.52 | 0 | 116.96 | 18.89 | 0
141 | SOUTH 24 PARGANAS | SM/11242 | Providing Functional Household Tap Connection (FHTC) in Zone-IV at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010828 | 40035025 | New | MVS | GO2223004327PH | 22/06/2022 | 186.05 | 0 | 186.05 | South 24 Pgs. W/S Division - I |  | 60 | 0 | 13.98 | 0 | 73.98 | 60 | 0 | 13.98 | 0 | 73.98 | 39.77 | 60
142 | SOUTH 24 PARGANAS | SM/11238 | Providing Functional Household Tap Connection (FHTC) in Zone-IX at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010833 | 40035374 | New | MVS | GO2223004323PH | 22/06/2022 | 286.44 | 0 | 286.44 | South 24 Pgs. W/S Division - I |  | 63.16 | 0 | 21.15 | 0 | 84.31 | 63.16 | 0 | 21.15 | 0 | 84.31 | 29.43 | 15
143 | SOUTH 24 PARGANAS | SM/11241 | Providing Functional Household Tap Connection (FHTC) in Zone-V at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010829 | 40035089 | New | MVS | GO2223004326PH | 22/06/2022 | 316.26 | 0 | 316.26 | South 24 Pgs. W/S Division - I |  | 185.61 | 0 | 23.59 | 0 | 209.2 | 185.61 | 0 | 23.59 | 0 | 209.2 | 66.15 | 80
144 | SOUTH 24 PARGANAS | SM/11240 | Providing Functional Household Tap Connection (FHTC) in Zone-VI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010830 | 40035257 | New | MVS | GO2223004325PH | 22/06/2022 | 265.35 | 0 | 265.35 | South 24 Pgs. W/S Division - I |  | 30.44 | 0 | 19.44 | 0 | 49.88 | 30.44 | 0 | 19.44 | 0 | 49.88 | 18.8 | 40
145 | SOUTH 24 PARGANAS | SM/11235 | Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010841 | 40035294 | New | MVS | GO2223004320PH | 22/06/2022 | 733.04 | 0 | 733.04 | South 24 Pgs. W/S Division - I |  | 103.68 | 0 | 56.63 | 0 | 160.31 | 103.68 | 0 | 56.63 | 0 | 160.31 | 21.87 | 10
146 | SOUTH 24 PARGANAS | SM/11239 | Providing Functional Household Tap Connection (FHTC) in Zone-VIII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010831 | 40035342 | New | MVS | GO2223004324PH | 22/06/2022 | 465.42 | 0 | 465.42 | South 24 Pgs. W/S Division - I |  | 49.11 | 0 | 34.83 | 0 | 83.94 | 49.11 | 0 | 34.83 | 0 | 83.94 | 18.04 | 15
147 | SOUTH 24 PARGANAS | SM/11237 | Providing Functional Household Tap Connection (FHTC) in Zone-X at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010836 | 40035397 | New | MVS | GO2223004316PH | 22/06/2022 | 468 | 0 | 468 | South 24 Pgs. W/S Division - I |  | 12.07 | 0 | 35.04 | 0 | 47.12 | 12.07 | 0 | 35.04 | 0 | 47.12 | 10.07 | 0
148 | SOUTH 24 PARGANAS | SM/11236 | Providing Functional Household Tap Connection (FHTC) in Zone-XI at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. | TSM/010837 | 40035411 | New | MVS | GO2223004321PH | 22/06/2022 | 190.17 | 0 | 190.17 | South 24 Pgs. W/S Division - I |  | 17.73 | 0 | 14.32 | 0 | 32.05 | 17.73 | 0 | 14.32 | 0 | 32.05 | 16.86 | 50
149 | SOUTH 24 PARGANAS | SM/16759 | Ramnagar Abad Piped Water Supply Scheme. | TSM/003913 | 40059615 | New | MVS | GO2223015682PH | 13/03/2023 | 910.64 | 37.82 | 948.46 | Alipore Division | South 24 Pgs Mechanical Division | 330.7 | 4.06 | 11.38 | 0 | 346.15 | 330.7 | 4.06 | 11.38 | 0 | 346.15 | 36.5 | 70
150 | SOUTH 24 PARGANAS | SM/11274 | SATBERIA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | TSM/010762 | 40026146 | New | MVS | GO2223004444PH | 24/06/2022 | 836.74 | 76.69 | 913.42 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 594.28 | 33.93 | 5.03 | 0 | 633.24 | 594.28 | 33.93 | 5.03 | 0 | 633.24 | 69.33 | 80
151 | SOUTH 24 PARGANAS | SM/11275 | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | TSM/010765 | 40026130 | New | MVS | GO2223004446PH | 24/06/2022 | 749.33 | 78.67 | 828 | South 24 Pgs. W/S Division - I | South 24 Pgs Mechanical Division | 427.79 | 26.29 | 20.54 | 0 | 474.62 | 427.79 | 26.29 | 20.54 | 0 | 474.62 | 57.32 | 80
152 | SOUTH 24 PARGANAS | SM/18129 | SHIBNAGAR ABAD PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/010989 | 40066193 | New | SVS | GO2223017944PH | 29/03/2023 | 644.01 | 47.25 | 691.26 | Alipore Division | South 24 Pgs Mechanical Division | 134.33 | 7.26 | 8.93 | 0 | 150.51 | 134.33 | 3.86 | 8.93 | 0 | 147.12 | 21.28 | 0
153 | SOUTH 24 PARGANAS | SM/18683 | UTTAR CHANDANPIRI & ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | TSM/011038 | 40066199 | New | MVS | 2245/PHE-28011/229/2023-ESTT CELL-Dept. of PHE | 04/08/2023 | 1056.86 | 46.32 | 1103.18 | Alipore Division | South 24 Pgs Mechanical Division | 367.82 | 0 | 49.73 | 0 | 417.55 | 361.9 | 0 | 49.73 | 0 | 411.63 | 37.31 | 60
Total | [9 empty] | 88139.23 | 8185.22 | 96324.45 |  |  | 30021.46 | 1538.85 | 4730.37 | 0 | 36290.68 | 29691.54 | 1458.39 | 4730.37 | 0 | 35880.3 | 37.25